Revision 3

August 2001

The Government of The Kingdom of Cambodia

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# The Vaccine Fund approved Cambodia’s application for introduction of hepatitis B vaccine in the first round.  The Government of the Kingdom of Cambodia is now applying for Immunisation Services Sub-Account (ISS) and for Injection Safety.

For the ISS the year 2000 baseline has been adjusted using the findings of a 4-province monitoring survey.  The survey used a modified version of the Data Quality Audit (DQA) that provides an adjustment with reported data.

The adjusted baseline number of children who received DTP3 in 2000 is: 252,390, and targets are for 289,498 (65%) in 2001, 319,250 (70%) in 2002 and 350,263 (75%) in 2003.  These coverage targets are as previously submitted to GAVI.  However the population cohort for children under one and total population figures have been amended based on the most recent census information and population projections from the Government.

Improving coverage will require paying health workers per diems and transport costs to increase outreach activities with increased supervision to ensure performance and quality of work.  Identifying and following up the target population is pivotal to this work, thus increasing first dose coverage and reducing dropout, with careful micro planning and management of data.  There is also a need for increased social mobilisation and communication to increase demand.  Pilot schemes to try out incentives and other approaches to improving coverage will also be tested.

As well as increasing coverage, the ISS funds will be used to improve the quality of immunization services.  This will include improved management of vaccine stocks and cold chain with a pilot for the accreditation of vaccine storage sites and personnel.

For Injection Safety support, a new strategic plan (2001-2005) and a 2002 work plan for injection safety are submitted to supplement the existing national policy. To build on progress to date and existing plans, the Government of the Kingdom of Cambodia requests the Injection Safety support as safe injection materials (66%) and a cash grant (34%). The funds will be used for injection safety activities proposed in the 2002 workplan to enable an accelerated introduction of AD syringes for all EPI vaccines by the end of 2002, in addition to those being funded by partners.

The Government of the Kingdom of Cambodia is committed to continuing use of ADs and safe disposal, beyond the three years of Vaccine Fund support, and has already established a line item in the national budget for safe injection materials.  The Government of Cambodia has requested Government of Japan to provide at least two years of safe injection materials from 2003.

The Immunization Coordination Sub-Committee (ICSC) has participated in the development of this proposal and endorses the proposal, and will support the Government of the Kingdom of Cambodia in finding the additional funding needed to achieve and maintain the planned increases in coverage and for supporting the injection safety and disposal activities.

In case the GAVI Secretariat have queries on this submission, please contact :

Name :  Professor Eng Huot		Title/Address :  Director General for Health

Tel.No. :  (855) 23 880 406	   		              Ministry of Health

Fax No. :  (855) 23 880 407	 		               #151-153 Kampuchea Krom Avenue

E-mail :  dghhout@bigpond.com.kh                           Phnom Penh, Cambodia

Alternative address :

Name : Dr Sann Chan Soeung	Title/Address :  NIP Manager

Tel.No. :  (855) 12 933 344				  Ministry of Health

Fax No. :  (855) 23 426 167 					  #151-153 Kampuchea Krom Avenue

E-mail :  msi.study@bigpond.com.kh                          Phnom Penh, Cambodia

- Immunization-related fact sheet

In previous application

# Profile of the Inter Agency Co-ordinating Committee (ICC)

In previous application

# Multi-Year Immunization Plan

In previous application

Baseline data for year 2000 on DTP3 numbers are now available.  The monitoring survey (based on the Data Quality Audit (DQA)) of August 2001 also provides an adjustment factor (Appended as document 1).

Summary of major action points for improving immunization coverage:

- Payment of per diems and transport to increase outreach activities (policy already exists, but money not paid in advance)

- Identification of target population through pregnancy and birth reporting at local level

- Improved supervision to monitor performance and quality of work

- Training of health workers and supervisors

- Reducing drop-outs (15% in 2000) to 5% by 2003 and 3% by 2005

- Micro planning with regular meetings for health workers at ODs

- Community involvement in planning and delivery

- Increased demand through communication strategies and social mobilisation

- Piloting incentives and other strategies to improve coverage

It is anticipated that the shift to exclusive use of AD syringes will also increase coverage.  There are also efforts to improve the management of adverse events following immunisation (AEFI) that will increase confidence in the immunization programme.

# Injection safety

6.1	Summary of the injection safety strategy for immunization

The target is to have 100% of immunization injections given with AD syringes that are properly disposed of in safety boxes and effectively incinerated by 2005.  Support from the Vaccine Fund will enable accelerated achievement of the 2005 target.

A phased introduction during 2002, by province, is planned in line with availability of incinerators in each province and following on from the immunization campaigns that are planned and where ADs will be used.  The specific objectives of the 2002 workplan are to:

- achieve the transition to exclusive use of ADs for EPI vaccines by the end of 2002.

- establish adequate incineration facilities for every province.

- pilot and establish an ‘exchange strategy’ for used injection materials.

- increase health worker knowledge and practice on safe injection and disposal.

- increase community awareness of the importance of safe injection and disposal.

| Attached are copies of national policy, Strategic Plan of Action for 2001-2005 to improve Injection Safety for EPI vaccines, and 2002 Workplan | Document numbers 2-4. |
| --- | --- |

6.2	Injection safety equipment

The following tables calculate the amount of supplies requested for injection safety:

Table 4: Target coverage and numbers for each vaccine

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Infant Population | 445,382 | 456,071 | 467,017 | 478,225 | 489,703 |
| BCG Coverage (%) | 80 | 80 | 80 | 80 | 80 |
| Infants vaccinated | 356,306 | 364,857 | 373,614 | 382,580 | 391,762 |
| DTP-Hep B3 Coverage (%) | 65 | 70 | 75 | 80 | 80 |
| Target Pop. (phased introd.) | 19,111 | 38,223 | 140,105 | 286,935 | 489,703 |
| Infants vaccinated | 12,422 | 26,756 | 105,079 | 229,548 | 391,762 |
| DTP3 Coverage Targets (%) | 65 | 70 | 75 | 80 | 0 |
| Target Pop. (phased withdrawal) | 426,271 | 417,848 | 326,912 | 191,290 | 0 |
| Infants vaccinated | 277,076 | 292,494 | 245,184 | 153,032 | 0 |
| Measles Coverage (%) | 60 | 70 | 75 | 80 | 80 |
| Infants vaccinated | 267,229 | 319,250 | 350,263 | 382,580 | 391,762 |
| TT for PW Coverage (%) | 40 | 50 | 70 | 85 | 100 |
| Pregnant Women vaccinated | 178,153 | 228,036 | 326,912 | 406,492 | 489,703 |
| Total DTP3 | 289,498 | 319,250 | 350,263 | 382,580 | 391,762 |

Table 6.1: Estimated supplies for safe injection with BCG Vaccine

| BCG vaccine | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Target no. of children | 364,857 | 373,614 | 382,580 | 391,762 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 364,857 | 373,614 | 382,580 | 391,762 |
| AD syringes (+10%) | 405,397 | 415,126 | 425,089 | 435,291 |
| AD syringes buffer (25%) | 101,349 | 2,432 | 2,491 | 2,551 |
| AD syringes | 506,746 | 417,559 | 427,580 | 437,842 |
| Doses per vial | 20 | 20 | 20 | 20 |
| Wastage factor | 5.1 | 4.5 | 3.5 | 2.5 |
| Effective doses per vial | 3.9 | 4.4 | 5.7 | 8.0 |
| Reconstitution syringes | 103,376 | 93,403 | 74,391 | 54,411 |
| Safety boxes (+10%) | 6,779 | 5,677 | 5,577 | 5,469 |

Table 6.2:  Estimated supplies for safe injection with Measles Vaccine

| Measles Vaccine | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Target no. of children | 319,250 | 350,263 | 382,580 | 391,762 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 319,250 | 350,263 | 382,580 | 391,762 |
| AD syringes (+10%) | 354,722 | 389,181 | 425,089 | 435,291 |
| AD syringes buffer (25%) | 88,681 | 8,615 | 8,977 | 2,551 |
| AD syringes | 443,403 | 397,795 | 434,066 | 437,842 |
| Doses per vial | 10 | 10 | 10 | 10 |
| Wastage factor | 3.1 | 2.5 | 1.8 | 1.3 |
| Effective doses per vial | 3.3 | 4.0 | 5.6 | 7.5 |
| Reconst.syringe | 108,190 | 97,295 | 76,516 | 57,894 |
| Safety boxes (+10%) | 6,129 | 5,501 | 5,673 | 5,508 |

Table 6.3:  Estimated supplies for safe injection with DTP Vaccine

| DPT Vaccine | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Target no. of children | 292,494 | 245,184 | 153,032 | 0 |
| Doses per child | 3.00 | 3.00 | 3.00 | 0.00 |
| Total no. of doses | 877,481 | 735,552 | 459,096 | 0 |
| AD syringes (+10%) | 974,979 | 817,280 | 510,107 | 0 |
| AD syringes buffer (25%) | 243,745 | 0 | 0 | 0 |
| AD syringes | 1,218,724 | 817,280 | 510,107 | 0 |
| Safety boxes (+10%) | 13,541 | 9,081 | 5,668 | 0 |

Table 6.4:  Estimated supplies for safe injection with DTP- Hep B Vaccine

| DPT-Hep B Vaccine | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Target no. of children | 26,756 | 105,079 | 229,548 | 391,762 |
| Doses per child | 3.00 | 3.00 | 3.00 | 3.00 |
| Total no. of doses | 80,268 | 315,236 | 688,644 | 1,175,287 |
| AD syringes (+10%) | 89,187 | 350,263 | 765,161 | 1,305,874 |
| AD syringes buffer (25%) | 22,297 | 25,844 | 26,931 | 7,652 |
| AD syringes | 111,484 | 376,107 | 792,092 | 1,313,526 |
| Safety boxes (+10%) | 1,239 | 4,179 | 8,801 | 14,595 |

Table 6.5:  Estimated supplies for safe injection with TT Vaccine

| TT Vaccine | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Target of Pregnant Women | 228,036 | 326,912 | 406,492 | 489,703 |
| No. Of doses per women | 3.5 | 3.5 | 3.5 | 3.5 |
| Total No. of doses | 798,125 | 1,144,191 | 1,422,720 | 1,713,960 |
| AD syringes (+10%) | 886,805 | 1,271,324 | 1,580,800 | 1,904,400 |
| AD syringes buffer (25%) | 221,701 | 96,130 | 77,369 | 80,900 |
| Total No. of AD syringe | 1,108,506 | 1,367,454 | 1,658,170 | 1,985,299 |
| No. Of safety box (+10%) | 12,317 | 15,194 | 18,424 | 22,059 |

Table 6.6:  Summary of total injection safety supplies (incl. DTP- Hep B)

| ITEM | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Total AD syringe (BCG) | 506,746 | 417,559 | 427,580 | 437,842 |
| Total AD syringes (all other) | 2,882,117 | 2,958,635 | 3,394,435 | 3,736,667 |
| Total Reconst. Syringes | 211,566 | 190,699 | 150,907 | 112,305 |
| Total Safety boxes | 24,403 | 39,632 | 44,144 | 47,631 |

Table 6.7:  Costs of total injection safety supplies (incl. DTP- Hep B)

| ITEM | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Total AD syringe (BCG) | $34,459 | $28,394 | $29,075 | $29,773 |
| Total AD syringes (all other) | $195,984 | $201,187 | $230,822 | $254,093 |
| Reconst. Syringes | $9,520 | $8,581 | $6,791 | $5,054 |
| Safety boxes | $13,422 | $21,798 | $24,279 | $26,197 |
| UNICEF service charge (6%) | $15,203 | $15,598 | $17,458 | $18,907 |
| TOTAL | $268,588 | $275,558 | $308,425 | $334,025 |

The introduction of ADs and safety boxes will be phased in, starting with provinces that have established incinerators and that have recently conducted measles immunization campaigns (where ADs and safety boxes are used).  Based on the month on introduction, the total supplies are adjusted.  That adjustment does not reflect the requirement for 25% buffer stock, which will be needed, irrespective of month of start date.  Therefore, the volume of supplies needed for 2002 will be 66% of the full annual requirement.  The remaining 34% is sought as cash grant to support injection safety activities ($91,750).

| Table 7: Month of introduction of AD, by province |  |
| --- | --- |
| Province | % of total | Start | Adjusted |
|  | population | month | usage |
| Kg.Chhang | 3.7 | Jan | 3.7 |
| Kandal | 9.4 | Feb | 8.2 |
| Kg. Speu | 5.1 | Feb | 4.5 |
| P.Penh | 8.6 | Feb | 7.5 |
| Siem Reap | 6.1 | Feb | 5.3 |
| Kraitie | 2.2 | Mar | 1.7 |
| Mondolkiri | 0.3 | Mar | 0.2 |
| Preh Vihear | 1.0 | Mar | 0.8 |
| Prey Veng | 8.7 | Mar | 6.9 |
| Rattanakiri | 0.8 | Mar | 0.6 |
| Strung Treng | 0.7 | Mar | 0.6 |
| Takeo | 7.2 | Mar | 5.7 |
| Palin | 0.3 | April | 0.2 |
| B.M.Chey | 5.5 | May | 3.4 |
| Kg. Thom | 5.0 | May | 3.1 |
| Kampot | 4.7 | Aug | 1.8 |
| Kep | 0.2 | Aug | 0.1 |
| Pursat | 3.1 | Sep | 0.9 |
| Svay Rieng | 4.2 | Sep | 1.2 |
| Battambang | 6.7 | Oct | 1.4 |
| Kg. Cham | 13.6 | Oct | 2.8 |
| Odar.M.Chey | 0.3 | Nov | 0.0 |
| Siha.ville | 1.2 | Nov | 0.2 |
| Koh Kong | 1.1 | Dec | 0.0 |
| Total |  |  | 61.0 |
| Total 2002 need (adjusted for buffer stock) |  | 66% |

  - Areas for injection safety funds

List of areas of injection safety funded by different sources: (For the GAVI/Vaccine Fund support, fill in “areas of support”. For AD syringes and waste disposal, fill in “source of funds”.)

| Source of fund | Area of support | Start of fund utilization |
| --- | --- | --- |
| GAVI/Vaccine Fund | AD syringes and waste disposal boxes | Jan 2002 |
| Partners in-country | $131,000 as below – for incinerators, evaluation, assessment | Jan 2002 |
| GAVI/Vaccine Fund | $91,000 as below – for training and community awareness | Jan 2002 |

| Activity | Time (2002) | Source | Budget |
| --- | --- | --- | --- |
| Incinerator/Disposal |
| Install and build housing structure for a further 9 incinerators in remaining 9 provinces | Jan-Dec | WHO | $54,000 |
| Maintenance for existing incinerators; establish a maintenance and replacement programme | Jan-Dec | Fund | $12,000 |
| Investigate locally built incinerators at district level. | Jan-Jun | WHO | $5,000 |
| Review feasibility of alternative disposal methods | Mar-Oct | WHO | $25,000 |
| Further investigate operating parameters of incinerators to reduce environmental emissions | Jan-Feb |  | $15,000 |
| Training of provincial focal persons on incinerator use | Jan-Dec | Fund | $6,000 |
| Autodisable syringes and safety boxes |
| Evaluate Kampong Chhnang pilot introduction of ADs. | Jan | CVP | $10,000 |
| Progressive introduction of AD syringes and safety boxes into the routine immunization programme. | Feb-Dec | Fund |  |
| Pilot ‘exchange strategy’ | Jan-Mar | WHO | $2,000 |
| Implement ‘exchange strategy’. | Apr-Dec | WHO | $5,000 |
| Practice |
| Training of health workers on safe injection and disposal (including training materials, and evaluation) | Jan-Nov | Fund | $18,000 |
| Supervision of health worker practice and incineration | Jan-Dec | Fund | $15,000 |
| National assessment on injection safety | Dec | CVP | $15,000 |
| Community awareness |
| Development and dissemination of IEC materials | Jun-Dec | Fund | $20,000 |
| Media campaign | Oct-Dec | Fund | $20,000 |
|  |  | TOTAL | $222,000 |
|  |  | Fund | $91,000 |
|  |  | Partners | $131,000 |

# New and under-used vaccines

No new application

# Strategic directions to mobilise additional resources for immunization

In previous application.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of the Kingdom of Cambodia, considering that its DTP3 coverage for 2000 was 58% (adjusted using the modified DQA) corresponding to 252,390 children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund.

- Support for Immunization Services                       YES

- Support for New and Under-used vaccines          NO

- Support for Injection Safety                                  YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 1, namely 252,390.  Funds will also be requested for following years as estimated in table 1.

- The Government takes full responsibility to manage the in-country transfer of funds.

The funds will be transferred to an account that the Ministry of Health set up for Vaccine Fund support.

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

- The accounting for this account will use the standards and software established by the Ministry of Health (for its Health Sector Reform account in collaboration with partner agencies) in order to provide ease of future integration.  An accountant will be provided by the MOH or partner agencies, and monthly reports will be provided for the NIP and ICSC.  Funds will be distributed to Provincial and Operational District health departments according to funding requests that they submit based on a plan to improve routine immunization drafted by the NIP and approved by the ICSC.  The NIP will review these plans and request the transfer of funds to the Provinces and ODs.

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

n/a

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

The amount of supplies listed in table 8  (66% of annual need)

The equivalent amount of funds (remaining 34%)

Table 8: Summary of support requested from GAVI and the Vaccine Fund

| ITEM | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- |
| Total AD syringe (BCG) | 333,641 | tba | 0 | 0 |
| Total AD syringes (all other) | 1,897,586 | tba | 0 | 0 |
| Total Reconst. Syringes | 139,295 | tba | 0 | 0 |
| Total Safety boxes | 16,067 | tba | 0 | 0 |
| Cash | $91,750 | tba | tba | 0 |
| tba - request for 2003 to be advised by September 2002 with 2003 workplan |  |

ANNEX  1

Summary of documentation

Document 1: Monitoring survey report (modified DQA)

Document 2: National policy on injection safety (hard copy only)

Document 3:  Strategic Plan of Action for 2001-2005 to improve Injection Safety for EPI vaccines

Document 4: 2002 Workplan to improve Injection Safety for EPI vaccines

ANNEX  2

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  | Banking Details |
| --- | --- | --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of Cambodia hereby requests that a payment be made, via electronic bank transfer, as detailed below : |
| Name of Institution : (Account Holder) |  |
| Address : |  |
| City – Country : |  |
| Telephone No. : |  | Fax No. : |  |
| Amount in USD : | ( To be filled in by GAVI Secretariat ) | Currency of the bank account : |  |
| For credit to : Bank account’s title |  |
| Bank account No. : |  |
| At : Bank’s name |  |
| Is the bank account exclusively to be used by this programme? | YES ( ) NO ( ) |
| By whom is the account audited ? |  |
| Signature of Government’s authorizing official : |
| Name : |  | Seal : |
| Title : |  |  |
| Signature : |  |  |
| Date : |  |  |

| SECTION 2 ( To be completed by the Bank ) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name : |  |  |
| Branch Name : |  |  |
| Address : |  |  |
| City – Country : |  |  |
| Swift code : |  |  |
| Sort code : |  |  |
| ABA No. : |  |  |
| Telephone No : |  |  |
| Fax No : |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : | Name of bank’s authorizing official : |
| 1 Name : Title : |  | Signature : |  |
|  |  | Date: |  |
| 2 Name : Title : |  | Seal: |
| 3 Name : Title : |  |  |
| 4 Name : Title : |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative : |
| Name |  |
| Signature |  |
| Date |  |