Global Alliance for Vaccines and Immunization (GAVI)

APPLICATION FROM MALAWI

For Support to:

Immunization Services

30 May 2006

This document is accompanied by an electronic copy on CD for your convenience. Please return a copy of the CD with the original, signed hard-copy of the document to:

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be in English or French.

## CONTENTS

| SECTION |  | SUPPORT | PAGE |
| --- | --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies |  |  |
|  | - Government and the Health Sector Strategy Committee | HSS | 3 |
|  | - Government and the Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 4 |
|  | - The Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 5 |
| 3. | Immunization Programme Data | ALL | 6 |
|  | - Immunization Fact Sheet |  | 6 |
|  | - Comprehensive Multi-Year Immunization Plan |  | 7 |
| 4. | Immunization Services Support (ISS) | ISS | 10 |
| 5. | Health Systems Strengthening Support (HSS) | HSS | 12 |
|  | - Proposed GAVI Health Systems Strengthening Support |  | 14 |
|  | - HSS Financial Analysis and Planning |  | 16 |
|  | - Management and Accountability of GAVI HSS Funds |  | 17 |
|  | - Involvement of Partners in GAVI HSS Implementation |  | 18 |
| 6. | Injection Safety Support (INS) | INS | 19 |
| 7. | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | ALL | 20 |
| 8. | Documents required for each type of support | ALL | 21 |
| Annex 1 – Banking Form |  | ISS | 22 |

## Executive Summary

The Government of Malawi places great importance in the provision of sound health care services to its population. The high immunization coverage registered during the Universal Childhood Immunization (UCI) era was a result of government’s commitment and the financial and technical support towards improving the welfare of the children of Malawi.

The declining incidence of vaccine-preventable diseases such as measles and neonatal tetanus since the inception of EPI in the country is a clear testimony of the importance of strengthening the immunization activities. It is on this background that the government with its collaborating partners are asking for immunization services support from GAVI for provision and sustenance of quality immunization services in the country in order to achieve the Millennium Development Goal number four.

The EPI programme in Malawi changed its policy on safe injection in line with WHO/UNFPA policy.  The government in collaboration with ICC started implementing the use of auto-disable syringes bundled with vaccines in routine and supplemental immunization activities for vaccines in 2002 except for BCG. AD syringes for BCG were introduced in 2003. Since 2002 the injection materials except for DPT-HepB+Hib, were made available with support from DFID and KFW through UNICEF. Injection materials for DPT-HepB+Hib were supplied by GAVI during the same period.

Though Malawi has made significant progress towards eliminating measles, neonatal tetanus and polio, the need for equitable and sustainable immunization services for every child in Malawi cannot be overemphasised. In 2005 RED strategy was introduced in eight low performing districts with the intention to scale up to 16 districts by the end of 2006 with the aim of strengthening further routine immunisation activities in the districts. The goals of RED are consistent with the Millennium Development Goals.

The ICC has been very instrumental in the preparation of this proposal. The endorsement of this proposal by ICC members is a clear demonstration of their full support for the immunisation services in Malawi.

The Government of Malawi is therefore submitting this proposal to solicit support for Immunization Services starting from 2006 to 2010.

## Signatures of the Government and National Coordinating Bodies

## Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Malawi commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Signature: | Signature: …………………………………… |
| Title: | Title: …………………………………… |
| Date: | Date:6 |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the ICC met on the Malawi EPI ICC to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: ………

| Agency/Organisation | Name/Title |
| --- | --- |
| Ministry of Health |  |
| WHO |  |
| UNICEF |  |
| DFID |  |
| JICA |  |
| NORWEGIAN EMBASSY |  |
| USAID |  |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr H.S. Somanje | Title: Director of Preventive Health Services |
| --- | --- |
|  | Address: |
| Tel No.: +265 8 842 971 | Ministry of Health |
|  | P.O Box 30377 |
| Fax No.: +265 1 789 756 | Lilongwe 3 |
|  | Malawi |
| Email:somanjeh@globemw.net |  |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC is responsible for coordinating and guiding the use of the GAVI ISS support.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

| Name of the ICC: Malawi EPI ICC |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date of constitution of the current ICC: 1998 |  |  |  |  |
| Organisational structure (e.g., sub-committee, stand-alone): Stand-alone |  |  |  |  |
| Frequency of meetings: Quarterly |  |  |  |  |
| Composition: MOH, WHO, UNICEF, DFID, JICA, NORWEFIAN EMBASSY, USAID |  |  |  |  |
|  | Function | Title / Organization | Name |  |
|  | Chair | Director of Preventive Health Services Ministry of Health | Dr H Somanje |  |
|  | Secretary | National EPI Manager Ministry of Health | Mrs A D Katsulukuta |  |
|  | Members | - Resident Representative, WHO - Resident Representative, UNICEF - DFID - Child Health Specialist, USAID - JICA - First Secretary, NORWEGIAN EMBASSY | - Dr M. Moeti - Ms Aida Girma - Mr Christopher Phiri - Mrs C. Chiphazi - Ms Sato - Dr Michael Tawanda |  |

Major functions and responsibilities of the ICC:

- Coordination: The ICC coordinates the support for EPI from various partners to ensure efficient and effective functioning of the EPI programme in line with SWAp.

- Advocacy: The committee advocates for EPI at higher political level in the country and international level in order to effectively and efficiently execute all planned activities.

- Social mobilization: The committee is mandated to ensure that there is wide publicity of the programme for maximum community utilization of the immunization services.

- Transparency and Accountability: The committee mobilizes resources for the immunization activities and therefore is obliged to review and monitor the use of funds and other resources together with the EPI Unit and gives continuous feedback to donors and communities as need arises.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- Incorporation of SWAp secretariat into the ICC to ensuring that resources are mobilized for the procurement of both traditional and new vaccines through SWAp

- Incorporation of partners involved in other child health interventions into the ICC to ensure integration of childhood interventions with EPI as a platform

- Ensuring that quarterly meetings with all ICC members are conducted as planned. Whenever need arises, ad-hoc meetings are conducted. The minutes and agenda are circulated to members in time.

## Immunization Programme Data

Please complete the immunization fact sheet below, using data from available sources.

## Immunization Fact Sheet

Table 1: Basic facts for the year 2005 (most recent; specify dates of data provided)

| Population | 12,341,170 | GNI per capita | 160 $US |
| --- | --- | --- | --- |
| Surviving Infants* | 562903 | Infant mortality rate | 76/ 1,000 |
| Percentage of GDP allocated to Health | 7% | Percentage of Government expenditure on Health | 11% |

* Surviving infants = Infants surviving the first 12 months of life

Table 2: Trends of immunization coverage and disease burden

(As per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2004 | 2005 | 2003 | Age group |  | 2004 | 2005 |
| BCG |  | 91 | 104 | 90 | <1 yr | Tuberculosis* | 13,015 | 26,000 |
| DTP | DPT1 | 100 | 108 | 93 | <1 yr | Diphtheria | 0 | 0 |
|  | DPT3 | 84 | 93 | 84 | <1 yr | Pertussis | 0 | 0 |
| Polio 3 |  | 85 | 93 | 87 | <1 yr | Polio | 0 | 0 |
| Measles (first dose) |  | 77 | 82 | 72 | <1 yr | Measles | 167 | 184 |
| TT2+ (Pregnant women) |  | 87 | 63 | 70 | Peg | NN Tetanus | 7 | 6 |
| Hib3 |  | 84 | 93 | NA | NA | Hib ** | 24 | 7 |
| Yellow Fever |  | NA | NA | NA | NA | Yellow fever | NA | NA |
| HepB3 |  | 84 | 93 | NA | NA | HepB sero-Prevalence* | NA | NA |
| Vit A supplement | Mothers <6 weeks after delivery | 18 | 33 | 5 | Post natal mothers |  |  |  |
|  | Infants >6 months | 53 | 91 | 51 | <1 yr |  |  |  |

* If available ** Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

## Comprehensive Multi-Year Immunization Plan

  - A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER 2

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement

(cMYP page 11)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth or during first contact | x |  |  |
| DPT-HepB+Hib | 6, 10, 14 weeks | x |  | DPT-HepB+Hib vaccine was introduced in 2002 |
| OPV | At birth, 6, 10, 14 weeks | x |  |  |
| Measles | At 9 months | x |  |  |
| TT (15-49 yrs and pregnant) | First contact, 4 weeks, 6 weeks, 1 year, 1 year. | x |  |  |
| Vitamin A (children) | At 6 months and every 6 months up to 59 months | x |  |  |
| Vitamin A (post-natal Mothers) | Up to 2 months after delivery | x |  |  |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP

| Major Action Points (cMYP pages30-31) | Timeframe |
| --- | --- |
| - Sustaining high routine immunisation coverage | 2006-10 |
| - Sustaining high quality surveillance on AFP, Measles & NNT | 2006-10 |
| - Integrated implementation of child health intervention | 2006-10 |
| - Continued capacity building at all levels | 2006-10 |
| - Strengthening advocacy and social mobilisation activities | 2006-10 |

Table 4: Baseline and annual targets (cMYP pages 32-36)

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program |
|  |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Births |  | 621,445 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 | 797,828 |
| Infants’ deaths |  | 58,542 | 48,480 | 50,113 | 51,415 | 53,524 | 55,301 | 56,352 |
| Surviving infants |  | 562903 | 637,894 | 659,382 | 676,508 | 704,267 | 727,651 | 741,476 |
| Pregnant women |  | 621,445 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 | 797,828 |
| Infants vaccinated with BCG |  | 659,304 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 | 797,828 |
| BCG coverage* |  | 104% | 100% | 100% | 100% | 100% | 100% | 100% |
| Infants vaccinated with OPV3 |  | 538,474 | 605,999 | 633,006 | 649,448 | 683,139 | 713,098 | 726,646 |
| OPV3 coverage** |  | 94 | 95 | 96 | 96 | 97 | 98 | 100 |
| Infants vaccinated with DTP3*** |  | 533,707 | 605,999 | 633,006 | 649,448 | 683,139 | 713,098 | 726,646 |
| DTP3 coverage** |  | 93 | 95 | 96 | 96 | 97 | 98 | 100 |
| Infants vaccinated with DTP1*** |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| Wastage rate in base-year and planned thereafter |  | 7% | 6% | 5% | 5% | 5% | 5% | 5% |
| Infants vaccinated with 3rd dose of ………….. |  |  |  |  |  |  |  |  |
| …………. Coverage** |  |  |  |  |  |  |  |  |
| Infants vaccinated with 1st dose of …………….. |  |  |  |  |  |  |  |  |
| Wastage1 rate in base-year and planned thereafter |  |  |  |  |  |  |  |  |
| Infants vaccinated with Measles |  | 471,989 | 542,210 | 573,662 | 602,092 | 640,883 | 669,439 | 696,987 |
| Measles coverage** |  | 82 | 84 | 86 | 90 | 95 | 95 | 95 |
| Pregnant women vaccinated with TT+ |  | 400,673 | 480,462 | 510,836 | 545,942 | 583,500 | 626,362 | 638,262 |
| TT+ coverage**** |  | 61% | 65% | 70% | 75% | 80% | 82% | 85% |
| Vit A supplement | Mothers (<6 weeks from delivery) | 208,650 | 240,231 | 283,789 | 327,565 | 378,896 | 430,624 | 478,697 |
|  | Infants (>6 months) | 416,075 | 586,862 | 613,225 | 635,918 | 669,054 | 698,545 | 719,232 |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Please indicate the method used for calculating TT and coverage:

The proportion of pregnant women is 5% of the total population in Malawi. The formula for TT2 coverage in pregnant women is as follows: Number of pregnant women vaccinated with 2nd TT dose divided by total number of pregnant women multiplied by 100%

Table 5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |  |  |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 13% | 11% | 10% | 9% | 8% | 7% |  |  |

Table 6: Summary of current and future immunization programme budget (cMYP pages )

|  | Estimated costs per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| Routine recurrent costs | $9,883,767 | $12,113,068 | $10,683,264 | $10,975,296 | $11,281,586 | $10,923,160 |
| Routine capital costs | $2,900 | $8,180 | $2,161,198 | $531,035 | $835,889 | $351,281 |
| Campaigns | $1,285,863 | - | - | - | $1,629,518 | - |
| Other costs | $6,623,955 | $6,756,434 | $6,891,563 | $7,029,394 | $7,169,982 | $7,313,381 |
| GRAND TOTAL | $17,796,485 | $18,877,682 | $19,736,025 | $18,535,725 | $20,916,975 | $18,587,822 |

Table 7: Summary of current and future financing and sources of funds (cMYP pages )

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Funding source | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| Routine recurrent cost | Government | $449,438 | $469,958 | $496,244 | $578,158 | $534,653 | $519,344 |
|  | Sub-national | $739,512 | $758,017 | $739,869 | $739,869 | $739,869 | $739,869 |
|  | GAVI | $7,054,258 | $8,130,652 | $6,463,691 | $6,259,292 | $6,397,218 | $653,776 |
|  | UNICEF | $512,250 | $158,414 | $183,414 | $158,414 | $158,414 | $158,414 |
|  | WHO | $165,356 | $341,000 | $341,000 | $331,000 | $331,000 | $331,000 |
|  | KFW | $125,326 | - | - | - | - | - |
|  | DFID | $837,626 | - | - | - | - | - |
|  | SWAp | - | $1,929,698 | $1,992,817 | $1,772,813 | $1,816,687 | $1,870,388 |
| Routine capital cost | SWAp | - | - | - | - | - | - |
|  | UNF | - | - | - | - | - | - |
|  | WHO | $2,900 | $8,160 | - | - | - | - |
| Campaigns | SWAp | $849,863 | - | - | - | - | - |
|  | UNF | $436,000 | - | - | - | - | - |
|  | Unfunded | - | - | - | - | $1,629,518 | - |
| Other costs | Sub-national | $6,623,955 | $6,756,434 | $6,891,563 | $7,029,394 | $7,169,982 | $7,313,381 |
| GRAND TOTAL |  | $17,796,484 | $18,552,332 | $17,108,598 | $16,868,940 | $18,777,341 | $11,586,172 |

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 8: Estimate of fund expected from ISS

|  | Baseline Year 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 93% | 95% | 96% | 96% | 97% | 98% | 100% |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 533,707 | 605,999 | 633,006 | 649,448 | 683,139 | 713,098 | 726,646 |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 | - | 72,292 | 27,007 | 16,442 | 33,691 | 29,959 | 13,548 |
| Funds expected ($20 per additional infant) | - | 1,445,840 | 540,140 | 328, 840 | 673,820 | 599180 | 270,960 |

*  Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |

If you have not received ISS support before, please indicate:

a) When you would like the support to begin:

January 2007

b) When you would like the first DQA to occur:

2010

c) How you propose to channel the funds from GAVI into the country:

Through UNICEF to the Ministry of Health

d) How you propose to manage the funds in-country:

Monitoring of utilisation will be monitored by the Controller of Accounting services in the Ministry of health and through the ICC

e) Who will be responsible for authorising and approving expenditures?

The Secretary for Health

  - Please complete the banking form (annex 1) if required

## DOCUMENTS REQUIRED FOR EACH TYPE OF SUPPORT

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form | X | 2006 |
| ALL | Comprehensive Multi-Year Plan (cMYP) | X | 2006-10 |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed | X | 2006 |
| If relevant | Endorsed minutes of the ICC meeting discussing the requested GAVI support |  |  |
| HSS | National Health Sector Strategic Plan |  |  |
| HSS | Medium Term Expenditure Framework ** |  |  |
| HSS | Recent Health Sector Assessment documents |  |  |
| HSS | Outline of HSS Programme with budget and Justification for support or HSS Relevant parts of National Planning Document |  |  |
| HSS | Other Health Systems Strengthening Plans / estimates |  |  |
| Injection Safety | National Policy on Injection Safety including safe medical waste disposal (if separate from cMYP) |  |  |
| Injection Safety | Action plans for improving injection safety and safe management of sharps waste (if separate from cMYP) |  |  |
| Injection Safety | Evidence that alternative supplier complies with WHO requirements (if not procuring supplies from UNICEF) |  |  |

* Please indicate the duration of the plan / assessment / document where appropriate

** Where available

ANNEX 1

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Government of Malawi

Comprehensive EPI Multi-Year Plan

2006-10

Malawi

Expanded Programme on Immunisation

P.O Box 30377

Lilongwe 3

Malawi

December 2005

# Expanded Programme on Immunisation

# Ministry of Health

# Comprehensive EPI Multi-Year Plan

# 2006-10

# Table of Contents

Executive Summary										5

1.0 Background Information								7

1.1 Geography										7

1.2 Demography										7

1.3 Socio-economic Status									8

2.0 Health Care Delivery Systems							9

2.1 Health services										9

2.2 Policy of the Ministry of Health 							9

2.3 Sector Wide Approach (SWAp)							10

2.4 Essential Health Package (EHP)							10

2.5 Human Resources 									11

3.0 Situational Analysis									12

3.1 The Expanded Programme on Immunization					12

3.2 Programme Structure									12

3.3 Routine Immunisation									12

3.3.1 Routine Immunisation Strategies and Schedule				12

3.3.2 Routine Immunization Coverage						13

3.4 Reaching Every District (RED) Approach						14

3.5 Populations at risk of missing immunisation services				14

3.6 Supplemental Immunization Activities (SIAs)					15

3.6.1 National Polio Immunization and Vitamin A 					Supplementation Days								15

3.6.2 National Measles Immunization and Vitamin A  Campaigns		15

3.7 Disease Surveillance									16

3.7.1 AFP Surveillance								16

3.7.2 Measles Surveillance								17

3.7.3 Neonatal Tetanus Surveillance						17

3.7.4 Haemophilus influenzae type b (Hib) Surveillance			18

3.8 Epidemic Preparedness and Disease Outbreak Response			18

3.8.1 Measles Outbreaks								18

3.8.2 Polio										19

3.8.3 Neonatal Tetanus								19

3.9 Trends of Morbidity and Mortality for EPI Target Diseases				19

3.10 Data management and EPI Reporting System					20

3.11 Vaccine Quality, Supply and Utilization						20

3.11.1 Vaccine Procurement and Distribution					20

3.11.2 Utilization of vaccines							21

3.12 Cold Chain										21

3.12.1 The National Vaccine Store						21

3.12.2 Cold Chain Equipment							21

3.13 Transport										22

3.14 Surveys and Assessments								22

3.14.1: Effective Vaccine Store Management 				    				 Assessment									22

3.14.2	Injection Safety and Health Care Waste 	Management			23

3.14.2.1 Injection Safety								23

3.14.2.2 Health Care Waste management 					24

3.15	EPI Comprehensive Review 2003							24

3.16	EPI Communication 								25

3.16.1	Advocacy									25

3.16.2	Social mobilization								25

3.16.3	Programme communication						25

3.16.4	Other partners working in EPI 	communication			25

  - Implementation of the EPI Comprehensive MYP 2006-2010		26

  - The National Health Strategic Plan and the cMYP				26

  - The EPI Programme in the Ministry of Health					27

  - Programme Goal									27

  - Programme Objectives 								27

  - Strategic Areas									28

  - Targets										28

  - Governance and Partnerships 							28

  - Monitoring and Evaluation								29

5.0	The Immunization System Components					30

5.1	Service Delivery									30

5.2	Vaccine Supply, Quality and Logistics						30

5.3	Disease Surveillance								31

5.4	Advocacy, Social Mobilization and Communication				31

5.5	Programme Management								32

6.0 Cost, budget and Financing for the cMYP					44

  - Methodology for costing the cMYP						44

  - Macroeconomic information							45

  - Vaccines and injection equipment							45

  - Personnel costs (EPI specific and shared)					45

  - Vehicles, and transport costs							46

  - Cold chain equipment, maintenance and overhead				46

  - Operational costs for campaigns							46

  - Program activities, other recurrent costs and surveillance			46

  - Other equipment needs and capital costs					47

  - Overhead costs									47

  - Costs for Immunization activities during the period for the cMYP		47

  - Financing for the program								49

  - Interventions to improve the financial viability of the program			51

6.13.1	Securing probable resources						52

6.13.2	Securing probable resources						52

Abbreviations

| AD | Autodisable syringes |
| --- | --- |
| AEFI | Adverse Events Following Immunisation |
| AFP | Acute Flaccid Paralysis |
| AFRO | WHO Regional Office for Africa |
| ARCC | African Region Certification Commission |
| BCG | Bacilli Calmette Guerin |
| CHAM | Christian Health Association of Malawi. |
| CHSU | Community Health Sciences Unit |
| CSF | Cerebrospinal Fluid |
| DFID | Department for International Development. |
| DHMT | District Health Management Team. |
| DHO | District Health Officer |
| DHS | Demographic Health Survey. |
| DPT | Diphtheria Pertussis and Tetanus vaccine |
| EHP | Essential Health Package. |
| EPI | Expanded Programme on Immunization. |
| GAVI | Global Alliance for Vaccines and Immunizations |
| GDP | Gross Domestic Product. |
| Hib | Haemophilus influenza type b |
| HIV | Human Immuno-Deficiency Virus. |
| HSA | Health Surveillance Assistant. |
| IEC | Information Education and Communication |
| IgM | Immunoglobulin type M |
| IMCI | Integrated Management of Childhood Illnesses. |
| IMR | Infant Mortality Rate. |
| JICA | Japan International Cooperation Agency |
| KFW | Germany Development Bank |
| MCH | Maternal and Child Health. |
| MDG | Millennium Development Goals |
| MK | Malawi Kwacha. |
| MMR | Maternal Mortality Rate. |
| MoH | Ministry of Health. |
| NCC | National Certification Committee |
| NGO | Non-Governmental Organization. |
| NIDs | National Immunisation Days |
| NNT | Neonatal tetanus |
| NPEC | National Polio Expert Committee |
| NSO | National Statistics Office. |
| OPD | Out-Patient Department. |
| OPV | Oral polio Vaccine |
| PEI | Polio Eradication Initiative |
| RED | Reaching Every District Approach |
| SIAs | Supplemental Immunisation Activities |
| SMC | Suspected Measles Case |
| SNIDs | Sub-national Immunisation Days |
| SWAp | Sector Wide Approach. |
| TA | Traditional Authority |
| TT | Tetanus Toxoid vaccine |
| UCI | Universal Childhood Immunization |
| UNICEF | United Nations Children’s Fund |
| UNHCR | United Nations High Commissioner for Refugees |
| USAID | United States Agency for International Development. |
| WHO | World Health Organization. |

Executive Summary

The Expanded Programme on Immunization in Malawi is part of the Essential Health Care Package.  Its overall goal is to increase access to immunisation services, provide effective and potent vaccines and increase demand for the services in order to reduce infant morbidity and mortality rates due to vaccine preventable diseases.

Malawi has made substantial progress in sustaining high routine immunisation coverage through existing health service delivery structures and quality National Immunisation Days for measles and polio. The country has also achieved a polio free status, measles and neonatal tetanus elimination phase. The main challenge is how sustain the achievements made so far while EPI integrating with other child health interventions and reach the children who need the services most.

This document presents an EPI comprehensive plan for 5 years, highlighting the national goals, objectives, and strategies derived from a situational analysis. The analysis was done using the MoH Joint Programme of Work, 2003 EPI Review for Malawi, administrative EPI data and annual EPI reports.  These reviews highlighted the strengths and some of the weaknesses in the programme such as high immunisation drop out rates, unsatisfactory supervision, inadequate knowledge and skills regarding EPI management systems; inconsistent distribution of supplies which resulted in vaccine stock outs in some facilities and limited integrated interventions on child health activities.

The strategic planning was carried out by immunization system components rather than by targeted disease or initiative. Major areas of focus include provision of services to hard-to-reach areas, introduction of new vaccines, integrated interventions aimed at reducing child morbidity and mortality and taking immunisation beyond the traditional infant group. The EPI Multi-Year Plan 2006-10 document represents the country’s main strategy to achieve the fourth Millennium Development Goal.

- The success of the programme largely depends on adequate financing for all proposed activities to be undertaken during the planning period. It will be the responsibility of the EPI through the interagency Coordinating Committee to ensure that the programme gets adequate financial and material support both locally and internationally.

- With the advent of the SWAp basket financing, many of the program sources of financing are now channelling their support through this mechanism, leading to a reduction in the overall number of program funders, and an increase in funding from the SWAp basket. For the SWAp funds, the program will have to continue advocating for additional resources from this source, given its impact on overall sector objectives.

The program will, as part of its regular monitoring process, monitor the trends in financing, to ensure it is moving towards improved financial sustainability by reducing its financing gaps, and converting more probable financing to secure financing.

1.0 Background Information

1.1 Geography

Malawi is a land locked country in East Central Africa.  It lies south of the equator and covers an area of about 118,500 square kilometers.  It is bordered by Tanzania to the North, Zambia to the west and Mozambique to the east, south and southeast.  A quarter of the surface area is covered by Lake Malawi.

The country is divided into three geographical regions, northern, central and southern regions with a total of 26 districts. Within each district there are local administrative divisions known as Traditional Authorities (TAs), which are headed by chiefs. The smallest administrative unit is a village headed by a village headman.

1.2 Demography

The country’s population for 2005 was projected at 12,341,170. Five percent (617,059) of the population is under one year; 48% (5,923,762) is under 15 years of age.  Eighty-six percent (10,613,406) of the population lives in the rural areas. About 80% (9,872,294) of the total population has access to formal health care services.  The literacy rate for females is 48.6% and 72.1% for males. For vital health statistics of Malawi see Table 1.

Table 1:	Vital Statistics for Malawi

| ### Statistic | Indicator |
| --- | --- |
| ###### Annual Growth Rate | 1.9% |
| Crude Birth Rate | 41.2 per 1000 |
| Crude Death Rate | 14.1 per 1000 |
| Total Fertility Rate | 6.0 children per woman |
| Infant Mortality Rate | 76 per 1000 live births |
| Under-five Mortality Rate | 133 per 1000 live births |
| Maternal Mortality Rate | 940 per 100, 000 live births |
| Male Life Expectancy at birth | 37 years |
| Female Life Expectancy at birth | 39 years |

Source:  DHS 2004

1.3 Socio-economic Status

Malawi is one of the poorest countries in the world with GNP per capita (US $170). The country still suffers from serious inequities in the distribution of income, with over sixty percent of the population living below the absolute poverty line. The country is also currently undergoing economic transformation, following a period of huge fiscal deficit, large current account imbalance, rapid inflation, and a fluctuating GDP.

Malawi’s economy is agriculture-based, both in terms of subsistence activity and the formal sector.  The formal sector is dominated by the export of tobacco, which has suffered from uncompetitive production, high export tariffs and declining world demand. Consequently, Malawi’s economic growth is significantly below the 5-6% required to deliver widespread welfare gains to the population. Aggregate growth is declining towards negligible levels; the low levels and slow growth of economic activity prevents both individuals and households from lifting themselves out of poverty, and constrains the Malawi government’s ability to deliver services that could reduce poverty.

The government budget is highly reliant on donor support. Domestic revenue generation is unlikely to improve in the near future due to the low tax base and small formal sector, reduced trade tariffs inline with SADC trade harmonization and overall weak economic performance.

2.0 Health Care Delivery Systems

2.1 Health services

The Ministry of Health offers a wide variety of health services accounting for 60% of the facilities.  The Christian Hospital Association of Malawi (CHAM) provides 37% of the health care services while private institutions provide 3%. The government assists CHAM by providing it with an annual grant that covers local staff salaries. CHAM facilities charge user fees for treatment, with the exception of the growth monitoring, immunization, and community-based preventive services including treatment of specific communicable diseases such as TB and Leprosy.

- At primary level, services are delivered through rural hospitals, health centres, health posts, outreach clinics and community initiatives such as Drug Revolving Funds. District and CHAM hospitals provide secondary level health care services although some have specialist functions. The secondary level mainly functions to back up the activities of the primary level. Tertiary level hospitals (central hospitals) provide specialized services and secondary level health care where they are no district hospitals. Immunization services are offered at all levels.

2.2 Policy of the Ministry of Health

The policy of the Ministry of Health is to raise the level of health status of all Malawians through the development of a health delivery system capable of promoting health, preventing, reducing disease burden, protecting life, and fostering the general well-being and increased productivity, and reducing the occurrence of premature death.

The following is the vision and mission statement for the ministry of health:

Vision

To improve the health status of all Malawians through the provision of effective, efficient and safe health care (Vision 2020, 1999).

Mission

To stabilize and improve the health status of Malawians by improving access, quantity, cost-effectiveness and quality of the Essential Health Package (EHP) and related services so as to alleviate the suffering caused by illness, and promoting good health, thereby contributing to poverty reduction.

Malawi Government has made a policy to decentralize health services to District Assemblies as the local governance structures. The new Government Policy on decentralization is aimed at devolving administrative authority to the district level.  Government agencies at district and local levels will become one administrative unit, through the process of institutional integration, manpower absorption, composite budgeting and provision of funds.

District Assemblies will assume decision-making responsibility at district level.  This will necessitate direct budgetary allocation to the districts thus making District Health Management Teams (DHMTs) in turn to be accountable to the District Assemblies for decisions on financial planning and expenditures. The introduction of accountable and earmarked health grants to the District Assemblies will allow for some sector coherence although it may be difficult to immediately improve financial management. The development of standards, norms and accreditation systems based on the Essential Health Package (EHP) make it easy for the District Assemblies to be made accountable for the quantity and quality of services they provide. This arrangement also makes it easy to maintain some national consistency in the quality of care across District Assemblies. The introduction and implementation of the EHP is thus a convenient modality for such accountability to be achieved.

2.3 	Sector Wide Approach (SWAp)

The Sector-Wide Approach (SWAps) arose from the May 2000 Consultative Group (CG) meetings between the government and development partners. The SWAp has established several joint processes in terms of planning, funding and procurement and monitoring and review, and has adopted a single plan of action for the sector as a whole to implement. A broad range of stakeholders including development partners and NGOs has been brought onboard to implement this plan, with the overall process being driven by government.

The SWAp has considerable efficiency and equity gains for Malawi’s health service. Efficiency will increase as the transaction costs of utilizing and monitoring various sources of financial support fall, and joint planning ensures that duplication of service provision is minimized. Equity will improve as stakeholder coordination and resource allocation become systematic.

There will be some short-term risks to vertical service delivery structures, such as the immunization programme, as the SWAp develops. There will have to be a careful process of change management to ensure that individual MOH “success stories” (such as the EPI programme) are not eroded as the overall health system improves its performance. In the longer term, the improved efficiency and equity of health sector support, combined with the prospect of a greater totality of resources, will benefit immunization services, as it will the overall health system.

2.4 Essential Health Package (EHP)

- The Malawi EHP focuses on those conditions and service gaps that disproportionately affect the health of the poor and disadvantaged populations. The government has made a policy decision that the EHP services will be provided free of charge at the point delivery. This is in line with the Malawi Poverty Reduction Strategy Paper. Because the government of Malawi is experiencing a mismatch between health resources, health needs and demands for health care, it has become necessary to provide only a limited but effective range of priority services that the country can afford rather than provide all services, which at the end of the day are of poor quality.

- The EHP consists of a group of cost-effective and proven interventions which are combined and delivered together so as to reduce the cost to patients. This type of packaging of health services combines those services that can be delivered within the same facility and using the same level of technology. EHP is orientated around the 11 conditions that predominantly affect the rural poor. The majority of these conditions are preventable and communicable diseases, and thus non-treatment incurs societal costs, as well as costs to the individual.  To effectively standardize services, and move them closer to the client, the EHP envisages a massive expansion of the community level of health delivery; with for example one Health Surveillance Assistant (HSA) per 1,000 of the population, and for limited drug disbursement to occur at this level.

2.5	Human Resources

The coverage and quality of health services has been adversely affected by shortages of staff the facility level. It has been estimated that vacancies on established posts are up to 50% at some institutions. Whilst public health facilities are highly regarded, traditional healers often play a significant role in many peoples’ lives, especially those communities who live very far from health facilities. Some of the main challenges facing the sector are ensuring that adequate numbers of the various health workers are trained and how to ensure retention of all its trained workers.

3.0 Situational Analysis

3.1 The Expanded Programme on Immunization

The Malawi Expanded Programme on Immunization (EPI) was officially launched in 1979 and is integrated within the Preventive Health Services network as part of the Essential Health Package (EHP) and though presently runs as a vertical programme.

3.2 Programme Structure

At the central level, the programme is managed by the EPI Manager and assisted by a logistics Officer, Data Officer and Vaccine Stores Officer/Cold Chain Officer.  The Regional EPI Officers in the North and South are responsible for coordinating EPI activities in their respective regions and assisted by the Regional Cold Chain Technicians. In each district there are two EPI Coordinators assisted by Cold Chain Technicians who are responsible for control and allocation of supplies to health facilities.  At health centre level, all health workers participate in EPI activities.  Immunization activities are carried out along with growth monitoring, nutrition and antenatal care throughout the country.

3.3 Routine Immunisation

The programme currently offers measles, DPT-HepB+Hib, Polio, BCG and TT vaccines. Vitamin A supplementation is also administered alongside immunization services. Traditionally, the programme has been heavily dependent on collaborating partners and donors for procurement of vaccines, cold chain supplies and other logistics. These partners include UNICEF, WHO, GAVI, KFW, DFID, JICA, and Rotary International among others. All these organizations support Sector Wide Approach (SWAp) that has been introduced in Malawi.

In January 2002, Malawi introduced Hepatitis B and Haemophilus influenzae type b (Hib) vaccine into its routine immunization programme, in a pentavalent formulation (DPT-HepB+Hib) with support from the Global Alliance of Vaccines and Immunizations (GAVI) for a period of five years.  The government of Malawi has agreed with GAVI to bridge the financing of new vaccine in the second phase of GAVI support with an annual contribution of 20%.  The Ministry of Health is to submit its application to GAVI Secretariat for Immunization Strengthening Support (ISS) and Health Systems Support (HSS).

3.3.1 Routine Immunisation Strategies and Schedule

Measles, DPT-HepB+Hib, OPV and BCG vaccines are given to children under one year of age and tetanus toxoid vaccine to pregnant women and women of child bearing age (Table 2). Vitamin A capsules are routinely administered to children from 6 months up to 59 months at an interval of 6 months as well as postnatal mothers within two weeks of delivery.  These immunization services are presently delivered in about 710 static clinics and 3,096 outreach clinics.

Table 2: Malawi Immunization and Vitamin A

Supplementation Schedule

| Age | Vaccine |
| --- | --- |
| At birth or first contact | BCG |
| At birth up to 2 weeks | OPV ‘0’ |
| At 6 weeks | OPV 1 and DPT-HepB+Hib 1 |
| At 10 weeks | OPV 2 and DPT-HepB+Hib 2 |
| At 14 weeks | OPV 3 and DPT-HepB+Hib 3 |
| At 9 months | Measles |
| First contact (15-45 yrs and Pregnant women) | TT 1 |
| At 4 weeks after TT1 | TT 2 |
| At 6 months after TT2 | TT 3 |
| At 1 yr after TT3 | TT 4 |
| At 1 yr after TT 4 | TT 5 |
| At 6 months and every 6 months up to 59 months | Vitamin A (children) |
| Within two weeks of delivery | Vitamin A (post natal mothers) |

3.3.2 Routine Immunization Coverage

High routine immunization coverage for all childhood immunizations has been sustained since 2001 (table 4). The drop in immunization coverage in the year 2002 is considered to be due to change of target population from 4% to 5% for under ones, and changing of reporting system of Health Information Management System (HIMS) which led to loss of some coverage data. The EPI programme reverted back to vertical reporting system. Tetanus Toxoid (TT) vaccination coverage in pregnant women has however been maintained between 60-70%. Malawi introduced the new vaccine DPT-HepB+Hib in 2002 and the coverage for DPT3 from 2002 to 2005 is for DPT-HepB+Hib3

Figure 1	 Routine Immunization Coverage for Malawi: 2001- 2005

3.4 Reaching Every District (RED) Approach

The Ministry of Health and its partners are looking at innovations to improve routine EPI activities with the effort to meet the fourth millennium development goal (MDG). National and Regional EPI staff underwent training on RED Approach organized by WHO in December 2003. Micro-planning tools with emphasis at health centre levels were reviewed and some modifications were made. Malawi started implementing RED activities in 2005 in eight districts with DPT-HepB+Hib3 and measles coverage <80%. RED Approach training cascaded to District Health Management Teams (DHMT) and Health centre staff. Districts trained in RED approach were Chitipa, Mzimba, Kasungu, Ntchisi, Nkhotakota, Salima, Lilongwe, and Chiradzulu.

3.5 Populations at risk of missing immunisation services

###### Some religious groups for example Zion and Apostolic sects do not allow their members to have vaccination. The location of these religious groups are scattered all over the country and are a minority. Refugees and migrants in some parts of the country pose a potential threat for vaccine preventable disease outbreaks since their immunization status may not be known. There are also groups of people residing in hard to reach areas some of these are identified and planned for special strategies (table 3).

Table 3: Areas identified with children at risk of missing routine immunisations

| Group | Size of group | Location of group | Action taken to improve coverage |
| --- | --- | --- | --- |
| Refugees | 1,900 | Luwani (Mwanza) | Health centres were established at Luwani and Dzaleka by UNHCR and supervised by District Health Officer. All new arrivals at the camp are reported to the health facility. There are village health committees at each camp. |
|  | 9,773 | Dzaleka (Dowa) |  |
| Other migrants | No data | Urban areas (Lilongwe, Mzuzu, Blantyre, Zomba) | ###### They use existing health facilities |
| Religious groups (Zion, Apostolic) | No data | Scattered | Use of traditional and political leaders to persuade to take children for vaccinations |
| Hard to reach groups | No data | e.g. Kabuwa in Mzimba, Nyachikadza Swamps in Nsanje, Chisi island on Lake Chilwa Some forest and game reserve areas | Use of speed boats for outreach clinics Strengthening of transport mechanism |

3.6 Supplemental Immunization Activities (SIAs)

3.6.1 National Polio Immunization and Vitamin A Supplementation Days

Malawi conducted the first Polio National Immunization Days (NIDs) in 1996, as an effort to contribute to the global goal of polio eradication initiative. This was followed by other NIDs in 1997 and Sub-National Immunization Days (SNIDs) in 1999.  Vitamin A supplementation was administered in 1996 NIDs and 1999 SNIDs. Table 7 shows immunization and vitamin A coverage.

Table 4 	Polio and Vitamin A NIDs Coverage

| Year | Target Pop | ## Polio |  |  |  | Target Pop. | ## Vitamin A |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Round 1 |  | Round 2 |  |  | Round 1 |  | Round 2 |  |
|  |  | Doses | Cov. % | Doses | Cov % |  | Doses | Cov % | Doses | Cov % |
| 1996 | 2,040,152 | 1,348,799 | 66 | 1,566,308 | 78 | 1,916,262 | 1,177,693 | 61 | 1,368,406 | 71% |
| 1997 | 1,858,338 | 1,773,964 | 96 | 2,032,513 | 109 |  |  |  |  |  |
| 1999 SNIDs | 397,809 | 417,101 | 104 | 426,995 | 107 | 350,783 | 377,192 | 107 | 356,120 | 101 |

3.6.2 National Measles Immunization and Vitamin A Campaigns

In 1998, the strategy of providing a “second opportunity” through supplemental immunization was adopted and a nation-wide catch-up campaign targeting children from 9 months to 15 years was successfully conducted achieving coverage over 90%. This resulted in a remarkable reduction in measles incidence, and thus case-based surveillance was instituted in 1999. Sub –national Immunisation Days (SNIDs) were done in 1999 in urban areas of Mzuzu, Lilongwe, Blantyre and Zomba.

A nationwide follow-up campaign targeting children 9 to 59 months was conducted in 2002, with coverage over 95 %. A second follow-up national Measles Supplemental Immunisation Activities was conducted in September 2005 targeting 9 to 59 month old children (table 5).

Table 5: Measles NIDS and Vitamin A Supplementation Coverage

| YEAR | Measles Coverage |  |  | Vitamin A Coverage |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Target Pop | Doses given | % Cov | Target Pop | Doses Given | % Cov |
| 1998 NIDs | 4,179,229 | 4,747.452 | 114 | 1,609,075 | 1,892,714 | 118 |
| 1999 SNIDs | 156,154 | 153,073 | 98 | 156,154 | 153,496 | 98 |
| 2002 SIAs | 1,585,207 | 1,908,645 | 120 | 1,585,207 | 1,843,948 | 116 |
| 2005 SIAs | 1,851,176 | 2,118,950 | 114 | 1,851,176 | 2,029,220 | 110 |

3.7 Disease Surveillance

From community level, Health Surveillance Assistants (HSAs) facilitate case detection, specimen collection and transportation of specimens to health centres. At health centre level there are trained focal persons who are charged with surveillance activities. These are supervised by District MCH Coordinators. Case detection and reporting is done at community, health centres, district hospitals and central hospitals. Case investigation including stool collection is carried out by the health unit focal point. As soon as a case is detected, communication is made to the district, region and national level. Transport is arranged at regional level to collect specimens and deliver to the EPI Unit that in turn sends

- AFP stool specimens to WHO accredited laboratory in Harare, Zimbabwe.

- Measles blood specimens to Kamuzu Central Hospital Measles laboratory.

The EPI programme has adopted the integrated approach to surveillance activities regarding the three priority conditions: measles, NNT and AFP.

3.7.1 AFP Surveillance

Malawi has made substantial progress towards polio eradication, with improved OPV coverage, quality National Immunisation Days (NIDs) in 1998 and 1999, and strengthened routine surveillance activities. The last clinically confirmed case of polio was reported in 1992. Stool specimens are sent to the WHO accredited laboratory in Harare, Zimbabwe.

Malawi has maintained certification quality surveillance by detecting at least one case of AFP per 100,000 populations of children under fifteen and collecting at least 80% stool specimens within 14 days of onset of paralysis (Table 8). African Region Certification Commission (ARCC) accepted Malawi’s Polio documentation on polio free status in October 2005.

In order to increase AFP surveillance sensitivity, WHO has revised the target upward to 2 AFP cases per 100,000 under fifteen years population due to resurgence of wild poliovirus in other African countries. Accordingly, health worker briefings on detection, investigation, and reporting of AFP cases are ongoing.  At each admitting health facility, a focal person has been assigned to check in the admission registers for AFP on a weekly basis.

Table 6: AFP surveillance performance in Malawi from 2000

| Year | Expected Number of non-polio AFP cases | Total AFP cases reported | No of confirmed polio cases | Total non-polio cases reported | Non-polio AFP rate* | AFP cases with adequate stool samples % |
| --- | --- | --- | --- | --- | --- | --- |
| 2005 | 55 | 72 | 0 | 72 | 1.3 | 83 |
| 2004 | 54 | 76 | 0 | 76 | 1.4 | 88 |
| 2003 | 52 | 67 | 0 | 67 | 1.2 | 91 |
| 2002 | 51 | 70 | 0 | 70 | 1.3 | 84 |
| 2001 | 50 | 67 | 0 | 67 | 1.3 | 88 |
| 2000 | 49 | 103 | 0 | 103 | 2.1 | 83 |

*Based on 1 case per 100,000 population aged less than 15 years

3.7.2 Measles Surveillance

Malawi set itself a goal of measles elimination by the year 2003. In the early 1990s, Malawi was experiencing significantly high morbidity and mortality due to measles (fig 2). A decline in measles incidence has been observed after the 1998 catch up campaign. In 1999, case based surveillance was introduced. Malawi is in the elimination phase and the 2005 measles case detection rate was 1.5 per 100,000 population.

3.7.3 Neonatal Tetanus Surveillance

# Malawi achieved neonatal tetanus (NNT) elimination status in 2002 through Lot Quality Assurance assessment (LQA) and this has been maintained. In 2004 eight cases of NNT were reported, representing an incidence rate of 0.02/1,000 live births and in 2005, six cases of NNT were reported; representing an incidence rate of about 0.01/1,000 live births.  Training of health workers in detection, investigation and reporting of any single case of NNT using investigation form is ongoing. All neonatal deaths with unknown cause were investigated within 48 hours of notification.

3.7.4 Haemophilus influenzae type b (Hib) Surveillance

The Paediatric Bacterial Meningitis - Haemophilus influenzae (PBM-Hib) surveillance site, located at Queen Elizabeth Central Hospital (QECH) was established in November 2001 to monitor trends in Hib meningitis among under five children presenting with meningitis in order to assess the impact of the pentavalent vaccine.

Figure 3:

Surveillance data have shown that Hib meningitis trends have decreased dramatically in post introduction era of pentavalent vaccine (Refer fig. 3) In 2005, seven cases of Haemophilus influenzae type B meningitis were reported where as in 2004, 14 cases were reported in under five children at the sentinel site.

3.8 Epidemic Preparedness and Disease Outbreak Response

3.8.1 Measles Outbreaks

The country experienced sporadic measles outbreaks from November 2003 to December 2004 and a total of 1141 cases were reported. Outbreak response was conducted in affected areas but the outbreak continued spreading. In response to the outbreak a national follow up campaign scheduled for 2006 was done in 2005 targeting children aged 9 to 59 months with coverage of 114 %. Vitamin A was also administered during the campaign with coverage of 110 %.

3.8.2 Polio

## In order to rapidly detect and respond to polio outbreak, Malawi has a Polio Preparedness Plan. The objective of the plan is to detect wild poliovirus importation early and mount an appropriate containment of the wild poliovirus. Health workers are briefed on detection, investigation and reporting of AFP cases. In each admitting health facility, there is a trained disease surveillance focal point who reviews all hospital admission registers weekly. Each single case of AFP is considered as potential polio outbreak.

3.8.3 Neonatal Tetanus

Health workers are trained in detection, investigation and reporting of any single case of NNT using a standard case investigation form. All neonatal deaths with unknown cause are investigated within 48 hours. Upon clinical confirmation of an NNT case, supplemental immunization activity is carried out to all women of childbearing age living in the affected and surrounding areas regardless of their TT immunization status.

3.9 Trends of Morbidity and Mortality for EPI Target Diseases

In general there has been a decline in the incidence of all EPI target diseases in Malawi namely polio, measles, and neonatal tetanus (Table 7). This is partly attributable to high population immunity as a result of high routine immunisation coverage over a period of time.

Table 7   Trends of Morbidity and Mortality for Measles, Polio and NNT:  2001 - 2005

| DISEASE | Measles |  | Polio |  | NNT |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Suspected Cases | Deaths | Cases | Deaths | Cases | Deaths |
| 2001 | 150 | 0 | 0 | 0 | 15 | 15 |
| 2002 | 92 | 0 | 0 | 0 | 7 | 7 |
| 2003 | 167 | 0 | 0 | 0 | 7 | 7 |
| 2004 | 1,141 | 32 | 0 | 0 | 8 | 8 |
| 2005 | 184 | 0 | 0 | 0 | 6 | 6 |

3.10 Data management and EPI Reporting System

Routine immunisation and disease surveillance data are reported on a monthly basis except AFP data, which are reported on a weekly basis.  Reports are sent from health facilities to districts where the information is consolidated and sent to EPI Unit and Health Management Information System Unit using existing report forms. Each district monitors completeness and timeliness of all the reports received from every reporting unit within the district.  Both the district and health center report forms analyse immunization coverage, vaccine wastage rate and disease surveillance data. Periodically, surveys are conducted to ascertain the validity of the administrative data.

Surveillance data is used in designing and formulating programme plan of action as well as identification of weaknesses and strengths at various stages of implementation of EPI services in the country. Feedback to the districts is given through:

- Monthly active search

- Quarterly supportive supervisory using checklist

- EPI quarterly evaluation meetings

- Annual review meetings with District MCH Coordinators.

3.11 Vaccine Quality, Supply and Utilization

3.11.1 Vaccine Procurement and Distribution

The EPI Unit does forecasting and ordering of vaccines and supplies while procurement is done through UNICEF.  All traditional vaccines were being funded by various donors such as UNICEF, KFW, DFID, Rotary International, JICA and DPT-HepB+Hib vaccine is funded by GAVI.

Currently there is no National Regularly Authority (NRA) that is responsible for monitoring quality and safety of vaccines that arrive in the country. However, there is a Pharmacy, Medicines and Poisons Board (PMPB) that is anticipated to take the roles of NRA and will therefore be involved in vaccine quality and safety issues in the near future.

The distribution of the vaccines is done on a quarterly basis to regional vaccine stores. District Health Offices collect vaccines from regional vaccine stores and distribute monthly to health facilities.

There have been no vaccine stock-outs at national level since 2001 except in some health facilities due to irrational distribution.

3.11.2 Utilization of vaccines

Malawi introduced vaccine wastage surveillance in 2004 in 80 selected sentinel sites. The study also included 8 storage facilities (districts) and two regional vaccine stores in Mzuzu and Blantyre. The results show that wastage rate for DPT-HepB+Hib was 4% as opposed to 10% indicative wastage rate estimated by GAVI.

The vaccine wastage surveillance system is to be extended to all health facility by integrating it into routine reporting. Current reporting forms will be modified to accommodate parameters in the study report forms.

3.12 Cold Chain

3.12.1 The National Vaccine Store

A National Vaccine Storeroom is located in Lilongwe and has two chambers for storing vaccines. The cold room has a capacity of 43 cubic metre gross and a 17 cubic metre gross freezer room.  Both are fitted with twin refrigeration units, continuous chart recorders and a temperature alarm system that requires maintenance. There is a 50 KWA standby generator with automatic changeover.

The two chamber cold room and freezer room were constructed before the introduction of the new vaccine, DPT-HepB-Hib vaccine which is very much bulkier than the old multi-dose DPT presentation.  As a consequence of this, there have been times when both the cold room and the freezer room are overloaded despite the current changed delivery system. Addition cold room and freezer room are therefore needed at national level.

In addition to vaccines, the National Store stocks syringes and safety boxes supplied under the GAVI bundling policy and those procured by other donors.  It also stocks cold chain spare parts.

The regional vaccine store in Blantyre in the south is served with a small cold room, refrigerators and freezers whose capacity is not adequate for the population it is serving. The vaccine storeroom in Mzuzu in the northern region is similarly not adequate. Refrigerators and deep freezers are being used for storing vaccine.  Currently, districts from central region collect vaccines and other supplies from the national vaccine store. There is need to construct a regional vaccine storeroom for central region.

3.12.2 Cold Chain Equipment

The programme refurbished its cold chain equipment with funds from JICA and DFID in 2001. Most health centers were then supplied with new refrigerators and these are due for replacement. The source of energy for deep freezers and refrigerators varies from electricity, gas, kerosene and solar. Most of the districts in the southern region use gas due to its proximity to a gas plant in Blantyre.

Table 8	Percentage of Source of energy for refrigerators by region as of December 2005

| Region | Total Fridges | Kerosene |  | Gas |  | Electricity |  | Solar Energy |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. | % | No. | % | No. | % | No. | % |
| 1. North | 199 | 127 | 64 | 1 | 1 | 63 | 32 | 8 | 4 |
| 2. Centre | 443 | 61 | 14 | 117 | 26 | 203 | 46 | 62 | 14 |
| 3. South | 772 | 5 | 0.6 | 217 | 28 | 495 | 64 | 55 | 7 |
| National | 1414 | 193 | 14 | 335 | 24 | 761 | 54 | 141 | 10 |

3.13	Transport

From 2001 to 2005, KFW, JICA and DFID have donated vehicles, motorcycles and bicycles to all the districts in country through UNICEF.  These operate in a pool system within the district.  The motorcycles are also used for supervisory visits, distribution of vaccines and accessing outreach clinics.  Bicycles are mostly used for outreach clinics.  UNICEF donated boats for two districts, Nkhata Bay and Zomba. The District Health Officers (DHOs) are responsible for maintenance of vehicles, motorcycles and bicycles. Due to poor rood infrastructure in some districts contributing to wear and tear and inequitable distribution of the vehicles across the country, the need for regular replacement for the vehicles cannot be overemphasized.

3.14	 Surveys and Assessments

3.14.1: Effective Vaccine Store Management Assessment

An Effective Vaccine Store Management Assessment conducted in 2003 found the following:

Management Weaknesses

- The current delivery schedule for both vaccines and bundled injection is causing excessive overloading of the available cold chain equipment and dry goods warehousing

- There are failures of stock control and stock management which mean that the stock records do not accurately reflect physical counts

- Overstocking of the dry goods means that effective stock control and EEFO management of syringes is extremely difficult

Significant issues affecting Buildings and Equipment

- Temperature excursions in the cold room and freezer room appear to have been unacceptably severe for a significant portion of the review

- There is need for additional cold room capacity

- There is need for additional dry goods warehousing

- The existing cold room and freezer room should be fitted with a voltage regulator/surge protector

- Freezer-sensitive vaccine in the Central regional Store is being exposed to unnecessary risk because ice-lined refrigerators are not fitted with the vaccine storage baskets that are supplied with the equipment

3.14.2	Injection Safety and Health Care Waste Management

3.14.2.1	Injection Safety

A comprehensive injection safety assessment in Malawi was conducted by WHO/UNICEF in 2002 and major weaknesses were noted on safe injection practices and waste management. The assessment looked at injection safety issues both in preventive and curative services.

Main findings of Injection Safety Assessment

# Weaknesses

Injection Safety

- Inadequate infection control practices

- Overfilling of safety boxes

- Placing of needles in unsafe containers

- Unsafe storage of full safety boxes or other containers

Waste Management

- Inadequate sharps waste treatment facilities

- Organisation and health care waste collection are deficient

- Inadequate financial resources allocated to health care waste management

- Lack of public awareness about risk associated with health care waste

- Private providers not involved in health care waste management

The EPI programme adopted the new policy of using autodisable syringes in routine and supplemental vaccination in 2002.  Following the assessment on safe injection, a comprehensive safe injection policy and Strategic Plan has been developed and put in place and covers the following areas:

- Implementation frameworks which look at improving institutional and legal framework;

- Training and capacity building which looks at improving health care skills at all levels;

- Behaviour change intervention which looks at achieving safe injection practices, preventing injection overuse and raising public awareness on injection safety;

- Equipment and supplies which looks at protecting health workers from unsafe injections, providing sterile injection equipment and ensuring that injection safety equipment is available in all health facilities at all times;

- Sharps waste disposal, which looks at integrating sharps waste management into a comprehensive national health care waste management.

3.14.2.2	Health Care Waste management

## The Ministry of Health has in addition to safe injection policy, also developed a health care waste management policy and Strategic Plan with the following key areas:

- Institutional and legal framework

- Capacity building

- Information, Education and Communication.

- Appropriate technology of health care waste management

- Waste storage

- Waste transportation.

- Health care waste minimization and re-use.

- Public private partnership

The disposal of autodisable syringes in EPI programme is done by incineration at health facilities where incinerators are available.  At health facilities where incinerators are not available and at outreach clinics, safety boxes are burnt on spot and the remains thrown in a designated pit latrine. Most district hospital and health facilities do not have incinerators or functioning incinerators. This poses a big challenge in view of the amount of waste generated through the immunization programme with the introduction of AD syringes.

3.15	EPI Comprehensive Review 2003

###### In 2003 a comprehensive EPI review was conducted to identify the achievements and constraints facing the EPI programme and come up with recommendations for effective programme management. The main areas reviewed were EPI service delivery, disease surveillance, information education and communication, and vaccination coverage.

While the assessment noted some achievements over the past three years, there were some weaknesses as follows:

- Service delivery

- Vaccination tallying was done before the child is vaccinated in some facilities.

- Poor documentation of vitamin A supplementation for post-natal mothers.

- Booking system for vaccinations resulted into high missed opportunities in some health centers

- Institutional and human capacity most prominently at peripheral level.

  - In some health facilities, there was lack of compliance to national policy of checking for BCG scar and following recommended immunization schedule

The review recommended the following:

- Institutional and human capacity be strengthened in particular at health centre levels.

- Refresher courses on EPI be conducted periodically in order to improve knowledge and skills of health workers.

- District Health Management Teams should ensure that vaccines, injection materials and fuel for refrigerators are distributed timely to all health centres and that supervisory visits are conducted regularly to health centres.

- Health workers should be reminded to adhere to stipulated EPI policies.

- All health facilities should analyze immunization data against vaccine used during that period.

3.16	EPI Communication

Currently there is no document that outlines communication strategies for EPI routine and supplemental activities. For routine immunization there is no permanent committee, unlike in the supplemental immunization activities (SIAs) where committees to oversee issues such as material production conduct preparatory activities. These committees cease operations with the cessation of the supplemental immunization activities.

3.16.1	Advocacy

The Interagency Coordinating Committee (ICC) on EPI comprises MOH, WHO, UNICEF, JICA, DFID, Norwegian Embassy and USAID. The ICC is the major organ responsible for EPI resource mobilization in addition to resources made available for activities funded through the SWAp. Various leaders such as political, traditional, religious, etc were advocated to about the SIAs and eventually some of them were involved in message formation and dissemination. At lower, partnerships exist with other government sectors and the civil society.

3.16.2	Social mobilization

Communities are mobilized to participate in EPI activities using community health workers and traditional institutions such as Village Health Committees and volunteers. Health programmes aired on the radio and TV include Dokotala wapa wailesi, Umoyo, Umoyo wa Mtundu Wathu, Dziwani za TB, Uku Ndiko Kudya, and others.

3.16.3	Programme communication

Communication materials for routine immunisation, surveillance and supplemental activities are available in health facilities in form of posters, leaflet, fact sheets, manuals, training guides and immunization schedule charts.  In addition drama shows, traditional dances and health talks are used to disseminate EPI messages.

3.16.4	Other partners working in EPI communication

Several partners have been working closely with EPI in health communications.  Examples include the print and electronic media; NGOs who are conducting health related activities, traditional and political leaders, faith-based communities, and other extension workers in various government departments.

The print media is inconsistent in its coverage of health issues, as they depend on sponsors and editorial interests. The print media in Malawi usually uses English as a medium of communication, which is a disadvantage to most Malawians since the majority cannot read and/or understand English.

The other problem is that the papers are circulated only in urban and peri-urban areas. The majority of Malawians cannot afford to buy the papers. The only paper that is circulated widely free of charge in the rural areas is Boma Lathu, which is published by the Department of Information. This one covers mainly developmental issues and sometimes health issues in vernacular. However, due to problems in funding there are difficulties sometimes in distribution of the paper to rural areas. However there is inadequate data in EPI health communications activities in the country.

- Implementation of the EPI Comprehensive MYP 2006-2010

4.1 The National Health Strategic Plan and the cMYP

The National Health Strategic Plan, referred to as a joint Programme of Work (POW) for the Health Sector Wide Approach, was developed through a consultative process and consolidation of the work programs from the various programs and central Ministry of Health (MoH) departments in 2004. This POW follows the fourth National Health Plan 1999-2004 and covers a six-year period, July 2004 – June 2010. The MoH has adopted the Sector Wide Approach to health development as the overarching strategy for the implementation of the POW.

The POW outlines the strategic direction the health sector is following to operationalise different program areas, including immunization. The prevention and treatment of Vaccine Preventable Diseases is outlined as the first key intervention for the sector to implement during this time period.

This Comprehensive Multi Year Plan is a further elaboration of this intervention. In here, the sector details out, for the time period of the overall strategic plan,

- The interventions, and activities the sector will focus on with regard to actualizing its strategy regarding Vaccine Preventable Diseases from 2006 to 2010, the last year of the Joint Program of Work

- The resource implications of these interventions, and activities for the health sector

- Sources of financing for the interventions, with resource gaps

The cMYP will therefore guide the activities, and investment decisions in immunization activities of Government, and immunization partners over the remaining years of the Joint Program of Work. It acts as the sector-fundable document for immunization related activities. The actual implementation will be elaborated in the annual implementation plans for the sector. These detail actual activities to be carried out for the respective immunization interventions outlined in this cMYP, within the framework of the overall expected resource envelope for the respective year. Immunization activities in this plan shall be elaborated in line with implementing the interventions as outlined in this cMYP. Each Annual implementation Plan shall be a ‘slice’ of this cMYP. This relationship is outlined in the figure below.

|  | 2004/05 | 2005/06 | 2006/07 | 2007/08 | 2008/09 | 2009/10 |
| --- | --- | --- | --- | --- | --- | --- |
| Joint Program of Work |  |  |  |  |  |  |
| Immunization cMYP |  |  |  |  |  |  |
| Annual Implementation Plan | AIP 1 | AIP 2 | AIP 3 | AIP 4 | AIP 5 | AIP 6 |

  - The EPI Programme in the Ministry of Health

The EPI programme falls within the Directorate of Preventive Health Services of MoH. The programme has developed a programme-specific strategic plan based on the priorities referred to in the POW. The planning was further guided by evidence gathered through various assessments and programme reviews over the last three years. This process has been enriched by a financial analysis and costing of the plan to apportion available funds and highlight funding gaps. Covering the period 2006-2010, the comprehensive EPI multi-year plan focuses on the main components of the immunization systems with key strategies and activities aimed at addressing national priorities identified by MoH and supplemented by a thorough programme-based situation analysis. In each of the next five years beginning with 2006, annual EPI Plans will be derived from this strategic plan.

  - Programme Goal

The overall focus of the immunization activities is to actualize the intervention to prevent Vaccine Preventable Diseases, as outlined in the Joint Program of Work. This is elaborated in the program goal, which is to increase access to immunisation services, provide effective and potent vaccines and increase demand for the services in order to reduce infant morbidity and mortality rates due to vaccine preventable diseases.

  - Programme Objectives

- To fully immunize infants against childhood immunisable diseases before attaining the age of 12 months

- To vaccinate all pregnant women and women of childbearing with at least two doses of tetanus toxoid vaccine

- To sustain high community awareness on the importance of completing the immunization schedule

  - Strategic Areas

The 2006-2010 Comprehensive EPI Plan shall be implemented within the framework of Global Immunization Vision and Strategies (GIVS) in the four main strategic areas namely:

i)	     Protecting more people

ii)	     Introducing new vaccines and technologies

- Integrating immunization, other linked health interventions, and             surveillance in the health systems context

iv)	     Immunizing in a context of global interdependence

Activities for the above areas have been outlined within the immunization system components summarized as:

- Service Delivery

- Vaccine Supply, Quality and Logistics

- Disease Surveillance

- Advocacy, Social Mobilization and Communication

- Programme Management

  - Targets

Each component of the system has a set of planned activities with different targets for each year up to 2010. These targets have been outlined in tables 9 and 10 that are to be accomplished in order to achieve the objectives.

  - Governance and Partnerships

The Joint POW will be implemented on the basis of the SWAp guided and governed by a code of conduct and Memorandum of Understanding amongst the stakeholders. The implementation of the POW will be guided through Annual Work Plans, which are   based on activities outlined in the District Implementation Plans (DIPs) and Annual Work Programs for Central MoH Departments. The cMYP will be used to develop Annual Work Programmes for EPI.

Coordination of partners is done through the Inter-agency Coordination Committee (ICC). The ICC is chaired by MoH and comprises WHO, UNICEF, DFID, NORAD, JICA and USAID, and meets quarterly.  Recently the SWAp Secretariat was incorporated into the ICC.

The ICC was briefed about the development of the cMYP and monitored progress on its development. Both the ICC and the SWAp Secretariat will be monitoring the implementation of the plan on an annual basis. In addition, the ICC is particularly competent to play an advocacy role in the implementation of the plan.

  - Monitoring and Evaluation

The monitoring and evaluation framework for cMYP will be based on annual joint reviews involving all the stakeholders of the plan.  A monitoring framework will be developed and implemented, accompanied by a set of indicators to monitor the performance of the cMYP.  An evaluation will be done at expiry of the cMYP in 2010.

5.0	The Immunization System Components

5.1	Service Delivery

In the next five years, the programme will endeavor to sustain the gains made over the years by providing quality immunization services. In Malawi, a significant proportion of the immunizations take place in outreach clinics and the programme will ensure that the outreach strategy is sustained and where need arise, new outreach clinics will be opened in some health facilities. In hard to reach areas, catch up campaigns will be proposed and planned locally.  The current population at risk that is scattered in refugee camps and other places all over deserve a special attention and immunization campaigns will be conducted if justifiable.

Capacity building is one component that has to be strengthened at all levels. Health workers trainings on MLM and RED will be conducted to improve their managerial skills that will in turn impact on issues such as reduction on drop-out rate, safe injection and waste management, missed opportunities etc.

5.2	Vaccine Supply, Quality and Logistics

The EPI programme will ensure that adequate vaccines bundled with injection materials are procured through WHO/UNICEF approved mechanisms. Through ICC and SWAp, procurement of vaccines and other logistics will be prioritized to avoid disruption of the services. The current storage capacities for both vaccines and dry store materials at national and regional vaccine stores will be expanded to be in line with the growing population.  It is also planned to introduce computerized stock management system in the three regional vaccine storerooms to improve management of vaccines and injection materials and this will require procurement of computers and accessories. The programme will conduct re-assessment of the national vaccine store for effective vaccine store management in the first quarter of 2007.

At district and health centre levels, trainings will be conducted to improve on record keeping. The current reporting forms will be reviewed to incorporate the vaccine wastage surveillance system that is currently being done in selected sentinel sites and routinely reported.

Replacement of transport and refrigerators will be another focus in the 2006-2010 plan. As most of the outreach clinics are accessed by bicycles, in this planning period, the programme will ensure that new bicycles and spare-parts are procured and distributed to health facilities.  The programme will therefore advocate for more adequate resources in order to achieve its obligation.

Injection safety and waste management will be strengthened through the continued use of AD syringes in both routine and supplemental immunization services and proper disposal of injection materials. Health workers will from time to time receive training on safe injection and waste management. Although the programme introduced routine reporting of AEFI cases in 2002, it will strengthen the system through training of health workers involved in immunization services. Since health care waste management has to be tackled in a broader perspective, the EPI will compliment efforts made by the MoH and other stakeholders by providing incinerators to some health facilities through funding from HSS.

5.3	Disease Surveillance

The strides made in disease surveillance over the years have had significant impact in the history of EPI in the country. Malawi used to experience high morbidity and mortality rates due to measles before the 1998 national measles vaccination campaign that was successfully conducted with >95% coverage achieved by all districts. This led to closure of measles admission wards in all district hospitals.

Although the country was certified to have eliminated NNT and achieved polio-free status, the EPI programme will in the next five years strive to sustain the gains that have been attained in order to improve and maintain the current status in an integrated manner to maximize the resources.

Trainings for health workers will continue to be conducted to improve knowledge and skills of health workers in disease surveillance. Aggressive search for AFP cases will be encouraged in order to achieve the detection rate of two cases per 100,000 populations of under fifteen years and ensure that stool adequacy is achieved by all districts. The National Polio Expert Committee will ensure that all AFP cases that have reached 90 days of onset of paralysis are reviewed. National SIAs will be conducted periodically when need arises. Disease outbreak responses will also be conducted in affected areas to disrupt the transmission of the disease.

In the next five years, the EPI programme will expand the Hib surveillance sites to Lilongwe and later Mzuzu central hospitals.

5.4	Advocacy, Social Mobilization and Communication

Advocacy, social mobilization and communication is very crucial in EPI services. Through ICC and SWAp, the programme will lobby for more resources for effective implementation of the planned activities. Advocacy meetings will be conducted with District Assemblies, District Health Management Teams and other stakeholders for more EPI resource mobilization at district levels.

Key EPI messages will be developed and disseminated through print and electronic media. Other channels such as drama and community meetings will be encouraged and strengthened. Traditional Birth Attendants, Traditional Healers and other community-based agents will continue being briefed on disease surveillance and immunization in general.

The quarterly EPI newsletter will be revived in 2006 and distributed to all health facilities and pre-service health institutions. In addition, posters, leaflets and fact sheets will also be developed.

5.5	Programme Management

The EPI programme will endeavor to mobilize adequate resources for implementation of the activities. It will ensure that all gaps and challenges noted in the past years are addressed.

Monitoring and Evaluation will be strengthened at all levels of programme implementation. District and health centres will be encouraged to analyze the immunization and disease surveillance data on monthly basis and take action on identified gaps.  Monitoring tools may be reviewed to incorporate any new changes.  Annual review meetings will be conducted with districts and regional EPI staff to assess the immunization and disease surveillance data and status of implementation of activities. Periodic surveys will be conducted in collaboration with partners.

The programme will ensure that supportive supervision is conducted regularly and that district micro-plans are followed-up. It will also ensure that EPI policies are reviewed to incorporate any new developments in the EPI.

The programme will apply for Immunization Strengthening System (ISS) and Health System Strengthening (HSS) and submit to GAVI for approval in the 2006. The Ministry of Health and GAVI have agreed to bridge the financing of DPT-HepB+Hib in the next five years.

A wide consultation by the Ministry of Health and partners will be made on the introduction of new vaccines such as rotavirus, pneumococcal in the next five years.

National Priorities based on Situation Analysis

- Sustaining high routine immunisation coverage

- Sustaining high quality surveillance on AFP, Measles & NNT

- Integrated implementation of child health interventions

- Continued capacity building at all levels

- Improved documentation and data management

- Improved monitoring and supervision and feedback on performance to lower health facility levels

- Replacement and maintenance of cold chain equipment;

  - Expansion of existing cold room at national level

  - Construction of regional vaccine storerooms in the north, centre and south

  - Replacement of deep freezers and refrigerators

- Strengthening advocacy and social mobilisation activities

  - Strengthening of partnerships in health and improved community participation

  - Improving Radio/TV messages and print media coverage

- Replacement and maintenance of transport equipment (vehicles, motorcycles and bicycles)

- Strengthening safe injection practices and waste management.

- Introduction new vaccines

Table 9	National Priorities based on Situational Analysis

| - Description of national priorities | - National objectives based on national priority | - Milestones | - Order of Priority |
| --- | --- | --- | --- |
| - High routine immunisation coverage | - Sustain high routine immunisation beyond 2010 | - 2006: 95% national coverage and at least 82% in every district - 2007: 96% national coverage and at least 85% in every district - 2008: 96% national coverage and at least 88% in every district - 2009: 97% national coverage and at least 88% in every district - 2010: 98% national coverage and at least 90% in every district | - 1 |
| - High quality disease surveillance | - Sustain high quality AFP surveillance through 2010 | - 2006: Non polio AFP rate of at least 2/100,000 <15 population - 2007: Non polio AFP rate of at least 2/100,000 <15 population - 2008: Non polio AFP rate of at least 2/100,000 <15 population - 2009: Non polio AFP rate of at least 2/100,000 <15 population - 2010: Non polio AFP rate of at least 2/100,000 <15 population | - 2 |

| - Description of national priorities | - National objectives based on national priority | - Milestones | - Order of Priority |
| --- | --- | --- | --- |
| - High quality disease surveillance | - Sustain Measles elimination status through 2010 | - 2006: 80 % of the districts reporting at least one investigated case per year - 2007: 85 % of the districts reporting at least one investigated case per year - 2008: 90 % of the districts reporting at least one investigated case per year - 2009: 95 % of the districts reporting at least one investigated case per year - 2010: 98 % of the districts reporting at least one investigated case per year |  |
|  | - Sustain NNT elimination status through 2010 | - 2006-2010: <1 case per 1,000 live births each district each year |  |
| - Monitoring of EPI performance | - Conduct supportive supervisory visits to districts through 2010 | - 2006-2010: At least 2 supervisory visits conducted per district per year | - 3 |
|  | - Conduct quarterly /biannual review meetings with district teams beyond 2010 | - 2006-2010: Meetings conducted every quarter |  |
|  | - Produce quarterly EPI bulletin beyond 2010 | - 2006-10: bulletin produced every quarter |  |
|  | - Improve record keeping and documentation by 2006 | - 2006: All health facilities have improved EPI records in place. |  |

| - Description of national priorities | - National objectives based on national priority | - Milestones | - Order of Priority |
| --- | --- | --- | --- |
| - 5 Capacity building among health workers | - Train health workers on EPI delivery systems by 2007 | - 2006: -1,000 health workers - trained on MLM - -2,000 in RED - -150 cold chain technicians - refreshed - 2007: 1,000 health workers - trained in MLM | - 4 |
| - 6 No stock outs for vaccines and injection materials | - No stock outs nationally | - 2006-2010: 100% districts with no stock outs | - 5 |
| - 7 Enhance national immunization advocacy and communications | - Develop and implement annual communication plans | - 2006-2010: Annual communication plan developed each year | - 6 |
| 8. Strengthen Safe injection disposal | - All AD syringes disposed of safely | - 2007: Contribute 25% of incinerators in districts hospitals that have non-functional incinerators | - 7 |
| - Replacement and maintenance of cold chain equipment | - All cold chain equipment maintained and old equipment replaced | - 2006: 25% of the refrigerators replaced - 2007: 50% of the refrigerators replaced - 2008: 75% of the refrigerators replaced - 2010: 100% of the refrigerators replaced - 2008: National vaccine storerooms expanded and 3 regional vaccine storeroom constructed. | - 8 |
| - 10 Replacement and maintenance of transport | - All EPI transport equipment replaced and maintained | - 2006-2010: All non functional EPI transport replaced | - 9 |
| - 11 Introduction of new vaccines | - Introduce new vaccines by 2010 | - 2010: New vaccines introduced | - 10 |

Table 10	National Objectives Based on Global and Regional Goals

| Global goals (Until 2010) | - Regional goals (Until 2010) | National objectives based on global and regional goals | Targets |
| --- | --- | --- | --- |
| - Immunization Coverage By 2010 or sooner all countries will have routine immunization coverage at 90% nationally with at least 80% coverage in every district | By 2010 or sooner all countries will have routine immunization coverage at 90% nationally with at least 80% coverage in every district | By 2010 Malawi will have routine immunization coverage at 98% nationally with at least 90% coverage in every district | - 2006: 95% national coverage and at least 82% in every district - 2007: 96% national coverage and at least 85% in every district - 2008: 96% national coverage and at least 88% in every district - 2009: 97% national coverage and at least 88% in every district - 2010: 98% national coverage and at least 90% in every district |
|  |  | By 2010, 80% of the district will have drop out rate of <10% | - 2006: 40% of the districts with drop out rates of 10% - 2007: 49% of the districts with drop out rates of 10% - 2008: 58% of the districts with drop out rates of 10% - 2009: 70% of the districts with drop out rates of 10% - 2010: 80% of the districts with drop out rates of 10% |

| - Global goals - (Until 2010) | Regional goals (Until 2010) | National objectives based on global and regional goals | Targets |
| --- | --- | --- | --- |
| - Polio By 2005, the world will be certified polio-free | By 2005, the region will be certified polio-free | Maintain polio free status up to and beyond 2010 | 2006-2010: Polio free status sustained |
| - Measles2 90% reduction in infant mortality by 2010 compared to 2000 | - Measles elimination in all countries of the region by 2010. | - Sustain Measles elimination status up to 2010 | - 2006: 80 % of the districts reporting at least one investigated case per year - 2007: 85 % of the districts reporting at least one investigated case per year - 2008: 90 % of the districts reporting at least one investigated case per year - 2009: 95 % of the districts reporting at least one investigated case per year - 2010: 98 % of the districts reporting at least one investigated case per year |
| - NT Elimination in every district by 2005 | - NT Elimination in every district by 2005 | Sustain NNT elimination status up to 2010 and beyond | 2006-2010: <1 case per 1,000 live births each district each year |
|  |  | - By 2010, Malawi will introduce new vaccines | 2010: New vaccine introduced |
| - Safe Injection - 8. By the end of 2003, all countries would use only autodisable syringes for immunization. |  | Malawi will sustain the use of autodisable syringes for all injectable immunizations up to and beyond 2010 | - 2006-2010: Use of AD syringes in routine and supplemental immunization in all health facilities maintained |

Planning strategies and activities for System Components

Table 11 Service Delivery

| Objective | Strategy | Key Activities |
| --- | --- | --- |
| Sustain high routine Immunization | Strengthen immunization services | Open new clinics where necessary |
|  |  | Distribute bundled vaccines |
|  |  | Sustain existing outreach clinics |
|  |  | Conduct catch-up campaigns in hard to reach areas. |
|  |  | Monitor drop out rates |
|  |  | Manage and report AEFIs |
|  | RED strategy | Establish national database of district indicators |
|  |  | Train health workers on micro planning |
|  |  | Screening clients at all contact clinics |
|  |  | Defaulter tracing using community registers |
|  |  | Supportive supervision to districts |
| Sustain NNT elimination | Improve TT coverage | Vaccinate pregnant women and women of child bearing age with TT |
|  | Conduct outbreak response | Conduct TT SIAs |
| Sustain measles elimination | Conduct outbreak response | Conduct measles SIAs |
| Sustain high quality AFP surveillance | Conduct outbreak response | Conduct polio SIAs |

Table 12	 Vaccine Supply, Quality and Logistics

| Objective | Strategy | Key Activities |
| --- | --- | --- |
| Strengthen vaccines and logistics management | Vaccine forecasting and procurement | Forecast and procure bundled vaccines |
|  | Vaccine management monitoring | Monitor vaccine management |
|  | Training | Train health workers on vaccine and logistics management |
|  | Vaccine wastage surveillance | Monitor vaccine wastage |
| Improve record keeping and documentation | Training | Train health workers on documentation and record keeping |
|  | Procurement of computers | Procure computers and accessories |
| Maintain and Replace Cold Chain equipment | Procurement of cold chain equipment and spare parts | - Procure and replace cold chain equipment and spare parts. |
| Maintenance and replacement of EPI transport | Strengthen EPI transport system | - Procure new vehicles, motorcycles and bicycles - Procure spare parts for bicycles. |
| Improve storage capacity for vaccine storerooms and dry store warehouse | Construction of warehouse and vaccine store rooms | - Construct a national warehouse - Construct national vaccine store - Construct 3 regional vaccine stores and warehouses. |
| Improve health care waste management | Construction of incinerators | - Construct incinerators in some district hospitals |
| Procure and replace computers | Procurement of computers and accessories | - Procure computers and accessories |
| Sustain safe injection practices | Use of ADs | - Procure adequate injection materials |

Table 13	Disease Surveillance

| Objective (1) | Strategy (2) | Key Activities (3) |
| --- | --- | --- |
| Sustain high quality AFP surveillance | Training | District based briefings for health workers |
|  |  | Orientation of VHCs and traditional healers |
|  | Prioritization of surveillance sites Polio SIAs | Outbreak response |
|  |  | Review of AFP cases |
|  |  | Transportation of stool specimen |
|  |  | Offer Laboratory Support to national laboratories |
|  |  | Active search for AFP cases |
|  |  | Conduct polio SIAs |
| Sustain Measles elimination status | Improve surveillance | Use available data of monthly suspected measles cases to identify areas that have circulation of measles virus |
|  |  | Carry out case investigation and intensify laboratory diagnosis of suspected measles cases. |
|  | SIAs for measles | Procurement of Laboratory supplies e.g. reagents |
|  |  | Active search for suspected measles cases |
|  |  | Carry integrated disease surveillance briefings for health workers |
|  |  | Conduct measles SIAs |
| Sustain NNT elimination | Risk assessment | Identification of high risk district/ areas |
|  | Improve TT Coverage | Vaccinate pregnant women and women of child bearing age with TT |
|  | TT SIAs | Investigation of Neonatal deaths with unknown causes |
|  |  | Sensitization of HWs, Traditional healers, TBAs etc |
|  |  | Intensify active search in admitting hospitals |
|  |  | Line listing of NNT cases. |
|  |  | Conduct SIAs for TT |
| Hib surveillance | Training for Hib surveillance | Expand Hib surveillance sites |

Table 14 	Advocacy, Social Mobilization and Communication

| Objective (1) | Strategy (2) | Key Activities (3) |
| --- | --- | --- |
| Sustain high routine immunisation until and beyond 2010 Reduce immunisation drop out rate Sustain high quality AFP surveillance Sustain Measles elimination status | Communication plan | 1.Produce EPI bulletin |
|  |  | - Feedback to health workers following supervisory visits. |
|  |  | - Hold regularly meetings with DHMTs on prioritisation of EPI services. |
|  |  | - Review meetings with Health workers |
|  |  | - Develop key messages and IEC materials on EPI. |
|  |  | - Conduct ICC meetings |
|  | Use of existing structures within the community | - Sensitisation of communities on the importance completing immunisation |
|  |  | - Conduct social mobilisation activities on immunisation and surveillance through public rallies |
|  |  | - Drama performances |
|  |  | - Airing of radio & TV messages |
|  |  | - Discussions with local leaders on scheduling and sustaining outreach services |
|  |  | - Hold press conferences & press releases |
|  | RED strategy for every district | - Immunisation defaulter tracing through joint planning with the community |
|  | Greater partnerships in childhood interventions | - Conduct meetings with NGOs on other childhood disease interventions |
|  |  | - Broaden partnerships in ICC |
|  | Trainings on surveillance and immunisation | - MLM trainings on surveillance |
|  |  | - Conduct VHC, TBAs CBDs briefings on diseases surveillance |
|  | Advocacy meetings | - Meetings with local assemblies, local leadership |
| Sustain NNT elimination | Improve TT Coverage Clean delivery practices | - Sensitisation of health workers on MNT surveillance through briefings and training |
|  |  | - Including routine TT in district microplans |
|  |  | - Development and production of publicity materials for NNT |
|  | NNT SIAs | - Conduct NNT supplemental Immunisation activities. |
| Introduction of new vaccines | Advocacy meetings with policy makers and partners | - Advocate for introduction of new vaccines. |

Table 15 	Programme Management

| Objective (1) | Strategy (2) | Key Activities (3) |
| --- | --- | --- |
| Sustain high quality AFP surveillance Sustain high routine immunisation until and beyond 2010 Sustain Measles elimination status Sustain NNT elimination | Monitoring and evaluation | Data monitoring, analysis and timely reporting on surveillance & routine immunisation |
|  |  | Conduct supportive supervision and provide regular feedback |
|  |  | Conduct regular review meetings |
|  |  | Conduct periodic surveys |
|  | Trainings | MLM trainings |
|  |  | Health worker trainings/briefings |
|  |  | RED strategy trainings |
|  | RED strategy | Produce childhood profiles |
|  |  | Defaulter tracing |
|  |  | Sustain outreach services |
|  |  | Supervisory follow up priority districts |
|  |  | Follow up on district micro-plans |
|  | EPI Policy | Review EPI policies |
| Improve record keeping and documentation | Training on data management | Procure computers and accessories Train health workers |
| Introduce 2nd dose of measles vaccine | Feasibility study | Technical review on feasibility of measles 2nd dose Introduce 2nd dose of measles |
| Introduction of new vaccines | Disease burden study Training | Technical review on feasibility of introduction of new vaccines Train health workers Introduce new vaccines |

6.0 Cost, budget and Financing for the cMYP

The success of the programme largely depends on adequate financing for all proposed activities to be undertaken during the planning period. It will be the responsibility of the EPI through the Ministry of Health to ensure that the programme gets adequate financial and material support both locally and internationally.

In this section, we review the cost implications of the proposed program activities, and relate these to the known available financing for respective cost categories of the program to derive information relating to financing gaps. Also proposed are strategies and interventions the program needs to carry out, to improve its financial viability.

  - Methodology for costing the cMYP

The cMYP includes a series of interventions, which have associated activities, and inputs needed to actualize. These are illustrated in the table below.

| System Components | Inputs | Activities |
| --- | --- | --- |
| 1. Service delivery | Human resources/salaries, outreach per-diems, fuel for transport, operational cost of campaigns… | Training, workshops… |
| 2. Advocacy and communication | IEC materials (posters…) | Social mobilization, IEC, developing advocacy and communication plan |
| 3. Surveillance | Surveillance equipment | Surveillance activities (sentinel sites, outbreak investigation…) |
| 4. Vaccine, supply, quality and logistics | Vaccines, AD syringes, safety boxes, other injection supplies, cold chain equipment, vehicles, spare parts, incinerators…. | Monitoring, vaccine stock management activities |
| 5. Programme management | Computers, office supplies… | Meetings, planning, research, data management, EPI reviews, cold chain assessment… |

These activities and inputs are what are costed. The costs for the program are derived in a variety of costing methodologies, depending on the interventions planned. These include:

    - The ingredient approach, based on the product of unit prices, and quantities needed each year, adjusted for the proportion of time used for immunization. This is used for costing inputs such as vaccines, personnel, vehicles, cold chain equipment, etc

    - Rules of thumb, which are based on immunization practice, such as a percentage of fuel costs as representative of maintenance costs for vehicles. This is used for deriving costs for injection supplies, and maintenance of equipment, and vehicles

    - Past spending, where lump sum past expenditure is used to estimate future expenditure. For example, past cost/child for specific campaigns, training activities.

These different approaches are all brought together in a pre-designed cMYP excel costing tool. This derives costs based on the following components:

- Vaccines and injection supplies

- Personnel costs (EPI specific and shared)

- Vehicles, and transport costs

- Cold chain equipment, maintenance and overheads

- Operational costs for campaigns

- Program activities, other recurrent costs and surveillance

- Other equipment needs and capital costs

- Overhead costs

  - Macroeconomic information

For purposes of placing the costing and financing information within the wider financing framework, some macroeconomic information was included. This information is detailed in the table below.

Macro economic trends in Malawi, 2006 – 2010

|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- |
|  | $ | $ | $ | $ | $ | $ |
| GDP per capita | 310 | 326 | 342 | 359 | 377 | 396 |
| Total health expenditures (THE) per capita | 12.0 | 12.0 | 13.0 | 14.0 | 15.0 | 17.0 |
|  | (%) | (%) | (%) | (%) | (%) | (%) |
| Government health expenditures (GHE%THE) | 40.0% | 40.0% | 40.0% | 40.0% | 40.0% | 40.0% |

The GDP is estimated to increase at 5% per annum.

  - Vaccines and injection equipment

Costs are a function of the unit prices for individual vaccines, with quantities determined by the target population, adjusted for by coverage and wastage objectives. Prices are based on UNICEF prices, as supplied by the UNICEF Supply Division. Target populations for different antigens, coverage, and wastage objectives have been expounded on in earlier chapters.

  - Personnel costs (EPI specific and shared)

As with vaccines and injection equipment, cost estimates are based on unit expenditure on different personnel cadres working in EPI at the different levels of the system, and numbers of personnel, adjusted for by time spent on EPI-related activities. In addition, costs, and time spent on supervision, and outreach activities were included for the different cadres at the different levels of the system. Unit expenditures are based on Government gross wages. Time spent on EPI was estimated by a panel of experts, made up of operational staff at national, and sub national levels. Quantities available and needed in the life time of the cMYP were included.

  - Vehicles, and transport costs

The costs for vehicles were derived in the same manner as personnel. Additional maintenance costs were estimated as represented by 15% of fuel expenditure. Quantities available and needed in the life time of the cMYP were included.

  - Cold chain equipment, maintenance and overheads

Costs were derived as with personnel and vaccines. Quantities available and needed in the life time of the cMYP were included.

  - Operational costs for campaigns

These were based on operational costs for past campaigns, with the cost per child derived.

  - Program activities, other recurrent costs and surveillance

Costs for program activities were also derived based on the past trends in expenditure, with future estimates for costs based on these, modified where necessary. Costs are illustrated in the table below.

|  | Expenditure | Future Budget Needs |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Program Activities and Other Recurrent Costs | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
|  | $ | $ | $ | $ | $ | $ |
| Social Mobilization, Advocacy, and Communication Activities |  |  |  |  |  |  |
| Social Mobilization, Advocacy, and Communication Activities | 56,339 | 242,295 | 150,000 | 150,000 | 150,000 | 150,000 |
| Training and Workshops |  |  |  |  |  |  |
| Training activities | 219,447 | 265,000 | 265,000 | 265,000 | 265,000 | 265,000 |
| Program Management |  |  |  |  |  |  |
| Meetings | 234,648 | 300,000 | 300,000 | 300,000 | 300,000 | 300,000 |
| Surveillance and Monitoring | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| Detection and Notification |  |  |  |  |  |  |
| Active surveillance | 34,702 | 102,500 | 120,000 | 120,000 | 120,000 | 120,000 |
| Case and outbreak verification and investigation |  |  |  |  |  |  |
| Dispatch of specimens to the lab | 6,064 | 7,500 | 7,500 | 7,500 | 7,500 | 7,500 |
| Fuel for AFP specimens | 5,000 | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 |
| Data Management |  |  |  |  |  |  |
| Internet conection & telephone bills | 1,370 | 1,400 | 1,500 | 1,500 | 1,500 | 1,500 |
| telephone bills | 9,800 | 10,000 | 10,000 | 10,000 | 10,000 | 10,000 |
| Laboratory |  |  |  |  |  |  |
| Lab containment activities for AFP | 5,420 | 8,000 | 8,000 | 8,500 | 8,500 | 8,500 |
| Supportive Activities |  |  |  |  |  |  |
| Evaluation and planning | 44,000 | 85,000 | 85,000 | 85,000 | 85,000 | 85,000 |

Social mobilization costs for 2006 are based on the social mobilization plan, with estimates for future years adjusted for the reduction in start-up activities.

Costs for trainings meetings and surveillance activities are based on the 2005 expenditures, with future costs estimated with an adjustment factor to cater for activities not included in 2005.

  - Other equipment needs and capital costs

Additional costs for equipment not reflected above, such as office computers LCD’s, etc were included, and costed using the same methodology as with other equipment above.

  - Overhead costs

These too were included in the estimates, based on past expenditure trends.

  - Costs for Immunization activities during the period for the cMYP

Costs for the different cMYP components are presented in the table below.

- Costs for cMYP components, 2006 - 2010

|  | Future Resource Requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2006 | 2007 | 2008 | 2009 | 2010 | Total 2006 - 2010 |
| MYP Components | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccine Supply and Logistics | 10,068,530 | 10,617,706 | 9,129,109 | 9,983,502 | 9,385,605 | 49,184,452 |
| Service Delivery | 8,027,123 | 8,398,361 | 8,608,057 | 10,183,889 | 8,437,642 | 43,655,072 |
| Advocacy and Communication | 247,141 | 156,060 | 159,181 | 162,365 | 165,612 | 890,359 |
| Monitoring and Disease Surveillance | 228,888 | 251,777 | 257,343 | 262,490 | 267,740 | 1,268,237 |
| Programme Management | 306,000 | 312,120 | 382,035 | 324,730 | 331,224 | 1,656,109 |
| Grand Total | 18,877,682 | 19,736,025 | 18,535,725 | 20,916,975 | 18,587,822 | 96,654,229 |

- The program cost driver during the period of the cMYP is vaccine supply and logistics, contributing half the total costs.

- These costs are further broken down by cost categories, as illustrated below

- Costs for different program cost categories, 2006 - 2010

|  | Expenditures | Future Resource Requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Cost Category | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |  |
| Routine Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |  |
| Vaccines (routine vaccines only) | $7,884,661 | $9,568,274 | $7,928,573 | $8,032,105 | $8,213,906 | $8,408,154 |  |
| Traditional vaccines | $830,403 | $683,660 | $728,849 | $772,813 | $816,687 | $870,388 |  |
| New and underused vaccines | $7,054,258 | $8,884,614 | $7,199,724 | $7,259,292 | $7,397,218 | $7,537,766 |  |
| Injection supplies | $401,942 | $492,076 | $527,936 | $565,969 | $597,634 | $626,170 |  |
| Personnel | $390,558 | $398,369 | $406,337 | $414,463 | $422,753 | $431,208 |  |
| Salaries of full-time NIP health workers | $127,668 | $130,221 | $132,826 | $135,482 | $138,192 | $140,956 |  |
| Per-diems for outreach vaccinators/mobile teams |  |  |  |  |  |  |  |
| Per-diems for supervision and monitoring | $262,890 | $268,148 | $273,511 | $278,981 | $284,561 | $290,252 |  |
| Transportation | $23,800 | $24,276 | $24,846 | $25,343 | $25,849 | $89 |  |
| Fixed site and vaccine delivery | $22,123 | $22,565 | $23,095 | $23,557 | $24,028 | $83 |  |
| Outreach activities | $1,677 | $1,711 | $1,751 | $1,786 | $1,822 | $6 |  |
| Maintenance and overhead | $566,015 | $577,744 | $799,911 | $857,637 | $985,016 | $400,382 |  |
| Cold chain maintenance and overheads | $557,140 | $568,283 | $773,458 | $822,339 | $939,134 | $353,307 |  |
| Maintenance of other capital equipment | $8,875 | $9,461 | $26,452 | $35,298 | $45,882 | $47,075 |  |
| Building overheads (electricity, water…) |  |  |  |  |  |  |  |
| Short-term training | $219,447 | $270,300 | $275,706 | $281,220 | $286,845 | $292,581 |  |
| IEC/social mobilization | $56,339 | $247,141 | $156,060 | $159,181 | $162,365 | $165,612 |  |
| Disease surveillance | $106,356 | $228,888 | $251,777 | $257,343 | $262,490 | $267,740 |  |
| Programme management | $234,648 | $306,000 | $312,120 | $382,035 | $324,730 | $331,224 |  |
| Subtotal Recurrent Costs | $9,883,767 | $12,113,068 | $10,683,264 | $10,975,296 | $11,281,586 | $10,923,160 |  |
| Routine Capital Cost |  |  |  |  |  |  |  |
| Vehicles |  |  | $31,212 |  |  |  |  |
| Cold chain equipment |  | $20 | $2,093,572 | $517,504 | $820,193 | $335,272 |  |
| Other capital equipment | $2,900 | $8,160 | $36,414 | $13,530 | $15,695 | $16,009 |  |
| Subtotal Capital Costs | $2,900 | $8,180 | $2,161,198 | $531,035 | $835,889 | $351,281 |  |
| Campaigns |  |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |  |
| Vaccines |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |
| Measles | $1,285,863 |  |  |  | $1,629,518 |  |  |
| Vaccines and supplies | $467,408 |  |  |  | $336,074 |  |  |
| Other operational costs | $818,455 |  |  |  | $1,293,445 |  |  |
| Subtotal Campaign Costs | $1,285,863 |  |  |  | $1,629,518 |  |  |
| Other Costs |  |  |  |  |  |  |  |
| Shared personnel costs | $2,941,837 | $3,000,674 | $3,060,688 | $3,121,901 | $3,184,339 | $3,248,026 |  |
| Shared transportation costs | $3,682,118 | $3,755,760 | $3,830,875 | $3,907,493 | $3,985,642 | $4,065,355 |  |
| Subtotal Optional | $6,623,955 | $6,756,434 | $6,891,563 | $7,029,394 | $7,169,982 | $7,313,381 |  |
| GRAND TOTAL | $17,796,485 | $18,877,682 | $19,736,025 | $18,535,725 | $20,916,975 | $18,587,822 |  |
| Routine (Fixed Delivery) | $15,812,479 | $18,022,392 | $18,981,467 | $17,760,553 | $18,490,665 | $17,817,979 |  |
| Routine (Outreach Activities) | $698,143 | $855,290 | $754,558 | $775,172 | $796,792 | $769,843 |  |
| Campaigns | $1,285,863 |  |  |  | $1,629,518 |  |  |

- The program costs are largely driven by the routine recurrent program, representing over 50% of the total costs. Shared costs represent under 30% of the total program costs. In the year when there is a measles campaign, costs due to the campaign represent approximately 5% of the total program costs.

- Additionally, the cost associated with the routine fixed service delivery represents the key cost-driving strategy for service delivery during this period. This is in spite of the fact that the bulk of immunizations are carried out through outreaches. This is because it is comparatively cheaper to immunize through the outreaches as opposed to the fixed sites, though less sustainable.

  - Financing for the program

- The trends in program financing are presented in this section. Based on the program cost categories, past, and future financing available for the respective cost areas was derived from partners. Recognised partners supporting the program are:

- Government

- Sub national Government

- GAVI

- SWAP FUNDS

- UNICEF

- UN FOUNDATION

- WHO

- KFW

- DFID

- The breakdown of financing for the routine program expenditure in 2005 is illustrated in the figure below.

- The major source of financing for the routine program is the sub national Government, through which funding for the bulk of shared costs is channelled. This is followed by financing from GAVI, the bulk of which is new vaccines support, and DFID that supported traditional vaccine purchases in this year (2005).

- With the advent of the SWAp basket financing, many of the program sources of financing are now channelling their support through this mechanism, leading to a reduction in the overall number of program funders, and an increase in funding from the SWAp basket.

- Regarding the cMYP activities, the status of financing is highlighted in the table below.

- Financing status for the cMYP, 2006 – 2010

| Resource Requirements, Financing and Gaps* |  |  | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total Resource Requirements |  |  | $12,121,248 | $12,844,462 | $11,506,331 | $13,746,993 | $11,274,441 |
| Total Resource Requirements (Routine only) |  |  | $12,121,248 | $12,844,462 | $11,506,331 | $12,117,475 | $11,274,441 |
|  | per capita |  | $1.0 | $1.1 | $1.0 | $1.0 | $0.9 |
|  | per DTP targeted child |  | $23.9 | $24.6 | $21.3 | $21.6 | $19.7 |
|  | % Vaccines and supplies |  | 83% | 66% | 75% | 73% | 80% |
| Total Financing (Secured) |  |  | $10,656,882 | $8,992,752 | $578,158 | $534,653 | $519,344 |
| Government |  |  | $469,958 | $496,244 | $578,158 | $534,653 | $519,344 |
| GAVI |  |  | $8,130,652 | $6,463,691 | $0 | $0 | $0 |
| SWAP FUNDS |  |  | $1,929,698 | $1,992,817 | $0 | $0 | $0 |
| UNICEF |  |  | $68,414 | $0 | $0 | $0 | $0 |
| UN FOUNDATION |  |  | $0 | $0 | $0 | $0 | $0 |
| WHO |  |  | $58,160 | $40,000 | $0 | $0 | $0 |
| KfW |  |  | $0 | $0 | $0 | $0 | $0 |
| DfID |  |  | $0 | $0 | $0 | $0 | $0 |
| Funding Gap |  |  | $1,464,366 | $3,851,710 | $10,928,173 | $13,212,341 | $10,755,097 |
|  | % of Total Needs |  | 12% | 30% | 95% | 96% | 95% |
| Total Financing (Not Secured / Probable) |  |  | $381,000 | $484,414 | $8,521,519 | $8,703,320 | $8,897,568 |
| Government |  |  | $0 | $0 | $0 | $0 | $0 |
| GAVI |  |  | $0 | $0 | $6,259,292 | $6,397,218 | $6,537,766 |
| SWAP FUNDS |  |  | $0 | $0 | $1,772,813 | $1,816,687 | $1,870,388 |
| UNICEF |  |  | $90,000 | $183,414 | $158,414 | $158,414 | $158,414 |
| UN FOUNDATION |  |  | $0 | $0 | $0 | $0 | $0 |
| WHO |  |  | $291,000 | $301,000 | $331,000 | $331,000 | $331,000 |
| KfW |  |  | $0 | $0 | $0 | $0 | $0 |
| DfID |  |  | $0 | $0 | $0 | $0 | $0 |
| Funding Gap |  |  | $1,083,366 | $3,367,296 | $2,406,654 | $4,509,021 | $1,857,529 |
|  | % of Total Needs |  | 9% | 26% | 21% | 33% | 16% |

- We see a significant reduction in the availability of secured finances for the program, particularly after 2007, where the financing gap increases from 30% to 95% of the total routine program costs. A large amount of the resources are then classified as probable, as agreements on their availability are not completed. These include resources from GAVI, WHO, UNCEF, and SWAp funds.

- Regarding the composition of the funding gap, based on the secured resources, the operational program activities drive it in 2006, while the logistics do so in 2007, as a result of significant investment planned then in the cold chain, and other capital investments. After 2007, the funding gap is driven by the vaccines and injection equipment.

- Composition of the funding gap with secured resources

| Composition of the funding gap |  |  |  | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccines and injection equipment |  |  |  | $0 | $0 | $8,598,074 | $8,811,540 | $9,034,324 |
| Personnel |  |  |  | $0 | $73,511 | $78,981 | $84,561 | $90,252 |
| Transport |  |  |  | $0 | $0 | $0 | $0 | $0 |
| Activities and other recurrent costs |  |  |  | $706,329 | $877,132 | $980,214 | $1,110,964 | $539,371 |
| Logistics (Vehicles, cold chain and other equipment) |  |  |  | $20 | $2,161,198 | $531,035 | $835,889 | $351,281 |
| Campaigns |  |  |  | $0 | $0 | $0 | $1,629,518 | $0 |
| Total Funding Gap* |  |  |  | $706,349 | $3,111,841 | $10,188,304 | $12,472,472 | $10,015,228 |

- On the other hand, when the probable resources are included, then the funding gap in 2006 and 2007 is still driven by operational program activities, and cold chain investments respectively. The contribution by vaccines and injection equipment to the gap reduces significantly in 2008 onwards.

| Composition of the funding gap |  |  |  | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccines and injection equipment |  |  |  | $0 | $0 | $565,969 | $597,634 | $626,170 |
| Personnel |  |  |  | $0 | $38,511 | $78,981 | $84,561 | $90,252 |
| Transport |  |  |  | $0 | $0 | $0 | $0 | $0 |
| Activities and other recurrent costs |  |  |  | $325,329 | $427,718 | $490,800 | $621,550 | $49,957 |
| Logistics (Vehicles, cold chain and other equipment) |  |  |  | $20 | $2,161,198 | $531,035 | $835,889 | $351,281 |
| Campaigns |  |  |  | $0 | $0 | $0 | $1,629,518 | $0 |
| Total Funding Gap* |  |  |  | $325,349 | $2,627,427 | $1,666,785 | $3,769,152 | $1,117,660 |

  - Interventions to improve the financial viability of the program

- In light of the above information, we see that:

- The bulk of the funding gap for the program could be reduced if the probable resources are secured, and

- Some additional resources will be needed to support program investments in the immunization system, and operations.

    - Securing probable resources

- These are resources from GAVI, WHO, UNICEF and SWAp funds

- The GAVI probable resources reflect the expected contribution from GAVI bridge financing for the new vaccine, to supplement the Government contribution annually. The country negotiations for this will have to be completed in 2006, to enable re-classification as secured resources

- WHO and UNICEF funding is assumed to remain at present levels. To secure this, the program will have to participate with these multi laterals when they are developing their respective programs of work for the coming years.

- For the SWAp funds, the program will have to continue advocating for additional resources from this source, given its impact on overall sector objectives. The program has to ensure the Government commitment of at least US$ 1 million annually for vaccines is maintained.

    - Securing additional resources

- Additional resources are needed by the program to ensure it is able to implement its strategic objectives as outlined in this plan. As seen in the table above, additional funding will focus on the interventions in the respective system components where the funding gaps exist, for the respective years. These additional funds will focus on 2 main sources:

- Additional funding from the SWAp. This needs:

    - Technical analyses on the impact of additional financing on morbidity and mortality

    - Policy papers on the public health, and economic impact of improved financing for immunization

- Guided proposals for additional funding through GAVI phase 2, for Immunization Systems Strengthening, and Health Systems Strengthening. These proposals would focus on mobilising resources to close these identified gaps.

- The program will, as part of its regular monitoring process, monitor the trends in financing, to ensure it is moving towards improved financial sustainability by reducing its financing gaps, and converting more probable financing to secure financing. Indicators for financial sustainability the program will use will include:

    - % of funding gap to total program needs for period of cMYP (65% is baseline; target of 30%)

    - % total program costs financed by in country sources of financing( 57% baseline, target of 70%)

    - % of total program costs financed by Government (47% baseline, target of 60%)

Table 17	Gantt chart for Implementation of Activities

| Component and Key Activities | Year |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2006 | 2007 | 2008 | 2009 | 2010 |
| 1. Service Delivery |  |  |  |  |  |
| - Open new clinics where necessary | X | X | X | X | X |
| - Distribute bundled vaccines | X | X | X | X | X |
| - Sustain existing outreach clinics | X | X | X | X | X |
| - Monitor drop out rates | X | X | X | X | X |
| - Conduct catch-up campaigns in hard to reach areas. | X | X | X | X | X |
| - Manage and report AEFIs | X | X | X | X | X |
| - Establish national database of district indicators |  | X |  |  |  |
| - Train Health workers on RED micro planning | X | X | X | X | X |
| - Screening clients at all contact clinics | X | X | X | X | X |
| - Defaulter tracing using community registers | X | X | X | X | X |
| - Vaccinate pregnant women and women of child bearing age with TT | X | X | X | X | X |
| - Conduct mini-TT SIAs | X | X | X | X | X |
| - Conduct national measles SIAs |  |  |  | X |  |
| - Conduct mini Measles SIAs | X | X | X | X | X |
| - Conduct polio SIAs |  |  | X |  |  |
| 2. Disease Surveillance and Accelerated Disease Control |  |  |  |  |  |
| - Conduct district based briefings on integrated disease surveillance for health workers | X | X | X | X | X |
| - Orientation of VHCs and traditional healers, TBAs | X | X | X | X | X |
| - Outbreak response | X | X | X | X | X |
| - Review of AFP cases | X | X | X | X | X |
| - Transportation of stool specimen | X | X | X | X | X |
| - Offer Laboratory Support to national laboratories | X | X | X | X | X |
| - Active search for AFP cases | X | X | X | X | X |
| - Use available data of monthly suspected measles cases to identify areas that have circulation of measles virus | X | X | X | X | X |
| - Carry out case investigation and intensify laboratory diagnosis of suspected measles cases. | X | X | X | X | X |
| - Procurement of Laboratory supplies e.g. reagents | X | X | X | X | X |
| - Active search for suspected AFP, measles and NNT cases | X | X | X | X | X |
| - Identification of high risk district/ areas for NNT | X | X | X | X | X |
| - Investigation of Neonatal deaths with unknown causes | X | X | X | X | X |
| - Line listing of AFP, measles and NNT cases | X | X | X | X | X |
| - Expand Hib surveillance sites |  | X |  | X |  |
| Vaccine Supply, Quality and Logistics |  |  |  |  |  |
| - Forecast and procure vaccines and injection materials | X | X | X | X | X |
| - Monitor stock management | X | X | X | X | X |
| - Monitor vaccine wastage | X | X | X | X | X |
| - Train Health workers in vaccines, logistics management | X | X | X | X | X |
| - Procure and replace cold chain equipment | X | X | X | X | X |
| - Procure cold chain spare parts | X | X | X | X | X |
| - Procure new vehicles, motorcycles and bicycles | X | X | X | X | X |
| - Maintain EPI vehicles | X | X | X | X | X |
| - Procure spare parts for bicycles. | X | X | X | X | X |
| - Construct a national warehouse | X |  |  |  |  |
| - Construct national vaccine store |  | X |  |  |  |
| - Construct 3 regional vaccine stores and warehouses |  | X |  |  |  |
| - Construct incinerators in some district hospitals |  | X | X | X | X |
| - Procure computers and accessories | X | X | X | X | X |
| 4. Advocacy, Social Mobilisation and Communication |  |  |  |  |  |
| - Produce Child Health Bulletin | X | X | X | X | X |
| - Feedback to health workers following supervisory visits. | X | X | X | X | X |
| - Advocate for prioritisation of EPI services in District Implementation Plans | X | X | X | X | X |
| - Review meetings with Health workers | X | X | X | X | X |
| - Develop key messages and IEC materials on EPI. | X |  | X |  | X |
| - Conduct ICC meetings | X | X | X | X | X |
| - Sensitisation of communities on the importance completing immunisation | X | X | X | X | X |
| - Conduct social mobilisation activities on immunisation and surveillance through public rallies | X | X | X | X | X |
| - Drama performances | X | X | X | X | X |
| - Airing of radio & TV messages | X | X | X | X | X |
| - Discussions with local leaders on scheduling and sustaining outreach services | X | X | X | X | X |
| - Hold press conferences & press releases | X | X | X | X | X |
| - Immunisation defaulter tracing through joint planning with the community | X | X | X | X | X |
| - Conduct meetings with NGOs on other childhood disease interventions | X | X | X | X | X |
| - Broaden partnerships in ICC | X | X |  |  |  |
| - Conduct VHC, TBAs, CBDs, local assemblies briefings on childhood interventions | X | X | X | X | X |
| - Advocate for the introduction of new vaccines. | X | X | X | X | X |
| 5. Programme Management and Partnerships |  |  |  |  |  |
| - Data monitoring, analysis and timely reporting on surveillance & routine immunisation | X | X | X | X | X |
| - Conduct supportive supervisory visits and regular feedback | X | X | X | X | X |
| - Conduct regular review meetings | X | X | X | X | X |
| - Conduct comprehensive EPI Review |  |  | X |  |  |
| - Vaccine Management Assessment |  | X |  |  |  |
| - Conduct Data Quality Assessment |  |  |  | X |  |
| - MLM trainings | X | X | X | X | X |
| - H/worker trainings on EPI activities | X | X | X | X | X |
| - RED strategy trainings | X | X | X | X | X |
| - Follow up on district micro-plans | X | X | X | X | X |
| - Review EPI policies |  | X |  |  |  |
| - Technical review on the feasibility of measles 2nd dose and new vaccines |  | X | X | X |  |
| - Financial sustainability strategies for the program | X | X | X | X | X |

Table 18 Using the GIVS framework as a checklist

| GIVS strategies | Key activities | Activity included in MYP |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Strategic Area One: Protecting more people in a changing world |  | Y | N | Not applicable | New activity needed |
| Strategy 1: Use a combination of strategies to reach everyone targeted for immunization | National commitment to ongoing immunization services through policy and strategy development that also includes human resources and financial planning | Partial |  |  |  |
|  | Formulate and implement comprehensive multi-year national strategic plans and annual workplan based on data analysis and problem solving | y |  |  |  |
|  | Sustain high vaccination coverage, where it has been achieved | y |  |  |  |
|  | National strategies to immunize children who were not immunized during infancy | y |  |  |  |
|  | Where and when appropriate, include supplementary immunization activities as an integral part of the national plans | y |  |  |  |
| Strategy 2: Increase community demand for immunization | - Engage community members, NGOs and interest groups in immunization advocacy and implementation; | y |  |  |  |
|  | - Assess the existing communication gaps in reaching all communities and develop and implement a communication and social mobilization plan | y |  |  |  |
|  | Provide regular, reliable, and safe immunization services that match demand | y |  |  |  |
| Strategy 3: Ensure that the unreached are reached in every district at least four times a year | Micro-planning at the district or local level | y |  |  |  |
|  | Reduce the number of immunization drop-outs (incomplete vaccination) through improved management | y |  |  |  |
|  | Develop and update supervisory mechanisms and tools | y |  |  |  |
|  | Provide timely funding, logistic support and supplies for programme implementation | y |  |  |  |
| Strategy 4: Vaccinate beyond the traditional target group | Define target populations and age groups for vaccination appropriate to the national situation | y |  |  |  |
|  | Assess the cost-effectiveness of strategies |  | N |  |  |
| Strategy 5: Improve vaccine, immunization and injection safety Strategy 5: Improve vaccine, immunization and injection safety | Procure vaccines only from sources that meet internationally recognized quality standards | y |  |  |  |
|  | Ensure long-term forecasting for existing and new vaccines by improving vaccine management skills | y |  |  |  |
|  | National self-reliance in quality assurance and regulatory oversight |  | N |  |  |
|  | Introduce, sustain and monitor safe injection practices, including the use of autodisable (AD) syringes and other safe methods of vaccine administration | y |  |  |  |
|  | surveillance and response to adverse events following immunization | y |  |  |  |
|  | Be responsive to potential vaccine safety issues and address these urgently |  | N |  |  |
| Strategy 6: Improve and strengthen vaccine management systems | Accurate demand forecasting at national and district levels to ensure the uninterrupted supply of assured quality vaccines, AD syringes and safety boxes | y |  |  |  |
|  | Build capacity for effective vaccine management through training, supervision and the development of information systems | y |  |  |  |
|  | Increase access and coverage through a "safe chain" approach which includes taking vaccines beyond the cold chain, using a VVM-based vaccine management system | y |  |  |  |
|  | Move towards coordinated and sector-wide financing and management for transportation and communications | y |  |  |  |
| Strategy 7: Evaluate and strengthen the immunization programme. | Regular immunization programme evaluations at local, district and national levels and provide feedback on performance | y |  |  |  |
|  | Perform operations research and evaluation of “what works” to improve the delivery of immunization and to make systems more effective, efficient and equitable | y |  |  |  |

Annex 1	Summary of the Strengths and Weaknesses of the EPI

| Component | Strengths | Weaknesses |
| --- | --- | --- |
| 1. Service Delivery | - Immunization coverage has been sustained above 80%. - Introduction of DPT-HepB+Hib pentavalent vaccine. - Use of AD syringes in all health facilities - Successful implementation of a second measles follow up and vitamin A supplementation campaign | - Tallying/recording of vaccinations was done before the child is vaccinated in some health facilities. - In some health facilities, there was lack of compliance to national policy of checking for BCG scar and following recommended immunization schedule. - Poor documentation of vitamin A supplementation for post-natal mothers. - Booking system for vaccinations resulted into high missed opportunities in some health centers. |
| 2. Vaccine Supply, Quality and Logistics | - Rehabilitation and procurement of cold chain equipment, vehicles, motorcycles and bicycles. - Funding and procurement for vaccines, injection materials and equipment has been adequate and timely - At national level there was no stock out for vaccine and injection material since 2001. - Construction of the new national vaccine storeroom and dry store warehouse. - Installation of containers for dry stores materials in regions | - Inadequate supply of mixing syringes and vaccine stock outs in some facilities were due to inconsistent distribution system. - In some cases, transport is not readily available for EPI services - There were mismatching for quantities of vaccines for DPT-HepB and Hib, measles and BCG with diluents - Inadequate storage capacity for the national and regional vaccine storerooms. - Storage capacity for dry stores not adequate at all levels. - Some cold chain equipment have stayed more than 5 years resulting in frequent breakdowns - Old fleet of vehicles, motorcycles and bicycles which are due for replacement |

Summary of the Strengths and Weaknesses of the EPI

| Component | Strengths | Weaknesses |
| --- | --- | --- |
| 3. Vaccine Supply, Quality and Logistics cont. |  | - There are failures of stock control and stock management which means that the stock records do not accurately reflect physical counts - Overstocking of the dry goods means that effective stock control and EEFO management of syringes is extremely difficult - Inadequate sharps waste treatment facilities |

Summary of the Strengths and Weaknesses of the EPI cont.

| Component | Strengths | Weaknesses |
| --- | --- | --- |
| 3. Disease Surveillance | - Availability of Hib Sentinel Surveillance Site at Queen Elizabeth Central Hospital - Sustenance of quality AFP surveillance activities and achievement of polio free status - Measles case-cased surveillance - Sustained elimination of neonatal tetanus | - Some health facilities do not stock enough line listing forms - Active search in priority areas is not aggressively done. - Limited knowledge on disease surveillance among some health workers - Limited community participation in disease surveillance |
| - Advocacy, Social Mobilisation and Communication | - Active Interagency Coordinating Committee (ICC) - Political commitment - High awareness on immunization services - Structures exist in the community that can be used for communication in immunization services | - Limited community participation - Weak inter-personal communication between health worker and mothers - Lack of public awareness about risk associated with health care waste - Other channels of communication are largely confined to urban areas |

Summary of the Strengths and Weaknesses of the EPI cont.

| Component | Strengths | Weaknesses |
| --- | --- | --- |
| - Programme Management | 1. Programme considered as a priority intervention | 1. Supervision at all levels was unsatisfactory 2. Knowledge and skills regarding EPI management systems were inadequate. 3. Inadequate human resources 4. Irregular feedback to lower facilities on surveillance performance - Limited integrated implementation of childhood interventions. |

INTERAGENCY COORDINATING COMMITTEE (ICC) MEETING ON 7TH MARCH 2006 AT WHO CONFERENCE ROOM

MINUTE 03/06/2 MEMBERS PRESENT

- WHO-WR , Dr Moeti

- MOH-Director, Dr H. Somanje

- EPI Programme manager, Mrs A. Katsulukuta

- DFID-Mr Chris Phiri

- USAID- Catherine Chiphazi

- EPI-Mr M.J.M. Valle

- UNICEF-Mr Henry Mdebwe

- WHO-Dr Richard Banda

- EPI-Mr G.Z. Chirwa

MINUTE 03/06/2 APPOLOGY

Norwegian Embassy sent an apology for not participating. The Programme Manager also apologized for not sending an invitation to JICA. She further stated that it was an oversight.

MINUTE 03/06/3 WELCOME REMARKS

The chair person asked members to introduce themselves. He later welcomed members and asked them to participate fully as usual. The new WR was welcomed and thanked  for sparing time to come and participate. He also welcomed a new member from USAID, Mrs. Chiphazi. He further said that this was a long awaited meeting because of the measles SIAs. He apologized to members for starting the meeting late. He asked members to quickly look at the agenda which included:

- Feedback on measles SIAs

- Outcome on the polio documentation report

- Update on GAVI issues

- EPI Managers’ meeting for Southern Block

- Any other business

MINUTE 03/06/4 FEEDBACK ON MEASLES SIAs

The chairperson asked the EPI programme manage to give feedback on measles SIAs.

Minute 03/06/4/1 Coverage Results

The EPI Programme Manager informed members that measles SIAs was successful with coverage of 115% for measles and 111% for Vitamin A.  She further stated that following this campaign measles cases gradually dropped.

Minute 03/06/4/2 Funding

The EPI Programme Manager said funding for the measles SIAs was sourced from SWAp-US$1,163,670.00 and Measles partnership through UNICEF and WHO-US$436,190.00. The total cost of the campaign was US$1,599,860.00, and the cost of vaccinating a child was US$0.75. She also indicated that money from SWAp was accessed without problems. The director discussed with the PS and funds were released as required, and US$730,000.00 was released for vaccines.

Minute 03/06/4/3 Vaccines and Supplies

The EPI Manager also said that orders of vaccines and supplies through UNICEF came in time.  She further indicated that no stock out of vaccines and other supplies were experienced because the estimation was based on a higher target population.

It was learnt that initially the supply of cotton wool was a problem because the Internal Procurement Committee (IPC) system was slow to facility the purchase of the supply locally. The Director of Preventive Health Services came in strongly to enable the purchase of the supply.

It was also learnt that an assumption was made that pairs of scissors were available in the facilities considering the number of previous campaigns conducted; hence it was not planned for. This resulted in no supply of scissors in the sites.

Minute 03/06/4/4 Target

Members were informed that the target was changed; initially it was from 6 months to 59 months and was changed to 9 months to 59 months. The change was made in order not to confuse the public since during routine EPI services measles is given at 9 months.

Minute 03/06/4/5 Supervision

It was reported that supervisors at national level appreciated the type of partnership which was there during the measles SIAs.

Minute 03/06/4/6 Problem Makers

It was also reported that the MCH coordinators, who give problems during routine, were the ones giving problems during the SIAs. The WR posed a question what should be done to those problem makers. In response, it was indicated that the DHOs appoints them, and it was suggested that an attempt should be made to discuss with the DHOs.

It was further elaborated that previously DHOs and MCH coordinators were called to a meeting, and from those meetings DHOs learnt the experiences from other DHOs.

Minute 03/06/4/7 SWAp Funding

The WR said SWAp raised more money from donors, and did extremely well. There is need to support vertical programmes. She further said that there is need to do advocacy for SWAp mechanism to allow for unseen circumstances so that issues of emergencies are catered for.

It was also pointed out that the ministry should put up a case with donors that the money put in basket is not enough. It was reiterated that common basket at treasury will prove a problem; money meant for the Ministry of Health can go to the other ministries. It was therefore, suggested that someone should be appointed to oversee this.

Minute 03/06/4/8 Forecasting

It was felt that there is need to improve forecasting at district level. Distribution to health centres is problematic, more vaccine going to areas where there is less population.

Minute 03/06/4/9 Post Evaluation Survey (PES)

Members felt that it was important to do the post evaluation survey after conducting SIAs. However, they reiterated that timing was not appropriate. Members agreed that the PES should be planned together with the campaign next time, and the approach should be discussed.

Minute 03/06/4/10 Quality assurance

Members felt that there was need to improve districts which are performing badly. High risk areas should be targeted. In this regard members suggested that the quality assurance survey should be conducted.

Minute 03/06/4/11 Some Encountered Problems

The programme Manager informed members that some of the problems encountered included the following:

- The strike which was organized by the civil servants wanted to disrupt the campaign; however the Ministry of Health took a bold step to let the campaign proceed as planned.

- The process of getting the letter from OPC was a problem.

- SWAp meeting coincided with the SIAs

MINUTE 03/06/5 OUTCOME OF THE POLIO DOCUMENTATION REPORT

It was reported that the polio documentation report for Malawi was presented and accepted by the ARCC. The meeting took place in Zambia. It was further reported that the task force should continue meeting and sending updates to ARCC.

Members were also informed that WHO has increased the detection rate from 1 to 2 per 100,000 of under fifteen population. The rate of 1 is for certification and 2 for operational. It was also learnt that the NCC would meet the following day.

MINUTE 03/06/6 UPDATE ON GAVI ISSUES

Minute 03/06/6/1 Phase One Support for Malawi

Members learnt that phase 1 support of 5 years for Malawi ends 2006. Discussions were made on co-financing, and Malawi agreed to contribute 20% towards the purchase of pentavalent vaccine.

Minute 03/06/6/2 Malawi’s Contribution

Members were informed that in 2005, Malawi contributed US$1m. Members also learnt that an assumption was to the effect that:

- 1st price will drop, but went up

- 2nd economy will grow by 6%, but went down

- 3rd donor support will treble, but it did not.

Members also learnt that Malawi had pledged to contribute $1m per year. GAVI accepted and there are still going to be discussions between GAVI and countries.

Minute 03/06/6/3 Immunization Systems Strengthening (ISS) and Health Systems Strengthening (HSS)

Members were briefed on the ISS which is more for EPI and the HSS which is broader. They also agreed that there is need to develop the ISS and HSS proposal to GAVI which will require ICC approval and support. It was also indicated that the development of HSS should not be left to planning Unit alone; leaving it only to planning, some things will not be included. It is therefore, necessary for EPI to pioneer the development of the HSS.

Minute 03/06/6/4 GAVI Board Member

It was reported that GAVI has incorporated Malawi to be a member of GAVI board. The chairman commended Malawi for reaching that level.

Minute 03/06/6/5 Measles Second Dose

It was agreed that the introduction of the measles second dose be given ample time.

There is need for more information, more time for exploration and consultation. It was agreed that WHO should give technical support on this subject. It was also learnt that GAVI will be able to fund the measles second dose.

MINUTE 03/06/7 EPI MANAGERS MEETING FOR SOUTERN BLOCK

Minute 03/06/7/1 Dates and Venue of the Meeting

Members were informed that the EPI Managers’ meeting for Southern Block will take place from 20th to 24th March 2006 at Capital Hotel in Lilongwe, Malawi. It was learnt that the first 2 days were a preamble for the WHO focal point persons and the last 3 days for the main Programme Managers’ meeting.

Minute 03/06/7/2 Participation

Members were informed that about 80 international participants from 14 countries will participate. These included the EPI Programme Manager, Social Mobilization Officer, Logistics Officer, WHO and UNICEF focal point persons. It was suggested that Malawi should increase the number of participants because it was hosting. It was indicated that it was not yet agreed on the logistics.

Minute 03/06/7/3 Opening

Members recommended that the Minister of Health should open the meeting. The chairman thanked WHO for considering Malawi to host the function.

MINUTE 03/06/8 ANY OTHER USINESS

Minute 03/06/8/1 ICC in the Context of SWAp

Members wanted to know what would become of the ICC in view of SWAp. Members were enlightened that discussions are underway on the matter not only ICC but also other existing committees. It was further stated that an attempt by SWAp committee to come up with few committees was done three weeks ago.

Minute 03/06/8/2 Consultancy Commissioned by DFID

Mr Chris Phiri from DFID informed members that DFID commissioned the consultancy to look at the support given through UNICEF, lessons learnt, future of EPI and Malaria in the context of SWAp early April.

Minute 03/06/8/3 Farewell for Mr Henry Mdebwe from UNICEF

Mr Henry Mdebwe bid farewell to the members. He informed them that he would be leaving for Afghanistan on 22nd March for a new appointment for 2 years. He further said that Mr. Ketema or someone else will be attending ICC meetings. He also said that the advert has been put in the paper for his replacement. The chairman responded by saying that it was pleasing to have a member going abroad to assist Afghanistan. He wished him success in his contribution to global efforts.

Minute 03/06/8/4 Comprehensive Multi-year Plan (cMYP)

Members were informed that the cMYP was developed and is awaiting the WHO consultants to assist in the costing.

MINUTE 03/06/9 DATE OF NEXT MEETING

Members agreed that the date of the next meeting be 6th June, 2006 at 9.00 AM at the WHO conference room.

MINUTE 03/06/10 CLOSING

The chairman thanked also members for their active participation and he wished them good success.

Dr Habib Somanje						Geoffrey Z. Chirwa

CHAIRMAN						SECRETARY

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table   after Table 7.1.