Expanded Program on Immunization

Ministry of Health, Government of Pakistan

PROPOSAL

for support to:

IMMUNIZATION STRENGTHENING SERVICES

Under

Global Alliance for Vaccines and Immunization Phase-2

Submitted to GAVI by MOH Pakistan: April 2007

## CONTENTS

|  |  | Page |
| --- | --- | --- |
|  | Executive Summary | 2 |
|  | Signatures of the Government and National Coordinating Bodies | 3 |
|  | National Coordinating body (National Health sector Coordination Committee (NHSCC) and National Interagency Coordination Committee for Immunization (NICC)) | 4 |
|  | 2.2 National Inter-Agency Coordinating Committee for Immunization | 5 |
|  | Immunization Programme Data | 7 |
|  | Immunization Fact Sheet | 7 |
|  | Comprehensive Multi-Year Immunization Plan | 8 |
|  | Immunization Services Support (ISS) | 13 |
|  | Major lesson learned from Phase-1 | 13 |
|  | Summary of GAVI ISS (Phase-1) Funds Utilization mechanism | 14 |
|  | Financial Management and audit | 15 |
|  | Summary of the proposed mechanism for channeling and utilization of GAVI ISS (Phase-2) funds | 16 |
|  | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | 17 |
|  | Documents required for each type of support | 18 |
|  | Annex 1 – Banking Form | 19 |

## Executive Summary

Pakistan was approved for GAVI ISS support in 2001. Till date Pakistan has been approved for US$ 20.063 million, which includes US$ 10.020 million as investment and US$ 10.043 million as rewards. An amount of US$ 16,568 million has been disbursed to country and the remaining will be requested to be disbursed during 2007.

Pakistan is submitting this proposal to GAVI under Phase 2 for Immunization Services Strengthening support.  The EPI performance vis-à-vis DPT3 coverage for the period 2006 to 2010 is requested to be considered. The number of children vaccinated with DPT3 in 2005 was 3,804,921 whereas it was 4,599,341 in 2006 . This number is planned to increase to 4,702,184; 4,847,453; 5,061,601 and 5,107,962 in year 2007, 2008, 2009 and 2010 respectively. (Table 4.)  Based on this projection EPI Pakistan anticipates to receive a total of US$ 25.516 million as rewards for the period 2006-2010.

There was stagnation in the number of children reached with routine EPI antigens during 2004 and 2005. The BCG, DPT-3, HepB-3 and MCV1 coverage during 2005 was 89%, 72%, 73% and 77%. However overall  much improvement has been made in 2006 whereby  the BCG, DPT-3,HepB-3 and MCV1 coverage is reported to be 86%, 83%, 82% and 82% respectively. The TT2 coverage for pregnant women also increased from 46% in 2005 to 50% in 2006.

The basis of the proposal is the comprehensive multiyear plan of action (cMYP) 2005-2010. The population projections and the coverage targets in cMYP have been used in this proposal and are summarized below:

| Year | Target Population (live births) In million | Target population (surviving infants) in million | Planned % coverage of all Routine EPI antigens for 0-11 m | Target Population (pregnant women) In million | % coverage with TT2+ |
| --- | --- | --- | --- | --- | --- |
| 2006 | 5.911 | 5.426 | 80% | 5..911 | 65 |
| 2007 | 6.013 | 5.531 | 85% | 6.013 | 70 |
| 2008 | 6.037 | 5.572 | 87% | 6.037 | 80 |
| 2009 | 6.093 | 5.624 | 90% | 6.093 | 85 |
| 2010 | 6.149 | 5.676 | 90% | 6.149 | 90 |

The major bulk of the funds i.e. approximately 80% would be requested to be transferred to the State Bank of Pakistan. These would be utilized according to the government procedure. This will further require development of a comprehensive project document also known as PC-1. This document includes details and the estimated price of the activities and the hardware required at Federal, provincial and district level and is approved by concerned Government of Pakistan authorities. The utilization of these funds are also monitored by GOP authorities and audited annually by Auditor General of Pakistan. The remaining 20% would be requested to be transferred to WHO country office for utilization of EPI activities requiring urgent funds and for hiring short term human resource at all administrative levels for strengthening of routine EPI. These expenses would be authorised by ICC   under WHO financial rules and regulations.

This proposal has been developed in close collaboration with the key ICC members and has been discussed and approved by NICC  in its meeting held on 16th April at National Institute of Health, Islamabad.

## Signatures of the Government and National Coordinating Bodies

2.1	Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Pakistan commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Minister of Health (or senior official): | Minister of Finance (or senior official): |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: | Title: |
| Date: | Date: |

2.2	National Coordinating body  (National Health sector Coordination Committee (NHSCC) and National Interagency Coordination Committee for Immunization (NICC)):

We, the members of the ICC met on the 16th April 2007, to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1

| SN | Agency/Organisation | Name & Designation |
| --- | --- | --- |
| 1 | Ministry of Health, Government of Pakistan | Mr. Mohammad Nasir Khan, Minister for Health |
| 2 |  | Mr. Khushnood Akhtar Lashari Secretary Health |
| 3 |  | Dr. Abdul Majid Rajput, DG Health |
| 4 |  | Maj Gen (Retd) Masood Anwar,Executive Director NIH/ NC EPI |
| 5 |  | DR Huma Qureshi, Executive Director Pakistan Medical Research Council (PMRC) |
| 6 |  | Dr. Rehan A. Hafiz, National Programme Manager, EPI |
| 7 |  | Dr. Altaf Hussain Bosan, Deputy National Programme Manager, EPI |
| 8 |  | Mr. Mazhar Nisar Sheikh, Health Education Advisor |
| 9 | Provincial Health Department | Dr. Muhammad Aslam Chaudhri, Director General Health Services (DGHS), Punjab |
| 10 |  | Dr. Ruhullah Jan, DGHSs office, NWFP, Peshawar |
| 11 |  | Dr. Muhammad Qurban, DGHSs, AJK, Muzaffarabad |
| 12 | WHO | Dr. Khalif Bile Mahmoud, WHO Country Representative |
| 13 |  | Dr. Ahmed Shadoul |
| 14 |  | Dr. Werner Bouhler |
| 15 |  | Ghiasuddin Baloch |
| 16 |  | Dr. Quamrul Hasan, STC |
| 17 | WHO EMRO | Mounir Farag |
| 18 | WHO HQ Geneva | Piva Paolo |
| 19 | Rotary International Paksitan | Mr. Abdul Haiy Khan,Chairman |
| 20 | Civil Society Organization | Dr. Sania Nishter, President Heartfile, Islamabad |
| 21 | Agha Khan University | Dr. Anita Zaidi, Assistant Professor |
| 22 | World Bank | Dr. Inamul Haq, Senior Consultant |
| 23 | UNICEF | Dr. Azhar Abid Raza, Project Officer MCHC |
| 24 | DFID | Jane Edmondson, Health and Population Advisor |
| 25 | JICA | Hiloyuki Nod, Programme Officer, JICA |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr. Rehan A Hafiz | Title: National Program Manager, EPI |
| --- | --- |
| Tel No: 00 92 51 9255101, 9255360, 9255370 | Address: Federal EPI, National Institute of Health, Park Road, Chack Shahzad, Islamabad, Pakistan |
| Fax No.: 00 92 51 9255086, 9255460 |  |
| Email: drrehan@mail.comsats.net.pk |  |

The GAVI Secretariat is unable to return documents and attachments.  Unless otherwise specified by the country, documents may be shared with the GAVI Alliance partners and collaborators

2.3	National Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC are responsible for coordinating and guiding the use of the GAVI Alliance New and Under-Used Vaccine support, as well as all other immunization activities in the country.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

Name of the ICC: National Interagency Coordination Committee (NIACC/ICC)

Date of constitution of the current ICC: 21ST February 2000

Organisational structure (e.g., sub-committee, stand-alone): Stand-alone

Frequency of meetings: Quarterly

Composition.

| SN | Agency/Organisation | Name & Designation |
| --- | --- | --- |
| 1 | Ministry of Health | Mr. Mohammad Nasir Khan, Minister for Health |
| 2 |  | Mr. Khushnood Akhtar Lashari Secretary Health |
| 3 |  | Dr. Abdul Majid Rajput, DG Health |
| 4 |  | Dr. Rehan A. Hafiz, National Programme Manager, EPI |
| 5 |  | Dr. Altaf Hussain Bosan, Deputy National Programme Manager, EPI |
| 6 | Planning & Development Division | Dr. Muhammad Shafiquddin, Chief |
| 7 |  | Dr. Ali Asghar Abbasi, Deputy Chief |
| 8 | Provincial Health Department | Dr. Muhammad Aslam Chaudhri, Director General Health Services (DGHS), Punjab |
| 9 |  | Dr. Ruhullah Jan, DGHSs office, NWFP, Peshawar |
| 10 |  | Dr. Muhammad Qurban, DGHSs, AJK, Muzaffarabad |
| 11 | WHO | Dr. Khalif Bile Mahmoud, WHO Country Representative |
| 12 |  | Dr. Quamrul Hasan, STC |
| 13 | Rotary International Paksitan | Mr. Abdul Haiy Khan,Chairman |
| 14 | Civil Society Organization | Dr. Sania Nishter, President Heartfile, Islamabad |
| 15 | Agha Khan University | Dr. Anita Zaidi, Assistant Professor |
| 16 | World Bank | Dr. Inamul Haq, Senior Consultant |
| 17 | UNICEF | Dr. Azhar Abid Raza, Project Officer MCHC |
| 18 | DFID | Jane Edmondson, Health and Population Advisor |
| 19 | JICA | Hiloyuki Nod, Programme Officer, JICA |

Major functions and responsibilities of the ICC:

1. Coordinate support at national level from government and partner agencies to strengthen EPI and polio eradication activities in Pakistan.

2. Mobilize the national government and NGOs to eradicate polio and control other vaccine preventable diseases.

3. Assist Pakistan in becoming self-sufficient in its immunization programmes.

4. Establish a forum of exchange of information and dialogue on immunization programmes in the country and facilitate that dialogue by making data information sources readily available.

5. Ensure the availability of appropriate policies, advice and tools to the Pakistan government.

6. Assist the international and national community in identifying and developing support for new disease control programmes when appropriate intervention tools such as new vaccines, become available.

7. Advise the government in specific areas related to EPI and Polio Eradication where partner agencies have specialized expertise.

8. Review progress towards polio eradication, improving routine EPI coverage, and plans for further strengthening of EPI

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1.  Regular   NICC meetings at least one in each quarter. Including at least one joint NICC and National Health Sector Coordination Committee meeting in six months.

2. Expansion of NICC to include further representatives from   reputable CSO and Research institutions

3. Active involvement of NICC or its sub committees in quarterly   EPI review   meetings being held at provincial headquarters.

3.	Immunization Programme Data. (Please complete the immunization fact sheet below.)

Immunization fact sheet

Table 3.1: Basic facts for the year 2007 (most recent; specify dates of data provided and source)

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population (2007) | 168.432 million | 2007 | Federal EPI population projection based on 1998 Census and cMYP 2005-2010 |
| Infant mortality rate (per 1000) | 77 | 2007 | -do- |
| Surviving Infants* | 5.532 million | 2007 | -do- |
| GNI per capita (US$) | 847 | 2005-2006 | Pakistan Economic Survey 2005-2006. Finance Division, Government of Pakistan |
| Percentage of GDP allocated to Health | 0.51 |  | -do- |
| Percentage of Government expenditure on Health | 27.7 |  | WHO EMRO – Country Profiles (http://www.emro.who.int/emrinfo/index.asp) |

* Surviving infants = Infants surviving the first 12 months of life

Table 3.2: Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2005 | 2006 | 2005 | 2006 |  | 2005 | 2006 |
| BCG | 89 | 86 | 82 | 77.7% | Tuberculosis* | 265 | 439 |
| DTP | DTP1 | 84 | 92 | 74.6% | 74.6% | Diphtheria | 23 | 42 |
|  | DTP3 | 72 | 83 | 64.5% | 64.5% | Pertussis | 133 | 313 |
| Polio 3 | 77 | 83 | 81 | 64.4% | Polio | 28 | 6 |
| Measles (first dose) | 77 | 82 | 78 | 62.6% | Measles | 2981 | 7641 |
| TT2+ (Pregnant women) | 46 | 50 |  | 62.5% | Neonatal Tetanus *** | 518 | 548 |
| Hib3 |  |  |  | ND | Hib *** |  |  |
| Yellow Fever |  |  |  | ND | Yellow fever |  |  |
| HepB3 | 73 | 82 | ND | 60.7% | Hepatitis B sero-prevalence* |  |  |
| Vit A supplement | Mothers (<6 weeks post-delivery) |  |  | ND | ND |  |  |  |
|  | Infants (>6 months) |  |  | ND | ND |  |  |  |

* If available ** Note: JRF asks for HiB meningitis.

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

## Comprehensive Multi-Year Immunization Plan

  - A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER  2.

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3.3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement

(cMYP page  9)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: | Comments |
| --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | At Birth | X |  |  |
| OPV | At Birth & 6,10,& 14 weeks | X |  |  |
| DPT | At the age of 6.10, 14 weeks | X |  |  |
| Hep B | At the age of 6.10, 14 weeks | X |  |  |
| Tetravalent(DPT-HepB) | At the age of 6.10, 14 weeks | X |  |  |
| Measles | After the age of 9th months | X |  |  |
| TT | TT1st Dose at first contact or as early as possible during pregnancy, TT2 at least 4 weeks after TT1 TT3 at least 6 months after TT2 TT4 at least 1 year after TT3 TT5 at least 1 year after TT4 | X |  |  |
| Vitamin A |  |  | X | Pilot campaign in this regards has been undertaken. Being implemented in selected districts and will be expanded to other districts in 2007. |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP

| Major Action Points (cMYP pages 21-30) | Timeframe |
| --- | --- |
| 1. Development / updating and implementation of district micro plans (page 21) | On going |
| 2. Increase the number of static EPI centers (Page 21) | On going |
| 3. Reduced DPT-1-DPT-3 dropout rate (page 21) | On going |
| 4. Training of the staff especially y supervisors ( page 22) | On going |
| 5. Provision of required hard ware (transport and cold chain ) (page 22) | Continuous |
| 6. Involvement of LHWs for EPI activities (Page-23) | On going |
| 7 Improve financial management for timely availability of funds at district level (page-22) | On going would be strengthened in 2007 and 2008. |
| 8. Establish and implement EPI communication plan at all level (pages 26) | On going would be strengthened in 2007 and 2008. |

Table 3.4: Baseline and annual targets (cMYP page 32)

| Number | Baseline and targets |
| --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program | Year 6 of Program |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| Births | 5.689 | 5.971 | 6.013 | 6.037 | 6.093 | 6.149 | 6.204 | 6.258 | 6.311 |
| Infants’ deaths |  | 0.447 | 0.481 | 0.465 | 0.469 | 0.473 | 0.478 | 0.482 | 0.486 |
| Surviving infants | 5.262 | 5.524 | 5.532 | 5.572 | 5.624 | 5.676 | 5.762 | 5.776 | 5.825 |
| Pregnant women | 6.602 | 6.748 | 6.013 | 6.037 | 6.093 | 6.149 | 6.204 | 6.258 | 6.311 |
| Infants vaccinated with BCG | 5.044 | 5.166 | 5.111 | 5.252 | 5.484 | 5.534 | 5.708 | 5.883 | 6.059 |
| BCG coverage* | 89% | 86.5% | 85 | 87 | 90 | 90 | 92 | 94 | 96 |
| Infants vaccinated with OPV3 | 4.045 | 4.583 | 4.702 | 4.848 | 5.062 | 5.108 | 5.301 | 5.429 | 5.592 |
| OPV3 coverage** | 77% | 82.9% | 85 | 87 | 90 | 90 | 92 | 94 | 96 |
| Infants vaccinated with DTP3*** | 3.805 | 4.599 | 1.176 |  |  |  |  |  |  |
| DTP3 coverage** | 72% | 83.3% | 85 |  |  |  |  |  |  |
| Infants vaccinated with DTP1*** | 4.437 | 5.084 | 1.314 |  |  |  |  |  |  |
| Wastage rate in base-year and planned thereafter |  | 32 |  |  |  |  |  |  |  |
| Infants vaccinated with 3rd dose of Tetra(DPT-HepB) |  | 0.094 | 4.702 | 2.424 | - | - | - | - | - |
| Infants vaccinated with 1st dose of Pentavalent (DPT-Hep B-Hib) 1dose/vial all liquid vaccine |  |  |  | 2.424 | 5.062 | 5.108 | 5.301 | 5.429 | 5.592 |
| Wastage1 rate in base-year and planned thereafter |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 |
| Infants vaccinated with Measles |  |  | 4.702 | 4.848 | 5.062 | 5.108 | 5.301 | 5.429 | 5.592 |
| Measles %age coverage** |  |  | 85 | 87 | 90 | 90 | 92 | 94 | 96 |
| Pregnant women vaccinated with TT2+ |  |  | 5.111 | 5.252 | 5.484 | 5.534 | 5.708 | 5.883 | 6.059 |
| TT2+ coverage**** |  |  | 85 | 87 | 90 | 90 | 92 | 94 | 96 |
| Vit A supplement | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |  |  |
|  | Infants (>6 months) |  |  |  |  |  |  |  |  |  |  |
| Annual DPT Drop out rate(DPT1-DPT3/DPT1)*100 |  |  |  |  |  |  |  |  |  |  |
| Annual Measles Drop out rate(for countries applying for YF) |  |  |  |  |  |  |  |  |  |  |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

1 The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

Please indicate the method used for calculating TT coverage:

The reported data from the districts regarding the TT2 coverage of pregnant women is compiled at the provincial and national level

Table 3.5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |
| --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 14% | 10% | < 10% | < 10% | < 10% | < 10% | < 8% | < 6% |

Table 3.6: Summary of current and future immunization programme budget (cMYP page 32)

|  | Expenditures | Future Resource Requirements |  |
| --- | --- | --- | --- |
| Cost Category | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | Total 2006 – 2010 |
| Routine Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ | US$ |
| 1. Vaccines (routine vaccines only) | $8,524,565 | $16,016,667 | $35,038,949 | $76,784,552 | $70,165,360 | $70,808,034 | $268,813,563 |
|  | a. Traditional vaccines | $5,414,342 | $7,165,816 | $7,288,998 | $7,317,583 | $7,386,159 | $7,453,812 | $36,612,369 |
|  | b. New and underused vaccines | $3,110,223 | $8,850,850 | $27,749,951 | $69,466,969 | $62,779,201 | $63,354,222 | $232,201,194 |
| 2. Injection supplies | $1,705,563 | $3,802,850 | $4,491,568 | $4,916,869 | $4,922,471 | $4,959,615 | $23,093,373 |
| 3. Personnel | $25,117,889 | $25,620,247 | $26,140,492 | $26,663,302 | $27,196,568 | $27,740,500 | $133,361,109 |
|  | a. Salaries of full-time NIP health workers (immunization specific) | $19,270,859 | $19,656,276 | $20,049,402 | $20,450,390 | $20,859,398 | $21,276,586 | $102,292,052 |
|  | b. Per-diems for outreach vaccinators/mobile teams | $5,668,740 | $5,782,115 | $5,897,757 | $6,015,712 | $6,136,026 | $6,258,747 | $30,090,358 |
|  | c. Per-diems for supervision and monitoring | $178,290 | $181,856 | $193,333 | $197,200 | $201,144 | $205,167 | $978,700 |
| 4. Transportation | $6,877,175 | $16,879,932 | $22,596,887 | $29,083,638 | $32,722,839 | $33,826,597 | $135,109,893 |
|  | a. Fixed site and vaccine delivery | $3,964,291 | $9,714,442 | $13,258,648 | $21,773,129 | $24,496,845 | $25,323,039 | $94,566,102 |
|  | b. Outreach activities | $2,912,884 | $7,165,491 | $9,338,240 | $7,310,509 | $8,225,994 | $8,503,558 | $40,543,791 |
| 5. Maintenance and overhead | $3,910,257 | $9,521,360 | $10,673,854 | $11,585,246 | $12,324,973 | $15,083,891 | $59,189,324 |
|  | a. Cold chain maintenance and overheads | $2,965,990 | $8,539,494 | $9,653,129 | $10,518,360 | $11,213,116 | $13,990,300 | $53,914,398 |
|  | b. Maintenance of other capital equipment | $58,392 | $60,557 | $62,563 | $70,396 | $75,509 | $15,788 | $284,813 |
|  | c. Building overheads (electricity, water…) | $885,875 | $921,310 | $958,162 | $996,489 | $1,036,348 | $1,077,802 | $4,990,112 |
| 6.Short-term training | $728,867 | $793,423 | $1,047,486 | $1,153,692 | $1,268,228 | $1,461,459 | $5,724,287 |
| 7. IEC/social mobilization | $1,932,700 | $1,996,475 | $2,109,800 | $3,248,599 | $3,465,638 | $3,749,491 | $14,570,003 |
| 8. Disease surveillance | $1,679,358 | $1,712,587 | $2,175,231 | $2,060,851 | $2,097,170 | $1,852,979 | $9,898,818 |
| 9. Programme management | $964,710 | $1,132,005 | $1,824,070 | $1,935,661 | $2,026,309 | $2,122,122 | $9,040,168 |
| 10. Other routine recurrent costs | $3,039,511 | $2,241,694 | $5,080,230 | $491,667 | $501,500 | $511,530 | $8,826,621 |
|  | Subtotal Recurrent Costs | $54,480,594 | $79,717,241 | $111,178,567 | $157,924,076 | $156,691,057 | $162,116,218 | $667,627,159 |
| Routine Capital Cost |  |  |  |  |  |  |  |
| 11. Vehicles | $3,349,000 | $31,695,140 | $14,410,580 | $7,089,046 | $6,314,188 | $26,134,513 | $85,643,467 |
| 12. Cold chain equipment | $2,939,995 | $20,756,448 | $2,896,758 | $2,275,121 | $1,780,005 | $21,078,905 | $48,787,235 |
| 13. Other capital equipment | $34,500 | $5,440 | $4,335 | $35,904 | $20,205 | $17,665 | $83,550 |

|  | Subtotal Capital Costs | $6,323,495 | $52,457,028 | $17,311,673 | $9,400,071 | $8,114,398 | $47,231,083 | $134,514,252 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Campaigns |  |  |  |  |  |  |  |
| 14. Polio | $62,771,400 | $99,086,071 | $74,762,471 | $55,537,292 | $56,727,985 |  | $286,113,818 |
|  | a. Vaccines | $25,011,896 | $35,241,953 | $26,252,471 | $19,251,812 | $19,410,918 |  | $100,157,153 |
|  | b. Other operational costs | $37,759,504 | $63,844,118 | $48,510,000 | $36,285,480 | $37,317,067 |  | $185,956,665 |
| 15. Measles |  |  | $41,030,817 |  |  |  | $41,030,817 |
|  | a. Vaccines and supplies |  |  | $20,621,047 |  |  |  | $20,621,047 |
|  | b. Other operational costs |  |  | $20,409,770 |  |  |  | $20,409,770 |
| 16. MNT campaigns | $1,831,061 | $462,775 | $7,135,533 |  |  |  | $7,598,308 |
|  | a. Vaccines and supplies | $1,086,061 | $282,775 | $4,326,453 |  |  |  | $4,609,228 |
|  | b. Other operational costs | $745,000 | $180,000 | $2,809,080 |  |  |  | $2,989,080 |
| Subtotal Campaign Costs | $64,602,461 | $99,548,845 | $122,928,820 | $55,537,292 | $56,727,985 |  | $334,742,942 |
| Other Costs |  |  |  |  |  |  |  |
| 17. Shared personnel costs | $28,386,411 | $28,954,139 | $29,533,222 | $30,123,887 | $30,726,364 | $31,340,892 | $150,678,504 |
| 18. Shared transportation costs |  |  |  |  |  |  |  |
| 19. Construction of new buildings |  |  |  |  |  |  |  |
| Subtotal Optional | $28,386,411 | $28,954,139 | $29,533,222 | $30,123,887 | $30,726,364 | $31,340,892 | $150,678,504 |
| GRAND TOTAL | $153,792,962 | $260,677,254 | $280,952,282 | $252,985,325 | $252,259,804 | $240,688,192 | $1,287,562,857 |
| 20. Routine (Fixed Delivery) | $61,094,215 | $119,792,653 | $103,091,356 | $147,740,955 | $145,359,776 | $188,851,604 | $704,836,343 |
| 21. Routine (Outreach Activities) | $28,096,285 | $41,335,755 | $54,932,106 | $49,707,079 | $50,172,043 | $51,836,588 | $247,983,572 |
| 22. Campaigns | $64,602,461 | $99,548,845 | $122,928,820 | $55,537,292 | $56,727,985 |  | $334,742,942 |

Table 3.7  : Summary of current and future financing and sources of funds  (cMYP page 32.)

(Part A of Table 3.7  :  For  2005, 2006 , 2007)

| Future Financing of the Multi-Year Plan for Immunization for Pakistan (in US$) |
| --- |
|  | 2005 | 2006 | 2007 |
| Cost Category | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners |
| Routine Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |  | US$ | US$ |
| Vaccines (routine vaccines only) | - | - | - | - | - | - | - | - | - |
| Traditional vaccines | 5,414,342 | - | - | 7,165,816 | - | - | 7,288,998 | - | - |
| New and underused vaccines | - | 3,110,223 | - | - | 8,850,850 | - | - | 27,749,951 | - |
| Injection supplies | 1,235,442 | 281,621 | 188,500 | 2,717,350 | 362,000 | 723,500 | 2,442,467 | 1,325,601 | 723,500 |
| Personnel | - | - | - | - | - | - | - | - | - |
| Salaries of full-time NIP health workers (immunization specific) | 17,696,287 | 1,492,572 | 82,000 | 18,031,065 | 761,212 | 864,000 | 18,391,686 | 388,218 | 864,000 |
| Per-diems for outreach vaccinators/mobile teams | 5,236,836 | 431,904 | - | 5,341,573 | 220,271 | - | 5,448,404 | 112,338 | - |
| Per-diems for supervision and monitoring | 52,578 | - | 125,712 | 53,630 | - | 128,226 | 54,702 | - | 138,631 |
| Transportation | - | - | - | - | - | - | - | - | - |
| Fixed site and vaccine delivery | 3,586,291 | 198,000 | 180,000 | 3,730,355 | 301,000 | 140,000 | 3,847,661 | 415,000 | 170,000 |
| Outreach activities | 2,912,884 | - | - | 2,971,141 | - | - | 3,030,564 | - | - |
| Maintenance and overhead | - | - | - | - | - | - | - | - | - |
| Cold chain maintenance and overheads | 2,694,490 | - | 271,500 | 2,818,706 | - | 318,000 | 2,887,098 | - | 318,000 |
| Maintenance of other capital equipment | 58,392 | - | - | 60,557 | - | - | 62,563 | - | - |
| Building overheads (electricity, water…) | 885,875 | - | - | 903,831 | - | - | 922,142 | - | - |
| Short-term training | 42,867 | 504,000 | 182,000 | 78,423 | 222,000 | 493,000 | 173,486 | 381,000 | 493,000 |
| IEC/social mobilization | 1,150,200 | 354,000 | 428,500 | 1,100,475 | 262,000 | 634,000 | 1,222,800 | 253,000 | 634,000 |
| Disease surveillance | - | - | 1,679,358 | - | - | 1,712,587 | - | - | 2,175,231 |
| Programme management | 210,710 | 354,000 | 400,000 | 732,005 | - | 400,000 | 1,424,070 | - | 400,000 |
| Other routine recurrent costs | - | 3,039,511 | - | - | 1,120,847 | - | - | 3,977,756 | - |
| Subtotal Recurrent Costs | 41,177,193 | 9,765,831 | 3,537,570 | 45,704,927 | 12,100,180 | 5,413,314 | 47,196,641 | 34,602,864 | 5,916,362 |
| Routine Capital Cost |  |  |  |  |  |  |  |  |  |
| Vehicles | 710,417 | 330,000 | 2,308,583 | 887,667 | 1,964,678 | 670,000 | 1,673,917 | 2,818,092 | 650,000 |
| Cold chain equipment | 1,035,768 | 763,000 | 1,141,227 | 795,698 | 1,848,678 | 1,555,000 | 1,063,125 | 1,753,633 | 80,000 |
| Other capital equipment | - | 34,500 | - | - | 5,440 | - | - | 4,335 | - |
| Subtotal Capital Costs | 1,746,185 | 1,127,500 | 3,449,810 | 1,683,365 | 3,818,795 | 2,225,000 | 2,737,042 | 4,576,060 | 730,000 |
| Campaigns |  |  |  |  |  |  |  |  |  |
| Polio | - | - | - | - | - | - | - | - | - |
| Vaccines | - | - | 25,011,896 | - | - | 35,241,953 | - | - | 21,790,921 |
| Other operational costs | - | - | 30,207,603 | - | - | 63,844,118 | - | - | 31,455,614 |
| Measles | - | - | - | - | - | - | - | - | - |
| Vaccines and supplies | - | - | - | - | - | - | 5,155,262 | - | 15,465,785 |
| Other operational costs | - | - | - | - | - | - | - | - | 20,409,770 |
| MNT campaigns | - | - | - | - | - | - | - | - | - |
| Vaccines and supplies | - | - | 1,086,061 | - | - | 282,775 | - | - | 4,326,453 |
| Other operational costs | - | - | 745,000 | - | - | 180,000 | - | - | 2,809,080 |
| Subtotal Campaign Costs | - | - | 57,050,560 | - | - | 99,548,845 | 5,155,262 | - | 96,257,623 |
| Other Costs | - | - | - | - | - | - | - | - | - |
| Shared personnel costs | 28,386,411 | - | - | 28,954,139 | - | - | 29,533,222 | - | - |
| Shared transportation costs | - | - | - | - | - | - | - | - | - |
| Construction of new buildings | - | - | - | - | - | - | - | - | - |
| Subtotal Optional | 28,386,411 | - | - | 28,954,139 | - | - | 29,533,222 | - | - |
| GRAND TOTAL | 71,309,789 | 10,893,331 | 64,037,941 | 76,342,431 | 15,918,975 | 107,187,159 | 84,622,167 | 39,178,924 | 102,903,985 |
| Routine Services (Fixed and Outreach) | 71,309,789 | 10,893,331 | 6,987,381 | 76,342,431 | 15,918,975 | 7,638,314 | 79,466,905 | 39,178,924 | 6,646,362 |
| Supplemental Immunization Activities | - | - | 57,050,560 | - | - | 99,548,845 | 5,155,262 | - | 96,257,623 |
|  | - | - | - | - | - | - | - | - | - |
| Total Secure Funding | 71,309,789 | 10,893,331 | 64,037,941 | 75,287,588 | 15,918,975 | 79,652,850 | 82,720,356 | 39,178,924 | 40,689,495 |
| Total Probable Funding | - | - | - | - | - | 27,029,309 | - | - | 62,214,490 |
| Supplemental Immunization Activities | - | - | 57,050,560 | - | - | 99,548,845 | 5,155,262 | - | 96,257,623 |
|  | - | - | - | - | - | - | - | - | - |
| Total Secure Funding | 71,309,789 | 10,893,331 | 64,037,941 | 75,287,588 | 15,918,975 | 79,652,850 | 82,720,356 | 39,178,924 | 40,689,495 |
| Total Probable Funding | - | - | - | - | - | 27,029,309 | - | - | 62,214,490 |

(Part B of Table 3.7  :  For  2008, 2009 , 2010)

| Future Financing of the Multi-Year Plan for Immunization for Pakistan (in US$) |
| --- |
|  | 2008 | 2009 | 2010 |
| Cost Category | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners | Government of Pakistan( with Sub-national) | GAVI | Other EPI Partners |
| Routine Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines (routine vaccines only) | - | - | - | - | - | - | - | - | - |
| Traditional vaccines | 7,317,583 | - | - | 7,386,159 | - | - | 7,453,812 | - | - |
| New and underused vaccines | 4,244,487 | 65,222,482 | - | 4,935,472 | 57,843,730 | - | 4,980,678 | 58,373,545 | - |
| Injection supplies | 3,190,815 | 1,002,554 | 723,500 | 2,473,109 | 1,725,861 | 723,500 | 2,494,446 | 1,741,669 | 723,500 |
| Personnel | - | - | - | - | - | - | - | - | - |
| Salaries of full-time NIP health workers (immunization specific) | 18,759,520 | - | 864,000 | 19,134,710 | - | 864,000 | 19,517,404 | - | 864,000 |
| Per-diems for outreach vaccinators/mobile teams | 5,557,372 | - | - | 5,668,520 | - | - | 5,781,890 | - | - |
| Per-diems for supervision and monitoring | 55,796 | - | 141,404 | 56,912 | - | 144,232 | 58,050 | - | 147,117 |
| Transportation | - | - | - | - | - | - | - | - | - |
| Fixed site and vaccine delivery | 4,029,763 | 534,000 | 1,180,000 | 4,139,525 | - | 834,000 | 4,226,602 | - | 957,000 |
| Outreach activities | 3,091,175 | - | - | 3,152,999 | - | - | 3,216,059 | - | - |
| Maintenance and overhead | - | - | - | - | - | - | - | - | - |
| Cold chain maintenance and overheads | 2,953,408 | - | 2,318,000 | 3,018,650 | - | 2,318,000 | 3,111,564 | - | 2,318,000 |
| Maintenance of other capital equipment | 70,396 | - | - | 75,509 | - | - | 15,788 | - | - |
| Building overheads (electricity, water…) | 940,829 | - | - | 959,900 | - | - | 979,362 | - | - |
| Short-term training | 640,692 | - | 1,016,000 | 755,228 | - | 1,067,000 | 948,459 | - | 1,122,000 |
| IEC/social mobilization | 1,318,599 | - | 1,930,000 | 1,455,638 | - | 2,010,000 | 1,600,491 | - | 2,149,000 |
| Disease surveillance | - | - | 2,060,851 | - | - | 2,097,170 | - | - | 1,852,979 |
| Programme management | 1,535,661 | - | 400,000 | 1,626,309 | - | 400,000 | 1,722,122 | - | 400,000 |
| Other routine recurrent costs | - | - | 245,833 | - | - | 250,750 | - | - | 255,765 |
| Subtotal Recurrent Costs | 53,706,096 | 66,759,036 | 10,879,588 | 54,838,641 | 59,569,591 | 10,708,652 | 56,106,727 | 60,115,214 | 10,789,360 |
| Routine Capital Cost | - | - | - | - | - | - | - | - | - |
| Vehicles | 1,090,667 | - | 4,620,000 | 1,090,667 | - | 5,223,521 | 1,090,667 | - | 1,692,412 |
| Cold chain equipment | 980,195 | 1,174,667 | 80,000 | 1,174,304 | - | 605,701 | 1,009,818 | - | 4,080,000 |
| Other capital equipment | - | 35,904 | - | - | - | 20,205 | - | - | 17,665 |
| Subtotal Capital Costs | 2,070,862 | 1,210,571 | 4,700,000 | 2,264,970 | - | 5,849,427 | 2,100,485 | - | 5,790,077 |
| Campaigns | - | - | - | - | - | - | - | - | - |
| Polio | - | - | - | - | - | - | - | - | - |
| Vaccines | - | - | 19,251,812 | - | - | 19,410,918 | - | - | - |
| Other operational costs | - | - | 14,509,453 | - | - | 14,921,953 | - | - | - |
| Measles | - | - | - | - | - | - | - | - | - |
| Vaccines and supplies | - | - | - | - | - | - | - | - | - |
| Other operational costs | - | - | - | - | - | - | - | - | - |
| MNT campaigns | - | - | - | - | - | - | - | - | - |
| Vaccines and supplies | - | - | - | - | - | - | - | - | - |
| Other operational costs | - | - | - | - | - | - | - | - | - |
| Subtotal Campaign Costs | - | - | 33,761,265 | - | - | 34,332,871 | - | - | - |
| Other Costs | - | - | - | - | - | - | - | - | - |
| Shared personnel costs | 30,123,887 | - | - | 30,726,364 | - | - | 31,340,892 | - | - |
| Shared transportation costs | - | - | - | - | - | - | - | - | - |
| Construction of new buildings | - | - | - | - | - | - | - | - | - |
| Subtotal Optional | 30,123,887 | - | - | 30,726,364 | - | - | 31,340,892 | - | - |
| GRAND TOTAL | 85,900,845 | 67,969,607 | 49,340,853 | 87,829,976 | 59,569,591 | 50,890,950 | 89,548,103 | 60,115,214 | 16,579,438 |
| Routine Services (Fixed and Outreach) | 85,900,845 | 67,969,607 | 15,579,588 | 87,829,976 | 59,569,591 | 16,558,079 | 89,548,103 | 60,115,214 | 16,579,438 |
| Supplemental Immunization Activities | - | - | 33,761,265 | - | - | 34,332,871 | - | - | - |
|  | - | - | - | - | - | - | - | - | - |
| Total Secure Funding | 83,300,191 | 1,744,571 | - | 84,980,057 | - | - | 49,662,750 | - | - |
| Total Probable Funding | - | 66,225,036 | 49,340,853 | - | 59,569,591 | 50,890,950 | 38,422,054 | 60,115,214 | 16,579,438 |

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 4.1: Estimate of fund expected from ISS

|  | Baseline Year (2005) | Current Year * (2006) | Year 1** (2007) | Year 2** (2008) | Year 3** (2009) | Year 4** (2010) |
| --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 72% | 83.3% | 85% | 87% | 90% | 90% |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 3,804,921 | 4,599,341 | 4,702,184 | 4,847,453 | 5,061,601 | 5,107,962 |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 | 0 | 767,191 | 102,843 | 145,269 | 214,148 | 46,361 |
| Funds expected ($20 per additional infant) | 0 | 15,343,820 | 2,056,857 | 2,905,382 | 4.282,959 | 927,216 |

* Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

| Major Lessons learned from Phase 1 | Implications for Phase 2 |
| --- | --- |
| 1. Receipt of funds from GAVI at State Bank of Pakistan for local level expenses and transfer to UNICEF Copenhagen for procurement of hard ware as per GOP request according to the need based on annual EPI Work plan, worked smoothly. |  |
| 2. A project document (PC-1) as per GOP procedure was prepared by all the sub national level of EPI i.e provinces/ areas -seven in number. The transfer of funds from the central level to the sub national level and further to the district level took long procedural time in most of the cases. Never the less this system has strong in built transparency mechanism. This government system is widely used in the country for utilisation of funds irrespective of their source if coming through the government channel . | Instead of individual PC1 for all provinces/areas one PC1 will be prepared |
| 3. The monthly monitoring reports required by Federal EPI Cell regarding funds utilisation at provincial and district level were usually sent late to federal EPI Cell for consolidation and had often inconsistencies. This was in turn because of lack of trained manpower at these levels and gathering of data from many persons/sources. | Under the proposed modified mechanism for phase 2 i.e one PC-1 at federal level, there would be minimum financial activities at these levels utilising funds coming through GOP channel, thus less workload for the staff. In addition where required short term staff could be recruited with relative ease through WHO administrative and financial system . |
| 4. The NICC in its various meetings critically examined the progress in funds utilization and greatly helped in facilitation of the process. | The NICC would be involved further for this purpose , through more in depth discussions on the progress towards GAVI ISS funds utilization. |
| 5. Funds were not readily or not at all available for the gaps identified in district micro plans for certain activities , because these were not envisaged at the time of development of PC1s. | A portion of the funds would be available through WHO for such activities ( explained below) |

Summary of GAVI ISS (Phase 1) Funds Utilization Mechanism

Pakistan was approved for GAVI ISS (Phase 1) funds in 2001. It was agreed by the ICC that these funds would be used through government channels, which required preparation and approval of the project documents (PC-1s). Consequently  project documents (PC-1s) were prepared for  all the provinces/areas (7 in number) including Federal EPI Cell. The share of each province/area was agreed by the ICC and approved by the competent authority of GoP.

The PC-1s were developed for a period of five years (2001-2006) corresponding with the duration of the GAVI ISS (Phase 1) support. The PC 1 describes the activities along with their budget line on annual basis. However the actual implementation started in 2003. Under this arrangement based on the cumulative requirements of the PC-1s, GAVI was requested each year for transfer of the required funds to:

- State Bank of Pakistan, for local level expenditures i.e. trainings, salaries, meetings, office & health facility furniture etc.

- UNICEF Copenhagen, for procurement of hardware i.e. cold chain equipment, office equipment, transport etc.

The utilization of the funds for local level expenditure was not often timely because of procedural delays and also availability of funds in some cases for similar activities through other donors requiring less procedural inputs.

The utilization of the funds for procurement through UNICEF was generally smooth and the procured hardware was delivered to province/areas according to the PC-1 schedule.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

The GAVI ISS (Phase 1) funds available to Pakistan  were used according to the project documents (PC-1s) prepared at the beginning of 2001, as explained above. These funds were not “flexible” in real terms. These were/are being used for the following:

- Cold chain equipment at different levels for replenishment of the old cold chain units and establishment of the new EPI Centres.

- Transport (bicycles, motorbikes, supervisory vehicles, trucks etc) for service delivery and supervision.

- Office equipment for strengthening of the recording and reporting.

- Office furniture mainly for establishment of static EPI Centres.

- Partial salaries of the vaccinators and other EPI staff recruited under the PC-1s.(The balance amount of the salaries is being provided by GoP).

- Trainings at all levels for supervision, district level micro planning, cold chain management, AEFI etc.

- Social mobilization activities

- Meetings for programme management and progress review.

- Performance rewards to individual  EPI staff /district EPI teams.

Financial Management and Audit

- The funds are utilized according to the Financial Management System for GAVI Funds utilization, prescribed by the Controller General of Accounts, Government of Pakistan.

- The system has strong inbuilt component for financial discipline and monitoring mechanism.

- The funds are audited by Government of Pakistan as per its procedure on annual basis.

- The funds transferred and utilized through GOP will be in accordance with the GOP financial rules. The funds transferred and utilized through WHO or UNICEF will  be spent as per financial rules of these organizations . All funds would be subject to  internal  and external  audit  in accordance with the rules and regulations of the respective a organization/agency through which these are being utilized.  ICC will be regularly updated on the utilization of the funds.

If you have not received ISS support before, please indicate:

a) when you would like the support to begin:

June 2008

b) when you would like the first DQA to occur:

1st DQA was conducted in 2003 .

Third party CES was conducted in 2006.

The next DQA may be conducted by GAVI when ever it requires.

c) How you propose to channel the funds from GAVI into the country:

Summary of the proposed mechanism for  channelling  and  utilization of GAVI ISS (Phase-2) funds

Based on the experience from the utilization of GAVI ISS (Phase-1) funds, it is proposed that the funds under this phase would be  channelled and utilized as follows:

- Through GoP:

Only one PC-1 at federal level would be developed which would have separate chapter for each provinces/area according to the share agreed by ICC. The major focus of the PC-1 would be to procure necessary hardware for the provinces/areas including districts and salaries of the additional staff recruited for EPI and to be ultimately absorbed in the health department after end of this support.

2. 	Through UNICEF

Based on the PC-1 requirements UNICEF may be requested to procure all or selective hardware as per recommendation of the ICC. The estimated funds for the procurements  through UNICEF and related expenses would be requested by the GoP to be transferred to UNICEF Copenhagen

3.	Through WHO:

Approximately 20% of the funds would be requested to be transferred to the WHO country office. These will be utilized for:

- Recruitment of temporary staff at different levels using WHO administrative and financial system and with the approval of ICC or its nominated sub committee.

- Provision of support / fund to the districts to undertake district level activities e.g. training, meeting, seminars, evaluation etc, based on the plans approved by the ICC or its nominated sub committee.

d) how you propose to manage the funds in-country:

Described above

e) who will be responsible for authorising and approving expenditures:

For funds to be channelled and utilized through GOP:

Project document  (PC1) will be developed  in close collaboration of National ICC This document  includes all the activities , recruitments,  procurements  etc  and their estimated cost. The expenditure will be authorized by the GOP nominated competent authority as per GOP procedures. This authority will also authorize expenditure for procurement  through UNICEF if agreed by NICC and GOP.

For funds to be channelled and utilized through WHO

National ICC will authorise all the expenditures. It may nominate a sub committee for this purpose.

  - Please complete the banking form (annex 1) if required

## 5. Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC)

National ICC   highly appreciates the role of GAVI  in improving the immunization services in the country through provision of its support under different windows.

ICC takes note with pleasure that EPI has shown a significant improvement in DPT3 coverage last year i.e 2006.

With decentralization taking its roots , the Districts are gradually taking increasing responsibility in ensuring that there target population receives maximum benefit of the immunization services.

Though GOP and respective provincial governments are providing maximum possible support for immunization programme in the country, the support under GAVI ISS phase 2 will further help in enhancing the availability of resource required for strengthening of the routine immunization.

## DOCUMENTS REQUIRED FOR EACH TYPE OF SUPPORT

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed | 1 | 16 April 2007 |
| ALL | Comprehensive Multi-Year Plan (cMYP) | 2 | 2005-2010 |
| ALL | WHO / UNICEF Joint Reporting Form | 3 | Jan-Dec 2005 to Dec 2006 |
| If relevant | Endorsed minutes of the ICC meeting discussing the requested GAVI support | 4 |  |
|  | Record note | 5 | 17 th March 2007 |

* Please indicate the duration of the plan / assessment / document where appropriate

** Where available

ANNEX 2: BANKING FORM

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  | Banking Form |
| --- | --- | --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |
| Name of Institution: (Account Holder) | Ministry of Health, Government of Pakistan. |
| Address: |  |
|  | C Block, Pak. Secretariat Buildings Islamabad. |
| City – Country: | Islamabad—Pakistan. |
| Telephone No.: | 051-9255101 | Fax No.: | 051-9255086 |
| Amount in USD: | (To be filled in by GAVI Secretariat) | Currency of the bank account: | Pak. Rupees. |
| For credit to: Bank account’s title | Government of Pakistan |
| Bank account No.: | Federal Government Account No. 1 (Non-Food) |
| At: Bank’s name | State Bank of Pakistan, Karachi |
| Is the bank account exclusively to be used by this program? | YES ( ) NO ( v ) |
| By whom is the account audited? | Auditor General of Pakistan |
| Signature of Government’s authorizing official: |
| Name: | S Ministry of Health, Government of Pakistan. C Block, Pak. Secretariat Buildings Islamabad. Islamabad—Pakistan. Government of Pakistan Federal Government Account No. 1 (Non-Food) State Bank of Pakistan, Karachi | Seal: |
| Title: | Secretary to the Government of Pakistan Ministry of Health, Islamabad. |  |
| Signature: |  |  |
| Date: |  |  |

| SECTION 2 (To be completed by the Bank) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name: |  |  |
| Branch Name: |  |  |
| Address: |  |  |
| City – Country: |  |  |
| Swift code: |  |  |
| Sort code: |  |  |
| ABA No.: |  |  |
| Telephone No.: |  |  |
| Fax No.: |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: | Name of bank’s authorizing official: |
| 1 Name: Title: |  | Signature: |  |
|  |  | Date: |  |
| 2 Name: Title: |  | Seal: |
| 3 Name: Title: |  |  |
| 4 Name: Title: |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative: |
| Name |  |
| Signature |  |
| Date |  |

# Footnotes

JRF   for Jan- Dec 2005

Federal EPI Data and draft JRF for Jan-Dec 2006

JRF   for Jan- Dec 2005

Federal EPI Data and draft JRF for Jan-Dec 2006

Except for 2006  target population  which is based on the JRF 2005 and Draft JRF 2006.

Rewards for 2006-2010

coverage evaluation survey by Contech International.

JRF (January-December 2006)

Draft JRF (January-December 2006)

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

Based on introduction of Hib vaccine as Pentavalent (DPT-HepB-Hib) in immunization schedule beginning July 2008.

Figures for 2005 , as per JRF Jan-Dec 2005

Draft JRF for Jan-Dec 2006

Including third dose of vaccine containing DPT

Provincial Health Departments, Provincial Planning & Development department, Ministry of Health and Planning & Development Division of Government of Pakistan.

Financial year(1st July 2003- 30th June 2004)

An amount of US $50,000 was transferred to WHO for recruitment of human resource as per PC-1s.