Здравствуйте, уважаемая госпожа Нилгун. Отправлем Вам ответы для комментарии IRC.

|  |  |  |
| --- | --- | --- |
| **Comment** | **Suggested way forward** | **Timeframe** |
|   | How will the comment be addressed | By which deadline/timeframe |
| Clarify the CSO involvement in the preparation and approval of the IPV submission and ICC decisions.   | CSO was not involved in the preparation and approval of IPV submission in Tajikistan. However, there are local volunteers currently working in GBAO, Sughd and Khatlon oblasts who could be involved in information dissemination during introduction of new vaccine. MOH is planning to involve these volunteers through partners-support for improving acceptance of the community. | Jun-Aug 2015 |
| Clarify the inconsistencies of VIG and Implementation plan (budget items are different, figures do not coincide, detailed budget on printing- unit cost, quantity for printing materials is not provided) . | Please find attached the revised implementation plan and detailed budget. |   |
| Clarify the status of the NITAG and its role in IPV introduction.  | In 2010 the NITAG was established in Tajikistan for providing technical support to the RCIP. However, committee is not fully functional at the moment due to retirement and transfer of members. New committee will be established in near future. |  1st quarter 2015 |
| Specify the timeline for the new cMYP development.  | With technical support from WHO EURO, UNICEF and other partners, cMYP for 2016-2020 will be developed next year. | 2nd quarter 2015  |
| Confirm that UNICEF procured and installed 4 cold rooms in 2013 along with 100 refrigerators  | UNICEF had installed 4 cold rooms; 2 in Dushanbe (30 cub meters), 1 in GBAO (10 cub meter) and 1 in Rasht valley (10 cub meter). Also, 100 refrigerators were purchased and distributed in the country last year. | Completed  |
| Confirm that the remaining short term storage capacity gap indicated in the introduction plan will be met by the equipment requested in the IPV budget and that this will be adequate to address most of the additional capacity needed to introduce Rota vaccine. | With the additional cold chain equipment budgeted in the rota -and IPV introduction grants, the cold chain gap in the country will be addressed. | a) Aug-Sep 2014 from Rota introduction grantb) Oct-Nov 2014 from IPV grant |
| The FIC data indicated in the horizontal bar chart on P12 of the application is not consistent with typical FIC values in similar vaccination calendars and indicates an important deficit in vaccine storage space. Please review this chart and explain why the text of the proposal indicates adequate storage space for the introduction of IPV and other vaccines if the data in this chart is correct.  | There is a mistake in the chart mentioned on page 12 of the application, hence we have removed it. Kindly consider the attached document as final. |   |
| Review the budgetary provision indicated for solar hybrid ILRs. (Not part of IPV/VIG however) | As per the available information the country is not planning to buy the solar hybrid ILRs |   |