Global Alliance for Vaccines and Immunization (GAVI)

APPLICATION FORM FOR COUNTRY PROPOSALS

For Support to:

Immunization Services

COUNTRY: VIETNAM

15 June 2006

This document is accompanied by an electronic copy on CD for your convenience. Please return a copy of the CD with the original, signed hard-copy of the document to:

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries to: Dr Julian Lob-Levyt, jloblevyt@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be in English or French.

## CONTENTS

| SECTION |  | SUPPORT | PAGE |
| --- | --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies |  | 3 |
|  | - Government and the Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 3 |
|  | - The Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 4 |
| 3. | Immunization Programme Data | ALL | 6 |
|  | - Immunization Fact Sheet |  | 6 |
|  | - Comprehensive Multi-Year Immunization Plan |  | 7 |
| 4. | Immunization Services Support (ISS) | ISS | 10 |
| 5. | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | ALL | 12 |
| 6. | Documents required for each type of support | ALL | 13 |
| Annex 1 – Banking Form |  | ISS | 15 |

## Executive Summary

This proposal of the Socialist Republic of Viet Nam seeks funding from the Global Alliance for Vaccine and Immunization (GAVI) under the scheme of the “Immunization Services Support” (ISS).  Funding is being requested to support the development of immunization services as part of the health system to all areas of the country.

The International EPI Review conducted in November 2003 revealed that Viet Nam’s EPI performed well and indeed was expanding, despite important financial, human, and geophysical access constraints. However, it identified wide variation and potential for improvement in the conduct of key activities, particularly in vaccinating children in difficult to reach areas. Injection safety was of a good standard, but certain other technical areas, such as waste disposal and the cold chain, were thought to merit close attention in future. That the EPI continued to perform well despite limited resources was a credit to the dedication of health workers at all levels.  Against a background of high routine coverage, polio-free status in 2000 and elimination of maternal and neonatal tetanus in 2005, Viet Nam has already made remarkable progress toward the new WHO Western Pacific Region goals of measles elimination and hepatitis B control. Cases of measles have decreased dramatically since the national campaign in 2002 and 2003, and the introduction of hepatitis B vaccine in the EPI has been very successful thanks to the phase I support of GAVI.

The review also indicated that more financial resources were needed to ensure that operational costs (for payment of allowances, local supplies, transport and communication), and supplies of vaccine are adequate for the challenge of service delivery, particularly for remote populations. Funding was also needed for the replacement of an ageing cold chain, training and safe injection materials.  Strengthening the number and capacity of human resources was also perceived to be a key to the achievement of Viet Nam’s future EPI goals.

This application for ISS requests a total of 2,403,080 USD on the basis of the intention to cover a total of 120,154 additional children from the target number of children required to maintain the current DPT3 coverage of 95% during 2006-2010 period.  Such additional efforts will raise the annual DPT3 coverage on average up to 96.5% instead. We propose the first data quality assessment (DQA) to take place in 2008.

Viet Nam requests the ISS to be transferred through its Ministry of Health.  The fund should subsequently be forwarded to the National Expanded Programme on Immunization.  The National Steering Committee for the EPI will have overall responsibility for managing ISS fund provided.  The Committee will coordinate closely with national and international partners through the Interagency Coordinating Committee (ICC) to meet related resource needs for the EPI.  The Ministry of Health, Viet Nam will authorize and approve all expenditures.  These arrangements are agreed upon by all ICC steering members.

## Signatures of the Government and National Coordinating Bodies

## Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Viet Nam commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: …………………………………… …………………………………………… | Title: …………………………………… …………………………………………… |
| Date: …………………………………… | Date: …………………………………… |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the ICC met on the 7th of June 2006 to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER 3.

| Agency/Organisation | Name/Title |
| --- | --- |
| WHO | Dr. Hans Troedsson, WHO Representative in Viet Nam |
| UNICEF | Mr. Jesper Morch, UNICEF Representative in Viet Nam |
| PATH | Mrs. Michelle Gardner, PATH Representative in Viet Nam |
| JICA | Ms. Junko Sato, Project Formulation Advisor, JICA |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Prof. Do Si Hien | Title: National EPI Manager |
| --- | --- |
| Tel No. +84 4 8214 680 | Address: National Institute of Hygien and |
|  | Epidemiology, |
| Fax No.: +84 4 8213782 | 1 Yersin street, Hanoi, |
|  | Vietnam |
| Email: dshien@fpt.vn |  |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC are responsible for coordinating and guiding the use of the GAVI ISS support.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

|  | - Name of the ICC: Inter-agency Co-ordinating Committee for EPI (ICC). In addition, there is a National Steering Committee for EPI (NSC) consisting of national partners (governmental and non-governmental) responsible for direct management of the EPI in Viet Nam. |  |  |  |
| --- | --- | --- | --- | --- |
|  | Date of constitution of the current ICC: 2001 |  |  |  |
|  | Organisational structure (e.g., sub-committee, stand-alone): |  |  |  |
|  | Steering Committees for EPI have been established and are functioning at all levels, including: - Central level: National Steering Committee for EPI (NSC) - Provincial level: Provincial Steering Committee for EPI - District level: District Steering Committee for EPI - Commune level: Communal Steering Committee for EPI In addition to the above, from September 2000, the Inter-agency Co-ordinating Committee (ICC) was reconvened with terms of reference and composition described in Document 5. |  |  |  |
|  | Frequency of meetings: Quarterly and whenever necessary. |  |  |  |
|  | Composition: |  |  |  |
| Function |  | Title / Organization | Name |  |
| Chair |  | See Document 5 | See Document 5 |  |
| Secretary |  | See Document 5 | See Document 5 |  |
| Members |  | See Document 5 | See Document |  |

Major functions and responsibilities of the ICC:

- Review and endorse annual and five-year plans, country proposals and reports and other relevant documents prepared by the National EPI;

- Review progress in achieving milestones/objectives;

- Co-ordinate actions needed to overcome constraints and achieve milestones/objectives;

- Mobilise funding and assist in planning and monitoring in areas of priority as determined by the National Steering Committee for EPI.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

- To more regularize the ICC meeting organization.

- To form the ICC  working group on donor communication for EPI funding following the ICC decision taken during its 12th meeting on 3 March 2006..

3.   ICC working group to cooperate more closely with the National EPI quarterly review meetings.

## Immunization Programme Data

Please complete the immunization fact sheet below, using data from available sources.

## Immunization Fact Sheet

Table 1: Basic facts for the year 2005 (most recent; specify dates of data provided)

| Population | 83,123,000 (World Health Report 2006) | GNI per capita** | 540 $US |
| --- | --- | --- | --- |
| Surviving Infants* | 1,545,475 | Infant mortality rate | 18.1 /1000 (as of 2004, ref. Health Statistics Yearbook 2004) |
| Percentage of GDP allocated to Health | 5.4% as of 2003 (World Health Report 2006) | Percentage of Government expenditure on Health | 5.6% as of 2003 (World Health Report 2006) |

* Surviving infants = Infants surviving the first 12 months of life

** World Development Indicators database, World Bank, 18 April 2006

Table 2: Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2004 | 2005 | 1998 | 2003 |  | 2004 | 2005 |
| BCG |  | 95.6 | 94.8 | 95 | 95.7 | Tuberculosis* |  |  |
| DTP | DTP1 | 91.6 | 94.3 | ND | 94.8 | Diphtheria | 49 | 36 |
|  | DTP3 | 96.2 | 94.6 | 92.2 | 91.6 | Pertussis | 328 | 194 |
| Polio 3 |  | 96.3 | 94.5 | 92.1 | 92.8 | Polio | 0 | 0 |
| Measles (first dose) |  | 97.1 | 95.2 | 82.6 | 82 | Measles | 217 | 410 |
| TT2+ (Pregnant women) |  | 89.5 | 93 | 92 | 86.6 | NN Tetanus | 46 | 35 |
| Hib3 |  | NA | NA | NA | NA | Hib ** | ND | ND |
| Yellow Fever |  | NA | NA | NA | NA | Yellow fever | NR | NR |
| HepB3 |  | 94.2 | 93.7 | ND | ND | hepB sero-prevalence* | ND | ND |
| Vit A supplement | Mothers (<6 weeks post-delivery) | 80.5 | 81.2 | 52.2 (2000 survey) | 61 (2004 survey) |  |  |  |
|  | Infants (>6 months to 36 months) | ND | 99.2 |  |  |  |  |  |

* If available ** Note: JRF asks for Hin meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

1998 International EPI Review (EPI coverage survey including children aged 9-23 months old)

2003 International EPI Review (EPI coverage survey including children aged 9-23 months old)

2000 vitamin A supplementation survey (mothers <6 weeks of delivery and children 6-36 months old)

2004 vitamin A supplementation survey (mothers <6 weeks of delivery and children 6-36 months old)

## Comprehensive Multi-Year Immunization Plan

A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER 2

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement

(cMYP pages…1……………)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | Birth |  |  |  |
| Hep B | Birth, 2 months, 4 months |  |  |  |
| DPT | 2 months, 3 months, 4 months |  |  |  |
| Td booster | Planned at 2 years old | * |  | Proposed to be introduced from 2008 |
| Measles | 9 months |  |  |  |
| Measles 2nd dose | 6 years |  |  | Planned to be introduced in 2006. Since 2007 with GAVI support |
| Japanese encephalitis | 12 months, 13 months, 25months |  |  |  |
| Cholera | Two doses 2-5 years |  |  |  |
| Typhoid | Single dose 3-10 years |  |  |  |
| Hib vaccine |  |  |  |  |
| Rubella | Vaccination for 14 year-old girls and subsequent gradual introduction of the routine dose for <1 year |  |  | Vaccination for 14 year-old girls during 2007-2010 and gradual introduction of the routine dose for <1 year starting from 2007 and nation-wide implementation from 2009 |
| Vitamin A | 6 month to 36 months every 6 months |  |  |  |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP

| Major Action Points (cMYP pages 12-15) | Timeframe |
| --- | --- |
| 1. Strengthening of data management at district level. Strengthening of AEFI surveillance system at national and lower levels. | 2006-2010 |
| 2. >90% children under 1 year old fully immunized with seven antigens at district level | By 2010 |
| 3. Training and retraining of the health workers at commune health level to increase the health workers competence and capacity | 2006-2010 |
| 4.Introduce and expand new vaccines and underutilized vaccines such as vaccine for Japanese encephalitis, introduction of 2nd dose of measles, booster for DPT vaccine and rubella | 2007-2010 |
| 5. Increase government funding of immunization programs by taking over funding of AD syringes and other injection safety supplies | 2007 |

Table 4: Baseline and annual targets (cMYP pages 19.)

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program | Year 6 of Program |
|  |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Births |  |  |  |  |  |  |  |  |  |
| Infants’ deaths |  |  |  |  |  |  |  |  |  |
| Surviving infants |  | 1545475 | 1567657 | 1594187 | 1616070 | 1640310 | 1664920 |  |  |
| Pregnant women |  | 1545475 | 1567657 | 1594187 | 1616070 | 1640310 | 1664920 |  |  |
| Infants vaccinated with BCG |  | 1465055 | 1490224 | 1512578 | 1535266 | 1558295 | 1581674 |  |  |
| BCG coverage* |  | 94.8% | 95% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated with OPV3 |  | 1459908 | 1490224 | 1512578 | 1535266 | 1558295 | 1581674 |  |  |
| OPV3 coverage** |  | 94.5% | 95% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated with DTP3*** |  | 1461520 | 1490224 | 1512578 | 1535266 | 1558295 | 1581674 |  |  |
| DTP3 coverage** |  | 94.6% | 95% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated with DTP1*** |  | 1457302 | 1505911 | 1528499 | 1551427 | 1574698 | 1598323 |  |  |
| Wastage rate in base-year and planned thereafter |  | 38% | 36% | 34% | 32% | 31% | 30% |  |  |
| Infants vaccinated with 3rd dose of Hep B |  | 1448721 | 1411792 | 1432968 | 1454463 | 1558295 | 1581674 |  |  |
| Hep3 Coverage** |  | 93.7% | 90% | 90% | 90% | 95% | 95% |  |  |
| Infants vaccinated with 1st dose of Hep B |  | 1476503 | 1490224 | 1514477 | 1535266 | 1574698 | 1598323 |  |  |
| Wastage1 rate in base-year and planned thereafter |  | 18% | 18% | 18% | 15% | 15% | 15% |  |  |
| Infants vaccinated with Measles |  | 1471332 | 1490224 | 1512578 | 1535266 | 1558295 | 1581674 |  |  |
| Measles coverage** |  | 95.2% | 95% | 95% | 95% | 95% | 95% |  |  |
| Pregnant women vaccinated with TT+ |  | 1436015 | 1411791 | 1432968 | 1454463 | 1476279 | 1498428 |  |  |
| TT+ coverage**** |  | 93% | 90% | 90% | 90% | 90% | 90% |  |  |
| Vit A supplement2 | Mothers (<6 weeks from delivery) | 81.2% |  |  |  |  |  |  |  |
|  | Infants (>6 months) | 99% |  |  |  |  |  |  |  |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Please indicate the method used for calculating TT and coverage:

…………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………

Table 5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 20… | 20… |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | -0.3 | 1 | 1 | 1 | 1 | 1 |  |  |

Table 6: Summary of current and future immunization programme budget (cMYP pages 16-19)

|  | Estimated costs per annum in US$ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Current Year 2006 | Year 1 2007 | Year 2 2008 | Year 3 2009 | Year 4 2010 | Year 5 |
| Title 1 Vaccines | 7,258,220 | 9,534,303 | 9,703,413 | 11,012,156 | 10,816,700 |  |
| Title 2 injection equipment | 2,915,110 | 3,396,560 | 3,267,240 | 3,544,344 | 3,456,324 |  |
| Title 3 cold chain equipment | 469,167 | 3,322,456 | 4,403,584 | 4,350,000 | 4,900,000 |  |
| Title 4 Operational costs at central and regional levels | 603,164 | 632,911 | 632,911 | 632,911 | 632,911 |  |
| Title 5 Operational costs at local levels | 2,545,368 | 4,226,380 | 2,598,321 | 2,678,912 | 2,656,760 |  |
| Title 6 Total operational costs at all levels | 3,148,532 | 4,859,291 | 3,231,232 | 3,311,823 | 3,289,671 |  |
| …………………………. |  |  |  |  |  |  |
| …………………………… |  |  |  |  |  |  |
| GRAND TOTAL | 13,791,029 | 21,112,610 | 20,605,469 | 22,218,323 | 22,462,695 |  |

Table 7: Summary of current and future financing and sources of funds (cMYP pages 16-19)

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Funding source | Current Year 2006 | Year1 2007 | Year 2 2008 | Year 3 2009 | Year 4 2010 | Year 5 |
| 1 | Government (central govt) | 8,171,972 | 11,071,702 | 13,015,038 | 15,430,318 | 14,880,252 |  |
| 2 | WHO | 125,000 | 2,625,000 | 302,000 | 100,000 | 100,000 |  |
| 3 | UNICEF | 150,000 | 100,000 | 100,000 | 100,000 | 100,000 |  |
| 4 | PATH | 65,000 | 20,000 | 0 | 0 | 0 |  |
| 5 | JICA | 349,167 | 274,926 | 272,289 | 0 | 0 |  |
| 6 | GAVI | 3,302,500 | 1,940,000 | 1,050,000 | 1,100,000 | 1,100,000 |  |
| 7 | Luxembourg Gov. | 0 | 2,352,600 | 3,600,000 | 3,600,000 | 4,500,000 |  |
| 8 | Local governments | 1,385,314 | 1,200,000 | 1,200,000 | 1,200,000 | 1,200,000 |  |
| GRAND TOTAL |  | 13,548,953 | 19,584,228 | 19,539,327 | 21,530,318 | 21,880,252 |  |

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 8: Estimate of fund expected from ISS

|  | Baseline Year | Current Year * 2006 | Year 1** 2007 | Year 2** 2008 | Year 3** 2009 | Year 4** 2010 | Year 5** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 94.6 | 95 | 95 | 95 | 95 | 95 |  |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 1461520 | 1490224 | 1512578 | 1535266 | 1558295 | 1581674 |  |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  | 28704 | 22354 | 22688 | 23029 | 23379 |  |
| Funds expected ($20 per additional infant) |  | 574080 | 447080 | 453760 | 460580 | 467580 |  |

*  Projected figures

**  As per duration of the cMYP

If you have not received ISS support before, please indicate:

a) when you would like the support to begin: 2006

b) when you would like the first DQA to occur: 2008

c) how you propose to channel the funds from GAVI into the country:

GAVI – MOH - EPI

d) how you propose to manage the funds in-country:

The National Steering Committee for the EPI will have overall responsibility for managing ISS, this committee will coordinate closely with national and international partners through the Interagency Coordinating Committee to meet related resource needs for the EPI

e) who will be responsible for authorising and approving expenditures:

MOH

  - Please complete the banking form (annex 1) if required

## 5. Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC)

- The goal of universal childhood immunisation (UCI) and high immunisation coverage with six conventional EPI antigens has been achieved and maintained since 1989.  With support from GAVI hepatitis B vaccine was introduced in the routine EPI nationwide in 2002.  In 2005, 1,461,520 children <1 year were immunised with DPT3, representing about 94.6% of the total eligible children.

- More financial resources are needed to ensure that operational costs (for payment of allowances, local supplies, transport and communication), and supplies of vaccine are adequate for the challenge of service delivery, particularly for remote populations. Funding is also needed for the replacement of an ageing cold chain, training and safe injection materials.

- Support to Viet Nam in the ISS is strongly advocated by all ICC partners, including WHO, UNICEF, JICA and PATH/CVP.

## DOCUMENTS REQUIRED FOR EACH TYPE OF SUPPORT

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form | 1 | 2005 |
| ALL | Comprehensive Multi-Year Plan (cMYP) | 2 | 2006-2010 |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed | 3 | 16 Mar 2006 & 7 Jun 2006 |
| If relevant | Endorsed minutes of the ICC meeting discussing the requested GAVI support | None (Until the last ICC meeting on 3 March, the GAVI phase II application guidelines was not available.) |  |
|  | Terms of Reference of the Interagency Coordinating Committee for the EPI. | 5 |  |

* Please indicate the duration of the plan / assessment / document where appropriate

** Where available

ANNEX 1

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

Completeness of reporting

* VPD or Surv

Examples:

| - Immunization Schedule | - Source of vaccine, vitamin A and AD syringes |
| --- | --- |
| Complete the following table to describe the 2005 national immunization schedule (routine services). Include all doses administered to young children, adolescents and adults on a routine basis. Include vitamin A if delivered through routine immunization services. If there are plans to introduce the vaccine, enter month and year of planned introduction in column G. Please add any other vaccines that do not appear in this list at end of this section. | Complete the following form to show source of vaccine and AD syringe distributed by the Ministry of Health for routine immunizations for the reporting period 1 January – 31 December 2005. If different vial sizes or manufacturers were used for the same vaccine, please split the row or use extra row(s) at end of this section |

| #### W2005 | Have there been any changes to the immunization schedule in 2005 or planned for 2006/7? | Yes No | If yes, please provide details: |
| --- | --- | --- | --- |

| Vaccine/supplement |  |  |  |  |  | Recommended age of administration |  |  |  |  |  |  |  |  | G. planned (Month/Year) |  | Geographic area Check “x” |  |  | K. Vial size (no. of doses) | L. Manufacturer name & country of manufacturer | M. Procurement source(s) Indicate if - procured through UNICEF, WHO, PAHO, or - if donated (name agency) or - if procured directly from producer (put MOH) |  | N. Total number of doses received at national level |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | B=Birth; D=Days; W=Weeks; M=Months; Y=Years |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| For Pertussis the whole cell vaccine is assumed unless the "a" (acellular) box is checked |  |  |  |  |  | A. 1st dose | B. 2nd dose |  | C. 3rd dose |  | D. 4th dose |  | E. 5th dose | F. 6th dose |  |  | H. Nat-ional | I. Sub-national | J. Indicate specific target groups |  |  |  |  |  |
| 2010 | BCG | Bacille Calmette-Guérin vaccine |  |  |  | B |  |  |  |  |  |  |  |  | / |  |  |  |  | 10&20 | IVAC & Pasteur Institute HCM City, Vietnam | MOH | 4,000,000 |  |
| 2020 | DTP | Diphtheria and tetanus toxoid with pertussis vaccine |  |  | a | M2 | M3 |  | M4 |  |  |  |  |  | / |  |  |  |  | 20 | IVAC, Vietnam | MOH | 7,500,000 |  |
| 2030 | DTPHepB | Diphtheria and tetanus toxoid with pertussis and HepB vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2040 | DTPHepBIPV | Diphtheria and tetanus toxoid with pertussis, HepB and IPV vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2050 | DTP Hib HepB | Diphtheria and tetanus toxoid with pertussis, Hib and HepB vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2060 | DTP Hib | Diphtheria and tetanus toxoid with pertussis and Hib vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2070 | DTP Hib IPV | Diphtheria and tetanus toxoid with pertussis, Hib and IPV vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2080 | DTP Hib HepB IPV | Diphtheria, tetanus toxoid with pertussis, Hib, hepatitis B and IPV vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2090 | DTP IPV | Diphtheria and tetanus toxoid with pertussis vaccine and IPV |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2100 | Dip | Diphtheria vaccine |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2110 | DT | Tetanus and diphtheria toxoid children's dose |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2120 | Td | Tetanus and diphtheria toxoid for older children/adults |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2130 | P | Pertussis vaccine |  |  | a |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2140 | HepA | Hepatitis A vaccine |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2150 | HepB | Hepatitis B vaccine |  |  |  | B | M2 |  | M4 |  |  |  |  |  | / |  |  |  |  | 1 2 2 | Shantha Biotechies PVT. Ltd., India LG life Sciences Ltd., Korea VABIOTEC No1, Vietnam | GAVI through UNICEF GAVI through UNICEF MOH | 1,352,700 2,705,400 700,000 |  |
| 2160 | Hib |  | Haemophilus influenzae type b vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2170 | OPV |  | Oral polio vaccine |  |  | M2 | M3 |  | M4 |  |  |  |  |  | / |  |  |  |  | 20 | POLIOVAC, Vietnam | MOH | 5,330,000 |  |
| 2180 | IPV |  | Inactivated polio vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2190 | Measles |  | Measles vaccine |  |  | M9 |  |  |  |  |  |  |  |  | / |  |  |  |  | 10 | Sanofi Pasteur, France | MOH | 2,300,000 |  |
| 2200 | MM |  | Measles and mumps vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2210 | MR |  | Measles and rubella vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2220 | MMR |  | Measles mumps rubella vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2230 | Mumps |  | Mumps vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2240 | JE |  | Japanese encephalitis |  |  | M12 | M13 |  | M25 |  |  |  |  |  | / |  |  |  | 1-5y | 10 | VABIOTEC No1, Vietnam | MOH | 2,800,000 |  |
| 2250 | Influenza |  | Influenza |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2260 | MenC_conj |  | Meningococcal C conjugate vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2270 | Men AC |  | Meningococcal AC |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2280 | Men ACW |  | Meningococcal ACW |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2290 | Men ACWY |  | Meningococcal ACWY |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2300 | Pneumoco_conj |  | Pneumococcal conjugate vaccine | Number of valent |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2310 | Pneumo_ps |  | Pneumococcal polysaccharide vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2320 | Rubella |  | Rubella vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2330 | Typhoid |  | Typhoid fever vaccine |  |  | Y3 |  |  |  |  |  |  |  |  | / |  |  |  | 3-10Y | 20 20 | IVAC, Vietnam Sanofi Pasteur, France | MOH | 500,000 700,000 |  |
| 2340 | Varicella |  | Varicella vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2350 | YF |  | Yellow fever vaccine |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |  |
| 2360 | Vit A |  | Vitamin A supplementation |  |  | M6-11 | M12-17 |  | M18-23 |  | M24-29 |  | M30-36 |  | / |  |  |  | 6-36 month children |  | CIDA donation in kinds |  | 9,550,802 capsules 200,000iu |  |
| 2370 | TT |  | Tetanus toxoid |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  | PW &CBAW | 20 | IVAC, Vietnam | MOH | 6,500,000 |  |
| 2380 | AD - BCG |  | AD (auto-disable) syringes BCG |  |  | NR | NR |  | NR |  | NR |  | NR | NR | / |  |  |  |  | NR | BD | MOH | 1,815,900 |  |
| 2390 | AD – inj |  | AD syringes |  |  | NR | NR |  | NR |  | NR |  | NR | NR | / |  |  |  |  | NR | Mediplas, Vietnam | MOH | 26,521,000 |  |
| 2400 | AD - Rec |  | AD syringes reconstitution |  |  | NR | NR |  | NR |  | NR |  | NR | NR | / |  |  |  |  | NR | Mediplas, Vietnam | MOH | 1,472,136 |  |
| Use the space below for any other vaccines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2410 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |
| 2420 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |
| 2430 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |
| 2440 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |
| 2450 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |
| 2460 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | / |  |  |  |  |  |  |  |  |

INSTRUCTION SHEET

Table 4 A is for reporting routine immunization coverage using the administrative method (i.e. registry system of doses administered).  Include only doses given during routine immunization services.  Routine immunization may include pulse campaigns to increase routine coverage. It does not include mass campaigns, national immunization days or other supplemental activities. Supplementary Immunization Activities (SIA) for immunization and vitamin A should be reported in table 8 at the end of the document.

Column A: in some instances the target group has been specified (e.g. Surviving infants for DTP3). In others, it is not specified therefore, please describe the target group (e.g. MCV2 : 6 years old children).

We acknowledge that in some countries the target population may be different than the one specified in column A (e.g. For yellow fever the target group specified in the column A is surviving infants. In some countries, yellow fever may be given to the whole population; similarly for  TT2+, the target group specified in the column A is pregnant women but TT may be given to all child bearing age women). However, in order to get standardized and comparable information across countries, we request that you provide figures related to the specific target population mentioned in the column A.

Column B,

4140:	the number of live births can be used as a proxy for total number of pregnant women.

Some countries may use live births as the official denominator for DPT1, DPT3, Polio3, HepB3, Hib3, and yellow fever. In that case, simply put the denominator used by the country in column B.

4020:	if a birth dose (within 24 hours of birth) is not in the national schedule, write “NR”.

4050:	Polio 3: 3rd dose of polio, excluding polio 0 (zero) if in country schedule.

4060:	Hepatitis B 3: 3rd dose of hepatitis B vaccine, including birth dose, if in country schedule

4080-4100: Measles containing vaccine (MCV): i.e. measles vaccine, measles-rubella vaccine, or measles-mumps-rubella vaccine. Fill in information for both MCV and rubella even if given in combination.

4120-30: refers to first and second vitamin A doses given to the specified target group (6-59 months) in 2005.

4150: PAB = number of children, as recorded during their DTP1 visit, who can be considered as  protected at birth by their mother’s TT status and/or delivery status, divided by number of live births. If not calculated in the country leave blank.

- Immunization and Vitamin A coverage

4A.  National administrative coverage:

| Vaccine/Intervention Please fill in all vaccines separately even if given in combination (e.g. DTP3 and HepB3) |  | A. Description of target group used as denominator in coverage calculation |  | B. Number in target group (denominator) |  | C. Number of doses administered through routine services (numerator) |  | D. Percent coverage C/Bx100 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4010 | BCG | Live births |  | 1,545,475 |  | 1,465,055 |  | 94.8 |  |
| 4020 | HepB - birth dose (given within 24 hours of birth) | Live births |  | 1,545,475 |  | 961,618 |  | 62.2 |  |
| W4025 | HepB – birth dose (including those given after 24 hours of birth) | Live births |  | 1,545,475 |  | 1,476,503 |  | 95.5 |  |
| 4030 | DTP1 | Surviving infants |  | 1,545,475 |  | 1,457,302 |  | 94.3 |  |
| 4040 | DTP3 | Surviving infants |  | 1,545,475 |  | 1,461,520 |  | 94.6 |  |
| 4050 | Polio3 (OPV or IPV) | Surviving infants |  | 1,545,475 |  | 1,459,908 |  | 94.5 |  |
| 4060 | HepB3 | Surviving infants |  | 1,545,475 |  | 1,448,721 |  | 93.7 |  |
| 4070 | Hib3 | Surviving infants |  | NR |  |  |  |  |  |
| 4080 | MCV1 (the first dose of Measles Containing Vaccine) | Specify target group |  | 1,545,475 |  | 1,471,332 |  | 95.2 |  |
| 4090 | Rubella 1 Rubella containing vaccine | Specify target group |  | NR |  |  |  |  |  |
| 4100 | MCV2 (the second dose of Measles Containing Vaccine) | Specify target group 6 years old |  | 26,823 |  | 26,731 |  | 99.6 |  |
| 4110 | Yellow Fever | Surviving infants |  | NR |  |  |  |  |  |
| 4120 | Vitamin A – 1st dose | 6-59 months |  | 3,924,464 |  | 3,885,220 |  | 99% (for 6-36 month children) |  |
| 4130 | Vitamin A – 2nd dose | 6-59 months |  | 3,944, 986 |  | 3,912,931 |  | 99.2 % (for 6-36 month children) |  |
| 4140 | TT2+ | Pregnant women |  | 1,545,475 |  | 1,436,015 |  | 93 |  |
| 4150 | Protection at birth (PAB) against neonatal tetanus | Live births |  | 1,545,475 |  | 1,327,204 |  | 85.9 |  |
| 4160 | Vitamin A doses provided to post-partum mothers | Live births |  | 1,478, 423 |  | 1,201,090 |  | 81.2% |  |
| W4163 | What is the source of denominator data used in 2005? |  | Census data (year ) Census plus projected growth from year |  |  |  | Registered population Other..Report from provinces 2003 and growth rate from census 1999 |  |  |
| W4167 | Do sub-national levels use the same denominator and source? |  |  |  | Yes No (If no, please provide details under questions 4190 and 4200 "Factors limiting the accuracy of the numerator and denominator") |  |  |  |  |

INSTRUCTION SHEET

Completeness of reporting

4170/4180: these rows aim to indicate the completeness of district reporting, i.e. the main reporting system which produced Table 4A.  In some countries, disease surveillance and immunization coverage reporting are integrated hence the completeness will be the same as for 1120-1130.

4180: The number of expected reports is equal to the number of districts multiplied by the number of reporting periods in the year

4190-4200. The coverage estimates reported in Table 4A (in percents, column D) can be biased because of inaccurate numerators (4190) or denominator problems (4200).

Numerator problems may be due to data that are:

- underestimated  because of incomplete reporting from reporting units, non inclusion of other vaccinating sources (e.g. private sector, NGOs, etc..); or

- overestimated because of over-reporting from reporting units (inclusion of other target groups, etc…)

Denominator problems may be due to :

- population movements

- inaccurate census estimations or projections

- numerous sources of denominator data, etc…

| Coverage reporting completeness |  |  |
| --- | --- | --- |
| 4170 | Total number of reports expected at the national level from districts in 2005 | 669 |
| 4180 | Total number of reports actually received at the national level from district in 2005 | 669 |

| Mention any factors limiting the accuracy of your administrative coverage estimates |  |
| --- | --- |
| 4190 | Factors limiting the accuracy of the numerator Number of children vaccinated use for caculate the coverage rate of children under 1 in some areas may be include chidren more than 11 months old particulalry in mountainous and remote areas. |
| 4200 | Factors limiting the accuracy of the denominator Population movement, mobile population and the estimate come from provinces some time not correct |

INSTRUCTION SHEET

Table 4B refers to a second way of estimating immunization coverage, through surveys. Data should include surveys conducted at the national level only,  The most common types of surveys are: MICS (Multiple Indicator Cluster Survey), DHS (Demographic Health Survey) and EPI cluster survey (Immunization coverage cluster survey reference manual - WHO 2004)

4220-4350: Please enter information for crude coverage only.  While issues of valid doses (doses that were administered when the child had reached the minimum age for the vaccine, and were administered with the proper spacing between doses according the national schedule) is important we request that crude coverage figures, without an eventual correction due to non valid doses be reported.

4350. PAB refers to Protection at birth. While calculations of PAB during a survey are calculated differently (from 4150) please report the proportion of children who are protected at birth against tetanus due to an adequate TT  immunization status of their mother.

4B.  Coverage surveys:  Complete this table on surveys that include immunization coverage (including MICS2).

If a national survey was conducted during 2003-2005, complete the rest of this page with most recent survey data available.  If no national survey was conducted from 2003-2005, proceed to next page.

| 4210 |  |  | What year was the survey conducted? |  |  | 2003 2004 2005 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Full title of survey (in original report language) |  |  |  | Review of the expanded programme on immunization, Vietnam, 16 - 27 Nov. 2003 Tong dieu tra suy dinh duong tre em 2004 |  |  |  |
|  |  |  | Full title of survey (in English) |  |  |  | Review of the expanded programme on immunization, Vietnam, 16 - 27 Nov. 2003 National Nutrition survey 2004 |  |  |  |
| W4213 |  |  | Indicate agencies technically involved in the survey |  |  |  | MOH CSO** WHO |  | UNICEF DHS Other (specify): PATH |  |
| W4217 |  |  | Indicate the sampling methodology used |  |  |  | Cluster Lot quality Other (specify): |  |  |  |
| CHILDREN surveyed aged 12-23 month |  |  |  | % received immunization by 12 months of age* |  |  |  | % received immunization anytime before survey |  |  |
|  |  |  |  | A. By card only | B. By card or history |  |  | C. By card only |  | D. By card or history |
| 4220 | BCG |  |  | 95.7 | ND |  |  | 97.5 |  | 97.8 |
| 4230 | HepB - birth dose |  |  | ND | ND |  |  | ND |  | ND |
| 4240 | DTP1 |  |  | 94.8 | ND |  |  | 95.6 |  | 98.6 |
| 4250 | DTP3 |  |  | 91.6 | ND |  |  | 95.4 |  | 96.9 |
| 4260 | Polio3 |  |  | 92.8 | ND |  |  | 95.2 |  | 97.1 |
| 4270 | HepB3 |  |  | ND | ND |  |  | ND |  | ND |
| 4280 | Hib3 |  |  | ND | ND |  |  | ND |  | ND |
| 4290 | MCV1 (measles containing vaccine) |  |  | 82.0 | ND |  |  | 88.1 |  | 96.1 |
| 4300 | Rubella 1 (rubella containing vaccine) |  |  | NR | NR |  |  | NR |  | NR |
| 4310 | Yellow fever |  |  | NR | NR |  |  | NR |  | NR |
| 4320 | Vitamin A-1 |  |  | ND | ND |  |  | ND |  | ND |
| WOMEN |  |  |  | A. % women received immunization among those who gave birth in the past 12 months (by card only) |  |  |  | B. % women received immunization among those who gave birth in the past 12 months (by card or history) |  |  |
| 4330 |  | TT2+ |  | 86.6 |  |  |  | 91.9 |  |  |
| 4340 |  | Vitamin A among post-partum women |  | ND |  |  |  | 61% (2004 survey) |  |  |
| 4350 |  | PAB (protection at birth) |  | ND |  |  |  | 85.8 |  |  |

*(or 23 months for MCV1 or Rubella 1 if the schedule calls for a dose between 1-2 years of age)

** Central Statistics Office or Bureau of Statistics

Please attach a copy of all immunization coverage survey reports during 2003-2005

INSTRUCTION SHEET

Table 5

Taking into account the data provided in the previous tables as well as any other available information on factors affecting immunization coverage figures (e.g. private or NGO sector contributions to immunizations, difficulties with demographic data, incomplete reporting), indicate your official estimates of national immunization coverage among infants (or by 23 months for MCV1-rubella 1 if the schedule calls for a dose between 1-2 years of age).

It is important to understand that figures from Table 4A and 4B can be biased or inaccurate. Hence, the national authorities are given the opportunity in Table 5 to provide estimates of what their most likely true coverage is. The official estimates may be based on data from the administrative method, from surveys, or from other sources.  This exercise is extremely important to interpret the data.

These estimates will be reproduced in the Global and Regional level reports as the officially reported coverage figures.

- Official country estimates of immunization coverage for the year 2005.

| W5000 | Are your administrative coverage figures the same as your official estimates? | Yes No |
| --- | --- | --- |

If no, please provide official estimates below and justification (under question 5160) as to why they differ from administrative coverage.

Please fill in each vaccine/supplement separately even if given in combination (e.g. DTP3 and HepB3)

|  | Vaccines | Official Estimates (percent coverage) |
| --- | --- | --- |
| 5010 | BCG |  |
| 5020 | HepB – birth dose |  |
| 5030 | DTP1 |  |
| 5040 | DTP3 |  |
| 5050 | Polio3 |  |
| 5060 | HepB3 |  |
| 5070 | Hib3 |  |
| 5080 | MCV1 measles containing vaccine |  |
| 5090 | Rubella 1 containing vaccine |  |
| 5100 | MCV2 measles containing vaccine |  |
| 5110 | Yellow Fever |  |
| 5120 | Vitamin A1 | 89.4% |
| 5130 | Vitamin A2 | ND |
| 5140 | Vitamin A for post-partum mothers | 61% |
| 5150 | TT2+ for pregnant women |  |

5160. Please provide explanatory comments/justification on why these are your official estimates:

For vitamin A, the reporting system from the local up is often over estimated, the data provided in above table was from a cluster sampling survey,so the data is more reliable to represent the general country coverage. It is worthy to note that one of the weakness of the cluster survey for vitaminA coverage is that child care givers might not always remember or realized even if their child got the A capsules, especially when the interview date is too far from the date their children actually get.

- Immunization system indicators

Complete the following table of indicators on immunization system performance covering the year 2005 and provide any needed explanatory comments.

| System Indicators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Indicator |  | Response |  | Comments |  |
| W6003 | What percentage of total births in 2005 took place in a hospital or other health facility? |  | 70%E |  |  |  |
| W6008 | What percentage of births at home in 2005 was attended by a health worker? |  | 95% |  | Data from health statistic year book 2004 |  |
| W6122 | What percentage of the population received immunization services by: Fixed sites: Outreach: |  | 90%E % 10%E % |  |  |  |
| W6124 W6126 | Is immunization services provided for any population groups through: Home to home services Outreach through mobile clinics |  | Yes No If yes, what percentage? Yes No If yes, what percentage?1% |  |  |  |
| 6010 | Was there any negative publicity* concerning immunizations and/or vitamin A supplementation during 2005? |  | Yes No |  |  |  |
| 6020 | If yes, describe the negative publicity (i.e. during SIAs or routine, any adverse events, related to which antigen, etc). |  |  |  |  |  |
| 6030 | Describe response (if any) |  |  |  |  |  |
| *6010 Examples of negative publicity may be 1) rumours, 2) research related information, 3) adverse events related to vaccines or 4) vaccine shortages. |  |  |  |  |  |  |
| 6040 | Was there a strategic plan* for the national immunization system that covers three to five years? * Plan of action (POA), Multi-year plan, … |  |  | Yes No | Specify the years of the plans: FSP 2004 - 2014 |  |
| 6050 | Was there an annual activity work plan for immunization services? |  |  | Yes No |  |  |
| W6052 | Did it include an updated, detailed plan for measles elimination? |  |  | Yes No |  |  |
| W6054 | Did it include an updated, detailed plan for Hepatitis B control? |  |  | Yes No |  |  |
| 6060 | Did it contain an advocacy and communications strategic component? |  |  | Yes No |  |  |
| 6070 | Was there an annual budget for advocacy and communication? |  |  | Yes No |  |  |
| 6080 | Was there a communication & advocacy designated focal point? |  |  | Yes No |  |  |
| W6075 | Do you have an updated plan for the detection of and response to imported wild poliovirus or circulating VDPV (either standalone or part of a multi-year plan)? |  |  | Yes No | In November 2005 a Subnational campaign was conducted for identified hirisk areas |  |
| 6090 | Number of districts with updated micro plans that include activities to raise immunization coverage? |  |  | ND |  |  |
| 6100 | How many Inter-Agency Coordinating Committee (ICC) meetings were held that covered routine immunization services? |  |  | 1 |  |  |
| W6102 | Reviews done in 2005? | EPI Cold Chain Injection Safety Data quality Surveillance Immunization financing |  |  |  |  |
| W6104 | What are NIP's current priority needs? - Supply enough cold chain equipment for provincial, district levels. - Supply enough EPI vaccine include measles vaccine for routine immunization and SIA - Improuve AEFI system at all levels - Identify wastage rate for EPI vaccines - Introduction new vaccine in EPI - Operation cost for SIA and disease surveillance |  |  |  |  |  |
| W6106 | Were there any training programmes in 2005 organized at the national or subnational level for: |  |  | Data Management Cold Chain Vaccine Logistics Injection Safety Disease Surveillance Micro Planning |  |  |
| W6107 | Is regular comprehensive training provided to EPI workers? |  |  | Yes No If yes, how many times per year? 1 |  |  |
| W6108 6110 W6115 | Do you have a cold chain management system that includes: - Cold chain policy - Updated (2005) inventory (models, location, age and working status) of all refrigeration equipment assigned for public immunization services in the country (Update can refer to a new inventory or regular status reports.) - Planned replacement programme for future needs? |  |  | Yes No Yes No Partially Yes No |  | Year 2005 If no, please specify where is the gap: |
| W6118 | What are your current needs regarding cold chain? |  |  | Cold chain equipment for replace at provincial and distric levels |  |  |

| System performance |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6120 | Total number of districts not reporting in 2005 |  |  |  | Number: 14 (not reporting for DPT3) |  |  |
| District coverage reported for routine immunization services in 2005 |  |  | Fill in number of districts reporting within each range of coverage |  |  |  |  |
|  |  |  | A. | B. |  | C. | D |
| DTP3 |  |  | <50% | 50-79% |  | 80-89% | >=90% |
| 6130 | Number of districts with DTP3 coverage |  | 4 | 12 |  | 48 | 591 |
| 6140 | Number of surviving infants in these districts |  | 10,704 | 36,932 |  | 93,595 | 1,357,932 |
| Measles |  |  | <50% | 50-79% |  | 80-89% | >=90% |
| 6150 | Number of districts with measles (MCV1) coverage |  | 3 | 11 |  | 24 | 631 |
| 6160 | Number of surviving infants in these districts |  | 6,904 | 37,833 |  | 44,773 | 1,455,965 |
| TT2+ (pregnant women) |  |  | <50% | 50-79% |  | 80-89% | >=90% |
| 6170 | Number of districts with TT2+ coverage |  | 21 | 55 |  | 102 | 491 |
| 6180 | Number of live births in these districts |  | 66,680 | 120,295 |  | 205,666 | 1,152,834 |
| Drop-out and supervision |  |  |  |  |  | Number of districts |  |
| 6190 |  | Number of districts reporting drop-out rates greater than 10% Drop-out rate = (DTP1-DTP3) x 100 DTP1 |  |  |  | 0 |  |
| W6195 |  | Number of districts reporting >10% difference between DTP3 and HepB3 coverage |  |  |  | 30 (DPT3 > HepB3) 12 (DPT3 < HepB3) |  |
| 6200 |  | Number of districts reporting at least one supervisory visit to each health facility in the district during 2005 |  |  |  | ND |  |
| Wastage |  |  |  |  |  |  |  |
| W6205 |  | Is the multi-dose vial policy (formerly known as “open vial policy”) adopted? |  |  |  | Yes No |  |
| Reported vaccine wastage (in %) occurring in the country including both opened and unopened vials ; it includes both programme and system related wastage. If there were special studies to estimate the vaccine wastage in the country, enter an "E" (for Estimated) after the %. If wastage is not part of routine reporting or there have been no special studies please enter "ND" for no data. Please fill in each vaccine separately, even if given in combination |  |  |  |  |  | Percentage |  |
| 6210 |  | DTP |  |  |  | 23% Estimate? Yes No |  |
| 6220 |  | Hepatitis B vaccine |  |  |  | 6% Estimate? Yes No |  |
| 6230 |  | Hib vaccine |  |  |  | NR Estimate? Yes No |  |

| Vaccine supply for routine services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Vaccine - supply |  | National store |  | District stores |  |
| Please fill in each vaccine separately, even if given in combination (e.g. DTP and HepB) |  | A. Was there a stock-out (no remaining doses for any period of time) at national level during 2005 | B. If yes, specify duration in months* | C. Was there a stock-out in any district during 2005 | D. If yes, indicate number of districts with stock-out |
| 6310 | BCG | Yes No NR |  | Yes No NR |  |
| 6320 | DTP | Yes No |  | Yes No |  |
| 6330 | Hepatitis B | Yes No NR |  | Yes No NR |  |
| 6340 | Hib | Yes No NR |  | Yes No NR |  |
| 6350 | Polio (OPV or IPV) | Yes No |  | Yes No |  |
| 6360 | Measles | Yes No | 1 | Yes No |  |
| 6370 | Yellow fever | Yes No NR |  | Yes No NR |  |
| 6380 | Tetanus toxoid | Yes No NR |  | Yes No NR |  |
| 6390 | Vitamin A | Yes No NR |  | Yes No NR | ND |
| 6400 | AD syringes | Yes No NR |  | Yes No NR |  |
| 6410 | Safety boxes | Yes No NR |  | Yes No NR |  |

* Column B: if stock-out duration is less than one month (a few days or weeks), enter the number 1

Columns C and D: District stock out is not necessarily related to national store stock-out.

If a district has no permanent vaccine store (e.g. store at provincial or higher level) but health units have been affected by vaccine shortage, the district should be mentioned as a Yes in the C column and counted in the D column.

| Surveillance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 6510 | Was written feedback on the immunization system and surveillance performance distributed to the district level? | Yes No |  |  |  |
| 6520 | If yes: How many times per year? | 4 times |  |  |  |
| 6530 6540 W6545 W6547 | Did the feedback include: (a) Coverage by district (at least DTP3)? (b) Disease cases (at least measles, NT, and AFP)? (c) AFP Indicators? (d) Coverage of timely birth dose of HepB | Yes No Yes No Yes No Yes No |  |  |  |
| Safety |  |  |  |  |  |
| 6550 | In 2005 was there an activity workplan for: (a) immunization injection safety? (b) waste management? | Yes No Yes No |  |  | ND ND |
| 6551 |  |  |  |  |  |
| 6560 | Indicate the type(s) of injection equipment used for routine immunization (excluding reconstitution syringes) and the number of districts using each type. Check all that apply. | Auto-Disable (AD) syringes Non-AD disposables Sterilizable syringes | Y | N | No of districts 669 |
| W6565 | Year that all EPI injections are planned to be given with ADs? | 2003 |  |  |  |
| 6570 | Were safety boxes distributed with all vaccine deliveries to vaccination sites? | Yes No |  |  | 669 |
| 6580 | Was there a national system to monitor adverse events following immunization? (A national system must include: 1. written guidelines on monitoring and investigation of reported adverse events; 2. written list of events to monitor; 3. established mechanism to communicate data for regulatory action; 4. implementation of points 1, 2, and 3.) | Yes No If all 4 conditions are not met, check 'No'. |  |  |  |
| W6582 | If no national system to monitor AEFI, are there plans to develop one? | Yes No |  |  |  |
| W6588 | Is there an annual report on AEFI? | Yes No |  |  |  |
| 6590 | If there is a national system to monitor AEFI, how many adverse events, either suspected or confirmed, were reported to the national level in 2005? If no adverse events were reported, enter "0". | Number of adverse events reported 8 |  |  | Number of adverse events investigated 8 |
| 6600 | What was your national policy or recommended practice for disposal of immunization waste in2005? Check all that apply. | Incinerator* Open burning Burial Other (specify)** No policy | Y | N | If answered “Yes” to “other”, please specify: |

* 6600. Incinerator refers to closed methods of burning at temperatures  800°C. Open burning refers to pit burning and drum burning. Burial refers to waste burial pits and encapsulation with cement or other immobilizing agent (sand, plaster).

** 6600. Specify in "Comments" column, for example: disposal of sharps in purpose-built lined pits, or steam sterilization and shredding, etc

| Financing |  |  |
| --- | --- | --- |
| 6610 | What percent of all spending on routine immunization was financed using government funds? (Please provide the percentage of all of recurrent immunization specific spending that was financed using government funds only (for all recurrent inputs including vaccines, injection supplies, salaries and per-diems of health staff working full-time on immunization, transport, vehicles and cold chain maintenance, training, social mobilization, monitoring and surveillance....). This excludes any external financing from external donors. If the exact percentage is not known then please provide an estimate and affix the letter “E” to the number (for example: 35% E). The estimate provided can be from a previous year or a “best guess”. If no estimate can be provided then please enter ND (No Data) and not zero. These numbers should be available from a GAVI financial sustainability plan or from a multiyear plan for immunization with a costing and financing component to it.) | 60%E% Estimate? Yes No |
| W6625 | What percentage of government funding for immunization services including vaccines is sourced from the following levels: National Provincial/Regional District/Local | ND% ND% ND% |
| 6620 | What percent of all spending on vaccines was financed using government funds? (Please provide the percentage of all vaccine spending that was financed using government funds only. This excludes any external financing from donors. If the exact percentage is not known then please provide an estimate and affix the letter “E” to the number (for example: 35% E). The estimate provided can be from a previous year or a “best guess”. If no estimate can be provided then please enter ND (No Data) and not zero. These numbers should be available from a GAVI financial sustainability plan or from a multiyear plan for immunization with a costing and financing component to it) | 70E% Estimate? Yes No |
| 6630 | Is there a line item in the national budget for purchase of vaccines used in routine immunizations? | Yes No |
| 6640 | Is there a line item in the national budget for purchase of injection supplies (syringes, needles, safety boxes) for routine immunizations? | Yes No |
| W6650 | Estimated total cost to fully immunize each child according to schedule by 1 year of age. | ND |
| W6670 | What is the level of government funding in real terms for immunization now compared to five years ago? | Increased Decreased No change |

- Maternal and neonatal tetanus (MNT) elimination

The countries* that are considered as not having eliminated MNT (or have not documented it) should complete this table.

|  |  | A. | B. |
| --- | --- | --- | --- |
|  | For the year 2005: | Number of districts | Number of CBAW |
| 7010 | Specify the age range of Child Bearing Age Women (CBAW): to |  |  |
| 7020 | Districts at low risk for MNT |  |  |
| 7030 | Districts at high risk for MNT |  |  |
| 7040 | Districts at unknown** risk for MNT (**where more data are needed to determine high risk/low risk status) |  |  |

*Afghanistan, Angola, Bangladesh, Benin, Burkina Faso, Burundi, Cambodia, Cameroon, Central African Republic, Chad, China, Comoros, Congo, Cote d'Ivoire, Democratic Republic of the Congo, Egypt, Equatorial Guinea, Ethiopia, Gabon, Ghana, Guinea, Guinea-Bissau, Haiti, India, Indonesia, Iraq, Kenya, Lao People's Democratic Republic, Liberia, Madagascar, Mali, Mauritania, Mozambique, Myanmar, , Niger, Nigeria, Pakistan, Papua New Guinea, Philippines, Senegal, Sierra Leone, Somalia, Sudan, Timor-Leste , Turkey, Uganda, United Republic of Tanzania,  Yemen, Zambia

7020. Low Risk Districts: districts identified as having a  Neonatal Tetanus incidence of less than 1 per 1000 live births.

7030. High Risk Districts: districts identified by locally adopted criteria as being at high risk for MNT. Criteria may be based on core and additional indicators.

7040. Unknown Risk Districts: districts that can be classified neither as high risk nor as low risk for MNT, and for which more information is required in order to determine the status

Column A. Number of districts: number of districts identified as high/low/unknown risk. The total should equal the total number of districts in the country.

Column B. Number of CBAW: total number of child bearing age women in the country

8A. Supplementary activities conducted during 2005

Record any supplemental activity (immunization campaign and vitamin A), including those conducted at national or sub-national level; (e.g. polio, yellow fever, measles, rubella, influenza, meningitis, tetanus toxoid vaccines, vitamin A, etc.)

Complete one line for each antigen in each campaign round.

| Vaccine / supplement If more than one antigen or supplement was provided in a single round, list each in separate line below. |  | A. Round and Type of activity* | B. Date | C. Indicate whether National (N) or Sub-national (S) | D. Target population (age group) | E. Estimated number in target population (numbers) | F. Total number of persons vaccinated/supplemented (numbers) | G. Coverage (%) (for measles, yellow fever, vitamin A, meningitis or polio) | Number of persons vaccinated for tetanus The total of TT1, TT2, TT3, TT4 and more equals the numbers in the column “Total number of persons vaccinated” |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Do not fill for tetanus | H. TT1 | I. TT2 | J. TT3 | K. TT4 or more |
| 8010 | OPV | Sub NIDs | Nov | N S | 0-5y | 2,641,628 | 2,526,751 | 96.6 |  |  |  |  |
| 8020 | TT | SIA | Apr | N S | 16-35y | 133,896 |  |  | 10972 | 9685 | 105317 | 438 |
| 8030 | Measles | Sub - national for second dose | Sep | N S | 6y | 26,823 | 26,731 | 99.6 |  |  |  |  |
| 8040 |  |  |  | N S |  |  |  |  |  |  |  |  |
| 8050 |  |  |  | N S |  |  |  |  |  |  |  |  |

*indicate the name: NIDs; Micronutritient day; Child health day, vaccination week, etc, and round number

Column G: Enter your official estimate for coverage (can be from a coverage survey and different from administrative calculation)

8B. Supplementary activities planned including 2006-7

Record any supplemental activity (immunization campaign and vitamin A), including those conducted at national or sub-national level; (e.g. polio, yellow fever, measles, rubella, influenza, meningitis, tetanus toxoid vaccines, vitamin A, etc.)

Complete one line for each antigen in each campaign round.

| Vaccine / supplement If more than one antigen or supplement was provided in a single round, list each in separate line below. |  | A. Round and Type of activity* | B. Month/Year |  | C. Indicate whether National (N) or Sub-national (S) | D. Target population (age group) | E. Estimated number in target population (numbers) | F. Estimated Cost including vaccine and operational costs (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8110 | OPV | Sub NIDs | Dec | 2006 | N S | 0-5y | 2,960,200 | 300,000 |
| 8120 | Measles | 2nd doses | Sep, Oct | 2006 | N S | 6y | 1,500,000 | 1,565,000 |
| 8130 | Measles | 2nd doses | Feb, Mar | 2007 | N S | 15-20y | 2,500,000 | 2,575,000 |
| 8140 | Measles | HRD | Oct, Nov | 2007 | N S | 9m-20y | 200,000 | 212,000 |
| 8150 | Measles | 2nd doses | Sep, Oct | 2007 | N S | 6y | 1,500,000 | 1,565,000 |

*indicate the name of campaign round: NIDs; Micronutritient day; Child health day, vaccination week, etc, and round number (e.g. first, second, third)

9. Measles

|  |  |  | Comments |
| --- | --- | --- | --- |
| #### W9010 | Is measles surveillance data case-based? (*case data means a line listing of every reported case with the name, age, date of rash onset, immunization status and lab results) | Yes No |  |
| W9020 | If no, are you planning to have case-based measles surveillance data in the future? | Yes No |  |
| W9040 | If yes, what percentage of your total measles cases have case-based data? (Please put an "E" for estimates) |  |  |
| W9060 | Do you have a national plan for measles elimination? | Yes No |  |
| W9080 | What is your national target date for elimination? | 2010 |  |

10. Rubella

|  |  |  | Comments |
| --- | --- | --- | --- |
| #### W10010 | Is there a legal requirement to notify all rubella cases? | Yes No |  |
| W10020 | Is there a rubella surveillance database at the National level? | Yes No |  |
| W10030 | If yes, is it case-based? | Yes No |  |
| W10040 | Is there a surveillance system for congenital rubella syndrome (CRS)? | Yes No |  |

11. Hepatitis B

|  |  |  | Comments |
| --- | --- | --- | --- |
| W11010 | Has a hepatitis B serosurvey been undertaken in the last two years? | None Only in specified age groups Entire population Sentinel targets |  |
| W11015 | What is the estimated national chronic infection rate in <5 population? | ND |  |
| W11020 | Chronic HBV infection (HbsAg positive) rate (%): post-vaccine among: Vaccinated cohorts Blood donors Antenatal testing | ND ND ND |  |
| W11030 | Is there a system to deliver timely birth dose of Hepatitis B - for births in hospitals - for births in health centers - for births at home | Yes No Yes No Yes No | The coverage rate is low in remote areas |
| W11040 | Is there a system to monitor timely delivery of birth dose of Hepatitis B - for births in hospitals - for births in health centers - for births at home | Yes No Yes No Yes No |  |

DOCUMENT 2.  Comprehensive Multi-Year Plan (cMYP) (2006 – 2010)

DOCUMENT 5. Terms of Reference of the Interagency Coordinating Committee for the EPI.

## OVERVIEW OF THE EPI IN VIET NAM

- The Expanded Program on Immunization (EPI) was initiated in Viet Nam in 1981 with assistance from UNICEF and WHO. In early 1986, the EPI implementation was expanded to cover the whole country and the universal child immunization (UCI) goal of 80% coverage was achieved by 1990.  Since 1986 the EPI has become one of the national priority health programs in Viet Nam.

## NATIONAL STEERING COMMITTEE FOR EPI

- To sustain the UCI levels and achieve the goals of poliomyelitis eradication and neonatal tetanus elimination, a National Steering Committee (NSC) for EPI was established in early 1990. The NSC for EPI is chaired by the Minister of Health and consists of Directors of relevant Departments of the Ministry of Health (MOH) and of National and Regional Institutes of Hygiene and Epidemiology. The role of the NSC for EPI is to coordinate and manage the implementation of EPI/UCI and other EPI-related goals in the whole country.

## MAIN PROBLEMS AND CONSTRAINTS

- Despite improved immunization services, there are still a number of “EPI-white” villages in remote mountainous and very difficult-to-reach areas where eligible children are not fully immunized.

- Safe injection issues are critical problems in many areas.

- Shortfalls of funds for procurement of vaccines.

## INTER-AGENCY COORDINATING COMMITTEE (ICC) FOR EPI

### PURPOSE

- To provide partner agencies with the opportunity to work closely with Government to strengthen the benefits of collaborative work in the EPI, and to identify the resources and assistance necessary to strengthen immunization services in a sustainable and self-sufficient manner.

### ROLE OF THE ICC

To:

- Promote common agreement on and support to program objectives and strategies;

- Identify program needs and technical assistance;

- Mobilize both national and international support;

- Help donors avoid duplication, gaps and inefficiencies;

- Provide a forum to discuss operational, programmatic and technical issues.

STRATEGIC OBJECTIVES

The ICC co-ordinates the support from partner agencies to assist the National EPI, Ministry of Health to:

- Ensure access to improved immunization services for all eligible children and women;

- Promote programmatic and financial sustainability of immunization services;

- Accelerate the introduction of new and under-used vaccines and associated safe injection policies, procedures and equipment into the Viet Nam EPI;

- Secure funding for immunization services;

- Sustain the achieved goals of UCI maintenance, poliomyelitis-free status, neonatal tetanus elimination and measles control.

### TERMS OF REFERENCE

The ICC will meet quarterly or whenever necessary to

- Review and endorse annual and five-year plans, country proposals and reports and other relevant documents prepared by the National EPI;

- Review progress in achieving milestones/objectives;

- Coordinate actions needed to overcome constraints and achieve milestones and objectives;

- Mobilize funding and assist in planning and monitoring in areas of priority as determined by the National Steering Committee for EPI.

The Permanent Vice-Minister of Health will invite the WHO Representative to serve as Chairperson of the ICC for the first two years and representatives from other ICC partners, including UNICEF, will be invited to act as chairperson for the consecutive years.

## The National EPI will prepare background documents for the ICC, maintain minutes of the ICC meetings and follow-up on implementation of recommendations.

## MEMBERSHIP

National

- Ministry of Health (MOH)

- Ministry of Planning and Investment (MPI)

- Ministry of Finance (MOFIN)

- Commission for Protection and Care of Children (CPCC)

#### International

- Asian Development Bank

- AusAID

- British Embassy

- Canadian Embassy

- European Union

- French Embassy

- Italian Embassy

- Japanese Embassy

- JICA

- Luxembourg Embassy

- Netherlands Embassy

- PATH/CVP

- Swedish Embassy

- US Embassy

- US CDC

- UNAIDS

- UNFPA

- UNICEF

- WHO

- World Bank

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table   after Table 7.1.

2 Data from NIN, it will be filled year by year