GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Democratic People's Republic of Korea

Date of submission: 15.05.2011 11:24:26

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | DTP-HepB-Hib, 1 dose/vial, Liquid | 2012 | 2015 | DTP-HepB-Hib, 10 doses/vial, Liquid |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( DTP-HepB-Hib, 1 dose/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - DTP-HepB-Hib, 1 dose/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine DTP-HepB-Hib, 1 dose/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine DTP-HepB-Hib, 1 dose/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Of estimated 10 million annual deaths worldwide amongst children under five, WHO estimates that more than 700,000 are caused by pneumococcal infections. In DPRK, severe pneumonia and diarrheal diseases are still the major causes of child morbidity and mortality. In order to reach MDG 4 by 2015, one of the cost effective, life saving and a fairly new intervention is to introduce Haemophilus Influenzae Type B (Hib) for delivery with DPT3 in routine immunization programme in DPRK. This combination vaccine will bring the added benefit of better compliance, coverage and injection safety for immunization programme.

EPI is one of the most successful and sustainable public health programme in DPRK. Routine immunization coverage is quite high and stable over the last couple of years particularly increase in coverage of DTP-HepB with 3 doses (82% in 2006 to 93% in 2010) among the children under 1 year. Immunization services are provided through more than 12,000 immunization posts, 7008 PHC units, and 433 county level clinics/hospitals. 130 central and provincial level hospitals and specialized hospitals. 

Over the past 10 years or so, the programme has received substantial assistance from both UNICEF and WHO in building a nation-wide cold chain system for the storage and distribution of vaccines for immunization programme. To understand the actual status of cold chain capacity, a nation-wide cold chain assessment was carried out in October 2008 with the technical guidance and close supervision of an international consultant. Based on assessment report, nation-wide cold chain replacement plan was developed and implementation of this cold chain replacement plan was completed in June 2010. This was a critical step in infra-structure building and strengthening cold chain capacity for the immunization programme in the country.

DPRK's cold chain system is now well-established and much investment and capacity building efforts have been undertaken in the last 2 years to improve it not only in the area of equipment replacement but also conducted series of cold chain maintenance training at different levels and raised awareness around proper vaccine handling and temperature monitoring through procuring more thermometers and designing, developing and distributing posters on cold chain issues to all health facilities in the country.

Effective Vaccine Management (EVM) assessment will be started from June 2011 with WHO and UNICEF's technical and financial support. 

The national EPI team updated their existing comprehensive multi-year plan (2011-2015) and will be submitted to GAVI along with 2010 APR on 15 May,2011. This plan provides the framework for the introduction of new vaccines. cMYP has also outlined financial implication of EPI program and long term strategies for financial sustainability (cMYP page-51) for its solution. The cMYP clearly stated introduction of DTP-HepB-Hib (pentavalent) vaccine in 2012.

Considering all above factors, national EPI team decided to introduce pentavalent vaccine (DTP-HepB-Hib) in its routine immunization program starting from July 2012 for an initial duration of four years. The estimated cost will be US$ 10.98 millions with 8.5% government co-financing. Birth cohorts will be around 350,000 per year with a coverage target of 95% for the 3rd doses of DTP-HepB-Hib in 2012; 96% in 2013 & 2014 and 97% in 2015. This was agreed by the ICC/HSCC members during the 1st meeting of the year (7 March 2011). It was also recommended by Technical Consultative Group of SEARO in the yearly meeting conducted in July, 2008. In addition, the letter from WHO-Geneva dated 27 July 2009 (see under attachments#15) provided DPRK specific data on Haemophilus Influenzae type B which is convincing and very useful information in guiding decisions for the introduction of Hib vaccine. 

Finally, this proposal was reviewed and endorsed by the existing ICC/HSCC committee which strongly recommend that the NVS support for penta vaccine by GAVI will greatly contribute to prevent diseases which are the major causes of child death in DPRK.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Democratic People's Republic of Korea would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for DTP-HepB-Hib 1 dose/vial Liquid introduction.

The Government of Democratic People's Republic of Korea commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of June.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Prof. CHOE Chang Sik | Name | PAK Su Gil |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr. KIM Jong Hwan | National EPI Manager, MOPH | 850-2-3814077 | Bogon.moph@star.co.net.kp |  |
| Dr. MUNGUN Tuya | Health Specialist | 850-191-2500553 ( mobile) | tmungun@unicef.org |  |
| Dr. ISLAM Kamrul | Chief, Health Section | 850-191-250-0495 (mobile) | kislam@unicef.org |  |
| Dr. MATHUR Arvind | Medical Officer | 850-191-250-0734 ( mobile) | mathura@searo.who.int |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 03.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| RI Pong Hun , Vice-Minister | Minstry of Public Health |  |  |
| PAK Myong Su, Director, State Hygienic | Minstry of Public Health |  |  |
| PAK Jong Min, Director, External Affairs Department, | Minstry of Public Health |  |  |
| KIM Bok Sil, Director, Department of Finance, | Minstry of Public Health |  |  |
| KIM Kwang Jin, Officer, Department of External Affairs, | Minstry of Public Health |  |  |
| KIM Jong Hwan, National EPI Program manager | Minstry of Public Health |  |  |
| RI Hyon Chol, Director of Medical Service | Minstry of Public Health |  |  |
| KI Kwang Ho, Director, Department of External Finance | Minstry of Finance |  |  |
| KIM Su Gil, Vice Director, Department of Cooperation | State Planning Commission |  |  |
| KO Kwang Jin, Vice Direcot, Academy of Medical Science | Academy of Medical Science |  |  |
| Dr. TEGEGN Yonas, Representative | WHO, DPRK |  |  |
| Mr. Bijaya RAJBHANDARI , Representative | UNICEF, DPRK |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr. Kim Kwang Jin | Title | Officer,Department of External Affairs, MOPH |
| --- | --- | --- | --- |
| Tel no | 850-2-3814077 |  |  |
| Fax no | 850-2-44104416 | Address | Sochaung-dong, Central District, P.O.B 44, Pyongyang city, DPRK |
| Email | bogon.moph@star.co.net.kp |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-Agency Coordinating Committee for Immunization |
| --- | --- |
| Year of constitution of the current committee | 2007 |
| Organisational structure (e.g., sub-committee, stand-alone) | Sub-Committee |
| Frequency of meetings | Quarterly meeting |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Vice Minister, Public Health | Prof. Ri Pong Hun |  |
| Secretary | National EPI Program Manager, MoPH | Dr. Kim Jong Hwan |  |
| Members | Director, State Hygiene & Communicable Disease Control Board, MoPH | PAK Myong Su | Action |
|  | Director, External Affairs Department, MOPH | Dr. Pak Jong Min |  |
|  | Director, Department of Finance, MOPH | Kim Bok Sil |  |
|  | Officer, Department of External Affairs, MOPH | Mr. Kim Kwang Jin |  |
|  | Director, Department of Medical Service, MOPH | Ri Hyon Chol |  |
|  | Director, Department of External Finance, Ministry of Finance | Ki Kwang Ho |  |
|  | Vice-Director, Department of Cooperation, State Planning Commission | Kim Su Gil |  |
|  | Vice- Director, Academy of Medical Science | Dr. Ko Kwang Jin |  |
|  | Representative, WHO | Dr. Tegegn Yonas |  |
|  | Representative, UNICEF | Mr. Bijaya Rajbhandari |  |

Major functions and responsibilities of the committee

1. Provide policy guidelines for immunization programme in the country and if necessary review the guidelines and make necessary modifications. 2. Act as an advisory board to the Government on matters related to EPI including self sufficiency in immunization programme, adequate national resource allocations, new developments and to acquire assistance for strengthening EPI. 3. Establish a forum for exchange of information and dialogue on global and national EPI status and coordination activities in the country. 4. Ensure that partner agencies are provided necessary support in strengthening EPI and diseases eradication,elimination and control activities in the country. 5. Assist the Ministry of Public Health and partner agencies in identifying and developing support for new programme strategies when required. 6. Facilitate resource mobilization for EPI programme. 7. Review the progress of EPI and advise Government on appropriate measures for achieving the targets. 8. Organize a subcommittee/task force for a specific EPI related activities for in depth review and implementation when necessary. 9. Act as a liaison with regional and global institutions in issues related to immunization. 10.Hold regular meetings and monitor implementation status of ICC annual workplan.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Provide technical support to review and finalize important documents like (i) Application Form for Country Proposal (ii) Annual progress report and (iii) WHO/UNICEF Joint Reporting form. |
| --- | --- |
| 2. | Ensure quarterly ICC meetings and circulating meeting minutes. |
| 3. | Strengthen provincial co-ordination through field monitoring visits. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 05.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 24,312,696 |  | 2010 | cMYP on EPI for 2011-2015 and WHO/UNICEF JRF for 2010 |
| Infant mortality rate (per 1000) | 26 |  | 2011 | State of the World's Children, UNICEF |
| Surviving Infants[1] | 345,730 |  | 2010 | cMYP on EPI for 2011-2015 and WHO/UNICEF JRF for 2010 |
| GNI per capita (US$) | 740 |  | 2010 | cMYP on EPI for 2011-2015 |
| Total Health Expenditure (THE) as a percentage of GDP | 6.08 | % | 2010 | cMYP on EPI for 2011-2015 |
| General government expenditure on health (GGHE) as % of General government expenditure | 5.55 | % | 2010 | cMYP on EPI for 2011-2015 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

MEDIUM TERM STRATEGIC PLAN FOR THE DEVELOPMENT OF THE HEALTH SECTOR IN DPRK (2010 – 2015)

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

YES

Please indicate the national planning budgeting cycle for health

Annual planning budgeting cycle (January to December)

Please indicate the national planning cycle for immunisation

Annual planning budgeting cycle (January to December)

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

NO

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

No. 2008 Coverage Evaluation Survey clearly showed that there is no gender difference with regards to vaccination.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | One dose within 24 hours after birth | Yes |  |  |
| HepB | One dose within 24 hours after birth | Yes |  |  |
| Polio | Three dose in 1.5, 2.5 and 3.5 month after birth | Yes |  |  |
| DTP+HepB | Three dose in 1.5, 2.5 and 3.5 month after birth | Yes |  |  |
| Measles | I dose at the age of 9 month and 2nd dose at the 15 months | Yes |  |  |
| TT | Two dose in 3rd and 4th month of pregnancy | Yes |  |  |
| Vitamin A | 6-59 month | Yes |  |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2008 |  |  | 2009 | 2010 |
| BCG |  | 98 | 98 | 97 |  | Tuberculosis |  |  |
| DTP | DTP1 | 94 | 94 | 94 |  | Diphtheria |  |  |
|  | DTP3 | 93 | 93 | 92 |  | Pertussis |  | 80 |
| Polio 3 |  | 98 | 99 | 99 |  | Polio |  |  |
| Measles (first dose) |  | 98 | 99 | 99 |  | Measles | 64 |  |
| TT2+ (Pregnant women) |  | 97 | 98 | 97 |  | NN Tetanus |  |  |
| Hib3 |  |  |  |  |  | Hib[2] |  |  |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 93 | 93 | 92 |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  | 98 |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 99 | 100 |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

"EPI COVERAGE EVALUATION SURVEY-2008" DPR Korea was conducted in 2008 under the technical guidance and supervision of an International consultant along with technical and financial asssitance from UNICEF and WHO local offices. Three different target populations surveyed as (i)1Children 12-23 months old for routine immunization coverage (ii) Children 0-11 months old for current immunization coverage and (iii) Mothers of infant 0-11 month old for TT vaccination coverage.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 352,534 | 356,352 | 358,276 | 360,211 | 362,156 |  |  |
| Total infants' deaths | 6,804 | 6,878 | 6,915 | 6,952 | 6,990 |  |  |
| Total surviving infants | 345,730 | 349,474 | 351,361 | 353,259 | 355,166 |  |  |
| Total pregnant women | 357,117 | 360,984 | 362,934 | 364,893 | 366,864 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 345,483 | 349,225 | 351,110 | 353,007 | 354,913 |  |  |
| BCG coverage (%)[1] | 98% | 98% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 341,927 | 345,979 | 347,847 | 349,726 | 351,970 |  |  |
| OPV3 coverage (%)[2] | 99% | 99% | 99% | 99% | 99% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 325,677 | 333,748 | 339,063 | 342,661 | 344,511 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 321,875 | 332,000 | 337,306 | 339,129 | 340,959 |  |  |
| DTP3 coverage (%)[2] | 93% | 95% | 96% | 96% | 96% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 30% | 30% | 30% | 30% | 30% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.43 | 1.43 | 1.43 | 1.43 | 1.43 |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of HepB and/or Hib | 348,656 | 349,225 | 351,110 | 353,007 | 354,913 |  |  |
| Infants vaccinated (to be vaccinated) with 3rd dose of HepB and/or Hib | 321,875 | 332,000 | 337,306 | 339,129 | 344,511 |  |  |
| HepB and/or Hib 3rd dose coverage (%)[2] | 93% | 95% | 96% | 96% | 97% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 342,273 | 342,484 | 344,334 | 346,194 | 348,063 |  |  |
| Measles coverage (%)[2] | 99% | 98% | 98% | 98% | 98% |  |  |
| Pregnant women vaccinated with TT+ | 349,260 | 353,764 | 355,675 | 358,325 | 360,260 |  |  |
| TT+ coverage (%)[4] | 98% | 98% | 98% | 98% | 98% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery | 352,534 | 356,352 | 358,276 | 360,211 | 362,156 |  |  |
| Vit A supplement to infants after 6 months | 342,273 | 342,484 | 344,334 | 346,194 | 348,063 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 1% | 1% | 1% | 1% | 1% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 1,796,002 | 6,276,786 | 13,406,579 | 11,882,480 | 12,087,366 |  |  |  |  |  |
| Traditional vaccines | 572,952 | 608,418 | 472,844 | 503,042 | 508,993 |  |  |  |  |  |
| New and underused vaccines | 1,223,050 | 5,668,368 | 12,933,735 | 11,379,438 | 11,578,373 |  |  |  |  |  |
| Injection supplies | 506,096 | 354,229 | 347,466 | 341,959 | 344,962 |  |  |  |  |  |
| Personnel | 1,142,794 | 1,735,190 | 1,769,893 | 1,805,291 | 1,841,397 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 789,871 | 1,192,453 | 1,216,302 | 1,240,628 | 1,265,441 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 352,923 | 542,737 | 553,591 | 564,663 | 575,956 |  |  |  |  |  |
| Transportation | 26,715 | 207,950 | 233,193 | 237,226 | 211,844 |  |  |  |  |  |
| Maintenance and overheads | 76,112 | 177,765 | 230,162 | 284,584 | 321,494 |  |  |  |  |  |
| Training |  | 185,233 | 162,407 | 111,534 | 113,764 |  |  |  |  |  |
| Social mobilisation and IEC |  | 43,697 | 44,571 |  |  |  |  |  |  |  |
| Disease surveillance | 1,189,500 | 1,990,805 | 1,966,949 | 2,006,288 | 2,046,414 |  |  |  |  |  |
| Program management | 270,000 | 310,039 | 348,076 | 300,916 | 306,934 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 5,007,219 | 11,281,694 | 18,509,296 | 16,970,278 | 17,274,175 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 76,000 | 377,540 | 482,892 | 492,550 | 418,491 |  |  |  |  |  |
| Cold chain equipment | 70,700 | 142,217 | 160,479 | 181,765 | 156,182 |  |  |  |  |  |
| Other capital equipment | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Subtotal Capital Costs | 146,700 | 519,757 | 643,371 | 674,315 | 574,673 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |  |  |  |  |
| Measles |  |  |  |  |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns |  |  |  |  |  |  |  |  |  |  |
| Other campaigns | 300,000 |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 300,000 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| GRAND TOTAL | 5,453,919 | 11,801,451 | 19,152,667 | 17,644,593 | 17,848,848 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Vaccines,devices,personnel,transportation,maintenance,training,IEC/SM,disease surveillance and prog.maangement | UNICEF,WHO,GAVI & GOVT | 5,007,219 | 11,281,694 | 18,509,296 | 16,970,278 | 17,274,175 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Vehicles and cold chain equipment | UNICEF and GAVI | 146,700 | 519,757 | 643,371 | 674,315 | 574,673 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| Operational cost | Government | 300,000 |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 5,453,919 | 11,801,451 | 19,152,667 | 17,644,593 | 17,848,848 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

Cold Chain Capacity and Readiness: The national immunization programme in DPR Korea has been established for more than 20 years, and reported administrative coverage for all the key antigens have been consistently high for the last ten years. Over the past 10 years or so, the programme has received substantial assistance from both UNICEF and WHO in building a nation-wide cold chain system for the storage and distribution of vaccines for immunization programme. To understand the actual status of cold chain capacity, a nation-wide cold chain assessment was carried out in October 2008 with the technical guidance and supervision of an international consultant. Based on assessment report, nation-wide cold chain replacement plan was developed and implementation of this replacement plan was completed in June 2010 which is a critical step in infra-structure building and strengthening cold chain capacity for the immunization programme in the country. Country did a cold chain analysis during the 2008 nation-wide cold chain assessment which is attached under attachments#16 (Figure-1, page-13). It shows the projected cold chain storage needs by province for 3 different scenarios (a) with the current vaccines and immunization schedule (b) with a revised schedule, assuming the new ‘pentavalent’ vaccine is introduced as an all-liquid formulation, presented in single vials, and (c) with a revised schedule, assuming the new ‘pentavalent’ vaccine is introduced in a part-liquid, part-lyophilised formulation, using two separate vials. In summary, DPRK's cold chain system is now well-established and much investment and capacity building efforts have been undertaken in the last 2 years to improve it not only in the area of equipment replacement but also in conducting series of cold chain maintenance training at different levels. Awareness generated around proper vaccine handling and temperature monitoring through procuring more thermometers and designing, developing and distributing posters on cold chain issues to all health facilities in the country.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Ref: cMYP page 43-45: The critical factors for facilitating decision making on new vaccine introduction include disease burden, program capacity, vaccine efficacy, vaccine safety and affordability. Although these are challenging areas for DPR Korea, the priority areas for development include disease burden, program capacity and vaccine safety. For the introduction of new vaccine, an introduction plan was developed (cMYP page 43-45) which includes resource requirements, IEC strategy, training plan, systems for monitoring and response to AEFI and surveillance strategy for monitoring impacts of vaccine introduction. Apart from developing main target with objectives on introduction of a new vaccine, cMYP has also outlined financial implication of EPI program and long term strategies for financial sustainability (cMYP page-51) for its solution. The cMYP clearly reflected introduction of DTP-HepB-Hib (pentavalent) vaccine in 2012. This was agreed by the ICC members during the 1st meeting of the year (7 March 2011). In addition, the letter dated 27 July 2009 from Dr. Thomas Cherian, Coordinator, EPI, WHO-Geneva provided DPRK specific data on Haemophilus Influenzae type B which is convincing and very useful information in guiding decisions for the introduction of Hib vaccine.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) m3 | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 11 | 32 | 28 | 28 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) m3 | # | 80 | 80 | 80 | 80 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 3 | 3 | 3 | 3 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -76 | -69 | -71 | -71 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ |  |  |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

cMYP has clearly outlined financial implication in case of new vaccine introduction and long term strategies for financial sustainability (cMYP page-51) for its solution. On the other hand, Government of DPRK already showed its commitment by providing co-financing for combined DTP-HepB vaccine since 2009. Even 2011 obligations are alreday transferred through UNICEF country office to UNICEF Copenhagen in March,2011. The co-financing amount will be paid by MoPH through UNICEF country office once in a year.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| See atatchment number-15 (DPRK_Hib_Spn_DiseaseBurden_WHO Letter_27 July'2009) |  |  |  |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| 1. Full vaccine storage capacity to be ensured from central to peripheral level health facilities for the introduction of new vaccine. | A. Central level cold chain facility was upgraded with two-walk in cold rooms along with a capacity of 80m3(each 40m3). B. Walk-in cold room (each 10m3)installed at 8 provincial medical warehouses. C. County level cold rooms are fully equipped with ice-lined refrigerators and deep freezers. D. Vaccine carriers were supplied to each Ri/village level clinic to conduct monthly outreach sessions. |  |
| 2. Cold chain maintenance from national to periphery needs to be monitored periodically. | Master trainers were trained on cold chain management with external consultant supported by UNICEF/WHO in May, 2009. Cascade training plan developed for the cold chain technicians and training completed between 2009-2010. All trainings were organised at the provincial levels and conducted by the trained master trainers. MoPH and UNICEF officials monitor the cold chain maintenance during their routine field trips. |  |
| 3. Reduce vaccine wastage is important | Introduced multi-dose vaccine vial policy and recommended weekly vaccination session at Ri clinics instead of monthly session to reduce the wastage. |  |
| 4. Coverage of HepB birth dose | The country is planning to implement OCC (Outside cold chain) policy for HepB vaccine to ensure vaccination within 24 hours of birth particularly in the rural areas (Ri clinics). Currently, all Ri clinics are conducting vaccination session once a month. |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

DTP-HepB+Hib(pentavalent)- 1 dose/vial,Liquid

# 6.3.1. Requested vaccine ( DTP-HepB-Hib, 1 dose/vial, Liquid )

As reported in the cMYP, the country plans to introduce DTP-HepB-Hib, 1 dose/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 349,225 | 351,110 | 353,007 | 354,913 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 332,000 | 337,306 | 339,129 | 344,511 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 95.00% | 96.00% | 96.00% | 97.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 104,700 | 89,700 | 102,600 | 112,900 |  |  |  |  |
| Number of AD syringes | # | 111,800 | 94,800 | 108,500 | 119,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,250 | 1,075 | 1,225 | 1,325 |  |  |  |  |
| Total value to be co-financed by country | $ | 275,500 | 221,500 | 223,000 | 224,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 1,270,400 | 1,017,900 | 1,010,900 | 1,006,700 |  |  |  |  |
| Number of AD syringes | # | 1,356,500 | 1,076,100 | 1,068,800 | 1,064,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 15,075 | 11,950 | 11,875 | 11,825 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 3,337,500 | 2,515,500 | 2,195,000 | 1,998,000 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the DTP-HepB-Hib, 1 dose/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 356,352 | 0.30 | 107,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the DTP-HepB-Hib, 1 dose/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 31,500 | 31,500 |  |
| Social Mobilization, IEC and Advocacy | 35,000 | 35,000 |  |
| Cold Chain Equipment & Maintenance | 0 | 0 |  |
| Vehicles and Transportation | 14,000 | 14,000 |  |
| Programme Management | 6,500 | 6,500 |  |
| Surveillance and Monitoring | 10,000 | 10,000 |  |
| Human Resources | 5,000 | 5,000 |  |
| Waste Management | 1,000 | 0 |  |
| Technical assistance | 20,000 | 5,000 |  |
| Conduct EVM Assessment | 20000 | 0 |  |
| Implement key components of EVM plan | 10000 | 0 |  |
| Management of any potential post-introduction complications | 20000 | 0 |  |
| Potential post-introduction evaluation in 2013 | 10000 | 0 |  |
| Totals | 183,000 | 107,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

Vaccines and vaccination devices will be procured through UNICEF which is the existing practice of DPRK Government.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

Not applicable.

- Please describe the introduction of the vaccines (refer to cMYP)

Pentavalent vaccine (DTP-HepB-Hib) will be introduced for the entire country from 2012 (refer to page-44,cMYP 2011-2015).

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Through UNICEF and WHO.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The co-financing amount will be paid by MoPH through UNICEF country office once a year.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Coverage will be monitored by routine EPI information system. Moreover joint field visits with UNICEF/WHO and MOPH officials will be made on a regular basis.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted?   -

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

- When is the next Effective Vaccine Management (EVM) Assessment planned? June  - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Routine immunization coverage is quite high and stable over the last few years particularly increased in the coverage of DTP-HepB with 3 doses (82% in 2006 to 93% in 2010) among the children under 1 year old. This high coverage was verified by independent Coverage Evaluation Survey conducted in 2008. DPRK's cold chain system is well-established and much investment and capacity building efforts have been undertaken in the last 2 years to improve it. Efforts were made both in the area of equipment replacement and cold chain maintenance training throughout the country. The updated cMYP (2011-2015) clearly reflected the introduction of DTP-HepB-Hib (pentavalent) vaccine in 2012. cMYP has also outlined financial implication of EPI program and long term strategies for financial sustainability for its solution.

# Annexes

# Annex 1

# Annex 1.1 – DTP-HepB-Hib, 1 dose/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 104,700 | 89,700 | 102,600 | 112,900 |  |  |  |  |
| Number of AD syringes | # | 111,800 | 94,800 | 108,500 | 119,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,250 | 1,075 | 1,225 | 1,325 |  |  |  |  |
| Total value to be co-financed by the country | $ | 275,500 | 221,500 | 223,000 | 224,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 1,270,400 | 1,017,900 | 1,010,900 | 1,006,700 |  |  |  |  |
| Number of AD syringes | # | 1,356,500 | 1,076,100 | 1,068,800 | 1,064,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 15,075 | 11,950 | 11,875 | 11,825 |  |  |  |  |
| Total value to be co-financed by the country | $ | 3,337,500 | 2,515,500 | 2,195,000 | 1,998,000 |  |  |  |  |

Table 1.1  C - Summary table for DTP-HepB-Hib, 1 dose/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 349,474 | 351,361 | 353,259 | 355,166 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 332,000 | 337,306 | 339,129 | 344,511 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 95.00% | 96.00% | 96.00% | 97.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 349,225 | 351,110 | 353,007 | 354,913 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 2.470 | 2.320 | 2.030 | 1.850 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 3.50 | 3.50 | 3.50 | 3.50 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 1 dose/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 7.61% |  |  | 8.09% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 349,225 | 26,587 | 322,638 | 351,110 | 28,418 | 322,692 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 1,047,675 | 79,761 | 967,914 | 1,053,330 | 85,253 | 968,077 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,100,059 | 83,749 | 1,016,310 | 1,105,997 | 89,515 | 1,016,482 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 275,015 | 20,938 | 254,077 | 1,485 | 121 | 1,364 |
| I | Total vaccine doses needed | F + G | 1,375,074 | 104,687 | 1,270,387 | 1,107,482 | 89,635 | 1,017,847 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,468,186 | 111,775 | 1,356,411 | 1,170,845 | 94,764 | 1,076,081 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 16,297 | 1,241 | 15,056 | 12,997 | 1,052 | 11,945 |
| N | Cost of vaccines needed | I * vaccine price per dose | 3,396,433 | 258,575 | 3,137,858 | 2,569,359 | 207,954 | 2,361,405 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 77,814 | 5,925 | 71,889 | 62,055 | 5,023 | 57,032 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 10,431 | 795 | 9,636 | 8,319 | 674 | 7,645 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 118,876 | 9,051 | 109,825 | 89,928 | 7,279 | 82,649 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 8,825 | 672 | 8,153 | 7,038 | 570 | 6,468 |
| T | Total fund needed | (N + O + P + Q + R + S) | 3,612,379 | 275,015 | 3,337,364 | 2,736,699 | 221,497 | 2,515,202 |
| U | Total country co-financing | I * country co-financing per dose | 275,015 |  |  | 221,497 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 7.61% |  |  | 8.09% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 1 dose/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 9.21% |  |  | 10.08% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 353,007 | 32,522 | 320,485 | 354,913 | 35,766 | 319,147 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 1,059,021 | 97,564 | 961,457 | 1,064,739 | 107,298 | 957,441 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,111,973 | 102,442 | 1,009,531 | 1,117,976 | 112,663 | 1,005,313 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,494 | 138 | 1,356 | 1,501 | 152 | 1,349 |
| I | Total vaccine doses needed | F + G | 1,113,467 | 102,580 | 1,010,887 | 1,119,477 | 112,814 | 1,006,663 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 1,177,172 | 108,448 | 1,068,724 | 1,183,527 | 119,269 | 1,064,258 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 13,067 | 1,204 | 11,863 | 13,138 | 1,324 | 11,814 |
| N | Cost of vaccines needed | I * vaccine price per dose | 2,260,339 | 208,236 | 2,052,103 | 2,071,033 | 208,706 | 1,862,327 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 62,391 | 5,748 | 56,643 | 62,727 | 6,322 | 56,405 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 8,363 | 771 | 7,592 | 8,409 | 848 | 7,561 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 79,112 | 7,289 | 71,823 | 72,487 | 7,305 | 65,182 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 7,076 | 652 | 6,424 | 7,114 | 717 | 6,397 |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,417,281 | 222,694 | 2,194,587 | 2,221,770 | 223,896 | 1,997,874 |
| U | Total country co-financing | I * country co-financing per dose | 222,694 |  |  | 223,896 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 9.21% |  |  | 10.08% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP-HepB-Hib, 1 dose/vial, Liquid | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 7, 12, 13 | Yes |
| Improvement plan based on EVM |  | Missing | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 10 |  |
| ICC/HSCC workplan for forthcoming 12 months |  | 11 |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 8 |  |
| Banking details |  | 9 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Ministers signature page of MoH & MoF | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Penta Application_MoH & MoF_Signature Pages.pdf Date/Time: 13.05.2011 10:11:14 Size: 1 MB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: Ministers signature page of MoF & MoH | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Penta Application_MoH & MoF_Signature Pages.pdf Date/Time: 13.05.2011 10:12:48 Size: 1 MB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: Signature pages of ICC/HSCC members | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Penta Application_ICC&HSCC_Signature Pages.pdf Date/Time: 13.05.2011 10:14:05 Size: 567 KB |  |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: ICC/HSCC Meeting minutes endorsed pentavalent proposal | File name: C:\DPRK Folder - 2011\EPI\ICC & HSCC minutes\ICC-HSCC - Meeting Minutes_ Endorsed Proposal_5 May 2011.doc Date/Time: 13.05.2011 10:16:37 Size: 86 KB |  |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: cMYP _Final Version_2011-2015 | File name: C:\DPRK Folder - 2011\EPI\cMYP__DPRK_Final Version_ 11 May 2011.docx Date/Time: 13.05.2011 10:18:06 Size: 335 KB |  |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: cMYP Costing tool_Final Version | File name: C:\DPRK Folder - 2011\EPI\cMYP_Costing Tool_DPRK_Final Version_11 May 2011.xlsx Date/Time: 13.05.2011 10:19:24 Size: 1 MB |  |  |  |
| 7 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: ICC/HSCC Meeting minutes_7 March 2011 | File name: C:\DPRK Folder - 2011\EPI\ICC & HSCC minutes\ICC-HSCC - Meeting Minutes_ 7 March 2011.doc Date/Time: 13.05.2011 10:24:17 Size: 82 KB |  |  |  |
| 8 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: Plan for NVS introduction ( part of cMYP) | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Plan for NVS introduction-cMYP_Page 43-45.docx Date/Time: 13.05.2011 10:49:33 Size: 22 KB |  |  |  |
| 9 | File Type: Banking details File Desc: Signature pages of banking form | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Penta Application_Banking Form_Signature Pages.pdf Date/Time: 13.05.2011 10:36:18 Size: 364 KB |  |  |  |
| 10 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: Joint Reporting Form_2010_Final | File name: C:\DPRK Folder - 2011\EPI\JRF_2010_Final_7 April_2011.xls Date/Time: 13.05.2011 10:52:39 Size: 327 KB |  |  |  |
| 11 | File Type: ICC/HSCC workplan for forthcoming 12 months File Desc: ICC-HSCC Annual workplan for 2011 | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\ICC- HSCC Workplan for 2011.doc Date/Time: 13.05.2011 11:20:39 Size: 61 KB |  |  |  |
| 12 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: ICC/HSCC Meeting Minutes_22 June,2010 | File name: C:\DPRK Folder - 2011\EPI\ICC & HSCC minutes\ICC-HSCC - Meeting Minutes_22 June 2010.doc Date/Time: 13.05.2011 10:33:49 Size: 69 KB |  |  |  |
| 13 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: ICC/HSCC Meeting Minutes_10 May,2010 | File name: C:\DPRK Folder - 2011\EPI\ICC & HSCC minutes\ICC-HSCC - Meeting Minutes_Endorsed APR_10May 2010.doc Date/Time: 13.05.2011 10:34:45 Size: 63 KB |  |  |  |
| 14 | File Type: other File Desc: Cover Page - Letter from the government | File name: C:\DPRK Folder - 2011\GAVI\New Proposal\Uploaded Documents\Cover Letter_Penta Application.pdf Date/Time: 13.05.2011 11:27:35 Size: 139 KB |  |  |  |
| 15 | File Type: other File Desc: DPRK_Hib_Spn_DiseaseBurden_WHO Letter_27 July'2009 | File name: D:\DPRK Folder - 2011\GAVI\New Proposal\DPRK_Hib_Spn_DiseaseBurden_WHO Letter_27 July'2009.pdf Date/Time: 14.05.2011 05:37:45 Size: 148 KB |  |  |  |
| 16 | File Type: other File Desc: Cold Chain Assessment 2008_DPR Korea_Final report | File name: D:\D-DRIVE\Data\DPRK Folder-2009\EPI\CES & CCA -2008\Cold Chain Assessment 2008_DPR Korea_Final Report.doc Date/Time: 14.05.2011 05:45:22 Size: 1 MB |  |  |  |