APPLICATION FORM FOR COUNTRY PROPOSAL: PHASE 2

For Support to:

New and Under-Used Vaccines

20 April 2007

This document is accompanied by an electronic copy on CD for your convenience.

Please return a copy of the CD with the original, signed hard-copy of the document to:

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

All documents and attachments must be in English or French.

Please direct any enquiries to:

Dr Ivone Rizzo irizzo@gavialliance.org or representatives of a GAVI Alliance partner agency.

## CONTENTS

|  | PAGE |
| --- | --- |
| 1. | Executive Summary | 2 |
| 2. | Signatures of the Government and National Coordinating Body | 3 |
|  | The Inter-Agency Coordinating Committee for Immunization (ICC) | 5 |
| 3. | Immunization Program Data | 6 |
| 4. | New and Under-Used Vaccine Support (NVS) | 11 |
|  | First Preference Vaccine | 13 |
|  | Procurement and Management of New and Under-Used Vaccines | 15 |
| 5. | Additional comments and recommendations from the Inter-Agency Coordinating Committee for Immunization (ICC) and other Health Sector Development Partners | 17 |
| 6. | Documents Required | 18 |
| ANNEX 1: Calculation of Required Supply and Related Co-Financing Budget | ** |

** Annex 1 is attached in excel spreadsheet format – please update and complete the tables.

## Executive Summary

To be completed for all proposals.  Please outline a synopsis of the proposal, including:

- The specific requests for support from GAVI, including:

  - the details relating to the requested vaccine(s)

  - the duration of support (which should be based on the relevant national planning cycle)

  - the total amount of funds requested

- Relevant baseline data, including:

  - DTP3 coverage data

  - Measles coverage data

  - Targets for increased coverage

- The nature of stakeholders participation in developing this proposal

  - Inter-Agency Coordinating Committee, health sector coordinating organization or other similar body.

The landlocked country of the Central African Republic included the Extended Program for Immmunization in its health activities in 1979. From 1986 to 1990, satisfactory results were recorded within the framework of the Operational Plan for Accelerated Development of the Extended Program for Immunization. The total coverage for all antigens was 75% according to the 1991 final assessment.

Since 1996 the EPI is facing many problems which have resulted in a persistent reduction of vaccination coverage year after year. Problems encountered include a loss of motivation of health personnel due to late payment of salaries, insufficient fuel oil for the cold chain, a shortage of EPI funds, a shortage of health personnel quantitatively and qualitatively and an irregular vaccine supply.

Faced with this situation, the Central African Government carried out an external review of the EPI in 2002, with the support of its development partners, in particular WHO and UNICEF.

The recommendations of this review led to the development of the 2003-2007 Multi Year Plan and to the injection safety policy, which were approved by the Government and its development partners. Moreover, during the same period, the Government submitted a proposal to the Global Alliance for Vaccines and Immunization (GAVI) and the Global Fund for Vaccines requesting EPI support for 2003-2007 and this was approved by these institutions.

With the support of GAVI and local partners, the program is growing in strength every year and vaccination coverage rates in 2006 have largely exceeded the 50% mark (except for TT2+). Continuous improvement in the areas of wastage and drop-out rate reduction, vaccine management and the epidemiological surveillance system has also been observed.

In order to increase the protection spectrum of Central African children from vaccine preventable diseases and thus contribute more effectively to child mortality and morbidity reduction in the country, the Ministry of Health has decided to include two new antigens (the vaccine against viral hepatitis B and haemophilus influenza type b) in the routine immunization program from 2008.

Coverage and drop-out rate objectives for the 2008-2011 period are as follows:

| Year | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| HepB3 coverage | N.A | 82% | 85% | 90% | 90% |
| Hib3 coverage | N.A | 82% | 85% | 90% | 90% |

The coverage and drop-out rate targets for other antigens included in the 2007-2011 comprehensive Multi Year Plan are reproduced below.

|  | Baseline data and targets |
| --- | --- |
|  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| BCG | 84.72% | 85% | 87% | 89% | 90% | 90% |
| OPV3 | 90.97% | 80% | 82% | 85% | 90% | 90% |
| DTP3 | 87.76% | 80% |  |  | 90% | 90% |
| DTP-HepB-Hib |  |  | 82% | 85% | 90% | 90% |
| MEAS | 107.97% | 80% | 82% | 85% | 90% | 90% |
| YF | 98.6% | 80% | 82% | 85% | 90% | 90% |
| TT2+ | 36.05% | 50% | 70% | 85% | 90% | 90% |

|  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- | --- |
| DTP1/DTP3 drop-out rate | 16% | 12% | 10% | 8% | 6% | 5% |

The Pentavalent vaccine DTP-HepB-Hib in liquid form and 10-dose vial is the chosen presentation for the introduction of hepatitis B and Hib vaccination in the EPI in the Central African Republic. If this presentation is unavailable, we will start with the lyophilised 2-dose vial presentation.

This vaccine will be introduced from January 2008 on the whole of the national territory. 2007 will be devoted to thoroughly preparing the introduction.

The choice of vaccine is justified by the following reasons:

• By administering several antigens at the same time, children will receive fewer injections, which will lead to increased parental acceptance;

• High immunization coverages will be reached rapidly for five antigens at the same time (because the vaccine will quickly follow the current DTP trend);

• Lower operational costs compared to monovalent vaccines: economy of syringes and needles, reduced volume of storage, transport and habitually produced waste, easier data management and time savings.

The pentavalent vaccine (DTP-HepB-Hib) will be administered by intramuscular injection to all children younger than one year of age who are taken to the immunization centres from the date of official launch of the vaccine on the whole of the national territory. From then onwards, all the children coming for their first dose of DTP series will receive an injection of pentavalent vaccine DTP-HepB-Hib until the end of their immunization series. Those children taken for their 2nd or 3rd DTP after the launch will receive the pentavalent vaccine to finish the series already started. No catching up vaccinations will be administered.

This proposal covers the last four years of the 5-year planning cycle of the 2007-2011 EPI comprehensive Multi Year Plan.

It has allowed for an overall budget of $1,677,662 for the first year with a co-financing portion from the Government of $0.15 per pentavalent vaccine dose, thus providing $75,409 in total. The remainder, which amounts to $1,602,253 will be financed by GAVI.

## Signatures of the Government and National Coordinating Body

The Government of the Central African Republic commits itself to developing national immunization services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan for Immunization (cMYP) or updated Multi-Year Plan presented with this document.

The table below shows the immunization targets outlined in the cMYP or updated Multi-Year Plan, the Government commitment to establish a partnership and participate with the GAVI Alliance in financing the plan for introduction of new vaccines, and the funds required from the GAVI Alliance.

| Table 2.1a: Targets and budgets for the introduction of DTP-HepB+Hib immunization using the lyophilized 2-dose vial vaccine |
| --- |
| Total requirements |  | 2007 | 2008 | 2009 | 2010 | 2011 |
| National target for children to be immunized | # |  | 107 249 | 113 438 | 122 558 | 125 057 |
| Total number of vaccine doses required | # |  | 502 730 | 401 571 | 408 118 | 416 440 |
| Total number of AD syringes required | # |  | 468 745 | 377 749 | 408 118 | 416 440 |
| Total number of reconstitution syringes required | # |  | 279 015 | 222 872 | 226 506 | 231 124 |
| Total number of safety boxes required | # |  | 8 300 | 6 667 | 7 044 | 7 188 |
| Total budget | Price per vaccine dose * | $ |  | 3.200 | 2.900 | 2.650 | 2.300 |
|  | Total funding required | $ |  | 1 677 662 | 1 220 345 | 1 139 309 | 1 015 328 |
| Country co-financing | Co-financing per dose | $ |  | 0.15 | 0.15 | 0.15 | 0.15 |
|  | Total country payment | $ |  | 75 409 | 60 236 | 61 218 | 62 466 |
| GAVI Alliance support requested | GAVI payment per dose | $ |  | 3.05 | 2.75 | 2.5 | 2.15 |
|  | Total GAVI payment | $ |  | 1 602 253 | 1 160 110 | 1 078 091 | 952 862 |

Following the regulations of the internal budgeting and financing cycles the Government will normally release its portion of the funds in the month of September 2007. Payment of the procurement of the first year of co-financed support will be around October 2007.

The Government agrees to use UNICEF Supply Division (Copenhagen) as its procurement agency for the purchase of the supply detailed in this application.  If this is not possible, the Government agrees to comply with the GAVI Alliance requirements, and has included details of the proposed mechanism in Section 6, with details of the relevant National Regulatory Authority procedures.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Minister of Health (or senior official): | Minister of Finance (or senior official): |
| --- | --- |
| Dr Bernard LALA | Mr Elie DOTE |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: Minister for Public Health and Citizenry …………………………………… | Title: Minister of Finance and the Budget …………………………………… |
| Date: 20.04.07 …………………………………… | Date: 20.04.07 …………………………………… |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the ICC met on the 18 April 2007 to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1………

| Name/Title | Agency/Organisation | Signature |
| --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr Régis MBARYDABA | Title: EPI/CAR Director |
| --- | --- |
| Tel No.: +236 50 04 27 | Address: BP 783 Bangui CAR |
| Email: mbaryregis@yahoo.fr |  |

The GAVI Secretariat is unable to return documents and attachments.  Unless otherwise specified by the country, documents may be shared with the GAVI Alliance partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).

The ICC are responsible for coordinating and guiding the use of the GAVI Alliance New and Under-Used Vaccine support, as well as all other immunization activities in the country.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

Name of the ICC: Inter-agency Coordinating Committee (ICC) of the Extended Program for Immunization

Date of constitution of the current ICC: 2004

Organisational structure (e.g., sub-committee, stand-alone): Technical Committee for Support to the Extended Program for Immunization (TCSEPI): Technical ICC

Frequency of meetings: Quarterly for the ICC and monthly for the TCSEPI

Major functions and responsibilities of the ICC:

1. Coordinate partner activities;

2. Contribute to the review and approval of plans concerning routine EPI, National /Local Immunization Days and the Integrated Epidemiological Surveillance of Diseases;

3. Mobilize necessary internal and external resources to carry out the activities;

4. Provide for transparent and responsible resource management by carrying out regular checks of program resource use with the EPI team;

5. Encourage and support information exchange at national operational as well as external levels;

6. Ensure smooth program implementation;

7. Investigate paths and means to resolve any constraints which might impede the smooth functioning of the program.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1. Advocacy for enhanced EPI visibility

2. Stengthening program performance monitoring on a regular basis

3. Technical, financial and material program support.

## Immunization Program Data

Please complete the tables below, using data from available sources.  Please identify the source of the data, and the date. Where possible use the most recent data, and attach the source document.

  - Please refer to the Comprehensive Multi-Year Plan for Immunization (or equivalent plan), and attach a complete copy (with an executive summary) as DOCUMENT NUMBER 2.

  - Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms on Vaccine Preventable Diseases and attach them as DOCUMENT NUMBERS 3.

  - Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

Table 3.1: Basic facts for the year 2006 (most recent; specify dates of data provided and source)

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population | 4,132,989 | RGPH 2003 | Ministry of Economy, Planning and International Cooperation |
| Infant mortality rate (per 1000) | 132/1000 | RGPH 2003 | Ministry of Economy, Planning and International Cooperation |
| Surviving Infants* | 125,643 | RGPH 2003 | Ministry of Economy, Planning and International Cooperation |
| GNI per capita (US$) | $331 | GDP 2004 | Ministry of Economy, Planning and International Cooperation |
| Percentage of GDP allocated to Health | 0.8% | GDP 2004 | Ministry of Economy, Planning and International Cooperation |
| Percentage of Government expenditure on Health | 5% | GDP 2004 | Ministry of Economy, Planning and International Cooperation |

* Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country:

Please indicate the name and date of the relevant planning document for health

National Health Development Plan II (NHDP II) 2006-2015

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content etc)

Comprehensive Multi Year Plan of the 2007-2011 EPI whose content and period fit in with the NHDP II.

Please indicate the national planning budgeting cycle for health

Triennial cycle with an annual sequence

Please indicate the national planning cycle for immunization

Annual cycle

Table 3.2: 	Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement (refer to cMYP pages or updated Multi-Year Plan)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: | Comments |
| --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | 0 to 15 days after birth | X |  |  |
| OPV 0 | 0 to 15 days after birth | X |  |  |
| DTP 1, OPV 1 | 6 weeks | X |  |  |
| DTP 2, OPV 2 | 10 weeks | X |  |  |
| DTP 3, OPV 3 | 14 weeks | X |  |  |
| MEAS | 9 months | X |  |  |
| YF | 9 months | X |  |  |
| TT 1 | 1st contact | X |  |  |
| TT 2 | 1 month after TT 1 | X |  |  |
| TT 3 | 6 months after TT 2 | X |  |  |
| TT 4 | 1 year after TT 3 | X |  |  |
| TT 5 | 1 year after TT 4 | X |  |  |
| Vitamin A | 6 to 11 months | X |  |  |

Table 3.3: Trends of routine immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2004 | 2005 | 2004 | 2005 |  | 2004 | 2005 |
| BCG | 69.1% | 59.49% | N/Av | N/Av | Tuberculosis* | 100 | N/Av |
| DTP | DTP1 | 72.56% | 63,88% | N/Av | N/Av | Diphtheria | 0 | 0 |
|  | DTP3 | 49.73% | 45,59% | N/Av | N/Av | Pertussis | 561 | 87 |
| Polio 3 | 48.79% | 53,39% | N/Av | N/Av | Polio | 30 | 0 |
| Measles (first dose) | 69.73% | 64,94% | N/Av | N/Av | Measles | 1233 | 473 |
| TT2+ (Pregnant women) | 34.13% | 41,53% | N/Av | N/Av | Neonatal Tetanus ** | 37 | 20 |
| Hib3 |  |  | N/Ap | N/Ap | Hib *** | N/Av | 22*** |
| Yellow Fever | 58.07% | 58,45% | N/Av | N/Av | Yellow fever | 0 | 0 |
| HepB3 |  |  |  |  | Hepatitis B sero-prevalence* | N/Av | N/Av |
| Vit A supplement | Mothers (<6 weeks post-delivery) | N/Av | N/Av | N/Ap | N/Ap |  |  |  |
|  | Infants (>6 months) | 78.5% | 87.2% | N/Av | N/Av |  |  |  |

* If available ** If ‘total’ tetanus data only is available, please give it and note that this is the case *** Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, and the age groups the data refers to:

Table 3.4: Baseline and annual targets (refer to cMYP pages or updated Multi-Year Plan)

| Number | Baseline and targets |
| --- | --- |
|  | Base year | Prog. Year 1 | Prog. Year 2 | Prog. Year 3 | Prog. Year 4 | Prog. Year 5 |
|  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Births | 144,655 | 147,582 | 150,583 | 15, 650 | 156,780 | 159,978 |
| Infant deaths | 19,012 | 19,395 | 19,791 | 20,194 | 20,605 | 21,026 |
| Surviving infants | 125,643 | 128,187 | 130,792 | 133,456 | 136,175 | 138,952 |
| Pregnant women | 165,320 | 168,667 | 172,094 | 175,600 | 179,178 | 182,832 |
| Infants vaccinated with BCG | 122,878 | 125,445 | 131,007 | 136,749 | 141,102 | 143,980 |
| BCG coverage* | 85% | 85% | 87% | 89% | 90% | 90% |
| Infants vaccinated with OPV3 | 114,487 | 102,550 | 107,249 | 113,438 | 122,558 | 125,057 |
| OPV3 coverage** | 91% | 80% | 82% | 85% | 90% | 90% |
| Infants vaccinated with DTP3*** | 110,821 | 102,550 |  |  |  |  |
| DTP3 coverage** | 88% | 80% |  |  |  |  |
| Infants vaccinated with DTP-HepB-Hib 3*** |  |  | 107,249 | 113,438 | 122,558 | 125,057 |
| DTP-HepB-Hib coverage** |  |  | 82% | 85% | 90% | 90% |
| Infants vaccinated with DTP1*** | 132,090 | 115,368 | 117,713 | 122,780 | 129,366 | 132,004 |
| Wastage rate in base-year and planned thereafter | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| DTP wastage rate | 24% | 20% | 15% | 10% | 5% | 5% |
| MEAS wastage rate | 35% | 22% | 20% | 18% | 15% | 15% |
| YF wastage rate | 35% | 33% | 28% | 20% | 15% | 15% |
| Infants vaccinated with Measles | 135,773 | 102,550 | 107,249 | 113,438 | 122,558 | 125,057 |
| Measles coverage** | 108% | 80% | 82% | 85% | 90% | 90% |
| Pregnant women vaccinated with TT+ | 59,798 | 84,334 | 120,466 | 149,260 | 161,260 | 164,549 |
| TT+ coverage**** | 36% | 50% | 70% | 85% | 90% | 90% |
| Vit A supplement | Mothers (<6 weeks from delivery) | 38% | 50% | 60% | 70% | 80% | 80% |
|  | Infants (>6 months) | 74% | 80% | 85% | 90% | 90% | 90% |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT+ out of total pregnant women

Table 3.5: Summary of current and future immunization budget (or refer to cMYP pages or updated Multi-Year Plan)

|  | Expenses | Future Resource Demand |
| --- | --- | --- |
| Cost Category | 2005 | 2007 | 2008 | 2009 | 2010 | 2011 |
| Recurrent Cost (routine vaccination) | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines | $237,549 | $374,313 | $2,256,032 | $1,938,596 | $2,041,661 | $2,106,676 |
| - Traditional vaccines | $149,637 | $205,307 | $140,733 | $146,769 | $152,369 | $156,934 |
| - New and under-used vaccines | $87,912 | $169,006 | $2,115,299 | $1,791,827 | $1,889,292 | $1,949,743 |
| Injection supplies | $81,434 | $113,632 | $140,587 | $154,751 | $166,528 | $171,337 |
| Personnel | $1,133,859 | $1,262,800 | $1,397,244 | $1,471,129 | $1,592,679 | $1,655,731 |
| - Salaries of full time health workers (central level, provinces) | $634,437 | $728,059 | $795,539 | $847,434 | $901,087 | $944,068 |
| - Per-diems for advanced strategy/mobile teams | $99,184 | $114,138 | $129,650 | $141,239 | $153,240 | $162,544 |
| - Per-diems for supervision | $400,239 | $420,603 | $472,055 | $482,456 | $538,352 | $549,119 |
| Transport | $93,710 | $146,934 | $147,160 | $186,936 | $202,568 | $222,563 |
| - Non mobile strategy and vaccine supply | $57,761 | $93,334 | $76,593 | $78,974 | $81,437 | $84,034 |
| - Advanced and mobile strategy | $35,949 | $53,600 | $70,566 | $107,963 | $121,131 | $138,529 |
| Maintenance and overheads | $677,843 | $775,726 | $870,498 | $947,799 | $1,006,220 | $1,072,720 |
| Cold chain | $500,554 | $552,354 | $617,231 | $674,046 | $763,344 | $805,055 |
| Other equipment | $42,018 | $82,283 | $109,356 | $126,964 | $93,152 | $114,945 |
| Buildings | $135,271 | $141,089 | $143,911 | $146,789 | $149,725 | $152,719 |
| Short-term training | $121,926 | $105,683 | $135,236 | $37,984 | $38,743 | $39,518 |
| Social mobilization and IEC | $23,548 | $66,292 | $31,359 | $20,991 | $18,352 | $17,679 |
| Disease control and surveillance | $162,053 | $244,416 | $271,451 | $266,885 | $272,223 | $277,667 |
| Program management | $205,338 | $176,779 | $225,393 | $183,921 | $187,599 | $232,949 |
| Other recurrent costs | $1,884 | $3,843 | $3,920 | $3,998 | $4,078 | $4,160 |
| Subtotal Recurrent Costs | $2,739,144 | $3,270,418 | $5,478,880 | $5,212,989 | $5,530,652 | $5,801,000 |
| Capital Costs (routine vaccination) |  |  |  |  |  |  |
| Vehicles | $64,050 | $14,411 | $125,436 | $33,985 | $206 971 | $0 |
| Cold chain equipment | $475,526 | $173,333 | $222,307 | $209,674 | $118 349 | $58 907 |
| Other capital equipment | $37,008 | $170,996 | $152,701 | $105,468 | $70 042 | $97 849 |
| Subtotal Capital Costs | $576,585 | $358,740 | $500,444 | $349,128 | $395 361 | $156 756 |
| Vaccination Campaigns | $0 | $0 | $0 | $0 | $0 | $0 |
| Polio | $1,961,567 | $286,803 | $291,435 | $0 | $0 | $0 |
| Vaccines | $481,361 | $55,241 | $55,241 | $0 | $0 | $0 |
| Operational cost | $1,480,205 | $231,563 | $236,194 | $0 | $0 | $0 |
| Measles | $1,648,567 | $0 | $1,034,496 | $0 | $0 | $0 |
| Vaccines and injection supplies | $583,409 | $0 | $242,383 | $0 | $0 | $0 |
| Operational cost | $1,065,159 | $0 | $792,113 | $0 | $0 | $0 |
| Yellow fever |  | $0 | $0 | $0 | $0 | $0 |
| Vaccines and injection supplies | $0 | $0 | $0 | $0 | $0 | $0 |
| Operational cost | $0 | $0 | $0 | $0 | $0 | $0 |
| Neonatal tetanus | $0 | $2,595,306 | $0 | $0 | $0 | $0 |
| Vaccines and injection supplies | $0 | $340,641 | $0 | $0 | $0 | $0 |
| Operational cost | $0 | $2,254,665 | $0 | $0 | $0 | $0 |
| Subtotal Campaign Costs | $3,610,134 | $2,882,109 | $1,325,931 | $0 | $0 | $0 |
| Shared Costs | $0 | $0 | $0 | $0 | $0 | $0 |
| Shared personnel costs | $1,050,206 | $1,115,701 | $1,273,497 | $1,301,066 | $1,476,792 | $1,508,075 |
| Shared transport costs | $1,705,350 | $1,739,457 | $1,774,246 | $1,809,731 | $1,845,926 | $1,882,844 |
| Buildings | $376,766 | $296,873 | $222,649 | $68,370 | $66,067 | $46,798 |
| Subtotal Shared Costs | $3,132,322 | $3,152,031 | $3,270,393 | $3,179,168 | $3,388,785 | $3,437,717 |
| GRAND TOTAL | $10,058,185 | $9,663,298 | $10,575,647 | $8,741,286 | $9,314,798 | $9,395,473 |

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunization program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners.

Table 3.6: Summary of financing and sources of funds in 2005 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | WHO | UNICEF | GAVI | Community Funding | Resource Demand |
| --- | --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |  |
| - Traditional vaccines |  |  | 149,637 |  |  | 149,637 |
| - New and under-used vaccines |  |  | 12,613 | 75,299 |  | 87,912 |
| Injection supplies |  |  | 27,434 | 54,000 |  | 81,434 |
| Personnel |  |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 634,437 |  |  |  |  | 634,437 |
| - Per-diems for advanced strategy/mobile teams |  | 99,184 |  |  |  | 99,184 |
| - Per-diems for supervision |  | 179,306 | 140,084 | 801 | 80,048 | 400,239 |
| Transport |  |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 5,600 | 15,000 | 35,001 |  | 2,160 | 57,761 |
| - Advanced and mobile strategy | 7,608 | 12,134 | 7,433 | 916 | 7,858 | 35,949 |
| Maintenance and overheads |  |  |  |  |  |  |
| Cold chain |  |  | 500,554 |  |  | 500,554 |
| Other equipment |  | 4,098 | 37,920 |  |  | 42,018 |
| Buildings | 128,218 |  | 7,053 |  |  | 135,271 |
| Short-term training |  | 121,926 |  |  |  | 121,926 |
| Social mobilization and IEC |  |  | 23,548 |  |  | 23,548 |
| Disease control and surveillance |  | 162,053 |  |  |  | 162,053 |
| Program management | 60,000 | 65,000 | 69,538 | 10,800 |  | 205,338 |
| Other recurrent costs |  |  |  |  | 1,884 | 1,884 |
| Subtotal Recurrent Costs | 835,863 | 658,701 | 1,010,815 | 141,816 | 91,950 | 2,739,144 |
| Capital Costs |  |  |  |  |  |  |
| Vehicles |  |  | 64.050 |  |  | 64,050 |
| Cold chain equipment |  | 10,000 | 465,526 |  |  | 475,526 |
| Other capital equipment |  | 10,000 | 19,461 |  | 7,547 | 37,008 |
| Subtotal Capital Costs |  | 20,000 | 549,037 |  | 7,547 | 576,585 |
| Vaccination Campaigns |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |
| Vaccines |  |  | 481,361 |  |  | 481,361 |
| Operational cost |  | 1,335,780 | 144,425 |  |  | 1,480,205 |
| Measles |  |  |  |  |  |  |
| Vaccines and injection supplies |  |  | 583,409 |  |  | 583,409 |
| Operational cost | 42,400 | 762,072 | 179,249 | 53,749 | 27,689 | 1,065,159 |
| Subtotal Campaign Costs | 42,400 | 2,097,852 | 1,388,444 | 53,749 | 27,689 | 3,610,134 |
| Shared costs |  |  |  |  |  |  |
| Shared personnel costs | 880,000 |  | 115,746 |  | 54,460 | 1,050,206 |
| Shared transport costs | 783,370 | 600,980 |  |  | 321,000 | 1,705,350 |
| Buildings | 376,766 |  |  |  |  | 376,766 |
| Subtotal Shared Costs | 2,040,136 | 600,980 | 115,746 |  | 375,460 | 3,132,322 |
| GRAND TOTAL | 2,918,399 | 3,377,533 | 3,064,042 | 195,565 | 502,646 | 10,058,185 |

Table 3.7: Summary of financing and sources of funds for 2007 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | WHO | UNICEF | GAVI | Community funding | Resource Demand |
| --- | --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |  |
| - Traditional vaccines |  |  | 205,307 | 102,653 |  | 205,307 |
| - New and under-used vaccines |  |  | 169,006 |  |  | 169,006 |
| Injection supplies |  |  | 113,632 |  |  | 113,632 |
| Personnel |  |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 728,059 |  |  |  |  | 728,059 |
| - Per-diems for advanced strategy/mobile teams |  | 60,000 |  | 42,060 |  | 114,138 |
| - Per-diems for supervision | 842 | 188,429 | 147,211 |  | 42,060 | 420,603 |
| Transport |  |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 9,325 | 40,137 | 40,137 |  | 3,734 | 93,334 |
| - Advanced and mobile strategy | 7,150 | 9,320 | 7,320 | 23,427 | 3,200 | 53,600 |
| Maintenance and overheads |  |  |  |  |  |  |
| Cold chain |  |  | 552,354 |  |  | 552,354 |
| Other equipment |  | 8,228 | 74,055 |  |  | 82,283 |
| Buildings | 141,089 |  |  |  |  | 141,089 |
| Short-term training |  |  |  |  |  | 105,683 |
| Social mobilization and IEC |  |  | 66,292 |  |  | 66,292 |
| Disease control and surveillance |  | 244,416 |  |  |  | 244,416 |
| Program management | 10,000 |  |  | 146,212 |  | 176,779 |
| Other recurrent costs |  |  |  |  | 3,843 | 3,843 |
| Subtotal Recurrent Costs | 896,465 | 550,531 | 1,375,315 | 314,351 | 52,837 | 3,270,418 |
| Capital Costs |  |  |  |  |  |  |
| Vehicles | 14,411 |  |  |  |  | 14,411 |
| Cold chain equipment |  |  | 123,373 |  |  | 173,333 |
| Other capital equipment | 170,996 |  |  |  |  | 170,996 |
| Subtotal Capital Costs | 185,407 |  | 123,373 |  |  | 358,740 |
| Vaccination Campaigns |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |
| Vaccines |  |  | 55,241 |  |  | 55,241 |
| Operational cost |  | 190,864 | 31,079 |  |  | 231,563 |
| Measles |  |  |  |  |  |  |
| Vaccines and injection supplies |  |  | 340,641 |  |  | 340,641 |
| Operational cost |  |  | 2,254,665 |  |  | 2,254,665 |
| Subtotal Campaign Costs |  | 190,864 | 2,681,626 |  |  | 2,882,109 |
| Shared costs |  |  |  |  |  |  |
| Shared personnel costs | 1,014,728 |  |  |  | 8,119 | 1,115,701 |
| Shared transport costs | 1,739,428 |  |  |  |  | 1,739,457 |
| Buildings | 247,108 |  |  | 48,737 |  | 296,873 |
| Subtotal Shared Costs | 3,001,264 |  |  | 48,737 | 8,119 | 3,152,031 |
| GRAND TOTAL | 4,083,136 | 741,395 | 4,180,314 | 363,089 | 60,956 | 9,663,298 |

Table 3.8: Summary of financing and sources of funds for 2008 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | WHO | UNICEF | GAVI | Community Funding | Resource Demand |
| --- | --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |  |
| - Traditional vaccines | 7,037 |  | 133,696 |  |  | 140,733 |
| - New and under-used vaccines | 105,765 |  |  | 2,009,534 |  | 2,115,299 |
| Injection supplies | 7,029 |  | 133,558 |  |  | 140,587 |
| Personnel |  |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 795,539 |  |  |  |  | 795,539 |
| - Per-diems for advanced strategy/mobile teams |  | 65,000 |  | 64,650 |  | 129,650 |
| - Per-diems for supervision | 945 | 211,479 | 165,220 | 47,206 | 47,206 | 472,055 |
| Transport |  |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 7661 | 32,935 | 32,935 |  | 3,064 | 76,593 |
| - Advanced and mobile strategy | 17,726 | 12,010 | 20,643 | 14,300 | 5,887 | 70,566 |
| Maintenance and overheads |  |  |  |  |  |  |
| Cold chain |  |  | 617,231 |  |  | 617,231 |
| Other equipment |  | 10,936 | 98,420 |  |  | 109,356 |
| Buildings | 143,911 |  |  |  |  | 143,911 |
| Short-term training |  | 135,236 |  |  |  | 135,236 |
| Social mobilization and IEC |  |  | 31,359 |  |  | 31,359 |
| Disease control and surveillance |  | 271,451 |  |  |  | 271,451 |
| Program management | 21,000 | 30,452 | 50,000 | 123,941 |  | 225,393 |
| Other recurrent costs |  |  |  |  | 3,920 | 3,920 |
| Subtotal Recurrent Costs | 1,106,613 | 769,499 | 1,283,062 | 2,259,631 | 60,076 | 5,478,880 |
| Capital Costs |  |  |  |  |  |  |
| Vehicles | 125,436 |  |  |  |  | 125,436 |
| Cold chain equipment |  |  | 222,307 |  |  | 222,307 |
| Other capital equipment | 152,701 |  |  |  |  | 152,701 |
| Subtotal Capital Costs | 278,137 |  | 222,307 |  |  | 500,444 |
| Vaccination Campaigns |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |
| Vaccines |  |  | 55,241 |  |  | 55,241 |
| Operational cost |  | 236,194 |  |  |  | 236,194 |
| Measles |  |  |  |  |  |  |
| Vaccines and injection supplies |  |  | 242,383 |  |  | 242,383 |
| Operational cost | 35,599 | 418,321 | 338,193 |  |  | 792,113 |
| Subtotal Campaign Costs | 35,599 | 654,515 | 635,817 |  |  | 1,325,931 |
| Shared costs |  |  |  |  |  |  |
| Shared personnel costs | 1,273,497 |  |  |  |  | 1,273,497 |
| Shared transport costs | 1,774,216 |  |  |  |  | 1,774,246 |
| Buildings | 163,696 |  |  | 41,314 |  | 222,649 |
| Subtotal Shared Costs | 3,211,409 |  |  | 41,314 |  | 3,270,393 |
| GRAND TOTAL | 4,631,758 | 1,424,014 | 2,141,186 | 2,300,945 | 60,076 | 10,575,647 |

Table 3.9: Summary of financing and sources of funds for 2009 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | WHO | UNICEF | GAVI | Community Funding | Resource Demand |
| --- | --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |  |
| - Traditional vaccines | 10,274 |  | 136,495 |  |  | 146,769 |
| - New and under-used vaccines | 89,591 |  |  | 1,702,236 |  | 1,791,827 |
| Injection supplies | 7,738 |  | 147,013 |  |  | 154,751 |
| Personnel |  |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 847,434 |  |  |  |  | 847,434 |
| - Per-diems for advanced strategy/mobile teams |  | 92,993 |  |  | 48,246 | 141,239 |
| - Per-diems for supervision | 966 | 216,139 | 168,860 | 96,491 |  | 482,456 |
| Transport |  |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 7,897 | 33,960 | 33,958 |  | 3,159 | 78,974 |
| - Advanced and mobile strategy | 18,014 | 23,895 | 36,029 | 24,019 | 6,005 | 107,963 |
| Maintenance and overheads |  |  |  |  |  |  |
| Cold chain |  |  | 674,046 |  |  | 674,046 |
| Other equipment |  | 12,679 | 114,285 |  |  | 126,964 |
| Buildings | 146,789 |  |  |  |  | 146,789 |
| Short-term training |  | 37,984 |  |  |  | 37,984 |
| Social mobilization and IEC |  |  | 20,991 |  |  | 20,991 |
| Disease control and surveillance |  | 266,885 |  |  |  | 266,885 |
| Program management | 35,000 |  | 69,061 | 79,859 |  | 183,921 |
| Other recurrent costs |  |  |  |  | 3,998 | 3,998 |
| Subtotal Recurrent Costs | 1,163,704 | 684,535 | 1,400,738 | 1,902,605 | 61,408 | 5,212,989 |
| Capital Costs |  |  |  |  |  |  |
| Vehicles | 33,985 |  |  |  |  | 33,985 |
| Cold chain equipment |  |  | 209,674 |  |  | 209,674 |
| Other capital equipment | 105,468 |  |  |  |  | 105,468 |
| Subtotal Capital Costs | 139,453 |  | 209,674 |  |  | 349,128 |
| Vaccination Campaigns |  |  |  |  |  |  |
| Shared costs |  |  |  |  |  |  |
| Shared personnel costs | 1,301,066 |  |  |  |  | 1,301,066 |
| Shared transport costs | 1,809,731 |  |  |  |  | 1,809,731 |
| Buildings | 41,751 |  |  | 26,620 |  | 68,370 |
| Subtotal Shared Costs | 3,152,548 |  |  | 26,620 |  | 3,179,168 |
| GRAND TOTAL | 4,455,705 | 684,535 | 1,610,412 | 1,929,225 | 61,408 | 8,741,286 |

Table 3.10: Summary of financing and sources of funds for 2010 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | UNICEF | GAVI | Community Funding | Resource Demand |
| --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |
| - Traditional vaccines | 12,190 | 140,179 |  |  | 152,369 |
| - New and under-used vaccines | 94,465 |  | 1,794,827 |  | 1,889,292 |
| Injection supplies | 8,326 | 158,202 |  |  | 166,528 |
| Personnel |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 901,087 |  |  |  | 901,087 |
| - Per-diems for advanced strategy/mobile teams |  |  | 52,313 | 53,835 | 153,240 |
| - Per-diems for supervision | 1,078 | 188,424 | 53,835 |  | 538,352 |
| Transport |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 8,144 | 35,019 |  | 3,257 | 81,437 |
| - Advanced and mobile strategy | 18,374 | 36,749 | 24,499 | 6,125 | 121,131 |
| Maintenance and overheads |  |  |  |  |  |
| Cold chain |  | 763,344 |  |  | 763,344 |
| Other equipment |  | 83,837 |  |  | 93,152 |
| Buildings | 149,725 |  |  |  | 149,725 |
| Short-term training |  |  |  |  | 38,743 |
| Social mobilization and IEC |  | 18,352 |  |  | 18,352 |
| Disease control and surveillance |  |  |  |  | 272,223 |
| Program management | 45,000 | 72,599 |  |  | 187,599 |
| Other recurrent costs |  |  |  | 4,078 | 4,078 |
| Subtotal Recurrent Costs | 1,238,389 | 1,496,705 | 1,925,474 | 67,295 | 5,530,652 |
| Capital Costs |  |  |  |  |  |
| Vehicles | 206,971 |  |  |  | 206,971 |
| Cold chain equipment |  | 109,488 |  |  | 118,349 |
| Other capital equipment | 70,042 |  |  |  | 70,042 |
| Subtotal Capital Costs | 277,013 | 109,488 |  |  | 395,361 |
| Vaccination Campaigns |  |  |  |  |  |
| Shared costs |  |  |  |  |  |
| Shared personnel costs | 1,476,792 |  |  |  | 1,476,792 |
| Shared transport costs | 1,845,926 |  |  |  | 1,845,926 |
| Buildings | 66,067 |  |  |  | 66,067 |
| Subtotal Shared Costs | 3,388,785 |  |  |  | 3,388,785 |
| GRAND TOTAL | 4,904,187 | 1,606,193 | 1,925,474 | 67,295 | 9,314,798 |
| Routine Services | 4,904,187 | 1,606,193 | 1,925,474 | 67,295 | 9,314,798 |
| Vaccination campaigns |  |  |  |  |  |

Table 3.11 : Summary of financing and sources of funds for 2011 (Source: 2007-2011 cMYP cost and financing analysis tool)

|  | National Government | WHO | UNICEF | GAVI | Community Funding | Resource Demand |
| --- | --- | --- | --- | --- | --- | --- |
| Recurrent Cost | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines |  |  |  |  |  |  |
| - Traditional vaccines | 15,693 |  | 141,241 |  |  | 156,934 |
| - New and under-used vaccines | 97,487 |  |  | 1,852,256 |  | 1,949,743 |
| Injection supplies | 8,567 |  | 162,770 |  |  | 171,337 |
| Personnel |  |  |  |  |  |  |
| - Salaries of full time health workers (central level, provinces) | 944,068 |  |  |  |  | 944,068 |
| - Per-diems for advanced strategy/mobile teams |  | 107,306 |  | 55,238 |  | 162,544 |
| - Per-diems for supervision | 1,099 | 273,910 | 192,192 | 27,006 |  | 549,119 |
| Transport |  |  |  |  |  |  |
| - Non mobile strategy and vaccine supply | 8,403 | 36,134 | 36,134 |  |  | 84,034 |
| - Advanced and mobile strategy | 18,742 | 37,484 | 37,484 | 24,989 |  | 138,529 |
| Maintenance and overheads |  |  |  |  |  |  |
| Cold chain |  |  | 805,055 |  |  | 805,055 |
| Other equipment |  | 11,494 | 103,451 |  |  | 114,945 |
| Buildings | 152,719 |  |  |  |  | 152,719 |
| Short-term training |  |  |  |  |  | 39,518 |
| Social mobilization and IEC |  |  | 17,679 |  |  | 17,679 |
| Disease control and surveillance |  | 277,667 |  |  |  | 277,667 |
| Program management | 75,000 | 70,000 | 87,949 |  |  | 232,949 |
| Other recurrent costs |  |  |  |  |  | 4,160 |
| Subtotal Recurrent Costs | 1,321,778 | 813,995 | 1,583,955 | 1,959,489 |  | 5,801,000 |
| Capital Costs |  |  |  |  |  |  |
| Vehicles |  |  |  |  |  |  |
| Cold chain equipment |  |  | 51,825 |  |  | 58,907 |
| Other capital equipment | 97,849 |  |  |  |  | 97,849 |
| Subtotal Capital Costs | 97,849 |  | 51,825 |  |  | 156,756 |
| Vaccination Campaigns |  |  |  |  |  |  |
| Shared costs |  |  |  |  |  |  |
| Shared personnel costs | 1,508,075 |  |  |  |  | 1,508,075 |
| Shared transport costs | 1,882,844 |  |  |  |  | 1,882,844 |
| Buildings | 46,798 |  |  |  |  | 46,798 |
| Subtotal Shared Costs | 3,437,717 |  |  |  |  | 3,437,717 |
| GRAND TOTAL | 4,857,344 | 813,995 | 1,635,780 | 1,959,489 |  | 9,395,473 |

## New and Under-Used Vaccines (NVS)

Please give a summary of those aspects of the comprehensive multi-year immunization plan that refer to the introduction of new and under-used vaccines (refer to the cMYP or Multi-Year Plan).  Please outline the key points that informed the decision-making process (data considered etc):

In CAR, as in other African countries, infections by viral hepatitis B and Haemophilus Influenzae type b are a major public health concern.

Implementation of the activities contained in the plan will be instrumental in reducing mortality and morbidity caused by these micro-organisms.

The plan will benefit from the extensive cold chain coverage in the country, as presented in the cold chain survey conducted during the end of August and September 2006.

The final choice of the Ministry of Health is the pentavalent DTP-HepB+Hib vaccine and it will be introduced in the whole of the country from January 2008.

The recently strengthened cold chain volume capacity is sufficient in its current state to accommodate the new vaccines introduced; however, given the ageing of some conservation equipment, efforts will be made to replace this gradually, as provided by the refurbishment plan ordered by the country.

New vaccine introduction will provide an opportunity for the EPI in CAR to sustain the impact achieved by the routine EPI.

Please describe (or refer to the relevant section of the cMYP or Multi-Year Plan) how your country intends to move towards financial sustainability for the chosen new vaccines, how the co-financing payments will be met, and any other issues regarding financial sustainability that were considered:

Please refer to the Chapter on “program viability and implementation strategies of the 2007-2011 cMYP”.

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation):

The Central African Republic  has chosen to introduce hepatitis B and Hib vaccination in the EPI using the pentavalent DTP-HepB+Hib vaccine in liquid form, which is a fixed dose combination in 10-dose vials. If this is not currently available on a large scale, we will start with the 2-dose lyophilised presentation.

Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Viral hepatitis | Hepatitis B prevalence at Bangui Paediatric Complex | November to December 2005 | - The study of 525 patients revealed an endemicity for hepatitis B of 22.3% in a hospital environment. - A high number of acute viral hepatitis B cases were found in children aged under five (19.5%), where HB antigens were found to be present. - For 25% of the patient population, the disease was acquired before one year of age, and for 75%, it occurred before the age of 3.7 years. |
| Haemophilus influenzae Meningitis | Study of acute bacterial forms of meningitis and sensitivity to antibiotics at Bangui Paediatric Complex | October 2004 to April 2005 | The study of 229 children showed that: - In Bangui, S. pneumoniae and H. influenzae were the most frequent causes of ABM in children (41% and 27% respectively). - The high overall ABM mortality (45.8%) was linked to delays in adequate patient management rather than to germ antibiotic resistance. - The ABM agent, S. pneumoniae, was still very sensitive to penicillin G. - 70% of ABM inducing H.influenzae harboured a ß-lactamase and 29% had reduced chloramphenicol sensitivity. |

If new or under-used vaccines have been already introduced, please give details of the lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc., and the action points to address them in the new plan:

| Lessons Learned | Action Points |
| --- | --- |
| 1. Vaccination schedule harmonization: The administration age of YF which was 12 months has been brought down to 9 months to coincide with the MEAS administration period. Because of this: - the drop-out rate between MEAS (9 months) and YF (12 months) has been reduced. - YF vaccination coverage has improved. | - Choice of pentavalent vaccine to reduce the number of injections given to children and the number of contacts. |

First Preference Vaccine

  - Please complete Table A.1 in Annex 1 (an excel spreadsheet), for the first vaccine required.

To fill out Table A.1, please update the figures in Table β and Table µ in Annex 1 with the most recent UNICEF Supply Division Prices and Charges on the UNICEF website.

Please refer to www.unicef.org/supply for the most recent GAVI Alliance Vaccine Product Selection Menu, and review the GAVI Alliance NVS Support Country Guidelines to identify the appropriate country category, and the minimum country co-financing level for each vaccine in each group.

Please indicate in the table below the required number of vaccine doses, the vaccine presentation, the associated injection safety material required and safety boxes for the first vaccine required as per the calculation made in Annex 1.

Table 4.1a:  Material requirements for the introduction of DTP-HepB+Hib immunization using the lyophilized two-dose vial vaccine

|  |  | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| National target for children to be immunized | # | 82% | 85% | 90% | 90% |
| Total number of vaccine doses required | # | 502,730 | 501,963 | 510,148 | 520,550 |
| Total number of AD syringes required | # | 468,745 | 489,184 | 521,371 | 532,002 |
| Total number of reconstitution syringes required | # | 279,015 | 278,590 | 283,132 | 288,905 |
| Total number of safety boxes required | # | 8,300 | 8,522 | 8,930 | 9,112 |

Please indicate in the table below the price per dose, the total funds required to meet the estimated demand, the country co-financing contribution, and the funds required from the GAVI Alliance according to the calculations made in the Annex 1 spreadsheet.

Table 4.2a:  Financial requirement for the introduction of DTP-HepB+Hib immunization using the two-dose lyophilized vial vaccine

|  |  | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| Total budget | Price per dose * | $ | 3.2 | 2.9 | 2.65 | 2.3 |
|  | Total funds required | $ | 1,677,662 | 1,526,917 | 1,425,116 | 1,270,161 |
| Country co-financing | Co-financing per dose | $ | 0.15 | 0.15 | 0.15 | 0.15 |
|  | Total country payment | $ | 75,409 | 75,294 | 76,522 | 78,082 |
| 3.05GAVI co-financing | GAVI payment per dose | $ | 3.05 | 2.75 | 2.5 | 2.15 |
|  | Total GAVI payment | $ | 1,602,253 | 1,451,622 | 1,348,594 | 1,192,078 |

* Total price pre dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc

  - Please complete an extra set of Tables A.3, A.4 for all new vaccines requested.

  - Please complete an extra set of Tables 4.1 and 4.2 for all new vaccines requested.

Procurement and Management of New and Under-Used Vaccines

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):

1. Vaccine and injection supplies will be procured through UNICEF.

2. The transfer of $100,000 for introduction promotion will be managed in accordance with the guidelines on GAVI funds use which are operative in the Central African Republic.

b) If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document:

- That the functions of the National Regulatory Authority comply with WHO requirements for procurement of vaccines and supply of assured quality.

- That the delivery in country of the procured supply is in compliance with the co-financing plan.

- That acceptable procurement principles and processes are applied.

c) Please describe the introduction of the vaccines (refer to cMYP or updated Multi-Year Plan)

(Please refer to the new vaccine introduction plan on Annex Page 24).

d) Please indicate how funds should be transferred to the country by the GAVI Alliance (if applicable)

The $100,000 amount will be transferred through UNICEF and held at the Banque Internationale pour le Centrafrique (BICA) in Account No. 360 630 164 01 – B, opened for immunization systems strengthening.

e) Please indicate how the co-financing amounts will be paid (and who is responsible for this)

- The co-payments from the Extended Program for Immunization Directorate (budget headings investment and operations) will be paid to UNICEF for the purchase and delivery of supplies.

- The Extended Program for Immunization Director will be responsible for the payment of the co-payment funds (budget heading administrator).

e) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP or updated Multi-Year Plan)

(Please refer to the cMYP: Chapter on cMYP monitoring and assessment, Page 78)

If you are approved for new vaccines support, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of each new vaccine. If you wish to receive these funds, please submit the attached “Banking Form” (in Annex 2) along with this proposal, if you have not yet already done so for other types of support from the GAVI Alliance.

## Additional Comments and Recommendations from the Inter-Agency Coordinating Committee for Immunization (ICC) and other Health Sector Development Partners

## The ICC:

- Supports the Government’s request to GAVI for the introduction of the pentavalent vaccine;

- Endorses the Ministry of Health’s final choice of pentavalent vaccine DTP-HepB+Hib, which will be introduced on the whole of the territory from 2008;

- Is satisfied that the Government of CAR has included a budget heading for EPI expenses in its budget during the last few years, covering items such as “vaccine and fuel oil purchases” and is pleased to see the efforts made by the Government in favour of the survival of children;

- Encourages the Government to honour its commitment to implement the proposed mechanism for contributing the co-payments for new vaccines.

- Commits to engaging in:

- the monitoring of activity implementation in accordance with the comprehensive Multi Year Plan;

- the monitoring of GAVI fund management and the preparation of management reports;

- partner and community mobilization for the promotion of pentavalent introduction;

- advocacy towards the Government and National Assembly for vaccination independence.

## Documents Required

| Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- |
| Comprehensive Multi-Year Plan (cMYP) or updated Multi-Year Plan | X |  |
| WHO / UNICEF Joint Reporting Form (last two) | X |  |
| Plan for introduction of New Vaccine (if not already included in the cMYP or updated Multi-Year Plan) | X |  |
| Endorsed minutes of the ICC meeting discussing the requested GAVI Alliance New and Under-Used Vaccine (NVS) support | X |  |
| Endorsed minutes of the National Coordinating Body meeting where the GAVI Alliance NVS proposal was endorsed | N/Av |  |
| Minutes of the three most recent ICC meetings | X |  |
| ICC workplan for the forthcoming 12 months | X |  |

* Please indicate the duration of the plan / assessment / document where appropriate

REPLY TO CONDITIONS:

CENTRAL AFRICAN REPUBLIC RESPONSES TO GAVI SUBMISSION CONDITIONS FOR THE INTRODUCTION OF LYOPHILIZED PENTAVALENT VACCINE (DTP-HepB+Hib) IN A DOUBLE DOSE VIAL

Bangui, September 2007

- Analytical Summary

On April 20, 2007, the Central African Republic (CAR) submitted to the Global Alliance for Vaccines and Immunization (GAVI) a proposal relative to obtaining New Vaccine Support (NVS) for the introduction of Hepatitis B and Haemophilus influenzae b with DTP-HepB+Hib vaccines. The Independent Review Board (IRB) examined the proposal and recommended that the Board of Directors of the Alliance grant it “Conditional Approval.”

In order to be eligible for final approval, the CAR must meet the following condition:

• Provide data relative to the cold chain volume capacity, showing the storage space currently available compared to what is required, and how to make up the deficit.

With GAVI’s approval for new vaccine support, the country will also receive a starting subsidy of $100,000. In order to obtain this vaccine introduction subsidy, the Central African Republic must prepare a budget table that breaks down global non-vaccine requirements for the introduction, and indicate how the allocated funds will be used to make up the deficits. This budgeted introduction plan must comply with the national vaccine introduction plan.

In order to provide a cold chain commodity response for the introduction of the pentavalent vaccine, the country took advantage of an external cold chain evaluation mission from August 11 to 26, 2007. The mission concluded that within the context of routine vaccination activities, the availability of the cold chain at the central and peripheral levels for both positive and negative storage is mostly sufficient. This storage volume has a surplus that shows that neither the introduction of the pentavalent vaccine in the routine Expanded Immunization Program in 2008 nor the supplemental measles and poliomyelitis immunization activities will require the current storage capacity to be increased.

In addition, taking into consideration the gradual aging of the cold chain, the country prepared a renovation plan for the period from 2008 to 2012. Funding requirements for the 2007-2011 period for cold chain equipment are entirely covered in accordance with the cMYP covering the same period.

In view of the foregoing, the CAR is sufficiently ready to introduce the pentavalent vaccine in the routine EIP beginning in January 2008.

CONDITION: Provide data relative to the cold chain volume capacity, showing the storage space currently available compared to what is required, and how to make up the deficit.

Availability of the cold chain

  - Availability of the cold chain at the Bangui central warehouse level

The National Office of the Expanded Immunization Program “OEIP” in the CAR has two cold chain elements: two positive coolers with a gross capacity of 30,000 liters each; and two negative coolers with a gross capacity of 20,000 liters each.

These coolers are recent; they were installed in July 2005 and comply with the WHO and UNICEF standards. Besides these preservation units, the EIP has two fully functional refrigerated trucks with a net capacity of 3,000 liters each to provide transportation to peripheral facilities (Health Prefectures) and can provide brief preservation of antigens.

Table 1 below summarizes the existing cold chain storage volume at the central level

Table 1: Existing cold chain storage volume at the central level

| Number of units | Total volume T°positive (liters) | Volume factor |
| --- | --- | --- |
| 2 Coolers + | Gross | Net |  |
|  | 60,000 | 15,000 | 4 |
|  | Total volume T° negative (liters) |  |
| 2 Coolers - | Gross | Net |  |
|  | 40,000 | 10,000 | 4 |

Table 2 below provides the required and available volumes as well as an estimate of any deficit with the introduction of the pentavalent vaccine in 2008 in the 2-dose size.

This table shows that the additional cold chain capacity is negative, resulting in a surplus storage capacity. Thus, the positive volume is much greater than demand based upon two supply deliveries per year at the central warehouse in Bangui up to 2012, at which time the coolers will be 7 years old, and it is anticipated that they will be replaced in 2013 or 2015 because of obsolescence and not lack of capacity.

Even with the Supplemental Immunization Activities (SIA), the current storage volume is sufficient enough for one supply per year.

Table 2: Available required volumes and an estimate of the deficit with the introduction of the pentavalent vaccine in 2008 in the routine EIP and positive capacity of the central level from 2008 to 2012

  - Summary of positive capacities of prefecture storage facilities from 2008 to 2012-Volume in liters

The current EIP organization in the CAR has selected direct delivery of vaccines by the central level of the Health Prefectures for all regions except the city of Bangui (the health districts are being organized into Health Prefectures) where the immunization units are supplied by the central level.

In 2007, standard minimum equipment for the peripheral level was instituted in order to meet quarterly needs.

This standard minimum consists of 2 Sibir refrigerators (Dométic V 170 KE 55 liters each net storage capacity and a Zero 230 freezer with 144 liters of capacity). The existing storage volume (available capacity) of the cold chain at the level of each Health Prefecture is calculated in Appendix 1.

Table 3 shows the annual required volume per Health Prefecture after the introduction of the pentavalent vaccine in the CAR

Table 3: the annual required volume per Health Prefecture after the introduction of the pentavalent vaccine in the CAR from 2008 to 2012

On the other hand, table 4 on the next page shows the required quarterly volumes, the available volumes at all prefecture storage facilities, and an estimate of any deficit with the introduction of the pentavalent vaccine from 2008 to 2012, in the 2 dose lyophilized form.

This table shows that the positive volume at the level of all Health Prefectures in the country is largely sufficient up to 2012. The details of the calculations made with the vaccine projection tool and the storage capacities per Health Prefecture appear in Appendix (Appendices 2 to 17).

Table 4: Summary of positives capacities of prefecture storage facilities from 2008 to 2012 in the CAR-Volume in liters

| HEALTH PREFECTURE BASES | Available capacity (liters) | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | required quarterly volume | deficit (liters) | required quarterly volume | deficit (liters) | required quarterly volume | deficit (liters) | required quarterly volume | deficit (liters) | required quarterly volume | deficit (liters) |

USD 100,000 subsidy for the introduction of new vaccines

Table 5 : Cost (and financing) for the introduction of the first preferred vaccine (US$)

| Cost category | Activities | Total required for introduction of the new vaccine | Financed with funds for introduction of the new vaccine |
| --- | --- | --- | --- |
| Training | 1. Train/retrain managers of central and regional storage facilities and members of the ECD in computerized vaccine management | 18,000 | 5,000 |
|  | 2. Train immunization center agents in vaccine management and other supplies | 90,000 | 10,000 |
|  | 3. Train/retrain agents in proper use and maintenance of cold chain equipment | 16,000 | 5,000 |
| Social mobilization, IEC and presentation of arguments | 1. Train/retrain in-house trainers in communication techniques | 20,000 |  |
|  | 2. Prepare and broadcast radio and TV microprograms supporting EIP (routine EIP, new vaccines) | 18,000 | 6,000 |
|  | 3. Organize radio and TV debates on EIP (routine EIP, new vaccines, SIA, AEFI, etc.) | 16,000 | 6,000 |
|  | 4. Publish information on EIP (routine EIP, new vaccines, SIA, AEFI, etc.) in the press | 16,000 | 6,000 |
|  | 5. Produce and edit a period bulletin on EIP activities (routine EIP, new vaccines, SIA, AEFI, etc.) | 16,000 | 6,000 |
|  | 6. Use theater troupes to disseminate information on EIP (routine EIP, new vaccines, SIA, AEFI, etc.) | 2,000 | 1,000 |
| Reinforcement of integrated epidemiological monitoring of diseases | 1. Strengthen the epidemiological monitoring system (biweekly, based on cases and monitoring agent) at all levels; | 60,000 | 13,000 |
|  | 2. Improve information gathering and analysis and feedback | 2,000 | 1,000 |
|  | 3. Conduct studies on AEFI | 3,000 | 1,000 |
| Strengthening of EIP logistical system | 1. Adapt and adopt EIP rules and procedures according to the Effective Storage facility Management Model Plan Manual | 2,000 | 1,000 |
|  | 2. Supply all levels with vaccine and immunization consumable supplies | 75,000 | 12,000 |
|  | 3. Computerize vaccine management by level | 80,000 | 15,000 |
|  | 4. Update the detailed plan to reduce vaccine waste | 4,000 | 2,000 |
| Improve program evaluation and follow-up | 1. Review data collection and the immunization schedule | 3,000 | 2,000 |
|  | 2. Disseminate and distribute media | 48,000 | 2,000 |
|  | 4. Organize semiannual evaluation meetings | 80,000 | 2,000 |
|  | 6. Provide monthly monitoring of EIP at all levels | 10,000 | 2,000 |
|  | 7. Perform internal quality audits of program information | 40,000 | 2,000 |
| TOTAL |  | 619,000 | 100,000 |

The various deficits in activities selected with the USD 100,000 joint financing in this table will be broken down according to the Complete 2007-2011 Multi-Year Plan. Thus, the USD 519,000 in joint financing of the USD 100,000 has already been secured.

Conclusion: The summary of the positive capacities of the central and peripheral levels shows that there will be no problem in preservation of vaccines up to 2012.

Although it is sufficient, in view of the gradual aging of the cold chain, a renovation plan was prepared covering the period from 2008 to 2012. This plan appears in an Appendix to this document (Appendix 18).

Funding for this renovation plan is secured up to 2011 by UNICEF in accordance with the  cMYP cost and financing tool.

The summary of the positive capacities of the central and peripheral levels shows that there will be no problem in preservation of vaccines up to 2012.

APPENDICES

Appendix 1 : Existing cold chain storage volume at the peripheral level

| Prefecture Health Base | Refrigerators (No. of units) | Total volume positive T. | Volume factor |
| --- | --- | --- | --- |
|  |  | Gross | Net |  |

Appendix 2 Analysis of positive capacities of Lobaye

Appendix 3 Analysis of positive capacities of Ombella Mpoko

Appendix 4 Analysis of positive capacities of Mambéré Kadéi

Appendix 5 Analysis of positive capacities of Nana Mambéré

Appendix 6 Analysis of positive capacities of Sangha Mbaéré

Appendix 7 Analysis of positive capacities of Ouham

Appendix 8 Analysis of positive capacities of Ouham Pendé

Appendix 9 Analysis of positive capacities of Nana Grebizi

Appendix 10 Analysis of positive capacities of Kémo

Appendix 11 Analysis of positive capacities of Ouaka

Appendix 12 Analysis of positive capacities of Haute Kotto

Appendix 13 Analysis of positive capacities of Vakaga

Appendix 14 Analysis of positive capacities of Bamingui Bangoran

Appendix 15 Analysis of positive capacities of Basse Kotto

Appendix 16 Analysis of positive capacities of Mbomou

Appendix 17 Analysis of positive capacities of Haut Mbomou

Appendix 18 : Plan de réhabilitation du matériel de la Cold chain de la CAR de 2008 à 2012

# Footnotes

Please complete all tables for the years that match the cMYP or updated Multi-Year Plan. This could be more or less than 5 years.

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

# Text boxes

MINISTRY OF PUBLIC HEALTH AND POPULATION

*********

OFFICE OF THE DIRECTOR

*********

GENERAL DEPARTMENT OF PUBLIC HEALTH *********

OFFICE OF THE EXPANDED PROGRAM ON IMMUNIZATION

*********

CENTRAL AFRICAN REPUBLIC

UNITY – DIGNITY – WORK

***********

C.A.R.

EPI

TOTAL RENOV.

STORAGE FACILITYS IN

MAINTENANCE

PREFECTURES

No.

CT MAINT

No.

CT MAINT

ANNUAL

No.

CT $

No.

CT $

No.

CT $

No.

CT $

No.

CT $

No.

CT $

COST IN $

OMBELLA MPOKO

1

106,29

23

1 523,36

1 629,65

3

13 500,00

0

0,00

0

0,00

1

4 500,00

11

46 200,00

15

64 200,00

65 829,65

LOBAYE

2

115,60

20

1 156,00

1 271,60

1

4 500,00

0

0,00

5

22 500,00

1

4 500,00

1

4 500,00

8

36 000,00

37 271,60

DRS I

1

106,29

1

106,29

212,58

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

212,58

TOTAL RSI

4

328,18

44

2 785,65

3 113,83

4

18 000,00

0

0,00

5

22 500,00

2

9 000,00

11

50 700,00

22

100 200,00

103 313,83

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

MAMBERE KADEI

1

57,80

23

1 329,40

1 387,20

2

9 000,00

0

0,00

3

13 500,00

1

4 500,00

4

18 000,00

10

45 000,00

46 387,20

NANA MAMBERE

2

164,09

21

1 262,29

1 426,38

3

13 500,00

3

13 500,00

3

13 500,00

1

4 500,00

4

18 000,00

14

63 000,00

64 426,38

SANGHA MBAERE

2

115,60

14

906,18

1 021,78

-

0,00

2

9 000,00

0

0,00

7

31 500,00

0

0,00

9

40 500,00

41 521,78

DRS II

0

0,00

2

115,60

115,60

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

115,60

TOTAL RSII

5

337,49

60

3 613,47

3 950,96

5

22 500,00

5

22 500,00

6

27 000,00

9

40 500,00

8

36 000,00

33

148 500,00

152 450,96

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

OUHAM

0

0,00

33

1 907,40

1 907,40

6

27 000,00

2

9 000,00

1

4 500,00

2

9 000,00

1

4 500,00

12

54 000,00

55 907,40

OUHAM PENDE

1

57,80

42

2 476,09

2 533,89

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

2 533,89

D

.

R S N°

3

.

1

57,80

1

57,80

115,60

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

115,60

TOTAL RSIII

2

115,60

76

4 441,29

4 556,89

6

27 000,00

2

9 000,00

1

4 500,00

2

9 000,00

1

4 500,00

12

54 000,00

58 556,89

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

OUAKA

0

0,00

37

2 138,60

2 138,60

12

54 000,00

2

9 000,00

2

9 000,00

0

0,00

3

13 500,00

19

85 500,00

87 638,60

KEMO

2

115,60

9

520,20

635,80

-

0,00

1

4 500,00

1

4 500,00

1

4 500,00

0

0,00

3

13 500,00

14 135,80

NANA GRIBIZI

1

57,80

5

289,00

346,80

-

0,00

2

9 000,00

0

0,00

0

0,00

0

0,00

2

9 000,00

9 346,80

TOTAL RSIV

3

231,20

51

3 063,40

3 294,60

12

54 000,00

5

22 500,00

3

13 500,00

1

4 500,00

3

13 500,00

24

108 000,00

111 294,60

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

HAUT KOTTO

2

115,60

14

906,18

1 021,78

1

4 500,00

0

0,00

0

0,00

4

18 000,00

0

0,00

5

22 500,00

23 521,78

BAMINGUI BANGORAN

1

57,80

6

346,80

404,60

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

404,60

VAKAGA

0

0,00

12

887,56

887,56

4

18 000,00

0

0,00

4

18 000,00

3

13 500,00

0

0,00

11

49 500,00

50 387,56

DRS

0

0,00

1

57,80

57,80

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

57,80

TOTAL RSV

3

173,40

33

2 198,34

2 371,74

5

22 500,00

0

0,00

4

18 000,00

7

31 500,00

0

0,00

16

72 000,00

74 371,74

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

MBOMOU

0

0,00

26

1 604,91

1 604,91

6

27 000,00

4

18 000,00

1

4 500,00

0

0,00

1

4 500,00

12

54 000,00

55 604,91

BASSE KOTTO

0

0,00

20

1 156,00

1 156,00

-

0,00

4

18 000,00

1

4 500,00

1

4 500,00

1

4 500,00

7

31 500,00

32 656,00

HAUT MBOMOU

0

0,00

11

942,13

942,13

3

13 500,00

2

9 000,00

0

0,00

0

0,00

0

0,00

5

22 500,00

23 442,13

DRS VI

2

115,60

2

115,60

231,20

-

0,00

0

0,00

2

5 700,00

0

0,00

0

0,00

2

5 700,00

5 931,20

TOTAL RSVI

2

115,60

59

3 818,64

3 934,24

9

40 500,00

10

45 000,00

3

14 700,00

1

4 500,00

2

9 000,00

25

113 700,00

117 634,24

0,00

0,00

0,00

-

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0

0,00

0,00

CITY OF  BANGUI

0

0,00

27

4 317,57

4 317,57

-

0,00

1

4 500,00

6

27 000,00

0

0,00

1

4 500,00

8

36 000,00

40 317,57

DRS VII

1

106,29

1

159,91

266,20

-

0,00

0

0,00

0

0,00

0

0,00

1

4 500,00

1

4 500,00

4 766,20

TOTAL RSVII

1

106,29

28

4 477,48

4 583,77

0

0,00

1

4 500,00

6

27 000,00

0

0,00

2

9 000,00

9

40 500,00

45 083,77

CENTRAL STORAGE FACILITY

0

0,00

Cost service

35

%

492,72

8 539,39

9 032,11

0,00

0,00

0,00

0,00

0,00

0

0,00

9 032,11

Cost spare parts

1 407,76

24 398,27

25 806,03

0,00

0,00

0,00

0,00

0,00

0

0,00

25 806,03

CAR

20

1 900,48

351

32 937,66

34 838,14

41

184 500,00

23

103 500,00

28

127 200,00

22

99 000,00

27

122 700,00

141

636 900,00

671 738,14

COST

T°

(1)

2008

2009

2010

2011

2012

Total

PREVENTIVE AND CORRECTIVE MAINTENANCE

Freezers

Refrigerators

REPLACEMENT OF EQUIPMENT

PLAN FOR RENOVATION OF FIXED COLD CHAIN EQUIPMENT IN THE CAR

PREVISION ANNUELLE PIECES DETACHEES ET MAINTENANCE CF RCA