|  |  |  |  |  | [V2.7] |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance |  |  |  |  |  |  |  |
| Application Form for Country Proposals |  |  |  |  |  |  |  |
| For Support to: |  |  |  |  |  |  |  |
| Preventive Campaign Support |  |  |  |  |  |  |  |
| Submitted by |  |  |  |  |  |  |  |
| The Government of |  |  |  |  |  |  |  |
| Viet Nam |  |  |  |  |  |  |  |
| Date of submission: 9/10/2012 |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012 |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) |  |  |  |  |  |  |  |
| Start Year | 2011 |  |  |  |  |  |  |
|  |  |  | End Year | 2015 |  |  |  |
| Form revised in 2012 |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012) |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland . The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. Application Specification Please specify for which type of GAVI support you would like to apply to.

Type of Support Vaccine Start Year End Year Preferred second presentation[1] Preventive Campaign Support MR, 10 dose(s) per vial, LYOPHILISED 2013 2014

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF

2. Table of Contents

1. Application Specification 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Bodies 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation 4.1.3. The Inter-Agency Coordinating Committee for Immunisation 4.2. National Immunization Technical Advisory Group for Immunisation 4.2.1. The NITAG Group for Immunisation 5. Immunisation Programme Data 5.1. Basic facts 5.1.1 MCV Immunisation coverage 5.2. Baseline and Annual Targets (NVS Routine Support) 5.3. Baseline and Annual Targets for Preventive Campaign(s) 5.3.1 Baseline and annual targets (MR campaign) 6. New and Under-Used Vaccines (NVS Routine) 7. NVS Preventive Campains 7.1. Assessment of burden of relevant diseases related to campaigns (if available) 7.2 Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support 7.2.1 Summary for MR campaign support 7.2.2 Grant Support for Operational Costs of the MR Campaign 7.2.3 Evidence of introduction of RCV in routine programme 7.2.4 Introduction planning for RCV 7.2.5 Measles surveillance indicators 7.2.6 Rubella Containing Vaccine introduction Grant 8. Procurement and Management 8.1. Procurement and Management of New and Under-Used Vaccines Routine 8.2. Procurement and Management for NVS Preventive Campaign(s) 8.2.1 Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign 8.3. Vaccine Management (EVSM/EVM/VMA) 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC) 10. Attachments 11. Annexes Annex 1 - NVS Routine Support Annex 2 - NVS Routine – Preferred Second Presentation Annex 3 - NVS Preventive campaign(s) Table Annex 3.1 C Summary table for vaccine MR, 10 dose(s) per vial, LYOPHILISED Table Annex 3.1 D Estimated numbers for MR, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking Form

3. Executive Summary

Please provide a summary of your country's proposal, including the following the information: l For each specific request, NVS routine support or NVS campaign : ¡ The duration of support ¡ The total amount of funds ¡ Details of the vaccine(s), if applicable l Relevant baseline data, including: ¡ DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form) ¡ Birth cohort, targets and immunisation coverage by vaccines l Country preparedness ¡ Summary of EVM assessment l The nature of stakeholders' participation in developing this proposal ¡ Inter-Agency Coordinating Committee The Government of Socialist Republic of Viet Nam seeks financial assistance with the introduction of MR vaccine from the GAVI alliance for conduct of rubella catch-up campaign by MR vaccine for target population of males and females aged 9 months to 14 years in 2013 and 2014. Support is requested from GAVI for 36,327,097 doses of vaccine; 31,925,468 AD syringes 0.5ML; 4,032,309 reconstitution disposable syringes 5ML and 399,132 safety boxes; US$ 14,901,575 for operation cost of MR campaign (US$ 0.65/target population) and US$ 1,357,208 for MR vaccine introduction grant with a total value of US$ 35,706,139. <?xml:namespace prefix = o /> Rubella occurred in cyclic patterns, with outbreaks at predictable intervals. In overall, from 2004 through 2011, the means number of reported cases was 3,648. The incidence of rubella ranged from 1.03/100,000 population in 2008 to 13.29/100,000 population in 2005. The sex ratio is 1:1. However, most of case occurred in children under 15 years old counting for 41.6% from 2005 to 2011. Age group under 15 years count for 82.9% during non-epidemic years. The figure suggested that rubella virus circulate continuously in children. This group play important role to maintain continuous chains of transmission. CRS sentinel surveillance was established in two central hospitals in 2011. The preliminary result of following 2010-2011 rubella outbreaks reveals 161 confirmed CRS cases among 189 suspected cases. 3 deaths and 82% of total case is multiple births defect including: deafness, blindness, heart defects, etc. This is health and social burden. A detailed catch-up campaign plan has been prepared including training, IEC and surveillance components, as enclosed with this application as document No 6. The vaccine procure only the WHO prequalified vaccine once it is also licensed in Viet Nam. The GAVI financed portion will be procured and supplied through UNICEF. The cold chain capacity analysis at different levels has shown sufficient capacity to accommodate the camping in three phases: 1) Oct. to Dec. 2013 for 5,373,072 target population 11-14 years old (6 - 9 grade); 2) Mar. to May 2014 for 6,995,664 target population 7 – 11 years (1 - 5 grade); and 3) Oct. to Dec. 2014 for 10,556,763 target population 9 months to 6 years. The Government commits itself to introduce of MR vaccine in the routine program for children 9 months instead of MCV1. Viet Nam has reached the target by which more than 90% of children under 1 year old were fully immunized from 1993. From 2003, rates of immunization have been being monitored even in suburban areas, the fact of more than 93% of them meet the rate of more than 90% people vaccinated is evident of success and considerable exertion of provincial health officers. Number of children vaccinated with DPT3 were more than 90% and drop out rate is only under 2%. The second dose of measles vaccine was introduced in 2007 nationwide and is provided at school age (grade 1) with support from GAVI. From 1st April 2011 the schedule of measles 2nd dose to 18 months of age will be instead of the current schedule at 6 years of age. In 2012 is the cost for implement MCV2 is coved by the fund from Government. The rate of MCV2 more than 90% since 2007. With support from PAHT, the EVM assessment was conducted in April 2012. Store keepers and health workers at provincial district stores and commune health facilities appear to have insufficient knowledge of vaccine storage temperatures. EVM advocates that temperature records are reviewed on a monthly basis so that systematic trends can be detected and appropriate action taken and recorded. There appears to be adequate storage capacity at all the stores visited for the existing schedule. The calculation on peak storage volumes is based on the principle that vaccine deliveries take place at the fixed intervals stated in national EPI policy: three monthly arrivals at regional stores; two monthly arrivals at provincial stores and with one monthly arrival at the district and commune levels. Dry storage capacity, to the extent that it was measured also seems generally to be adequate. The proposal for catch-up MR campaign has been reviewed and endorsed by the Inter-agency coordinating committee (ICC) on 27th August 2012. Signatures of members of the Interagency Coordinating Committee along with minutes of the meeting are also enclosed. Immunization Program data and summary information from the forecasted immunization budget from 2011-2015 is also enclosed.

| 4. Signatures |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation |  |  |
| The Government of Viet Nam would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for |  |  |
|  | MR, 10 dose(s) per vial, LYOPHILISED preventive campaigns |  |
| The Government of Viet Nam commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. |  |  |
| Table(s) in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only). |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January. |  |  |
| The payment for the first year of co-financed support will be around March 2013 for MR, 10 dose(s) per vial, LYOPHILISED. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. |  |  |
| Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name NGUYEN Thi Kim Tien Name VUONG Dinh Hue Date Date Signature Signature |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document): |  |  |
| Full name Position Telephone Email Nguyen Van CUONG Deputy Manager, National EPI +84 439725745 cuongepi@yahoo.com/and or vancuong@fpt.vn |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 27/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question. |  |  |
| The endorsed minutes of this meeting are attached as document number 4. |  |  |
| Name/Title* Agency/Organisation* Signature Akira Shimizu, Senior Representative JICA Craig Burgess, Chief, Child Survival and Development Section UNICEF Ramona Byrkit, PATH Country Representative PATH Toda Kohei, EPI Medical Officer WHO |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. |  |  |
| Profile of the ICC, HSCC, or equivalent committee |  |  |
| Name of the committee ICC Year of constitution of the current committee 2000 Organisational structure (e.g., sub-committee, stand-alone) Standa - alone Frequency of meetings 3 - 6 months |  |  |
| Composition |  |  |
| Function Title / Organisation Name Chair Chief, Child Survival and Development Section, UNICEF Dr. Craig Burgess Secretary Officer, Child Survival and Development Secton, UNICEF Nguyen Huy Du Members Chief, Child Survival and Development Section, UNICEF Dr. Craig Burgess EPI Merdical Officer, WHO in Viet Nam Dr. Toda Kohei Country Representative, PATH Ms. Ramona Byrkit Senior Representative JICA Mr. Akira Shimizu Director, National Institute of Hygiene and Epidemiology, Hanoi, Viet Nam Prof. Nguyen Tran Hien |  |  |
| Major functions and responsibilities of the ICC/HSCC: |  |  |
| - Review and endorse EPI annual and five-year plans, country proposals and reports and other relevant documents prepared by the National EPI - Review progress in achieving milestones/objectives - Co-ordinate actions needed to overcome constraints and achieve milestones/objectives - Mobilize funding and assist in planning and monitoring in areas of priority as determined by the National Steering Committee for EPI |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months |  |  |
| 1. To hold ICC meeting more regularly at least four times per year 2. To form a ICC working group on donor communication for EPI funding following the ICC decision taken during its 20th meeting on 13 December 2011 3. To form a ICC working group on donor communication for EPI funding following the ICC decision taken during its 20th meeting on 13 December 2011 |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation |  |  |
| (If it has been established in the country) |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. |  |  |
| The endorsed minutes of this meeting are attached as document number 4. |  |  |

4.2.1. The NITAG Group for Immunisation

Profile of the NITAG

Name of the NITAG Year of constitution of the current NITAG Organisational structure (e.g., sub-committee, stand-alone) Frequency of meetings

Composition

Function Title / Organisation Name Chair Secretary Members

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG's role and functions in the next 12 months

1. 2. 3.

5. Immunisation Programme Data

5.1. Basic facts

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6 ▪ Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7 ▪ Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

For the year 2011 (most recent; specify dates of data provided)

Figure Year Source Total population 87,840,000 2011 Statistic book 2011, GSO Infant mortality rate (per 1000) 16 2011 MIC4, GSO, December 2011 Surviving infants[1] 1,607,351 2011 JRF, 2011 GNI per capita (US$) 1,260 2011 Worl Bank, March 2011 Total Health Expenditure (THE) as a percentage of GDP 7 % 2009 MoH report to WHO: National health account in Viet Nam, 2009 General government expenditure on health (GGHE) as % of General government expenditure 9 % 2009 MoH report to WHO: National health account in Viet Nam, 2009

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country Among various preventive health programs, 10 priority programs are ranked in the 2011-2015 health 5-year plan as national target health programs, including the expanded program on immunization (EPI), malaria control, TB control, dengue fever control, HIV/AIDS control, nutrition program, mental health and food safety and hygiene, reproductive health, school health and military civilian health collaboration. These programs are established to achieve the objectives of the Government Policy and Strategy for Protection and Care of the People's health in the period of 2011-2015. The specific objectives are to reduce morbidity and mortality due to epidemic diseases, prevent, control and manage non-infectious diseases, enhance equity in access to and use of health care services and to improve quality of care Please indicate the name and date of the relevant planning document for health Five year plan for protection, care and promotion of people’s health for 2011-2015, December 2010 Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.) Yes, cMYP (2011-2015) is aligned with thi s document in timing (both national health plan and cMYP are for years 2011-2015) Please indicate the national planning budgeting cycle for health Multiyear health sector plans are prepared for five year period. The current plan is from 2011 to 2015. Annual plans with annual budget are prepared every year on the basis of multiyear plan. The budget for the implementation of health sector is approved on annual basis by the government. The financial year of Vietnam starts from January 1st and ends December 31st Please indicate the national planning cycle for immunisation The EPI prepares a multi-year plan to coincide with the national multiyear plan for the health sector. The current multiyear plan is from 2011 to 2015. In addition, EPI program prepares annual work plans based on the multiyear plan for annual budgeting and implementation purposes Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems The rate of immunization coverage by sex not include in immunization routine reporting systems. However, this information will be include in coverage survey conduct every 5 years in EPI review Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan It is note that, there was no significant difference in coverage level between boys and girls in the 30-cluster coverage survey done in 6 provinces in 2009 during EPI review. The high coverage (more than 95%) was maintained for all antigents. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys? Country should provide an outline of all preparatory activities for vaccine(s) introduction - Technical consultation with WHO on timing and costing of MR vaccine introduction including age cohorts for MR SIA<?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> - Development of MR vaccine introduction options and costing and presentation to the Technical Working Group for endorsement for making GAVI application - Updating of the cMYP and costing to incorporate MR vaccine introduction, development of MR SIA outline guidelines and GAVI MR application process - Assessment of cold chain capacity at all levels to support the introduction of MR vaccine into routine EPI schedule - Presentation of GAVI application outcome and NEPI plans in 2013 - 2014 for introduction of MR vaccine into the routine immunization schedule and scope and budgeting of the MR SIA at the Quarterly EPI meeting - Updating of NEPI Policy Guidelines for new immunization schedule, printing and distribution to all provinces, district and health centres (Q1 2013) - Developing detail National plan (Q1 2013) - Developing the regulations of expenditure at all levels and announcement, training for Regional & provincial managers and staff (Q1 2013) - Modification of infant immunization cards, immunization book for children <1 year and monitoring charts to incorporate switch from measles to MR vaccine and printing (Q2 2013) - Workshop for National and provincial EPI vaccine ordering focal points on the ordering requirements for the split MR/M schedule and updating of vaccine estimation forecasts (Q2 2013) - Estimated delivery of MR vaccine, and initiation of supply through the routine vaccine distribution system to be in all CHC by Q4 2013 and 2014 (Q3 2013)

5.1.1 MCV Immunisation coverage Please provide information concerning routine immunisation coverage related to measle-containing vaccines (MCV) Table 5.1.1: MCV Immunisation coverage Coverage 2005 2006 2007 Administrative1) WHO/UNICEF2) Administrative1) WHO/UNICEF2) Administrative1) WHO/UNICEF2) Measles 1st dose (%) 98.6 95 96.4 93 82.8 83 Measles 2st dose (%) 98.1 96.3 Supplementary Immunization Activities (SIA) (%) 97.3 Coverage 2008 2009 2010 Administrative1) WHO/UNICEF2) Administrative1) WHO/UNICEF2) Administrative1) WHO/UNICEF2) Measles 1st dose (%) 95.7 92 97 97 97.8 98 Measles 2st dose (%) 95.6 96.4 97.7 Supplementary Immunization Activities (SIA) (%) 97.3 96.5 Coverage 2011 Administrative1) WHO/UNICEF2) Measles 1st dose (%) 96.5 96 Measles 2st dose (%) 90.2 Supplementary Immunization Activities (SIA) (%) Note: 1)National reported Administrative Coverage 2)WHO/UNICEF estimated coverage Was the last Measles Supplementary Immunization Activities (SIA) administrative coverage or results of a survey of acceptable methodology Administrative coverage

5.2. Baseline and Annual Targets (NVS Routine Support)

No NVS Routine Support is requested

| 5.3. Baseline and Annual Targets for Preventive Campaign(s) |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (MR campaign) Please specify cohort for rubella-containing vaccines (RCV): RCV Start 9 months RCV End 14 years Cohort population = population 9 months - 14 years old GAVI supports no more than 15 cohorts. If the application is not within 9 months to 15 years, please provide justification Table 5.3.1 Baseline NVS preventive campaign figures for MR Number Base Year Baseline and Targets Baseline and Targets 2012 2013 2014 Total births 1,676,394 1,696,510 1,716,869 Total population 9 months - 14 years old 22,653,655 22,925,499 22,925,499 Target population vaccinated with MR 22,200,582 5,373,072 17,552,427 MR (campaign) coverage (%) [1] 98.00 % 23.44 % 76.56 % Wastage rate in base year and thereafter (%) for MR (campaign) 25 25 25 Wastage factor in base year and thereafter for MR 1.33 1.33 1.33 [1] Number of persons vaccinated out of total births |  |

6. New and Under-Used Vaccines (NVS Routine)

No NVS Routine Support is requested

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available)

Disease Title of the assessment Date Results

If MR vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them.

Lessons Learned Action Points

7.1.1 Epidemiology and disease burden for Measles-Rubella Please select at least one of the following information sources to justify RCV diseases burden results: Epidemiological information on burden of disease: þ 1 - Rubella data from the measles case-based surveillance system (including the age distribution of rubella cases) o 2 - Rubella seroprevalence surveys þ 3 - Congenital Rubella Syndrome (CRS) burden information, e.g. retrospective search, modelled estimates for CRS burden, prospective surveillance o 4 - Other

7.2.Requested for MR, 10 dose(s) per vial, LYOPHILISED campaign support 7.2.1. Summary for MR campaign support Please give a summary of the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of MR, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc): With support from GAVI a measles/rubella (MR) vaccine SIA will be undertaken in Q4 2013 and 2014, that targets 9 months to 14 years, 11 months (both males and female). The campaign will include three phases base on cold chain capacity analysis at different levels: <?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> Phase 1: From October to December 2013 for 5,373,072 target population 11-14 years old (6 - 9 grade); Phase 2: From April to June 2014 for 6,995,664 target population 7 - 11 years old (1 - 5 grade); and Phase 3: From October to December 2014 for 10,556,763 target population 9 months to 6 years old. The MR SIA will build on the lessons and success of the 2010 measles vaccine SIA, especially the strategy of the NEPI to identify, target and intensively monitor coverage in high risk communities (urban poor, remote rural, ethnic and migrant populations). Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled: A analysis of the cold chain capacity for the introduction MR was undertaken which found that their was sufficient cold chain storage capacity at all levels of vaccine storage to absorb the requirements of the MR. However, for catch-up measles/rubella (MR) vaccine SIA will be undertaken in Q4 2013 and 2014. With these three phases the cold chain capacity will be fine for campaign. The MR SIA will build on the lessons and success of the 2010 measles vaccine SIA for 8 million target population no impact in the shipment plans for routine vaccines. 7.2.2. Grant Support for Operational Costs of the MR Campaign Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). Table 7.2.2: calculation of grant to support the operational costs of the campaigns Year of MR support Target population vaccinated (from Table 5.3) Share per population 9 months-14 years old in US$ Total in US$ 2013 5,373,072 0.65 3,492,497 2014 17,552,427 0.65 11,409,078 [1] The Grant will be based on a maximum award of $0.65$ per cohort population Cost (and finance) of the MR, 10 dose(s) per vial, LYOPHILISED campaign US$ Cost Category Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ 2013 2013 Training 1,823,500 1,602,000 Social Mobilization, IEC and advocacy 1,395,295 847,000 Cold Chain Equipment & Maintenance 803,300 803,300 Vehicles and Transportation 200,000 200,000 Programme Management 200,000 200,000 Surveillance and Monitoring 475,450 366,750 Human Resources 2,637,957 1,838,000 Waste Management 100,000 100,000 Technical Assistance 48,000 48,000 Planning 1,037,700 954,600 Volunteer incentives 1,200,000 1,200,000 Other (please specify) Total 9,921,202 8,159,650 Cost Category Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ 2014 2014 Training 396,275 174,775 Social Mobilization, IEC and advocacy 947,295 399,000 Cold Chain Equipment & Maintenance 416,700 416,700 Vehicles and Transportation 300,000 300,000 Programme Management 200,000 200,000 Surveillance and Monitoring 813,450 727,450 Human Resources 4,576,000 3,776,000 Waste Management 100,000 100,000 Technical Assistance 48,000 48,000 Planning 0 0 Volunteer incentives 600,000 600,000 Other (please specify) Total 8,397,720 6,741,925 Please describe others sources of funding if available to cover your full needs Total operational costs for the SIA are estimated to be US$ 18,340,399 (or 0.80 USD per child), with GAVI funding US$ 14,901,575 (0.65 USD per child) and the remainder (US$3,438,824) being provided from central, local government and other donors (WHO, UNICEF,...). It is note that in 2010 Viet Nam received support from UN fund through UNICEF and WHO for measles campaing for cildren from 1 to 5 years old only vaccine and injection equipment. Operation cost for this campaign was coved by central and local gorvement. 7.2.3 Evidence of introduction of RCV in routine programme Please provide evidence that the country can finance the introduction of Rubella-Containing-Vaccine (RCV) into the routine programme through one of the following: o 1 - A commercial contract for purchase of MR/MMR (Meales Rubella/Meales Mumps Rubella) vaccine together with shipping documents, invoice, etc. o 2 - Proof that RCV has been integrated into the cMYP with the budget line for vaccines increased to include purchase of RCV as part of the health sector budget to indicate that RCV funds are allocated o 3 - A letter from the Minister of Finance or Budget ensuring additional funding for RCV purchase o 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of RCV for use in the routine programme þ 5 - Other Document N° Please briefly describe the document used as evidence: Agreement from MoH and Gov. for conduct MR catch-up campaign with support from GAVI and followed immediately by introduction of MR vaccine in the routine EPI for children 9 monhts instead of MCV1. In troduction of MR vaccine was mentioned in the MYP for Health 2012 - 2015 approved from government. It is note that in the past after support from GAVI for introduce Hepatitis B vaccine in EPI 2002-2007, INS 2004 - 2006 and MVC2 2007-2011 in Viet Nam, the fund from the government cover the cost for continues maintain theses.<?xml:namespace prefix = o /> 7.2.4 Introduction planning for RCV Countries should describe their plan for introduction including surveillance activities: Does Viet Nam’s cMYP include a plan for the introduction of RCV into the national programme? Yes Please describe a Plan Of Action (POA) for the introduction of RCV into the national programme or provide the POA as an attachment - Refer to section 10. Attachments. (Document N° ) Rubella vaccine will be introduced in Viet Nam through a two component strategy:<?xml:namespace prefix = o /> Catch-up campaign. With support from GAVI a measles/rubella (MR) vaccine SIA will be undertaken in Q4 2013 and 2014, that targets 9 months to 14 years, 11 months (both males and female). The campaign will include three phases base on cold chain capacity analysis at different levels: Phase 1: From October to December 2013 for 5,373,072 target population 11-14 years old (6 - 9 grade); Phase 2: From April to June 2014 for 6,995,664 target population 7 - 11 years old (1 - 5 grade); and Phase 3: From October to December 2014 for 10,556,763 target population 9 months to 6 years old. The MR SIA will build on the lessons and success of the 2010 measles vaccine SIA, especially the strategy of the NEIP to identify, target and intensively monitor coverage in high risk communities (urban poor, remote rural, ethnic and migrant populations). Total operational costs for the SIA are estimated to be US$ 18,340,399 (or 0.80 USD per child), with GAVI funding US$ 14,901,575 (0.65 USD per child) and the remainder (US$3,438,824) being provided from central, local government and other donors (WHO, UNICEF,...). Further information on the MR SIA 2013 is provided in the detailed planning guide that has been developed. Follow the completion of the MR SIA, the National Immunization Program will introduce MR vaccine to replace the current Measles vaccine given to all children at 9 months of age. The introduction of MR vaccine into the routine immunization schedule will have no impact on injection safety items requirements (AD and mixing syringes/safety boxes) given that this is a simple swap from a 10 dose measles vial to the 10 dose MR vial. MR vaccine introduction will require additional Government finances for vaccine procurement given its higher cost (approximately 0.49 USD per dose) over the currently used measles vaccine (approximately 0.22 USD per dose). However, given that the Ministry of Health currently fully funds measles vaccine, there will only be an incremental cost of 0.27 USD per dose for the switch from measles to MR vaccine. The total cost of MR vaccine procurement from 2015 onwards will be approximately US$ 1,117,200 per year, but the actual additional finances needed for the Ministry of Health’s vaccine procurement budget will be approximately US$615,600 per year which the current allocation of financing for measles vaccine procurement is taken into consideration. The Ministry of Health has committed to funding the additional costs of procurement of MR vaccine as part of its routine vaccine procurement budget and has increased the budget allocation by up to US$ 1,117,200 from 2015, which is easily sufficient to cover the expected additional financial requirements for the procurement of one dose of MR vaccine for the routine immunization program. A analysis of the cold chain capacity for the introduction MR was undertaken which found that their was sufficient cold chain storage capacity at all levels of vaccine storage to absorb the requirements of the MR. However, for catch-up measles/rubella (MR) vaccine SIA will be undertaken in Q4 2013 and 2014. Impact of rubella vaccine introduction will be monitored by the National. Immunization Program through the current Acute Fever and Rash (AFR) surveillance system which is fully integrated for testing all suspected measles/rubella cases that have blood samples (serum or dried blood spot) for both measles and rubella IgM at the National Institute of Public Health (WHO recognized National Measles Laboratory). The AFR surveillance system in Viet Nam is based on health centre/community detection of AFR cases. These are investigated by health staff, and blood samples taken from most cases for confirmatory testing. The priliminary result of following 2010-2011 rubella outbreak reveals 161 confirmed CRS cases among 189 suspected case. 3 deaths and 82% of total case is multiple birth defect including: deafness, blindness, heart defects, etc. This is health and social burden. The CRS sentinel surveillance project will continue under WHO support for three asentinel hospitals and include laboratory confirmation of rubella IgM for all compatible cases identified. (See Document 6)

INSTRUCTIONS Components of the POA/cMYP should include: a. Comprehensive vaccination strategy for the introduction of RCV including a description of: i. Initial Measles and rubella (MR) campaign ii. Replacing Measles containing vaccine (MCV) with Measles and rubella (MR) / Measles, mumps, and rubella (MMR) in the routine childhood vaccination programme iii. Strategies for targeting Women of Childbearing Age (WCBA), such as vaccination during routine services, post-partum, at 1st well baby visit, SIAs iv. Linkage to the current routine immunisation schedule v. Linkage to measles second dose, if applicable vi. Description of how the country plans to continue to maintain high MR/MMR vaccine coverage either through routine immunisation or through Supplementary Immunization Activities (SIAs) b. A brief description of the following surveillance activities: i. Integration of Rubella surveillance with case-based measles surveillance ii. Congenital Rubella Syndrome (CRS) surveillance or plans to establish sentinel site CRS surveillance iii. Adverse Event Following Immunization (AEFI) surveillance c. Vaccine coverage monitoring and reporting d. The communication strategy for the introduction of RCV 7.2.5 Measles surveillance indicators Please provide information on the following indicators of the quality of measles surveillance for at least two years prior to application (if available): Surveillance indicator 2010 2011 Reporting rate at national level 1) 3 16 100,000 100,000 Laboratory confirmation rate (%) 2) 41 3 Note: 1) Reporting rate at national level = number of discarded measles cases per 100,000 population per year 2) Laboratory confirmation rate (%) = number of suspected cases with specimens collected for testing divided by the number of suspected cases not confirmed through epidemiological linkage

7.2.6 Rubella Containing Vaccine introduction Grant Has a Rubella Containing vaccine already been introduced nationally on a routine basis? No Calculation of lump-sum for the MR, 10 dose(s) per vial, LYOPHILISED Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed. Year of New Vaccine Introduction Births (From Table 5.3) Share per Birth in US$ Total in US$ 2013 1,696,510 0.80 1,357,208 [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000 Cost (and finance) to introduce the MR, 10 dose(s) per vial, LYOPHILISED US$ Cost Category Full needs for new vaccine introduction in US$ Funded with GAVI introduction grant in US$ Training 573,000 384,000 Social Mobilization, IEC and advocacy 405,000 260,000 Cold Chain Equipment & Maintenance 250,000 0 Vehicles and Transportation 90,000 75,000 Programme Management 138,900 100,000 Surveillance and Monitoring 396,300 248,200 Human Resources 216,600 160,000 Waste Management 158,900 77,208 Technical Assistance 52,800 52,800 Other (please specify) Total 2,281,500 1,357,208

8. Procurement and Management

8.1. Procurement and Management of New and Under-Used Vaccines Routine

No NVS Routine Support is requested

8.2. Procurement and Management for NVS Preventive Campaign(s)

8.2.1. Procurement and Management for MR, 10 dose(s) per vial, LYOPHILISED campaign a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF): Viet Nam will prefer procuring of the MR vaccine and injection supplies which is financed by GAVI through the UNICEF supply system for rubella catch-up campaign. As per the regulations in the country, the vaccines imported in Viet Nam have to be licensed in the country, even if the vaccine is procured by UNICEF. Hence, for the supply of any vaccine either by UNICEF or self-procurement, the vaccine has to be both WHO prequalified as well as licensed in Viet Nam. It is very essential that that the MR vaccine to be procured by UNICEF on behalf of GAVI be licensed in Viet Nam as soon as possible in early 2013 to enable Viet Nam to conduct this campaign in October 2013.<?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> In addition, the cash grant ($14,858,920) for operation cost ($0.65 per target population) will be received in a bank account held by NIHE (National Institute of Hygiene and epidemiology), which is part of the MOH as specified in annex 1 on the banking form. NEPI, the national EPI steering group and the ICC will provide oversight over implementation of rubella catch-up campaign activities and its monitoring and supervision b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time). Base on the cold chain capacity analysis at different levels the rubella catch-up campaign for 9 months to 15 years old will be conducted in three phases: <?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> Phase one: From Oct. to Dec. 2013 for 6,716,340 target population 11-14 years old (6 - 9 class); Phase two: From Mar. to May 2014 for 6,995,664 target population 7 - 11 years (1 - 5 class); and Phase three: From Oct. to Dec. 2014 for 9,147,909 target population 9 months to 6 years. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the MR, 10 dose(s) per vial, LYOPHILISED campaign introduction plan) The EPI vaccines coverage include new vaccine will be monitored and reported through monthly routine report in EPI system from commune to national levels. Coverage survey will be conducted in 6 random selected provinces every 5 years in EPI review <?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> For the campaign the coverage will be monitored and reported during and after the campaign by EPI health staff at difference levels. Quick assessment will be conducted if necessary during the campaign.

8.3. Vaccine Management (EVSM/EVM/VMA)

Did the country have Effective Vaccine Management Assessment (VMA) in the past? No Did the country have Effective Vaccine Store Management (EVSM) in the past? No Did the country have Effective Vaccine Management (EVM) in the past? Yes When was the EVM conducted? April 2012 If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°8) A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM. IMPROVEMENT PLAN<?xml:namespace prefix = o ns = "urn:schemas-microsoft-com:office:office" /> General recommendations · Integrating EVM assessment in the final evaluation on EPI and supportive supervision. Implementation level: NEPI Starting from: 2012 Completed by: To be continued in the years to come National store/regional stores E1: Vaccine arrival procedures · Reporting every time vaccines are delivered and received. Implementation level: National/regional EPI Starting from: June 2012 Completed by: Continuing process for each time of receiving and distributing vaccine E2: Temperature monitoring · Providing and using continuous temperature monitoring devices with support from PATH ; the devices to be used for both vaccine storage and transport. Implementation level: NEPI/PATH (Optimize) Starting from: July 2012 Completed by: December 2012 · Conducting monthly reviews of the temperature records in order to identify long-term trends. Keep records of these reviews. Implementation level: NEPI and regional EPI Starting from: August 2012 Completed by: Monthly E4: Buildings, equipment and transport · Refurbishing the NVS to be certified for Good practice of Pharmaceuticals and Vaccines Storage, in accordance with the regulation of MOH. Implementation level: NIHE Starting from: April 2012 Completed by: July 2012 · Refurbishing the regional vaccine stores to be certified for Good practice of Pharmaceuticals and Vaccines Storage, in accordance with the regulation of MOH. Implementation level: Regional EPI Starting from: August 2012 Completed by: July 2013 · Developing guidelines to introduce continuous temperature monitoring devices for all regional stores when transporting vaccines to provincial level. Implementation level: NEPI Starting from: October 2012 Completed by: December 2012 E5: Maintenance · Finalizing and launching the national and regional technical teams to support maintenance services at lower levels. Implementation level: NEPI and regional EPI Starting from: July 2012 Completed by: To be maintained according to the needs for maintenance and repair of the regions E6: Stock management · Providing re-training for storekeepers on recording store registers and forms, as well as on recording the presentation of vaccines, diluents, VVM status and location of different vaccines in the store. Implementation level: NEPI, regional EPI Starting from: June 2012 Completed by: October 2012 E7: Distribution · Developing SOP and contingency plans for domestic vaccine distribution. Implementation level: NEPI Starting from: July 2012 Completed by: October 2012 E8: Vaccine management · Providing re-training for storekeepers on shake test and how to read VVM. Implementation level: NEPI, regional EPI Starting from: August 2012 Completed by: December 2012 E9: MIS and supportive functions · Selecting the most vital SOPs for developing and adapting in all stores. Implementation level: NEPI Starting from: August 2012 Completed by: December 2012 Provincial stores E4: Buildings, equipment and transport · Using continuous temperature monitoring device for vaccine refrigerators and freeze indicators in transporting vaccines. Implementation level: NEPI/PATH/VIE/025 Starting from: July 2012 Completed by: December 2012 E6: Stock management · Providing re-training for storekeepers on recording store registers and forms, as well as on recording the presentation of vaccines, diluents, VVM status and location of different vaccines in the store. Implementation level: NEPI, regional EPI Starting from: October 2012 Completed by: March 2013 E7: Distribution · Developing SOP and contingency plans for domestic vaccine distribution. Implementation level: NEPI Starting from: July 2012 Completed by: October 2012 District stores E4: Buildings, equipment and transport · Using freeze indicators for vaccine refrigerators. Implementation level: NEPI/VIE/025 Starting from: July 2012 Completed by: December 2012 E5: Maintenance · Implementing plans for quick repair of broken cold chain equipment. Implementation level: National/regional EPI. Starting from: July 2012 Completed by: No deadline E6: Stock management · Providing re-training for storekeepers on recording store registers and forms, as well as on recording the presentation of vaccines, diluents, VVM status and location of different vaccines in the store. Implementation level: Regional/provincial EPI Starting from: February 2013 Completed by: August 2013 E8: Vaccine management · Providing training and re-training for storekeepers and EPI staff on shake test and how to read VVM. Implementation level: Regional/provincial EPI Starting from: February 2013 Completed by: August 2013 CHCs E4: Buildings, equipment and transport · Providing guidelines on proper use of the issued standard practice. Implementation level: Provincial/district EPI Starting from: March 2013 Completed by: August 2013 E6: Stock management · Giving instructions on recording and reporting on immunization including information of vaccines, diluents, etc. Implementation level: Provincial/district EPI Starting from: March 2013 Completed by: August 2013 E8: Vaccine management · Providing re-training for health staff on recording immunization data. Implementation level: Provincial/district EPI Starting from: March 2013 Completed by: August 2013 Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? No

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

10. Attachments

10.1. List of documents attached to this proposal

Document Number Document Section Mandatory File MoF Signature_VNM.PDF 1 MoH Signature (or delegated authority) of Proposal File desc: Date/time: 9/7/2012 3:37:30 AM Size: 278746 MoF Signature_VNM.PDF 2 MoF Signature (or delegated authority) of Proposal File desc: Date/time: 9/7/2012 3:36:35 AM Size: 278746 Signatures of ICC in Proposal_VNM.PDF 3 Signatures of ICC or HSCC or equivalent in Proposal File desc: Date/time: 8/29/2012 12:37:09 AM Size: 233382 Minutes of 22nd ICC meeting endorsing proposal_VNM.docx 4 Minutes of ICC/HSCC meeting endorsing Proposal File desc: Date/time: 8/29/2012 2:20:33 AM Size: 26637 cMYP for EPI 2010-2015_VNM.doc 5 comprehensive Multi Year Plan - cMYP File desc: Date/time: 8/29/2012 9:42:44 PM Size: 877056 MYP Costing tool for EPI 2011-2015_VNM.xls 6 cMYP Costing tool for financial analysis File desc: Date/time: 8/29/2012 9:43:29 PM Size: 231936 Plan for MR introduction in Vietnam.doc 7 Plan for NVS introduction (if not part of cMYP) 5.1 File desc: Date/time: 9/10/2012 8:11:35 AM Size: 310272 Improvement plan based on EVM in VNM 2012.doc 8 Improvement plan based on EVM File desc: Date/time: 8/29/2012 12:38:01 AM Size: 43008 Letter from MoH.pdf 11 Evidence of introduction of RCV in routine programme 7.c.3 File desc: Date/time: 8/31/2012 6:52:48 AM Size: 1487122 Plan for MR introduction in Vietnam.doc 12 Plan Of Action for RCV introduction 7.c.4 File desc: Date/time: 9/10/2012 8:12:32 AM Size: 310272

11. Annexes

Annex 1 - NVS Routine Support

No NVS Routine Support is requested

Annex 2 - NVS Routine – Preferred Second Presentation

No NVS Routine – Preferred Second Presentation requested this year

Annex 3 - NVS Preventive campaign(s)

Annex 3.1 - NVS Preventive campaign(s) (MR, 10 dose(s) per vial, LYOPHILISED) Table Annex 3.1 C: Summary table for CAMPAIGN MR, 10 dose(s) per vial, LYOPHILISED Data from 2013 2014 Total campaign population Table 5.3.1 # 22,925,499 22,925,499 Immunization coverage Table 5.3.1 % 23.00 % 77.00 % Number of persons to be vaccinated Table 5.3.1 # 5,373,072 17,552,427 Number of doses per persons Parameter # 1 1 Estimated vaccine wastage factor Table 5.3.1 # 1.33 1.33 Number of doses per vial Parameter # 10 10 AD syringes required Parameter # Yes Yes Reconstitution syringes required Parameter # Yes Yes Safety boxes required Parameter # Yes Yes Vaccine price per dose Table Annexes 4A $ 0.494 0.494 AD syringe price per unit Table Annexes 4A $ 0.0465 0.0465 Reconstitution syringe price per unit Table Annexes 4A $ 0.0037 0.0037 Safety box price per unit Table Annexes 4A $ 0.0058 0.0058 Freight cost as % of vaccines value Table Annexes 4B % 13.00 % 13.00 % Freight cost as % of devices value Parameter % 0 0

Table Annex 3.1 D: Estimated number of MR, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1) Formula GAVI 2013 2014 B Number of persons to be vaccinated with the first dose 5,373,072 17,552,427 C Number of doses per persons 1 1 D Number of doses needed B x C 5,373,072 17,552,427 E Estimated vaccine wastage factor Wastage factor table 1.33 1.33 F Number of doses needed including wastage D x E 7,146,186 23,344,728 G Vaccines buffer stock (F – F of previous year) * 0.25 1,786,547 4,049,636 I Total vaccine doses needed F + G 8,932,733 27,394,364 J Number of doses per vial Vaccine parameter 10 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 7,947,178 23,978,290 L Reconstitution syringes (+ 10% wastage) needed I / J * 1.11 991,534 3,040,775 M Total of safety boxes (+ 10% of extra need) needed (K + L) /100 * 1.11 99,220 299,912 N Cost of vaccines needed I x g 0.494 0.494 O Cost of AD syringes needed K x ca 369,543.777 1,114,990.485 P Cost of reconstitution syringes needed L x cr 3,669 11,251 Q Cost of safety boxes needed M x cs 576 1,740 R Freight cost for vaccines needed N x fv 0 0 S Freight cost for devices needed (O+P+Q) x fd 0 0 T Total fund needed (N+O+P+Q+R+S) 4,786,559.777 14,660,797.485 Note: There is no cofinancing for NVS preventive campaigns

| Annex 4 |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost |  |  |
| Vaccine Presentation 2013 2014 2015 2016 DTP-HepB, 10 dose(s) per vial, LIQUID 10 DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 2.017 1.986 1.933 1.927 DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 2.017 1.986 1.933 1.927 DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED 2 2.017 1.986 1.933 1.927 HPV bivalent, 2 dose(s) per vial, LIQUID 2 5.000 5.000 5.000 5.000 HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5.000 5.000 5.000 5.000 Measles, 10 dose(s) per vial, LYOPHILISED 10 0.242 0.242 0.242 0.242 Meningogoccal, 10 dose(s) per vial, LIQUID 10 0.520 0.520 0.520 0.520 MR, 10 dose(s) per vial, LYOPHILISED 10 0.494 0.494 0.494 0.494 Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 3.500 3.500 3.500 3.500 Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 3.500 3.500 3.500 3.500 Rotavirus, 2-dose schedule 1 2.550 2.550 2.550 2.550 Rotavirus, 3-dose schedule 1 3.500 3.500 3.500 3.500 Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 0.900 0.900 0.900 0.900 Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 0.900 0.900 0.900 0.900 |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF |  |  |
| Supply Form 2013 2014 2015 2016 AD-SYRINGE SYRINGE 0.047 0.047 0.047 0.047 RECONSTIT-SYRINGE-PENTAVAL SYRINGE 0.047 0.047 0.047 0.047 RECONSTIT-SYRINGE-YF SYRINGE 0.004 0.004 0.004 0.004 SAFETY-BOX SAFETYBOX 0.006 0.006 0.006 0.006 |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised) |  |  |
| Table Annex 4B: Freight cost as percentage of value |  |  |
| Vaccine Antigen Vaccine Type No Threshold 500,000$ <= > DTP-HepB HEPBHIB 2.00 % DTP-HepB-Hib HEPBHIB 23.80 % 6.00 % HPV bivalent HPV 3.50 % HPV quadrivalent HPV 3.50 % Measles MEASLES 14.00 % Meningogoccal MENINACONJUGATE 10.20 % MR MR 13.20 % Pneumococcal (PCV10) PNEUMO 3.00 % Pneumococcal (PCV13) PNEUMO 6.00 % Rotavirus ROTA 5.00 % Yellow Fever YF 7.80 % |  |  |
| Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine. |  |  |
| Vaccine |  |  |
| Table Annex 4D: Wastage rates and factors |  |  |
| Countries are expected to plan for a maximal wastage rate of: |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial, |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial, |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and |  |  |
| • 5% - for a liquid vaccine in 1-dose vial |  |  |
| Vaccine wastage rate 5% 10% 15% 20% 25% 30% 35% 40% 45% 50% 55% 60% Equivalent wastage factor 1.05 1.11 1.18 1.25 1.33 1.43 1.54 1.67 1.82 2 2.22 2.5 |  |  |
| Vaccine Vaccine wastage rate VaccineWastageFactor MR, 10 dose(s) per vial, LYOPHILISED 25% 1.33 |  |  |
| Table Annex 4E: Vaccine maximum packed volumes |  |  |
| Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella freeze dried MR lyophilized SC 1 1 26.1 26.1 Measles-Rubella freeze dried MR lyophilized SC 1 2 13.1 13.1 Measles-Rubella freeze dried MR lyophilized SC 1 5 5.2 7 Measles-Rubella freeze dried MR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella freeze dried MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP-Hib liquid IM 3 1 32.3 DTP-HepB liquid + Hib freeze-dried DTP-Hib liquid IM 3 10 2.5 DTP-HepB liquid + Hib freeze-dried DTP-HepB+Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB+Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized SC 2 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 3 10 15 Japanese Encephalitis JE_lyo lyophilized SC 3 10 8.1 8.1 Japanese Encephalitis JE_lyo lyophilized SC 3 5 2.5 2.9 Japanese Encephalitis JE_lyo lyophilized SC 3 1 12.6 11.5 Japanese Encephalitis JE_liq liquid SC 3 10 3.4 Rota vaccine Rota_lyo lyophilized Oral 2 1 156 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 PFS 55.9 Pneumo. conjugate vaccine 7-valent PCV-7 liquid IM 3 1 21 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Papilomavirus vaccine HPV liquid IM 3 1 15 Human Papilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5 |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Viet Nam hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): See attachment Document number 14 (3 files) Address: City Country: Telephone no.: Fax no.: Currency of the bank account: For credit to: Bank account's title: Bank account no.: Bank's name: |  |
| Is the bank account exclusively to be used by this program? True |  |
| By who is the account audited? |  |
| Signature of Government's authorizing official |  |
| Seal Name: Title: Signature: Date: |  |
| FINANCIAL INSTITUTION Bank Name: Branch Name: Address: City Country: Swift Code: Sort Code: ABA No.: Telephone No.: FAX No.: | CORRESPONDENT BANK (In the United States) |
| I certify that the account No is held by at this banking institution The account is to be signed jointly by at least (number of signatories) of the following authorized signatories: 1 Name: Title: 2 Name: Title: 3 Name: Title: |  |
| Name of bank's authorizing official Signature: Date: Seal: |  |