ZAMBIA

GAVI Alliance Health System Strengthening (HSS) Applications

May 2007

An electronic version of this document is available on the GAVI Alliance website (www.gavialliance.org) and provided on CD. Email submissions are highly recommended, including scanned documents containing the required signatures. Please send the completed application to:

Dr Craig Burgess

Senior Programme Officer, HSS

GAVI Alliance Secretariat

c/o UNICEF, Palais des Nations

1211 Geneva 10, Switzerland

Email: cburgess@gavialliance.org

Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline. Proposals received after that date will not be taken into consideration for that review round. GAVI will not be responsible for delays or non-delivery of proposals by courier services.

All documents and attachments should be in English or French.  All required information should be included in this application form. No separate proposal documents will be accepted by the GAVI Secretariat. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents may be shared with the GAVI Alliance partners, collaborators and the general public.

Please direct all enquiries to:

Dr Craig Burgess (cburgess@gavialliance.org) or representatives of a GAVI partner agency.

Table of Contents

Page

Abbreviations and Acronyms

Application for GAVI Alliance Health System Strengthening Applications

Executive Summary	5

Section 1: Application Development Process	8

Section 2: Country Background Information	11

Section 3: Situation Analysis / Needs Assessment	12

Section 4: Goals and Objectives of GAVI HSS Support	14

Section 5: GAVI HSS Activities and Implementation Schedule	Error! Bookmark not defined.

Section 6: Monitoring, Evaluation and Operational Research	26

Section 7: Implementation Arrangements	29

Section 8: Costs and Funding for GAVI HSS	33

Section 9: Endorsement of the Application	35

Annexes

ANNEX 1 Documents Submitted in Support of the GAVI HSS Application	36

ANNEX 2 Banking Form	37

## LIST OF ABBREVIATIONS

AD					Auto Disable

## AIDS					Acquired Immune Deficiency Syndrome

## BCG						Bacille Calmette Guerin

## CBA						Community based agents

## CHAZ					Churches Health Association of Zambia

## CHW					Community health worker

## c-MYP				costed-Multi Year Plan

DFID					Department for International Development

DPT-Hep b+Hib	Diphtheria-Pertussis Tetanus, hepatitis B and Haemophilus influenzae vaccine

## EPI						Expanded program on Immunisation

EU					European Union

## GAVI					Global Alliance for Vaccines and Immunisation

## GRZ						Government of the Republic of Zambia

## ICC						Inter-agency Coordinating Committee

IGA					Income Generating Activities

INS					Injection Safety Support

ISS					Immunisation Support Services

HCP					Health Communication Partnership

## HSS						Health system Strengthening

HSSP					Health Systems Support Program

## HRHSP				Human Resource for Health Strategic Plan

HIV					Human Immune Deficiency Virus

## JICA						Japan International Cooperation Agency

OPV					Oral Polio Vaccine

MDGs					Millennium development Goals

## MoH						Ministry of Health

## MoFNP				Ministry of Finance and National Planning

## MTEF					Medium Term Expenditure Framework

MNTE					Maternal Neonatal Tetanus Elimination

NHC					Neighbourhood Health Committees

NHSP					National Health Strategic Plan

NIDs					National Immunisation days

RED					Reaching Every District

SIA					Supplementary Immunisation Activities

## SIDA					Swedish International Development Agency

TT					Tetanus toxoid

UNICEF				United Nations Children’s Emergency Fund

## USAID				US Agency for International Development

## WHO 					World Health Organisation

# Executive Summary

# The Government of the Republic of Zambia (GRZ) has developed this proposal in consultation with the technical members of the Interagency Coordination Committee for Child Health (ICC) and the Health Sector Steering Committee or Sector Advisory Group (SAG). The team comprised officials from the Ministry of Health (MoH), Ministry of Finance and Planning (MoFP), the World Health Organisation (WHO), United Nations Children’s Emergency Fund (UNICEF), Japan International Cooperation Agency (JICA), Churches Health Association of Zambia (CHAZ) and the United States Agency for International Development (USAID). This proposal seeks to request the Global Alliance on Vaccines and Immunisation (GAVI) for financial and technical assistance for Health Systems Strengthening (HSS) in Zambia.

# The requested financial support will contribute to addressing some of the health systems concerns in both the National Health Strategic Plan 2006-2010 and Human Resource for Health Strategic Plan (HRHSP) 2006-2010. Both documents highlight the severe human resource crisis that Zambia is under-going and is negatively affecting the delivery of health services including the Expanded Program on Immunization (EPI). In 2005 the country conducted an EPI program review in which similar findings of inadequate human resource to conduct EPI services were identified. Following the EPI review, a comprehensive costed-Multi Year Plan (c-MYP) 2006-2010 has been developed. The document spells out the vision, goals and strategies of the Immunisation program in Zambia.

Zambia’s immunization programme has recorded tremendous progress particularly during the implementation period of the 2000 – 2004 Multi Year Plan. The programme was implemented as part of the health reforms where child health activities constituted a critical component of the “Basic Health Care Package”. EPI is part of the Medium Term Expenditure Framework (MTEF) planning for 2006-2009 where vaccines have now been accorded a specific budget line in the Ministry of Health budget framework.

Zambia has made significant progress towards implementing the Vaccine Independence Initiative (VII) by financing about 80% of the cost of traditional vaccines and fully funded injection materials for traditional antigens. In addition, Zambia has started making contributions towards the cost of pentavalent vaccine. Immunisation activities are an important component of the Health Sector MTEF Plans for 2006 – 2009 at the National, Provincial, District and community level of the health care delivery system.

Existence of a strong health system is a necessary condition for successful implementation of EPI. The mid - term review of the National Health Strategic Plan (NHSP) for 2001-2005 identified the importance of having adequate and motivated human resource coupled with adequate transport for provision of health services.

The country has continued to record progress in the initiatives of polio eradication, measles control and maternal neonatal tetanus elimination (MNTE) during the period 2001-2006. In 2005, Zambia’s documentation for polio free certification was accepted by the African Region for Polio Certification Committee. This was as a result of the country not recording any polio cases since 2002 and running successful polio eradication programs and achieving high quality polio surveillance indicators. Zambia has started making efforts to eliminate measles as evidenced by the highly successful nationwide measles campaign that was conducted in 2003 with coverage over 95%. Consequently, measles cases and deaths have reduced to near zero.  For Maternal Neonatal Tetanus Elimination (MNTE) the country conducted campaigns in 18 high risk districts successfully and is on course for validation of MNT by 2007 and  having  eliminated NNT.

Despite all these major successes achieved under the EPI programme, the program has faced many challenges. A key constraint to rapid scale-up of health services is the worsening human resource crisis in health. Over the past few years, the Ministry of Health has seen a massive exodus of health workers, especially nurses to the domestic private sector and abroad, primarily due to the low level of wages and benefits in the civil service. The median salary level of health workers in Zambia is one of the lowest in the region. The staff attrition rates are high. The Ministry of Health indicated gaps in the establishment showed that available nurses in service in 2004 were 8,706 with a gap of 8,026 whereas in the case of clinical officers the number available was 2,620 with a gap of 1,161 with ratios of population served per health staff member being for nurses 1: 1,421 and clinical officers 1:8,583 in the same period.

The human resource crisis experienced by the health sector has been compounded by death of health workers due to mainly HIV/AIDS. The high health worker attrition has led to a situation where 50 percent of rural health centres in the country are run by unqualified staff and community health workers. Even those facilities that have qualified staff do not have the full complement of staff as per defined establishment. The low staffing levels in health facilities has compromised the quality of health service delivery and led to low utilisation of these services by communities.The inadequacy of appropriate transport is another challenge in a country were the majority of people have to cover long distances to get access to health services. The introduction of new vaccines has greatly increased the budget for vaccines and poses a heavy challenge for the government to sustain financing of the immunization programme.

The problems mentioned above were identified in a study on system wide barriers to immunisation that was conducted in 2004 as being key bottlenecks to successful implementation of the immunization program. In order to address some of these problems, the Ministry of Health has adopted the Reaching Every District (RED) strategy with the aim of increasing coverage in the low performing districts (these where defined as those districts with the highest proportion of un-immunised children for measles). A Human Resource for Health Strategic Plan has been developed in collaboration with co-operating partners to address the human resource for health crisis.

The Ministry of Health conducted a Health Facility Census in 2005 taking stock of state of infrastructure, availability of water supply and type, solar power, radio communication, transport (motor vehicle, motor bikes or other forms) and through this data base the gaps in the health systems were identified for each facility and it was noted that transport was not only inadequate but in some cases inappropriate for the particular geographical location. Twelve districts have been selected for Health Systems Strengthening. The criteria for selection of these districts are as follows:

- Districts with the lowest coverage for Measles and DPT 3 of the 72 districts nation wide,

- Districts with the highest proportion of un-immunised children for measles

- Geographical location

In view of the above mentioned scenario, Zambia has expressed interest in applying for GAVI Health System Strengthening financing to contribute to addressing of the human resource crisis and inadequate transport, for the implementation of EPI. The total amount of money that Zambia is applying for is US$ 6,604,638. The funds will be utilised to improve immunization coverage by improving the following:

- Motivation of health workers

It is envisaged that with the provision of basic amenities at the health facilities, health staff will be motivated to work as there will be communication facilities in place for improved service delivery, availability of water supply and power which is cardinal for quality service. This will not only be beneficial for the health systems but contribute to the retention of health workers at the facilities as basic amenities would be made available to improve staffs’ living environment/ conditions. The transport will be multi purpose for outreach services and referral of cases.

- The communities accessing health services from health facilities:

It is also envisaged that availability of transport, communication tools, solar power (cold chain) will improve services provided to communities while the provision of safe water supply at the facility will also benefit the surrounding communities. The funds requested for will go a long way in bridging the big funding gap in the financing of health services including EPI. Zambia has committed itself to meeting the Millennium Development Goals (MDGs) which include among others Reduction of the under-five mortality rate (currently standing at 168 per 1000 live births) by two-thirds between 1990 and 2015. In the National health strategic plan 2006-10 and the fifth National development plan 2006-10 EPI is identified as one of the child health programs that will contribute to the achievements of the MDG 4.  In the face of declining financing to the health sector, meeting these development goals is likely to prove a big challenge.

# Section 1: Application Development Process

## 1.1: The HSCC (or country equivalent)

Name of HSCC (or equivalent): Sector Advisory Group (SAG) on health.

HSCC operational since: The Sector Advisory Group evolved from the Health Sector Steering Committee operational since 1996.

Organisational structure (e.g., sub-committee, stand-alone): Monitoring & Evaluation Committee Common Income & Expenditure Committee

Frequency of meetings: SAG members meet every six months (biannually)

Overall role and function: The Health Sector Advisory Group (SAG) is a high level forum bringing together the Ministry of Health, Cooperating Partners and the Civil Society, to provide advice to the Ministry on aspects of health sector governance. As part of its mandate, SAG is responsible for overall steering of the implementation process. SAG members will meet every six months (biannually) to review progress, recommend solutions to identified bottlenecks and build consensus on the overall strategic direction of the NHSP.

## 1.2: Overview of application development process

Who coordinated and provided oversight to the application development process? Ministry of Health - Planning & Development Directorate.

Who led the drafting of the application and was any technical assistance provided? Principal Planner (Ministry of Health) with technical assistance provided by the two local consultants.

Give a brief time line of activities, meetings and reviews that led to the proposal submission. S/No. Activity Timeline 1 Invitation by the GAVI secretariat May 2006 2 Submission of letter of intent May 2006 3 Planning meeting to strategise – identification of mission and appointment of local consultants appointment of steering committee/ working group development of Terms of Reference July 2006 4 Hiring of local consultants August 2006 5 Development of first draft by the consultants 6 Review of draft by the steering committee August 2006 7 Presentation of & incorporation of comments from the ICC September 2006 8 Editing of the document by the steering group February 2007 9 Review of final draft using new guidelines March 2007 10 WHO AFRO for comments Dr P. Tumusiime April 2007 11 Presentation to the SAG on health for internal review April, 2007 12 Presentation to GAVI for external review May, 2007

Who was involved in reviewing the application, and what was the process that was adopted? The Child Health Technical Working Group Cooperating partners Civil Society The Ministry of Finance & National Planning The Sector Advisory Group

Who approved and endorsed the application before submission to the GAVI Secretariat? SAG on health

## 1.3: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organisation | SAG yes/no | Roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| Director Planning | Ministry of Health | YES | Oversight and strategic guidance |
| Director – Public Health | Ministry of Health | YES | Technical & Strategic Guidance |
| Immunisation officer | World Health Organisation. | YES | Technical Support |
| Chief – Health Section | United Nations Children’s Emergency Fund | YES | Technical Support |
| Assistant Program Officer | Japan International Cooperation Agency. | YES | Technical Support |
| President | Rotary International | YES | Comments & Consensus |
| Chief of Party | Health Systems Support Program | YES | Technical Support |
|  | USAID | YES | Technical Support |
| Health Desk Officer | Ministry of Finance and National Planning | YES | National Strategic Guidance |
| Director of Programs | Churches Health Association of Zambia | YES | Comments & Consensus |

# Section 2: Country Background Information

## 2.1: Current socio-demographic and economic country information

| Information | Value | Information | Value |
| --- | --- | --- | --- |
| Population | 11,653,658 | GNI per capita | 380 $US |
| Annual Birth Cohort | 605,990 | Under five mortality rate | 168/ 1000 |
| Surviving Infants* | 545,391 | Infant mortality rate | 95/ 1000 |
| Percentage of GNI allocated to Health | 2% | Percentage of Government expenditure on Health | 11.9% |

* Surviving infants = Infants surviving the first 12 months of life

## 2.2: Overview of the National Health Sector Strategic Plan

The provision of Zambians with equity of access to health care as close to the family as possible is the vision of the Zambian Government under the guiding principles of Leadership, Accountability, Partnership and sustainability. To facilitate the attainment of this vision, the Ministry of Health has adopted the Primary Health care strategy as the most appropriate vehicle to achieve it. The National Health Sector Plan (NHSP) stresses the need to adopting cost effective interventions better targeting of health subsidies and the need to forge stronger relationships with cooperating partners in the provision of health services.

The NHSP takes note of Zambia’s commitment to meeting the Millennium Development Goals (MDGs) which include among others,(a) Reduction of the under-five mortality rate ratio (currently standing at  168 per 1000 live births ) by two-thirds between 1990 and 2015, (b) Reduction of the maternal mortality ratio (currently standing at  729 per 100,000 live births ) by three-quarters between 1990 and 2015, ( c) Halting and beginning to reverse    the incidence of HIV/AIDS(currently standing at  16 percent ), malaria  and other major diseases.

| Survey | Neo-natal Mortality | Post Neo-natal Mortality | Infant Mortality | Child Mortality | Under-five Mortality |
| --- | --- | --- | --- | --- | --- |
| ZZDHS 01-02 | 37 | 58 | 95 | 81 | 168 |
| ZZDHS 1996 | 35 | 74 | 109 | 98 | 197 |
| ZZDHS 1992 | 43 | 65 | 107 | 94 | 191 |
| SSA (2002)* |  |  | 106 |  | 174 |

Sources:  Zambia ZDHS, 2001-2002; *UNICEF State of the World’s Children, 2004.

The NHSP focuses on 12 national health priorities.  These priority areas include 7 public health interventions (namely Child Health & Nutrition, Integrated Reproductive Health, HIV/AIDS ,Tuberculosis, Malaria, Epidemics Control & Public Health Surveillance and Environmental Health and Food Safety, and 5 systemic interventions (namely Human Resources, Essential Drugs and Medical Supplies, Infrastructure and Equipment, Systems Strengthening and Health Systems Governance).  The systemic interventions represent support services which facilitate the efficient and effective management of the health sector, and without which implementation of the public health priorities would not be possible.  These priorities have been selected on the basis of the health related MDGs and other national health priorities.

The NHSP recognises key challenges which

severely limits the effectiveness of various health interventions and undermine the contribution of health care towards improving the health status of Zambians. The major challenges are:

- Huge Burden of Preventable Diseases

- Inadequate financing of the health sector.

- Inequitable distribution of the benefits of investment in health services

- Shortages of essential drugs and medical supplies

# Section 3: Situation Analysis / Needs Assessment

## 3.1: Recent health system assessments

| Title of the assessment | Participating agencies | Areas / themes covered | Dates |
| --- | --- | --- | --- |
| HMIS review | MOH, EU | To assess the relevance of the HMIS to the general M&E framework of the health sector, capacity to meet NDP and NHSP information needs, and identify critical information gaps to the NDP monitoring of the Health sector | Oct 2006 |
| National Health Strategic Plan 2001-2005, Mid Term Review | WHO, MOH, CBOH, UNICEF, DANIDA, SIDA | Assessing progress in the implementation of the NHSP, 2001-2005; and, | February 2004 |
| Assessment of system wide barriers to immunization | WHO, GAVI, MOH, CBOH, UNICEF | To identify system wide barriers that affect EPI and document good practices that work to reduce these system wide barriers to immunization | May 2004 |
| EPI Review | WHO, CBOH, MOH, HSSP | To assess performance of EPI programme in line with the 2000-2004 Multi Year Plan | February 2005 |
| Human Resource for Health strategic plan | GRZ /HSSP | To ensure an adequate and equitable distribution of appropriately skilled and motivated health workers providing quality services | 2005 |

## 3.2: Major barriers to improving immunisation coverage identified in recent assessments

- There is unacceptably high infant and child morbidity/mortality from preventable diseases in Zambia.

- Inadequate health centres and health posts especially in rural areas therefore equity of access for quality health care not adequately achieved by majority of children in Zambia.

- Most of our health facilities are in a dilapidated condition and the majorities are operating with obsolete equipment where available.  There are many areas in the country were people have to cover long distances to get access to health services.

- Improved child survival is threatened by limited coverage of effective interventions and inadequate resource investment.

- Inadequate  transport to carry out outreach services (health centres and health posts)

- Inadequate financing for outreach activities services.

- Seasonal and geographical barriers reduce access to outreach activities.

- Concern about wastage which reduces immunisation services.

- Batteries for solar panels expensive.

- Stock out during transition from DPT to DPT-Hib.

## 3.3: Barriers that are being adequately addressed with existing resources

- Inadequate health centres and health posts especially in rural areas therefore equity of access for quality health care not adequately achieved by majority of children in Zambia.

- Concern about wastage which reduces immunisation services.

## 3.4: Barriers not being adequately addressed that require additional support from GAVI HSS

- A key constraint to rapid scale-up of health services is the worsening human resource crisis in health. Over the past few years, the MOH has seen a massive exodus of health workers, especially nurses, to the domestic private sector and abroad, due primarily to the low level of wages and benefits in the civil service.

- Most of health facilities are in a dilapidated condition and the majority are operating with obsolete equipment where available.  There are many areas in the country were people have to cover long distances to get access to health services.

- Poor transport and communication systems rendered the outreach and referral system futile. This tended to overburden the lower levels of care and the afflicted families.

- Inadequate financing for outreach activities services.

- Seasonal and geographical barriers reduce access to outreach activities.

- Batteries for solar panels expensive.

- Improved child survival threatened by limited coverage of effective interventions and inadequate resource investment.

# Section 4: Goals and Objectives of GAVI HSS Support

## 4.1: Goals of GAVI HSS support

- Health workforce mobilization, distribution and motivation targeted at those engaged in immunization and other health services at the district level and below.

- Supply, distribution and maintenance systems for drugs, equipment and infrastructure  for primary health care:

## 4.2: Objectives of GAVI HSS Support

- Contribute to addressing the human resource for health crisis through strengthening of retention mechanisms for health workers and provision of incentives to community health workers.

- To increase the transport system of the health sector for effective distribution of   supplies and enhanced provision of EPI services

Backgro BACKGROUND Zambia, a land locked country in Southern Africa, consists of nine (9) provinces and seventy-two (72) districts. It has a population of 11.6 million (CSO projection) and an area of 752,612 square kilometres. Some provinces are very sparsely populated, a challenge in reaching the un-reached. Access to immunization outreach posts and sites is often hampered by the topographic characteristics of the areas. Parts of the Northern, Central, Eastern and Southern provinces are mountainous, and often require four-wheel-drive vehicles to reach remote rural villages. Meandering through the country are five big rivers and four in-land lakes leading to parts of Luapula, Southern, Western and Eastern provinces being swampy with many islands that experience seasonal floods from rivers that drain through them. Reliable boats and canoes are usually required to reach these communities that live on the islands and across the rivers for immunization and other health services. Since the mid-1990s Zambia has been implementing health sector reforms based on decentralization of responsibilities of health care delivery including immunization to the districts. The vision of the health reforms is providing equity of access to a cost effective quality health care as close to the family as possible. The health sector in Zambia is facing a critical shortage of human resources and increasing attrition of staff which is a major obstacle to improved service delivery. The crisis is particularly acute in rural areas where more than 50% of rural health centres have only one qualified staff member and numerous facilities are without any professional staff at all. This situation has been triggered by poor working conditions (health and housing facilities, transport, supplies and equipment) and inadequate remuneration (pay, allowances and incentives) in the civil service resulting in mass exodus of workers in search of greener pastures. This situation has been compounded by the HIV and AIDS crisis which is decimating health workers still in the most productive age group. The impact of the human resource crisis is that planned interventions are not being implemented effectively because there is not enough staff or suitably trained staff in the health facilities to provide the services. Staffing shortages have resulted in increased workloads, low motivation and morale, poor performance and low productivity levels, and deterioration in the quality of services and the overall performance of the health sector. Optimal provision of health services will require an adequate and equitable distribution of appropriately skilled and motivated health workers providing quality services through implementation of a performance improvement scheme. In order to resolve the crisis and address the key issues the Ministry of Health has developed Human Resources for Health Strategic Plan (HRHSP), in consultation with key stakeholders. The strategies and activities outlined in the plan attempt to address the concerns of all the stakeholders consulted and to provide a framework to guide and direct interventions, investments and decision making in the planning, management and development of human resources for health. The HRH Strategic plan sets out strategies and options for 2006 to 2010 to address the human resource crisis in the health sector, within the timeframe of the Fifth National Development Plan (FNDP) and the National Health Strategic Plan (NHSP) 2006-2010.The overall aim of the HRHSP is to ensure an adequate and equitable distribution of appropriately motivated, skilled health workers providing quality services. A substantial part of health services in Zambia are provided by community health workers (CHW). Zambia has adopted the Reaching Every District (RED) strategy to enhance high immunisation coverage. RED has five components out of which linking immunisation services to communities and re-vitalizing out reach services are some of the strategies that are being used to improve immunisation coverage. The RED strategy aims to involve the community in all aspects of immunization services (planning, implementation, monitoring and identifying eligible children in the community.). This will foster community ownership of the program, contribute to its viability and generate a spontaneous demand for immunization services when they are not available. Involvement of community leaders and the structures that are known (Neighbourhood Health Committee, NHC) and facilitate increased acceptance of all health services, including immunization. Training of community health workers (CHWs) or health promoters has been a focus of this component, promoting their involvement in demand creation, defaulter tracing and mobilizing community resources. Their knowledge of immunization has been updated and they have more actively used data and community networks to increase acceptance and use of services. However, challenges and areas for improvement have arisen in the utilisation of CHWs to enhance community health services. There is high community health workers attrition due to lack of incentives. Community health promoters generally expected some kind of compensation for their work. The absence of incentives or sustained support for their involvement has often resulted in high turnover or participation limited to only short-term activities (e.g. campaigns). Existing and well-established community structures or community-based organizations are underutilized for advocating for services, providing information to the public, or participating in outreach activities. These structures and organizations are engaged primarily only during campaigns and SIAs and are not brought into the routine system for longer-term involvement and support. Community health workers are part of human resources that provide health services and should therefore be motivated for them to keep on volunteering. This proposal seeks to apply for GAVI HSS funds that will enable Zambia implement part of the HRHSP 2006-2010 and provide incentives that will enable CHWs to keep on with their voluntarism. GAVI HSS funds will be designated to the addressing of the human resource crisis through retention schemes that attract and retain more trained health workers and support CHWs. The health workers that will be targeted are those at health service delivery level who provide basic health care package including immunisation. The predominant cadre that have been identified are nurses, environmental health technicians and clinical officers. The funds will support both static and outreach health services in districts that are remote and low performing. A number of districts have been identified as low performing in terms of EPI immunisation coverage and other indicators that include; high number of un-immunised children with measles, low DPT3 coverage and low full immunisation coverage. A criterion that takes into account all these indicators was used to pick the neediest district among the many districts that have low immunisation coverage. Each indicator was given a scores and a district was picked as low performing if it had a high total score of all indicators. The other parameters consideration for a district to benefit from the GAVI HSS fund were; a district with a dilapidated physical infrastructure (health centres, staff houses), No availability of clean water supply, no radio communication and poor access due to difficult topographic terrain.

Description Theme 1: Health workforce mobilization, distribution and motivation targeted at those engaged in immunization and other health services at the district level and below: Objective: Contribute to addressing the human resource for health crisis through provision of retention mechanisms for trained health workers and provision of incentives to community health workers by 2010. The health workers and community health workers will be motivated through the following mechanisms: Implementation of a performance improvement scheme. Provision of Communication facilities Provision of transport (including 4X4 motor vehicles, motor bikes, Boats and bicycles). Provision of energy (lighting) solar powered lighting systems ( health centres and staff houses) Renovation of housing units and health centres Provision of clean Water supply to health workers Implementation of a performance improvement scheme. Although improvements have been noted in child health, the constraints in achieving high impact include the inadequate coverage of effective child health interventions and the poor quality of services provided. The major reasons for this include the critical shortage of skilled staff, weak infrastructure, and inadequate funding for child health interventions. The challenge for the health sector is to scale-up child survival interventions, including immunisation, management of childhood infections, and management of the new born, nutrition promotion, and strengthening of school health programmes. While the amount of resources might be the single most important determinant of performance, the quest for money should not overshadow critical policy decisions about resource management. Numerous ‘systems support issues’ affect the performance of most implementing health institutions and include logistic and management systems for drugs and supplies, and functioning cold chains for vaccines. Efforts to improve health worker performance that are directly related to the health workers themselves fall roughly into two categories which are training and supervision. In-service training has too often kept workers away from their jobs for extended periods and has often been uncoordinated, vertical and/or not well prepared. Supervision is not always regular and not sufficiently supportive or skilled in specific clinical issues and this has led to health workers being de-motivated. Furthermore health workers have looked for assistance from their supervisors in solving problems related to workload, patient perception, referral and transport that are all important in expanding access to and utilization of needed MCH and RH services. In this proposal low performing districts have been identified and to enhance performance a scheme is proposed that rewards districts that have improved performance in health care that includes immunization. Prizes that include a floating trophy will be given annually to the best performing district among the 12 districts after the claimed improvement has been confirmed by an independent body. A trophy will be purchased and will be awarded as a floating trophy to a district that has had the highest immunization coverage at a ceremony to be graced by a dignified personality from the central level. This function will be publicized and it is hoped that this activity will show “hard work” appreciation of the recipient district and bring in the element of celebrating success which at the end of the day will motivate district management teams (DHMT). Other prizes that will be given annually include that of ‘’the prize of the most improved district’’ which takes in account of a district that has improved immunization coverage by 10%. Incentives in terms of another floating trophy will be given to such a district. Overall other levels of the health system will be accorded some form of incentives award in form of 12 shields to be given to the best health centre and 12 NHC in each of the 12 selected districts. For this activity US$20,000 from GAVI HSS will be set aside for this initiative. Area 2: Organisation and management of health services. Objective: To improve the implementation of health services at the health centre and community level through effective communication and community empowerment by 2008. 1. Communication – Radio, Cellular phones and Letter writing. The delivery of health services in districts requires a functional communication system at all levels. Communication is required among the CHWs and the health centre, health centre and the district health office for referral, consultations, logistics management, timely reporting and updates on emerging (current) issues. The modes of communication available in most districts are radios, land line telephones, cellular phones and sending information through writing of letters. Rural Health Centres in some districts are connected to a radio system that is linked to the District Health Office (DHO) and District Hospital This promotes rapid response to emergencies and solving administrative problems from the RHCs. This service also provides opportunities for feedback on data to and from the RHCs. At a community level no systematic mode of communication has been put in place but most often CHWs communicate with the health centres through writing of letters. Letters are used for referral of patients from community health post to the RHC and for information sharing between the health workers at the health centres and the community health workers. These letters are usually transported to and from the health facility by hand using emissaries. It is important therefore that when planning for community communication a budget line of stationery should be considered. A number of districts that have been identified to benefit from the GAVI HSS fund have communication problems and need radios communication for the enhancement of health services. In some districts there is no radio communication facility and yet are accessible to cellular network. In such district 50% of the health centres will be accorded the facility of cell phone for effective communication. In this proposal it is therefore suggested that GAVI fund be used to acquire 120 radios, 83 handsets of cellular phones and stationery provided to 5 NHCs in the 12 districts 5 years at US$129,255. The total amount of GAVI HSS fund to be used on communication will be US$675,480 for the five year period. 2. Performance based incentive grants to the Neighbourhood Health Committees. Many of the activities included in child heath and nutrition require significant amounts of staff time to educate the community. Current staffing levels and staff competencies are inadequate to carry out sufficient health promotion and disease prevention activities. Community Health Workers (CHWs) have successfully been used to identify and treat childhood diseases in their communities. It would appear that Zambia is making limited use of these resources and that there is high turnover of the personnel trained. Given the geographical distances of some communities to health facilities, CHWs represent a valuable and indispensable resource and need innovative ways to engage and retain them. Community-based health care has been strengthened in past years through the Community Health Innovation Fund (CHIF), which was created in 1996. One of its aims has been to support the participation and empowerment of local neighbourhoods in planning and implementation of health care services, through the establishment of Committees at the level of neighbourhoods, Health Centres and Districts. However, these committees function with major shortcomings. Under RED strategy community involvement and demand creation from the community is cardinal for a versatile immunisation program. The linkage between the health centre and the community is through NHCs and CBAs. It is proposed that some of the funds from GAVI HSS be used to motivate the NHCs and CBAs through support of Income Generating Activities (IGAs) in the communities. The way this will function is through provision of community grants to NHCs. All NHCs will be encouraged to write project proposal for projects that are beneficial to communities that they serve. The projects to be originated by the NHC should be viable and provide a way of income generating (IGA) for that NHC. The proposal will be reviewed by a committee of experts constituted at the DHO. A revolving grant of 1000 USD will be put in place in each of the 12 districts and be disbursed to a successful NHC. IGA projects that range from chicken rearing, grinding mill, fish rearing, piggery, goat rearing and vegetable growing projects will be encouraged for community fund raising. The funds raised will be used by the NHC to benefit the local community and include provision of perks as incentives to CHW. These perks will be given to the CHW depending on how much money the IGA is able to raise. The provision of perks to CHW will motivate them and help retain them. To manage this business oriented IGA projects, capacity building on project management will have to be conducted for the NHC members. It is proposed that to start these IGAs in various communities in all the 12 selected districts a revolving fund of 24,000 USD will be set aside meaning each district would have a start up grant of 2,000 USD. Area 3: Supply, distribution and maintenance systems for drugs, equipment and infrastructure for primary health care: Objective: To increase the transport system of the health sector for effective distribution of drugs and supplies, enhanced provision of health services including EPI through effective referral and supportive supervision.. Access to basic health services shows a wide spatial variation with provinces closer to the ‘line of rail’ having better access to services. In urban areas, 99 percent of households are within 5km of a health facility while it is only 50 percent of households who are within 5km of a health facility in rural areas. In FNDP, the priority is to make available at least one first level hospital in each district, which would operate as a referral hospital to a satellite of health centres. To provide good health services in rural areas transport like communication is essential for outreach, referral, supportive supervision and distribution of logistics and supplies. In most RHC’s outreach sessions to provide child health services that include immunisations are not carried out due to lack of transport. The referral of critically ill patients is also affected by lack of transport. To ensure a smooth running health care the district health office has a critical role of providing supportive supervision to improve the quality of service delivery. The System Wide Barriers Assessment to immunisation cited inadequate supervision of health workers due to non-availability of appropriate transport and financial resources. 1. Transport management It is therefore important that the provision of motor bikes, 4x4 motor vehicles and water transport for the health system be made a priority to enable health workers to conduct outreach services, carry out effective referrals and to move equipment and supplies that include vaccines. When transport is provided to the district supportive supervision, cold chain maintenance and repair will also be made possible. Mobility in rural areas is difficult and makes work for health workers difficult. The provision of motor bikes to health worker for conducting outreach services will make available some form of transport that will make them mobile and be able to attend to some of their personal needs. This facility will act as motivator for the health workers and will in turn contribute to their being retained in rural areas where their services is required. The other form of transport that is important in the running of health services in rural areas of Zambia is use of bicycles. Bicycles when given to the CHWs will enable them to run around and carry out community health services that include social mobilisation. In the implementation of GAVI HSS activities it is suggested that CHW will be provided with bicycle that they will use for a period of five year at the end of which the bicycles will be surrendered to them as end of project benefits. The gesture of provision and surrendering of these bicycles to CHWs will motivate them and probably reduce on the high attrition rate. In total twelve (12), 4x4 motor vehicles, 4 speed boats, 215 motor bikes for health centres and 1000 bicycles will be acquired through GAVI HSS funds. All this transport will be used to increase health services that include EPI. The Zambia c-MYP (2006-2010) shows a short fall US$2,620,517 in the financing of transport costs for EPI. Zambia therefore seeks the assistance of GAVI secretariat to provide funds that will support health services support trough the procurement of motor vehicles, motor bikes, boats and bicycles. US$1,520,000 is being requested from GAVI HSS to address the identified gap in transport needs for the period 2006 to 2010. 2. Infrastructure development (renovation of health centres and staff housing units) According to the MoH mid term 2001-5 National health strategic plan (NHSP) assessment, by the year 2000, the deterioration of health infrastructure and equipment had reached a stage where urgent repairs and replacements were required if the health facilities were still to function effectively. Various reasons had contributed to this state of affairs, including: lack of financial resources, little use of existing capital-funding programmes; an emphasis on an expansion of the network rather than on the rehabilitation of the existing facilities; inadequate mobilization of community resources; lack of a preventive maintenance policy (and guidelines); and, lack of skilled staff for preventive and corrective maintenance. However, a ‘national framework’ for preventive maintenance has been launched. It was also observed that Co-operating Partners (CPs), as a group, commit proportionally little to infrastructure and equipment repairs and development. In the same document there were revelations that CBoH and MoH did not have a capital investment and procurement plan covering the NHSP period, which lists rehabilitation and construction works to health centres and housing. In 2005/6 JICA carried out a survey (JICA HFC) of all health infrastructure in the country and has come up with a data base. According to this data base a number of infrastructure are in a state of disrepair and need urgent repair works. The original design of health centres included the provision of three staff houses. Some of these structures (health centres and staff houses) are very old and as has been mentioned before are in dire need of rehabilitation and maintenance. Renovating these structures will result in creating a good living environment for the health workers who will in turn be motivated. It is proposed that US$2,396,138 from the GAVI fund will be used for this purpose. The renovation and installation of solar power in these staff housing units will benefit 234 health workers who will be motivated and probably be retained to work and provide health services in the rural areas of Zambia. 3. Solar powered lighting systems( health centres and staff houses) One of the many reasons why health workers do not want to work in rural area is the poor working conditions. They are subjected to poor housing units’ accommodation and work in health centres that do not have lighting. Many health facilities in Zambia are not connected to the National Grid (electric power) due to the high capital cost involved to have them connected to hydro power. Health workers therefore face a lot of challenges in providing emergency health services at night under candle light or lamps which provide poor lighting with sub optimal visibility. Further more health workers in rural areas do not have lighting in their housing units, a situation that makes them unable to use some electrical appliances like radios or engage in further studies using long distance studies. They are unable to study at night due to poor lighting in their housing units. In these health centres paraffin fridges are used for cold chain. Paraffin supplies to rural areas are usually erratic leading to disruption in health services and unproductive evenings for the heath workers. This state of affairs de-motivates health workers and as a result few of them voluntarily work in rural health centres. Solar power can be provided to both the health centre and housing units at a low cost because as a country, Zambia is endowed with abundant sun shine all year round which could be used as solar power for lighting of health centre and housing units. When this is put in place health workers would be able to use some domestic electrical appliances such as radio sets and use the solar power to light up their living quarters at night. It is with this fact that the supply of solar powered energy source in RHC be installed to make life less challenging for health workers. The solar power will involve installation of direct current power supply at selected health centres and staff housing units to provide lighting and activate cold chain equipment in the affected health centres. The health workers will be able to attend to emergencies at night leading to an improved quality of health service delivery and this will enhance cold chain for EPI. Solar power provides an enabling environment for the health worker be able to read news papers, magazines and academic materials which goes a along way in updating their knowledge. When solar power is provided this will motivate health workers and make them stay in rural areas and provide health services. It is with this in mind that the country is applying for US$1,291,500 GAVI funds to install solar power in 92 health centres and 234 housing units for the health workers. 4. Improved water supply: Most RHC have no clean water or inadequate water supply which has resulted in poor sanitation. Clean safe water supply is essential for the function of the health centre and staff and the communities living in the neighbourhoods of the health centres. In the past health centres were constructed with no provision of water supply (JICA HFC). Therefore addressing the provision of clean safe water supply to both health centres and staff is critical. The provision of clean water supply will improve the living condition of these health workers and more likely motivate them and make them work in rural areas. Clean water supply will be provided through the sinking of boreholes at the health centres. This activity will result in GAVI HSS providing 122 boreholes at a cost of USD 671, 000 to various health centres. In total $6,604,638 from GAVI for Health Systems Strengthening is being sought from GAVI HSS and this figure will be utilised to for activities for the period 2006-2010 and help retain 234 health workers whose houses will have been renovated and solar lighting installed. The transport situation on the selected districts will be improved as 215 motor bikes and 12 motor vehicles will be made available. Community health workers will be motivated to provide services through the income generation activities that will be commenced. Improved life style will be a result of provision of clean water to a good number of health workers through the sinking of 122 bore holes. Districts selected for GAVI HSS support in this proposal are as follows: Eastern Province: Chama, Chipata, Lundazi and Petauke Luapula Province: Mwense and Samfya Northern Province: Kaputa and Nakonde Western Province: Kalabo, Lukulu and Sesheke Copperbelt Province: Lufwanyama These requirements were arrived at from the Ministry of Health data base of the Health Facility Census that was conducted in 2005 and took stock of the state, at each health facility, of water supply, power source, availability of transport, human resource, infrastructure in terms of health facility and staff houses. Infrastructure proposed for rehabilitation is those that were poor rated both staff houses and health facilities. Health facilities earmarked for the different support items were selected on the basis of lack of availability of the utility or poor state at the facility. Below is a table showing the summary of requirement for each district. Summary of District Requirements The table below shows the summary of requirements for the 12 selected districts for health system strengthening. It was recognised that the greatest area of need was water supply and transport for outreach activities which the country proposes will be supported in the first year. Also to be considered in the same period we propose the support of income generation activities to increase the human resource available both at health facilities and communities carrying out EPI activities. It further proposed that in the second year radio communication and transport for the district health office be addressed. In the third year rehabilitation works for health facilities and staff houses to be followed in the last year by improved lighting.

| District | Chama | Chipata | Lundazi | Petauke | Mwense | Samfya | Kaputa | Nakonde | Lufwanyama | Kalabo | Lukulu | Sesheke | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Performance Improvement HC-shields | 19 | 32 | 23 | 26 | 21 | 27 | 6 | 6 | 8 | 16 | 9 | 17 | 210 |
| Perf. Impro. DHO- floating trophies |  |  |  |  |  |  |  |  |  |  |  |  | 2 |
| Radio com | 9 | 1 | 13 | 13 | 20 | 26 | 3 | 0 | 9 | 7 | 6 | 13 | 120 |
| Mobile phone | 10 | 10 | 10 | 9 | 8 | 8 | 3 | 4 | 4 | 5 | 4 | 8 | 83 |
| Stationery Pack | 469 | 675 | 650 | 625 | 450 | 600 | 150 | 175 | 80 | 450 | 250 | 350 | 4924 |
| M/ Bikes | 19 | 35 | 26 | 25 | 20 | 24 | 8 | 8 | 4 | 18 | 12 | 1 | 200 |
| Boats | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 4 |
| 4x4 M vehicles | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 |
| Bore holes | 11 | 6 | 8 | 11 | 14 | 24 | 3 | 4 | 6 | 15 | 10 | 10 | 122 |
| Bicycles | 95 | 130 | 130 | 125 | 80 | 120 | 30 | 40 | 20 | 90 | 60 | 80 | 1000 |
| Solar HC | 10 | 11 | 10 | 11 | 13 | 17 | 1 | 1 | 6 | 4 | 3 | 5 | 92 |
| Solar Staff | 21 | 33 | 22 | 28 | 30 | 40 | 5 | 2 | 15 | 13 | 10 | 15 | 234 |
| Rehab. HC | 5 | 11 | 7 | 7 | 16 | 8 | 5 | 1 | 8 | 3 | 3 | 5 | 79 |
| Rehab. Staff units | 14 | 15 | 5 | 10 | 11 | 19 | 6 | 4 | 8 | 10 | 6 | 10 | 118 |
| IGA grants | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 |

# Section 6: Monitoring, Evaluation and Operational Research

## 6.1: Impact and Outcome Indicators

| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National DTP3 coverage (%) | HMIS, DHS, IDSR | 91 | JRF | 2005 | 95 | 2010 |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | HMIS, DHS, IDSR | 58 | JRF | 2005 | 65 | 2010 |
| 3. Under five mortality rate (per 1000) | HMIS, DHS, IDSR | 168 | JRF | 2005 | 134 | 2010 |
| 4. National measles coverage | HMIS, DHS, IDSR | 79 | JRF | 2005 | 90 | 2010 |
| 5. Vitamin A supplementation rate | HMIS, DHS | 72 | JRF | 2005 | 80 | 2010 |
| 6. Antenatal care 2nd attendance | HMIS, DHS, IDSR |  | JRF | 2005 |  | 2010 |

## 6.2: Output Indicators

| Indicator | Numerator | Denominator | Data Source | Baseline Value4 | Source | Date of Baseline | Target | Date for Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Boreholes | HCs with new boreholes | Total number of HCs | MoH Annual Reports/PA Reports |  | Health Facility Census | 2005 | 122 boreholes | 2008 |
| Radio Communication | HCs with new radio equipment | Total number of HCs | MoH Annual Reports/PA Reports |  | Health Facility Census | 2005 | 120 radios | 2008 |
| Motor bikes | # of motor bikes procured | # of HCs being supported | MoH Annual Reports/PA Reports |  | Health Facility Census | 2005 | 215 bikes | 2009 |
| NHC performance incentive grants | # of approved NHC proposals | # of selected Districts | MoH Annual Reports/PA Reports |  | No baseline | N/A | 12 districts | 2008 |
| Motor vehicles for DHOs | # of motor vehicles procured | # of district being supported | MoH Annual Reports/PA Reports |  | Health Facility Census | 2005 | 12 | 2009 |
| Staff houses | # renovated | Total # of staff houses from selected HCs | MoH Annual Reports/PA Reports |  | Health Facility Census | 2005 | 234 | 2010 |

6.3: Data collection, analysis and use

| Indicator | Data collection | Data analysis | Use of data |
| --- | --- | --- | --- |
| Impact and outcome |  |  |  |
| 1. National DTP3 coverage (%) | HMIS | Routinely done by Management information | Used in planning & decision making |
| 2. Number / % of districts achieving ≥80% DTP3 coverage | HMIS | Routinely done by Management information | Used in planning & decision making |
| 3. Under five mortality rate (per 1000) | DHS | Analysis through CSO | Used in planning & decision making |
| 4. National measles coverage | HMIS | Routinely done by Management information | Used in planning & decision making |
| 5. Vitamin A supplementation rate | HMIS | Routinely done by Management information | Used in planning & decision making |
| 6. Antenatal care 2nd attendance | HMIS | Routinely done by Management information | Used in planning & decision making |
| Output |  |  |  |
| Boreholes | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |
| Radio Communication | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |
| Motor bikes | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |
| NHC performance incentive grants | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |
| Motor vehicles for DHOs | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |
| Staff houses | Performance Assessment | Analysis & report writing by the PHO | Used in planning & decision making |

## 6.4: Strengthening M&E system

The European Union is supporting the Ministry of Health to revise and strengthen the Health Management Information System (HMIS) with a view to increasing its capacity to meet the information needs of the National Development plan and the National Health strategic plan.

## 6.5: Operational Research

There is need to undertake operational research on utilization of grants and the impact of the grants health worker morale.

# Section 7: Implementation Arrangements

## 7.1: Management of GAVI HSS support

| Management mechanism | Description |
| --- | --- |
| Name of lead individual / unit responsible for managing GAVI HSS implementation / M&E etc. | Mr Kansembe /Planning unit |
| Role of HSCC (or equivalent) in implementation of GAVI HSS and M&E | Review all the implementation progress reports and sanction action plan ,timeline and budgets for GAVI HSS |
| Mechanism for coordinating GAVI HSS with other system activities and programs |  |

## 7.2: Roles and responsibilities of key partners (HSCC members and others)

| Title / Post | Organisation | SAG yes/no | Roles and responsibilities of this partner in the GAVI HSS application development |
| --- | --- | --- | --- |
| Director Planning | Ministry of Health | YES | Oversight and strategic guidance |
| Director – Public Health | Ministry of Health | YES | Technical & Strategic Guidance |
| Immunisation officer | World Health Organisation. | YES | Technical Support |
| Chief – Health Section | United Nations Children’s Emergency Fund | YES | Technical Support |
| Assistant Program Officer | Japan International Cooperation Agency. | YES | Technical Support |
| President | Rotary International | YES | Comments & Consensus |
| Chief of Party | Health Systems Support Program | YES | Technical Support |
|  | USAID | YES | Technical Support |
| Health Desk Officer | Ministry of Finance and National Planning | YES | National Strategic Guidance |
| Director of Programs | Churches Health Association of Zambia | YES | Comments & Consensus |

## 7.3: Financial management of GAVI HSS support

| Mechanism / procedure | Description |
| --- | --- |
| Mechanism for channelling GAVI HSS funds into the country | Through the existing GAVI channel for ISS account |
| Mechanism for channelling GAVI HSS funds from central level to the periphery | Through the existing MoH channel to the basket |
| Mechanism (and responsibility) for budget use and approval | Through the existing MoH mechanism by the Permanent Secretary of Health |
| Mechanism for disbursement of GAVI HSS funds | Through the MoH channel to the basket |
| Auditing procedures | By the MoH internal auditing system and government Auditor General’s office |

## 7.4: Procurement mechanisms

- By the MoH tender committee that scrutinises procedures of procurement

## 7.5: Reporting arrangements

The ICC has chosen to monitor the implementation of GAVI project using DPT3 coverage; drop out rates; supply of vaccines and AD syringes at facility level; and sentinel disease surveillance for Haemophilus influenzae type b. A Mid Term/EPI Review and an End of Term Evaluation will be conducted to monitor the progress of implementation and assess the impact of new vaccines.

The basket fund is managed through the MoH in consultation with the Health Sector Steering Committee.  The committee holds quarterly meetings to review progress on action plans, accounting/ financial reports from the Ministry of Health, and review the financial flow.  The MoH distributed summary financial statements, covering disbursements and actual expenditure from source of funding and item according to each level and cost-centre, together with cost-centre performance appraisals.

## 7.6: Technical assistance requirements

| Activities requiring technical assistance | Anticipated duration | Anticipated timing (year, quarter) | Anticipated source (local, partner etc.) |
| --- | --- | --- | --- |
| 1. Designing a SME/IGA for NHCs | 6 months | quarter | local |
| 2.Mid term review of GAVI HSS implementation | 2 months | quarter | International |
| 3. |  |  |  |
| 4. |  |  |  |

# Section 8: Costs and Funding for GAVI HSS

## 8.1: Cost of implementing GAVI HSS activities

| Activities | 2007 | 2007 | 2008 | 2009 | 2010 | 2011 | Total Costs |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Yr of GAVI application | Implementation |  |
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |
| Objective 1: Contribute to addressing the HR for health crisis through strengthening of retention mechanisms for health workers and provision of incentives to community health workers by 2010. |
| Activity 1.1 Support for Health facilities & staff |
| Boreholes |  | 671,000 |  |  |  |  | 671,000 |
| Radio Communication |  | 540,000 |  |  |  |  | 540,000 |
| Motor bikes |  | 860,000 |  |  |  |  | 860,000 |
| Activity 1.3: Implementation of a performance improvement scheme. |
| District Trophies |  |  | 250 |  |  |  | 250 |
| health centre Shields |  |  | 26,250 |  |  |  | 26,250 |
| Objective 2: To improve the implementation of health services at the health centre and community level through effective communication and community empowerment by 2008. |
| Activity 2.1: Communication – Radio, Cellular phones and Letter writing. |
| Mobile phones |  |  | 6,225 |  |  |  | 6,225 |
| Activity 2.2 Support for community based agents |
| NHC performance incentive grants |  | 24,000 |  |  |  |  | 24,000 |
| Bicycles for community health workers |  | 120,000 |  |  |  |  | 120,000 |
| Stationery for Communication at NHC level |  | 129,255 |  |  |  |  | 129,255 |
| Objective 3: To increase the transport system of the health sector for effective distribution of drugs and supplies, enhanced provision of health services including EPI through effective referral and supportive supervision.. |
| Activity 3.1: Provision of motor bikes, 4x4 motor vehicles and water transport for the health system and personal to holder bicycles. |
| Motor vehicles for DHOs |  |  | 420,000 |  |  |  | 420,000 |
| Water transport |  |  | 120,000 |  |  |  | 120,000 |
| Activity 3.2: Infrastructure development |
| Staff houses |  |  |  | 590,000 |  |  | 590,000 |
| Health centre renovation |  |  |  | 1,806,138 |  |  | 1,806,138 |
| Solar –Health Centre |  |  |  |  | 414,000 |  | 414,000 |
| Solar –Staff houses |  |  |  |  | 877,500 |  | 877,500 |
| Total |  |  |  |  |  |  | 6,604,618 |

## 8.2: Calculation of GAVI HSS country allocation

| GAVI HSS Allocation | Allocation per year (US$) |
| --- | --- |
|  | Yr of GAVI application | Implementation | TOTAL FUNDS |
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |
|  | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |  |
| Birth cohort | 636,140 | 651,977 | 668,346 | 685,264 | 702,753 | 720,831 |  |
| Allocation per newborn | $2.5 | $2.5 | $2.5 | $2.5 | $2.5 | $2.5 |  |
| Annual allocation |  | 1,629,943 | 1,670,865 | 1,713,160 | 1,756,883 | 1,802,078 | 8,572,928 |

Source and date of GNI and birth cohort information:

GNI:	US $ 490 (SOWC, 2007)Birth cohort:	GAVI progress report (2005)

Other:

## 8.3: Sources of all expected funding for health systems strengthening activities

| Funding Sources | Allocation per year (US$) |
| --- | --- |
|  | Yr of GAVI application | Implementation | TOTAL FUNDS |
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |
|  | 2007 | 2007 | 2008 | 2009 | 2010 | 2011 |  |
| GAVI HSS |  | 2,344,255 | 572,725 | 2,396,138 | 1,291,500 |  | 6,604,618 |
| Govt |  | 14,722,806 | 15,431,069 | 18,112,136 | 19,923,350 | 21,915,685 | 90,105,046 |
| EU |  | 1,500,000 | 1,500,000 |  |  |  | 3,000,000 |
| SIDA |  | 267,000 | 267,000 | 267,000 | 267,000 | 267,000 | 1,335,000 |
| TOTAL FUNDING |  | 18,567,061 | 17,503,794 | 20,508,274 | 21,214,850 | 21,915,685 | 99,709,664 |

Source of information on funding sources:

Government:	Medium Term Expenditure Framework( Ministry of Finance, Planning and National Development)

EU:	Poverty Reduction Budget Support Financing Agreement

SIDA:	Memorandum of Understanding between the Government of Zambia & SWAp Partners

Section 9: Endorsement of the Application

## 9.1: Government endorsement

The Government of REPUBLIC OF ZAMBIA commits itself to providing immunisation and other child and maternal health services on a sustainable basis. Performance on strengthening health systems will be reviewed annually through a transparent monitoring system. The Government requests that the GAVI Alliance funding partners contribute financial assistance to support the strengthening of health systems as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Name: Hon. Brig. Gen. Dr Brian Chituwo, MP | Name: Hon. Ng’andu Magande, MP |
| Title / Post: Hon. Minister of Health | Title / Post: Hon. Minister of Health |
| Signature:.............................. | Signature:............................ |
| Date:...................................... | Date:.................................... |

## 9.2: Endorsement by Health Sector Coordination Committee (HSCC) or country equivalent

Members of the Health Sector Coordination Committee or equivalent endorsed this application at a meeting on …………………………………... ………...The signed minutes are attached as Annex 1.

| Chair of HSCC (or equivalent): |  |
| --- | --- |
| Name: Dr S.K. Miti | Post / Organisation: Ministry of Health |
| Signature:................................ | Date:........................................ |

9.3: Person to contact in case of enquiries:

Name: Dr. S.K. Miti  	Title: 		Permanent Secretary

Tel No: +260 1 25 30 40 -	Address: 	P.O. Box 30205, Lusaka

ZAMBIA

Fax No.+260 1 253344

Email:

# ANNEX 1 Documents Submitted in Support of the GAVI HSS Application

| Document (with equivalent name used in-country) | Available (Yes/No) | Duration | Attachment Number |
| --- | --- | --- | --- |
| National Health Sector Strategic Plan (or equivalent) | √ | 2006 -2010 |  |
| cMYP | √ | 2006 -2010 |  |
| MTEF | √ | 2006 - 2009 |  |
| PRSP8 | N/A |  |  |
| Recent Health Sector Assessment documents | √ | 2004 |  |
| HSCC minutes, signed by Chair of HSCC | TO BE SENT | March -April 2007 |  |
| Human Resource Strategic Plan | √ | 2006 - 2010 |  |

# Footnotes

Minutes from HSCC meetings related to HSS should be attached as supporting documentation, together with the minutes of the HSCC meeting when the application was endorsed. The minutes should be signed by the HSCC Chair. The minutes of the meeting endorsing this GAVI HSS application should be signed by all members of the HSCC.

If the application identifies activities that are to be undertaken at a sub-national level, sub-national data will need to be provided where it is available. This will be in addition to the national data requested.

Within the last 3 years.

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

Indicative estimate for 2010 and 2011

EU support towards strengthening HMIS

SIDA Towards the HR Strategic Plan

If available – and if not, the National Immunisation Plan plus Financial Sustainability Plan

if available please forward the pages relevant to Health Systems Strengthening and this GAVI HSS application

# Text boxes

Figure 1: Zambia – Population Density by District