January 2005 (revised)

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: GEORGIA

Date of submission: 15 .05.2006…………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

Having applied to the GAVI/Vaccine Fund Support in October 2001 the Government of Georgia (GoG) has received approval for all three sub-accounts of the application (Ref.: GAVI/01/199/jd dated 10.12.2001), specifically:

- 16,604.65 USD has been approved as the 2nd instalment disbursed for the Immunization Service Support (ISS) sub-account in 2003. No additional funds have been received in 2005.

- Hep B vaccine supply support for 2005 national immunization programme (160,080  doses of HepB, 178,400 AD syringes and 1,400 5 ml safety boxes) was received on 21.06.05 & 05.09.05.

- Financial support for the 3rd sub-account - 20,800 USD was issued to the Government of Georgia in March 2003. The funds are planned to be utilised for ensuring sustainability of injection safety supplies and improvement of injection and waste management practices within NIP for 2006 and beyond. The country was not eligible for additional disbursements or supply assistance within the 3rd sub-account in 2005.

Implementation of the plans approved by ICC for ISS and New and Under-used Vaccine sub-accounts started in 2003. Details of the fund utilization and performance are provided in sections 1.1, 1.2 and 1.3.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

As per 2005 annual progress report total funds available for the ISS comprised 51,000 USD (17,000 USD from 2nd trench in March 2003 & 34,000 USD received in 2004) the amount of 17,000 USD) . The second trench of of 17,000 USD received in 2003 (deducted to 16,604.65 USD due to exchange rate) was issued as premial funds of the primary health care providers engaged in NIP throughout the country. The decision was made by ICC and funds disbursed to 66 district public health care centres countrywide. Overall 191 public health managers responsible for logistics, monitoring & evaluation & reporting for the national immunization programme have benefited form the premium funds. The incentive payment for immunization staff served to improve the motivation of the pubic health staff for maintaining and further improving the NIP management. The payments as in 2003 will be accompanied by introductory note from the MLMHSA re: source and purpose of the financial support, thereby increasing the awareness of the front-line workers on the assistance Global Alliance is providing to the Government of Georgia The 34,000 USD funds received in 2004 has been distributed as follows: 1. 7,655.49USD for renovation of the national vaccine store & cold-chain department at the National Centre for Disease Control & Medical Statistics. 2. 5,854.05 USD for procurement of a 4xw vehicle for one of the most vulnerable and hard to reach region (Racha-Lechkhumi PH Regional Centre) affected by severe floods emergency in April-May 2005. Due to the floods emergency with subsequent landslides & mobility restrictions, the immunization programme ioperation has been disrupted in the region. The ICC has made a decision for the emergency response to immunization programme continuation in the region. 3. 5364.81 USD - Miscellaneous services covered within the NIP management: 3.1. Translation of WHO modules “Immunization in Practice’’ – 1,336.40 USD. 50 courses of “Immunization in Practice’’ training co-funded by UNICEF Georgia. 3.2. Telephone communication for the immunization department, NCDCMS - 193.41 USD 3.3. Procurement of the IT equipment (2 notebooks, 3 USB) for the immunization department at NCDC - 4835 USD Remaining funds for FY 2006: 14,521.00 USD

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005         - 0-

Remaining funds (carry over) from 2004 ____51.000

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0 |  |  |  |  |
| Injection supplies | 0 |  |  |  |  |
| Personnel | 16,60465** | 4,358.64 (26%) ** | 0 | 12,246.01 (74%)** | 0 |
| Transportation | 0 |  |  |  |  |
| Maintenance and overheads | 7,655.49 | 7,655.49 |  |  |  |
| Training | 0 |  |  |  |  |
| IEC / social mobilization | 0 |  |  |  |  |
| Outreach | 0 |  |  |  |  |
| Supervision | 0 |  |  |  |  |
| Monitoring and evaluation | 0 |  |  |  |  |
| Epidemiological surveillance | 0 |  |  |  |  |
| Vehicles | 5,854.05 |  | 5,854.05 |  |  |
| Cold chain equipment | 0 |  |  |  |  |
| Other … (specify) 1) Translation services 2) IT equipment 3) Tele-communication cost | 1)1,336.40 2) 4,835 3) 193.41 | 1,336.40 4835 193.41 |  |  |  |
| Total: | 36,479.00 | 18,378.94 | 5,854.05 | 12,246.01 |  |
| Remaining funds for next year: | 14521.00 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

** Expenditure in 2005 – premium funds for the health care workers distributed at central and 66 district levels (public health centres) countrywide.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed. Attached please find the ICC minutes #3.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

In 2005 the country has witnessed improvements in the national immunization programme performance reflected in increased time-appropriate NIP coverage vs. 2004 data, specifically, antigen-specific age-appropriate (timely) coverage for 2005 has comprised: BCG - 95%, DPT 3 – 82% OPV3 – 81.5% Measles (MCV1 within MMR) – 91.6% HepB 3 – 72% However as Georgia is still missing out from the global & national tarets of >90% NIP coverage for every vaccines countrywide, the Government is prioritizing to address the gaps in timely vaccination coverage through strengthened advocacy and communication. The country is still struggling to overcome the continued delays in start of the age-appropriate vaccination series. Despite the fact that over 90% of children do receive the 9 NIP antigens up to age of 2 years, under-12 month coverage against DPT3 (82%) and OPV3 (81,5%) remains a challenge. The major factor impeding timely completion of the vaccination is the fear of parents and health care providers stemming from the negative media publicity of suspected AEFI cases from Hep B in 2002, MMR and VPP in 2004. 2. As noted HepB-3 timely vaccination has increased from 63.7% in 2004 to 72% in 2005. The achievement is conditioned by the continuous IEC and national staff capacity building for changing attitudes to the newly introduced vaccines, though negative publicity from 2002 AEFI was renewed in 2004 due to the media coverage of the court trial of the 2002 suspected AEFI. The Supreme Court of Georgia obliged the Ministry of Labour, Health & Social Affairs to pay life-time Pension fund & a compensation of 60,000 GEL (est. 33,000 USD) to the affected child. The latter has affected coverage of HepB as well as other NIP antigens. In 2005 in order to address the negative publicity & re-gain public trust, ICC intensified efforts for IEC. TV-talk-shows has been arranged for NIP, the First Lady (with the newborn child) has been actively involved in immunization communication, UNICEF has supported development of a COMBI plan (communication for behaviour impact) focusing on improvement of timely immunization coverage. The COMBI plan implementation will be launched in June 2006. 3. In 2005 VRF has supported implementation of the “Adolescent Immunization Campaign” among 13-14 years age group. Coverage rate comprised 93,5%. 4. 50 2-day “Immunization in Practice” trainings for 1200 PHC workers (27 trainings in 2005, and 23 in 2006) has been supported by UNICEF country office, The training is based on up-to-date WHO ICC methodology. 5. 11 training sessions on AEFI has been supported by WHO for 220 PHC managers countrywide. 6. In 2005 UNICEF has supported monitoring and 1-day training sessions for HepB and BCG vaccination among all maternity hospitals (89 total). The performance was evaluated for the periods 2004 & Jan-Jun 2005. The monitoring has provided proven evidence & underlying factors for the differences between the vaccination coverage of HepB birth dose (75%) and BCG (91%) administered at the maternity hospital levels. The findings have demonstrated persistent resistance & fear of health care providers and parents to HepB vaccination. The ICC has prioritized continuous training & advocacy among the maternity hospital staff and managers.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

UNICEF in 2005 has supported implementation of MICS2 (Multiple Indicator Cluster Survey 2). The survey data is under processing and the final report is expected to be available by September 2006.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH… September YEAR…2002…………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Georgia received the Hepatitis B vaccine and matching quantities of injection supplies in 03.11.2004. The assistance included 160 080 doses of HepB vaccines, 178,400 AD syringes and 1,400 safety boxes for the 2nd sub-account. General condition of the vaccine and injection safety supplies received by NIP through GAVI/VF assistance was good.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

As noted in the ISS section, the 2002 suspected AEFI case for HepB vaccination & publicity of the Supreme Court trial obliging the Government to cover 60,000 GEL (33,000 USDD) compensation costs & life-time pension fund to the affected child, has substantially affected the HepB vaccination scale-up. Despite the challenge the Government has managed to retain the progressively increasing trend of the HepB vaccination coverage and reaching 73,5% HepB 3 coverage in 2005 vs. 63.7% in 2004. Continuous in-service training of NIP workers countrywide – 1,200 health care providers trained on immunization-in-practice methodology Training of 89 maternity hospital staff throughout the country on immunization-in-practice. The training has been complemented by monitoring the BCG & HepB 1 coverage & analysis of the key bottlenecks. Training of 220 PHD workers countrywide on AEFI management supported by WHO; Media advocacy & communication through supporting special talk-shows on child vaccination & engagement of the First Lady in the communication through publicizing the immunization visits of the newly born child. For 2006 the following activities have been prioritized by ICC: Implementation of the COMBI (communication for behaviour impact plan) for immunization focusing on promotion of the age-appropriate immunization coverage on basic antigens. The 1-year plan to be launched in June 2006 envisages a wide scope of advocacy, media & inter-personal communication for improving the NIP performance. A series of child health programme will be continued through USAID & UNICEF support in 2006, covering 2 sessions on immunization. Along with MICS survey, UNICEF and WHO will be supporting a comprehensive evaluation of the national immunization programme to be translated in the renewed strategy and multi-year plan of action for the child vaccination programme in Georgia. The evaluation will be commissions in July-Sept 2006 period, covering conflict affected zone (Abkhazia) as well.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

As per the 2005 annual progress report balance from the supplementary support funds by end 2004 comprised 13,112.85 USD. The funds have not been expended in 2005, due to no identified target priority by ICC. The funds have been left as a contingency support for NIP management needs. One of the options considered by ICC is to ensure co-funding to cold-chain upgrading in 2006 under primary health care reform, with a major investment of >100,000 USD considered by USAID/UNICEF. The second alternative is support to outreach immunization team operations, upon finalization of the organization, restructuring and determination of functional links among primary health care providers & public health authorities under review in 2005-2006.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The country was not eligible for additional disbursements or supply assistance within the 3rd sub-account in 2005.

#### Progress of transition plan for safe injections and safe management of sharps waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. Injection Safety Assessment | FY 2002 | Assessment as per WHO/SIGN methodology carried out in Oct 2002 by WHO/EURO experts. Final report provided with 2nd annual report to GAVI/VF in 2004. Financial support provided through UNICEF/USAID. |  |  |
| 2. Waste Management assessment and planning | FY 2002 | Waste management assessment and planning exercise completed in February 2004. Financial support provided through UNICEF/USAID. | Delay in implementation of injection safety assessment and political turmoil in the country in 2003 |  |
| 3. Elaboration of detailed plan of action for injection safety, including safe disposal | FY 2002 | Accomplished as of FY 2004 |  |  |
| 4. Introduction of the injection safety policy and plan at the national and sub-national levels | FY 2002 | Injection safety policy and plan incorporated in the revised Ministerial Decree on NIP management #122/n – June 2003. Training of EPI staff supported at all levels of programme mngt. |  |  |
| Develop training curriculum for physicians, nurses, pharmacists and other health professionals on injection safety | FY 2003 | Training curriculum developed in 2002 and included in the Ministerial Decree #122/n. |  |  |
| 6. Train focal points on management and surveillance of injection safety, including safe disposal & AEFI | FY 2003 | Accomplished within the scope of training on implementation of the revised Ministerial Decree #122/n |  | Continuous training of health care providers prioritized within NIP. |
| 7. Inclusion of injection safety in the education curriculum for medical students | FY 2003 | Pending | Major transformation & merging of the State Medical University & Medical Academy in 2005-2006 | FY 2006 |
| 8. Advocacy and communication on injection safety | YY 2002-2006 | Advocacy and communication workshop with involvement of 40 PHD and MLHSA rep-s supported by UNICEF in Nov’02. Training on injection safety by BD International in Feb’02 for 24 rep-s of NCDC/PHDs. Injection safety training included in NIP training in 2003 & 2004 based on Ministerial Decree. IIP training, including injection safety component supported countrywide for 1,200 front-line workers in 2005-April 2006. |  | Continuous advocacy and training on injection safety prioritised within NIP planning. |
| 9. Provision of adequate supplies of safe injection and disposal equipment (safety boxes and incinerators) at national and sub-national levels | YY 2002-2006 | Non-interrupted provision of injection safety equips ‘’bundled’’ to vaccine supplies ensured throughout reporting period. | Waste mngt assessment completed in Feb’04. Decision on waste-management equipment subject to finalization of primary health care reform (legal status, management systems) | Continue to supply matching quantities of injection safety supplies. Provision of incinerators & construction of waste disposal pits – FY 2005-06. |
| 10. Local adaptation/ implementation of the waste management plan according to destruction methodologies chosen. | YY 2003-2005 | Waste management assessment and planning exercise completed in February 2004. Implementation of the consultant’s recommendations subject to finalization of primary health care reform (legal status, management systems) |  |  |
| 11. Transition to AD syringes for all injections | YY 2002-2005 | Exclusive use of Ads for immunisation achieved by end 2004. Disposal & reconstitution syringes used for lyophilised vaccines. |  |  |
| 12. Revise the open vial policy | FY 2003 | Open vial policy adopted through Ministerial Decree #122/n |  |  |
| 13. Establish AEFI monitoring and surveillance system at all levels of service delivery | YY 2003-2004 | AEFI surveillance system revised and included within the new health information systems for NIP management (#122/n decree) |  | Continuous monitoring and supervision for endorsement of AEFI surveillance system |
| 14. Review potential for local production of safety boxes | FY 2005 | Pending | Competing priorities within NP & health care reform process. | End 2006 |
| 15. Revise and refine the safe immunization policy in compliance with WHO recommendations | YY 2002-2006 | Safe immunisation policy continuously discussed and revised by ICC partners |  |  |
| 16. Evaluate impact of injection safety policy | YY 2004-2006 | Comprehensive immunization review, including injection safety component planned in July-Sept 2006 |  |  |
| 17. Achieve 100% immunization injection safety | FY 2006 | Exclusive use of Ads for immunisation achieved by end 2004. Disposal & reconstitution syringes used for lyophilised vaccines. |  | Ensure continued monitoring of the procurement and utilization of injection supplies for NIP. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

| The financial support for the 3rd sub-account - 20,800 USD was issued to the Government of Georgia back in March 2003. The funds are planned to be utilised for ensuring sustainability of injection safety supplies and improvement of injection and waste management practices within NIP for 2006 and beyond. Up-to-date the Government of Georgia has been efficient in meeting the commitment under the Financial Sustainability Plan (2005-2010), thereby no need for complementary funding has been raised. The funds are considered as a contingency planning for the routine NIP as well as the supplemental immunization activities (i.e. MR NIDs planned in late 2007-early 2008). | N/A - |
| --- | --- |

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The Financial Sustainability Report was endorsed by the Government of Georgia and ICC and submitted to GAVI/VF in January 2005. The main objectives of the national immunization program articulated within the NIP Financial Sustainability Plan envisage (in order to prioritization): Improving the timely immunization coverage against all 9 antigens up to 90% at the national levels and at least to 80% at all district levels throughout the country. Status: Improved coverage rates from 2004 for all NIP antigens, through still 90% coverage could not be attained in 2005. Age-appropriate vaccination rates in 2005: BCG - 95%, DPT 3 – 82%, OPV3 – 81,5%, Measles (MCV1 within MMR) – 91,6%, HepB 3 – 72% Sustaining Polio free status and continuing accelerated disease control activities for Measles and Diphtheria - Status: Target Met Decreasing vaccine wastage rates. Status: Improved performance reported, though 2005 targets have not been fully met: DPT wastage in 2005 - 1.28 (vs. 1.3 in 2004). Traget: 1.18, HepB wastage in 2005 - 1.21 (vs. 1.22 in 2004). Target: 1.18 Introduction of new vaccines based on epidemiological and cost-benefit analysis: Status: not applicable for the reporting period Improving immunization coverage and program management capacities in conflict affected zones. Status: NIP supplies continuously provided to conflict-affected zoned within GoG/USAID/UNICEF/GAVI/VRF support. Monitoring & reporting from the conflict affected zones has been improving. UNICEF has established a sub-office in Abkhazia targeting at improvement of the programme monitoring & supply distribution. Contractual arrangements are in place with international NGO (ADRA) in South Ossetia for improved management & monitoring of the child vaccination programme. Cold-chain supplies provided to conflict-zones through UNICEF/USAID support. In 2005 UNICEF & WHO/Euro will be supporting a comprehensive NIP evaluation, including in Abkhazia. The assessment will facilitate defining the 2007-2010 strategies & action plans for improved program performance in conflict affected zones. UNICEF through USAID support is also planning a capacity building exercise for local health care providers in Abkhazia.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for …HEPB……….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2002..** | 2003.. | 2004.. | 2005.. | 2006.. | 2007.. | 2008.. | 2009.. | 2010.. | 2011.. |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 100 | 100 | 100 | 90 | 60 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 100 | 100 | 100 |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Resource Mobilization & Advocacy |
| Error! Reference source not found. | To revise the legislation to enable state procurements directly from UNICEF To conduct market assessment to identify suppliers with the lowest prices (meeting quality standards) To strengthen state procurement capacity and transparency | 1. Met: National Law on 2006 State Budget including provision on UNICEF procurement services (PS) 2. N/A for 2006 procurement ( UNICEF SD arrangements 3. TA provided to MLHSA for UNICEF SP, NCDC trained in EVSM | Legislative review process – time-constraints | Baseline: No international procurement arrangements in place in 2005 Output indicator: Purchase of quality vaccines with use of international procurement mechanism or direct procurement with price differential of less than ten percent from UNICEF prices in 2006 | international procurement arrangements introduced in 2006 Target Met – 2006 vaccine/ injection safety procurement by GoG in process under UNICEF PS |  |
| Error! Reference source not found. | To update the FSP (as an advocacy and planning tool) regularly together with ICC partners To conduct intensive consultations with the ICC partners during the planning of their programming cycles | 1. No official update of FSP performed. Subject to NIP evaluation in 2006 & review of the multi-year operational plan 2. FSP & operation plan used as reference guidance for the programme planning. ICC member agencies ensuring intensive consultations & integrated planning for NIP |  | Updated FSP for 2007 Continuity & consistency of ICC meetings & consultation for NIP planning | 1. N/A for 2006 – subject to 2006 NIP evaluation & planning review 2. Met – joint consultative & decision making process for 2006 programme planning, WHO/CDC missions on MR SIAs, procurement services, JRF & GAVI reporting. | 1. Revised FSP for 2007-2010 |
| Error! Reference source not found. | 1. To present the findings of the FSP to policy makers in the MoF and achieve consensus To hold working meetings with the policy makers and technical decision makers (in charge of MTEF) in the MoLHSA | 1. Met as of 2005 Met as of 2005-2006 for 2006-2008 MTEF planning |  | Existence of laws (budget law), statutes, regulations and/or official decrees specifying amounts or allocations to be dedicated to immunization programs | Law on 2006 State Budget 2006 National Immunization Programme |  |
| Efficiency & effectiveness |
| Error! Reference source not found. | 1. To prepare technical documents and training materials (Preparation, adaptation, translation, printing and distribution of technical documents and training materials, based on MLM and IIP modules) 2. To train managers (conduct EPI Mid-Level Management (MLM) training course for region and district immunization managers) 3. To translate and adopt the WHO-UNICEF Effective Vaccine Store Management (EVSM) Initiative 4. To conduct vaccine store management and immunization safety training course - 12 regions and 66 districts for 2-3 days | 1. IIP modules translated/adopted/printed/distributed in 2005 (UNICEF/USAID). 1,200 HCWs countrywide trained. MLM modules under translation 2. MLM training planned in 2006 for regional & district NIP managers 3. National NIP logistics manager & key staff trained in EVSM in 2005-06 Injection 4. Training pending due to adaptation of the EVSM tools. Injection safety training provided in 2005 under IIP sessions. |  | Technical documents and training materials available Number of managers/ professionals trained (or in % out of total) | IIP modules available EVSM & MLM under translation. >90% of NIP managers & front line workers country wide trained in IIP, including injection safety |  |
| Error! Reference source not found. | To upgrade existing software for the MIS to meet more advanced (managerial) requirements To conduct a training course on EPI and standard used software for regional and district Public Health Centre (PHC) | 1. MIS updated for district level management (GeoVac) by USAID/ Curatio IF/ Abts assoc. project in 2005. Financial component has not been included up to now. 2. All regional & district level managers trained in 2004-2005 in GeoVac administration | Subject to finalization of the PHC reform process (underway) | Existence of an accounting system for the immunization program or a broader accounting system where expenditures can be disaggregated by program | Monthly/quarterly/annual rpt financial reports on NIP management, except for financial accounts available country-wide. |  |
| Error! Reference source not found. | To participate in the elaboration of the PHC provider reimbursement schemes To develop policy recommendations To conduct workshops & debates | 1. ICC partners engaged in PHC reform process as per agency profiles 2. ICC partners agency profiles engaged in PHC policy recommendations review 3. advocacy workshops & annual review meetings by UNICEF, Curatio IF, Public Health Department | Ongoing PHC Reform process. PHC policy, system organization & financial mechanisms to be finalized in 2006. | Reimbursement schemes of PHC providers consider appropriate incentives for immunization services | UNICEF in 2006 planning external consultancy on incentives/reimbursement schemes for NIP |  |
| Error! Reference source not found. | To participate in the design of PHC facility standards (enforced by licensing or contracting mechanisms) and integrate the needs of the NIP To participate in the design of the functional plans and the scope of work of medical professionals of PHC institutions to integrate the needs of the NIP To participate in the human resource development planning and ensure that training (education) curriculum reflects immunization related topics To participate in the development of PHC provider contracts and suggest mechanism for their enforcement concerning the NIP objectives | 1-4 ICC partners engaged in PHC reform working group defining the standards for PHC facilities, legal status of PHCs, JDs, HR development plans, M&E mechanisms | Ongoing PHC Reform process. PHC system organization, standards & financial mechanisms to be finalized in 2006. | Cold chain equipment at PHC level is incorporated in the standards of the primary health care facilities PHC medical personnel responsibilities are defined in the payment contracts and enforced | The degree of the NIP institutional & human resource needs integration into PHCs to be agreed by end 2006. |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 489201 | 48920 | 48920 | 48920 | 48920 | 48920 | 48920 | 48920 | 48920 |
| Infants’ deaths | 11782 | 1178 | 1178 | 1178 | 1178 | 1178 | 1178 | 1178 | 1178 |
| Surviving infants | 443263 | 44326 | 44326 | 44326 | 44326 | 44326 | 44326 | 44326 | 44326 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 40906 92% | 41325 95% | 41325 95% | 41325 95% | 41325 95% | 41325 95% | 41325 95% | 41325 95% | 41325 95% |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 36633 82% | 38720 89% | 40020 92% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* …HEPB......... (new vaccine) | 45479 93% | 46470 95% | 46470 95% | 46470 95% | 46470 95% | 46470 95% | 46470 95% | 46470 95% | 46470 95% |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of… HEPB......... ( new vaccine) | 31978 72% | 34800 80 | 36970 85% | 39150 90% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% |
| Wastage rate in 2005 and plan for 2006 beyond*** …… HEPB......... …….. ( new vaccine) | 1,21 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 | 1,18 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | NR | NR | NR | NR | NR | NR | NR | NR | NR |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 46622 95% | 46622 95% | 46622 95% | 46622 95% | 46622 95% | 46622 95% | 46622 95% | 46622 95% | 46622 95% |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 39677 91,6% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% | 40325 95% |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

The number of live-births is preliminary, final official data will be available in mid 2006

2  Official figure of infants death for 2004 amounts to 1178. 2005 year data are not available, therefore previous year figure is provided.

3  Number of surviving infants is derived from the Immunization HIS which is based on the target groups (under 1 year) defined by the districts.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Data provided in table 3 correspond to the 2005 WHO/UNICEF JRF. It is envisioned that in mid 2006 Official Statistical data will be available. Denominators provided by the Official statistics may exceed the figures given in the table 3. Consequently coverage rates will be recalculated based on the Official denominators. Number of the vaccinated children is final and is not subject to changes. Updated coverage data (if different) will be forwarded to WHO/EURO and UNICEF HQs to ensure compliance of country level reporting to WHO/UNICEF and GAVI/VF.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The updated forecast for HepB vaccine and injection safety supplies for 2007 will be incorporated in the overall NIP supply forecast in October 2006 for UNICEF SD reference.

Table 4: Estimated number of doses of …HEPB… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Not application for Georgia NIP starting from 2005.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Drop-out rate for DPT3 and HepB3 | DPT3 – 11.6% HepB3 – 15.3% | 10,5% - DPT3 drop-out 11,7 % – HepB drop-out (HB2-Hb3) |  | Targets identified in the country application are left unchanged for DPT3 and updated for HepB3 for realistic targets DPT 3 drop out: 9 %– 2006 8 % -2007 8%-2008 HepB drop-out: 10 % – 2006 9 %- 2007 9%-2008 |
| Age-appropriate HepB-3 coverage; | HepB 3 – 72 % | Age-appropriate – 72 % | Low awareness and commitment to the new vaccine remains a key constraint. The suspected AEFI case to HepB in 2002 further increasing mistrust to the new vaccine among the population | Hep3 coverage targets: 80%- 2006 85%- 2007 90%-2008 |
| Vaccine wastage – DPT and HepB | 1.18 (DPT) 1.18 (HepB) | DPT wastage - 1.28 (1.3 in 2004) HepB wastage - 1.21 (1.22 in 2004) | Open vial policy for non-lyophilised vaccines introduced in 2003, expected to improve the existing rates of vaccine wastage. | DPT and HepB wastage: 1.18 – 2006 1.18 – 2007 1,18- 2008 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | X | 15 May 2005 |
| Reporting Period (consistent with previous calendar year) | X | Report covering Jan-Dec 2005 period |
| Table 1 filled-in | X |  |
| DQA reported on | X |  |
| Reported on use of 100,000 US$ | X |  |
| Injection Safety Reported on | X |  |
| FSP Reported on (progress against country FSP indicators) | X | Progress report N/A for 2005-2010 FSP |
| Table 2 filled-in | X |  |
| New Vaccine Request completed | X |  |
| Revised request for injection safety completed (where applicable) | X | Not applicable for the report |
| ICC minutes attached to the report | X | Attachments |
| Government signatures | X |  |
| ICC endorsed |  | ICC meetings held on May 2006 has revised the preliminary draft of the report. Revised document was signed by ICC on 15st May and endorsed by MLHSA on May 2006 |

6.  	Comments

ICC/RWG comments:

# Text boxes

Partnering with The Vaccine Fund

---_-------

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2007: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes