GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Ethiopia

Date of submission: 21.06.2011 04:33:41

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Rotavirus 2-dose schedule | 2012 | 2015 | Rotavirus 3-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Rotavirus 2-dose schedule

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.1  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Executive summary

Ethiopia is a country with about 1.1 million sq kilometers and a population of 79 million residing in 9 regions and two councils. The immunization coverage has been steadily increasing for the last seven years (from 52% in 2003 to 86% in 2010). The improvement is mainly attributed to the implementation of the RED approach since 2003 and continued GAVI ISS support, technical and financial support from partners in health and deployment of the health extension workers in each village with a population of approximately 5,000 who are also providing immunization services.

Ethiopia is has a high infant and under five mortality rate of 77 and 123 per thousand live births respectively (DHS, 2005). Pneumonia, which accounts for 28% of child deaths, is the leading cause of under five deaths followed by diarrhea (20%), malaria (20%), and measles (4%). Malnutrition and HIV/AIDS as underlying causes contribute for 57% and 11% of under-five deaths in Ethiopia respectively. Routine immunization began in Ethiopia in 1980 and since then the coverage has been gradually improving and has reached DPT-HepB-Hib3 coverage of 86% in 2010.

In an attempt to document the burden of rotavirus disease through surveillance and monitoring, the Federal Ministry of Health in collaboration with WHO, has established two rotavirus sentinel surveillance sites in two hospitals in the country since September 2007. According to the preliminary data of the ongoing rotavirus surveillance being conducted from September 2007 up to June 2009, it was found that 30% (106) of acute gastroenteritis cases were due to rotavirus. This finding is highly consistent with the previous studies done in Ethiopia and with reports of other African countries. Although the viral strains show considerable diversity, 5 serotypes are responsible for the majority of human rotavirus disease. The prevalence of the Ethiopian rotavirus strain data obtained from hospital based surveillance sites showed that G1,G2,G10, G12 and un-type-able strains accounts for 30%, 30%,26%,9% and 4% respectively. 

Introduction of rotavirus vaccine has tremendous potential impact on reduction of under five mortality, prevention of hospitalization, reduction of morbidity and socioeconomic burden in Ethiopia so as to achieve the MDG 4 goal. The program is also considered is cost-effective in all GAVI-eligible countries. Opportunities for affordable, sustainable rotavirus vaccination and expanding the funding base for vaccines make the introduction of rotavirus vaccine in Ethiopia recommendable. 

In 2009, Ethiopia conducted a Vaccine Management Assessment (VMA). According to the assessment results, the vaccine arrival process, cold storage capacity, effective VVMs use and implementation of MDVP components showed better performance compared to the 2002 VMA whereas, vaccine wastage control, stock management, Effective vaccine delivery, buildings, cold chain equipment and transport, vaccine storage temperature components were areas with gaps that need to be improved. Activities carried out to address gaps identified by the VMA were the following: 

- Upgrading of cold rooms at National level to expand cold chain storage space 
- Procurement and distribution of refrigerators to health posts
- Printing and distribution of a standardised temperature monitoring chart to reach the health facility level
- Reinitiating stock management using a stock management tool (SMT) at national and regions levels.
- Training of mid level cold chain technicians in each woreda

Effective vaccine management training for cold store managers on vaccine management: stock management, importance of correct use and handling of diluents, vaccine wastage monitoring, contingency plan development, reception and distribution plan development and vaccine forecasting has been conducted.

Taking into consideration the costs and benefits of introducing the rotavirus vaccine in the country, and after thorough discussion with partners, The Federal Ministry of Health has decided to introduce the vaccine by March 2012. To meet the vaccine storage capacity needs at primary level, the Ministry has already managed to have additional central storage capacity of 500 m3 in 2010 which is more than enough to accommodate the introduction of Rota vaccine in 2012. The total net available positive temperature storage space at the central level is 284,285 liters which can accommodate the introduction of Rotavirus vaccine by 2012 with two consignments per year. . 

The first choice of rotavirus vaccine presentation is oral liquid monvalent vaccine in a 1-dose squeeze tube formulation with a two dose schedule. The first dose should be given between 6 and 14 weeks and should go with the DPT-HepB-Hib vaccination schedule. The interval between doses should not be less than 4 weeks. The schedule will be given with penta 1 and 2 vaccinations. All eligible children in the country who are below one year of age (1st dose between 6 - 14 weeks) as of March 2012 are going to be given the rotavirus vaccine irrespective of their status with regards to other routine vaccines. The alterantive option is the three dose pentavalent Rota vaccine.

Vaccine will be procured by UNICEF with VVMs attached and delivered 4 times per year. The vaccine will be stored initially at the central store and distributed to regions, zones and woredas according to the vaccine forecast and distribution plan. The Government of Ethiopia is committed to cover the amount of costs to be paid as co-financing while the current trend of support from partners will continue and the Government will put in place an aggressive resource mobilization strategy to ensure the availability of the required resources in the planning period.

Regardless of the implementation plan for rotavirus vaccination, a coordinated strategy for prevention and treatment of childhood diarrheal diseases through improvements in hygiene and sanitation levels, as well as awareness and access to oral rehydration therapy, zinc supplementation and other effective treatments as recommended by WHO will continue to be carried out in the country. 

Pre-Rotavirus vaccine introduction activities will be coordinating by ICC under the new vaccine introduction coordinating committee. The activities will include cascaded training on Rotavirus vaccine introduction for health workers and EPI managers at various levels. In addition to the cascaded training, job aid wall charts with the revised immunization schedule, supportive supervision and on the job training after rota virus vaccine introduction will be implemented. Revision of recording and reporting forms, revision of the national immunization schedule, an effective vaccine management assessment, communication and social mobilization for Rotavirus vaccine introduction and launching of vaccine introduction as well as monitoring of preparations will be condcuted. The pre and introduction activities funding is secured and so far there is no budget gap for these activities. 

The total vaccine costs, and GAVI and Ethiopia contributions are summarized below:

Total Required vaccine and cost 2012	 2013	 2014	 2015 	 Total
Total vaccine required	 7,228,386	6,049,489	6,200,726	6,355,744	25,834,345
Amount to be financed by GAVI	 44,093,156	30,549,918	24,802,902	22,753,564	122,199,540
Country co-financing	 1,445,677	1,209,898	1,240,145	1,271,149	5,166,869
Total vaccine cost	 45,538,833	31,759,816	26,043,048	24,024,713	127,366,409

Partners working in health are coordinated through the Interagency Coordinating Committee(ICC) and significantly contribute technically and financially to the EPI program in Ethiopia. WHO and UNICEF are mainly engaged in the surveillance of polio, measles and neonatal tetanus, supporting implementation of Polio, TT and Measles SIAs, and capacity building on various EPI programs. UNICEF supports procurement of traditional vaccines and cold chain equipment. Civil Society Organizations (CSO) like Ethiopian Public Health Association, CORE GROUP/CRDA and Afar People Development Association (APDA) are supporting capacity building, supervision and in case of APDA in provision of EPI services in hard to reach areas unreached by the EPI program. 

The total required funds, based on the CMYP, for the year 2012 is USD 164, 633,082 of which the secured funding is USD 158,783.074; the gap is about USD 5,850,007. The funding gap for the remaining year is between 4-6% for the period between 2013-2015. The bulk of the funding (secured and probable) is from Government of Ethiopia, GAVI, UNICEF and other partners. This does not include health systems costs which are shared with various programs. The Government of Ethiopia has committed to start co-financing Rotavirus vaccine from March 2012 if the vaccine is introduced according to plan.

The FMOH has established a budget line for vaccine procurement. It has also cofinanced the measles SIAs operational cost in 2010. Regarding the strategies and actions for financial sustainability and filling the financial gap, the following strategies will be followed: working aggressively on mobilising additional resources, improving programme efficiency, continuing to commit on co-financing and increasing allocation of government budget for EPI. The responsibility for implementing financial sustainability rests with the Policy, Planning and Finance Directorate of the FMOH and the ICC and its Immunization Partners Technical Working Group. The implementation of financial sustainability strategies will be followed by the ICC and will be regularly updated by the Technical Working Group on the implementation status.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Ethiopia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Rotavirus 2-dose schedule introduction.

The Government of Ethiopia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Dr Tedros Adhanom | Name | Mr Sofian Ahmed |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr Neghist Tesfaye | Urban HPDP Directorate Director | +251-913539697 | netesfaye@yahoo.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 1.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr Kesetebrhan Admasu /State Minister | Ministry of Health |  |  |
| Ms Roman Tesfaye/ Policy, Plan and Finance General Directorate director | Ministry of Health |  |  |
| Dr.Neghist Tesfaye/ Urban Health Promotion and Disease Prevention Directorate Director | Ministry of Health |  |  |
| Dr. Tizita Hailue/ Pastoralist Health Promotion and Disease Prevention Directorate Director | Ministry of Health |  |  |
| Ms. Mihret Hiluf/ Agrarian Health Promotion and Diseases Prevention Directorate Director | Ministry of Health |  |  |
| Dr. Fatoumata Nafo-Traoré/ WHO Representative | WHO/Ethiopia |  |  |
| Mr. Ted Chaiban /UNICEF Representative | UNICEF/Ethiopia |  |  |
| Ms Meri Sinnitt, Chief of Health Population and Nutrition | USAID/Ethiopia |  |  |
| Mr Nahusenay Araya, Rotary International Chair Person | Rotary International |  |  |
| Dr.Filimona Bisrat | CORE Group |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr Neghist Tesfaye | Title | Urban HPDP Directorate Director |
| --- | --- | --- | --- |
| Tel no | +251-913539697 |  |  |
| Fax no | +251ii5159657 | Address | Federal Monistry of Health P.O.Box 1234 Addis Ababa, Ethiopia, |
| Email | netesfaye@yahoo.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter Agency Coordinating Comittee |
| --- | --- |
| Year of constitution of the current committee | 1996 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand alone |
| Frequency of meetings | Quarterly |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | State Minister/ Ministry of Health | Dr Keseteberhan Admasu |  |
| Secretary | Immunization officer/ WHO | Dr Teklay Kidane |  |
| Members | Policy Plan and Finance General Directorate Director/ Ministry of Health | Ms Roman Tesaye | Action |
|  | Urban Health Promotion and Disease Prevention Directorate Director /Ministry of Health | Dr.Neghist Tesfaye |  |
|  | Pastoralist Health Promotion and Disease Prevention Directorate Director/ Ministry of Health | Dr. Tizita Hailu |  |
|  | Agrarian Health Promotion and Diseases Prevention Directorate Director/Ministry of Health | Ms. Mihret Hiluf |  |
|  | WHO Representative / WHO-Ethiopia | Dr. Fatoumata Nafo-Traoré |  |
|  | UNICEF Representative/ UNICEF-Ethiopia | Mr. Ted Chaiban |  |
|  | USAID/ Ethiopia | Ms Meri Sinnitt |  |
|  | Chair Person/ Rotary International | Mr Nahusenay Araya |  |
|  | CORE Group/ COREGROUP Ethiopia | Dr.Filimona Bisrat |  |

Major functions and responsibilities of the committee

-Coordinate partners resources for immunization activities -Advise MOH on immunization services -Promote resource mobilization and allocation for EPI/plus in country and externally -Approve plans and reports on EPI/plus -Provide technical support for EPI/plus activities for both central and sub-national levels

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Include new ICC members such as regions(Oromia and Addis Ababa regional health bureau,) and newly established agencies under MOH(PFSA) working on vaccine storage and distribution |
| --- | --- |
| 2. | Strengthen and establish Sub national/regional ICCs. |
| 3. | Provide orientation program on financial sustainability, co-financing,and global situation on immunization funding |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 2

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 79,498,150 |  | 2010 | Projected from 2007 census |
| Infant mortality rate (per 1000) | 77 |  | 2005 | DHS 2005 |
| Surviving Infants[1] | 2,702,300 |  | 2010 | Projected from 2007 census |
| GNI per capita (US$) | 232 |  | 2010 | 2010 National 5 Year Growth Transformation plan MOFED |
| Total Health Expenditure (THE) as a percentage of GDP | 4.30 | % | 2009 | NHA Ethiopia |
| General government expenditure on health (GGHE) as % of General government expenditure | 11.40 | % | 2009 | NHA Ethiopia |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The Federal Ministry of Health (FMOH) prepares annual plans by compiling districct-based National Plans. During this exercise, plans are aligned with national priorities and the activities that are planned by partners are harmonized with the FMOH annual plans. The FMOH also prepares the five year Health Sector Development Plan (HSDP). Different funding channels are used for funding the health programs. Recently, the Health sector development plan IV (HSDP IV 2011-2015) was developed.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

Yes, the cMYP is aligned with the HSDP IV in terms of time frame, targets, startegies and content. Increasing coverage with avilable vaccines and introduction of new vaccines are stratiegies stipulated in the National Child Survival Strategy to decrease under five mortality and achieve the MDG4.

Please indicate the national planning budgeting cycle for health

Health sector development plan IV (HSDP IV) 2011-2015: every year the planning cycle is from July to June.

Please indicate the national planning cycle for immunisation

The immunization cMYP is from 2011 to 2015 which is aligned with the HSDP IV

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

No

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

Yes, review of disaggregated data shows that there is no significant difference in immunization service utilization between males and females, as documented in the National EPI coverage survey 2006. This will be also assessed in the upcoming 2011 EPI coverage survey.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes |  |  |
| Polio | at birth, 6,10,14 weeks | Yes |  |  |
| Penta | 6,10,14 weeks | Yes |  |  |
| Measles | 9 months | Yes |  |  |
| TT | Women of reporductive age 15-49 years | Yes |  |  |
| Vitamin A | at 9 months age | Yes |  |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2000 | 2005 |  | 2009 | 2010 |
| BCG |  | 77 | 69 | 76 | 83 | Tuberculosis | 928 | 0 |
| DTP | DTP1 | 86 | 90 | 75 | 84 | Diphtheria | 18 | 0 |
|  | DTP3 | 79 | 86 | 56 | 66 | Pertussis | 45 | 0 |
| Polio 3 |  | 75 | 86 | 53 | 67 | Polio | 0 | 0 |
| Measles (first dose) |  | 75 | 81 | 52 | 54 | Measles | 1,776 | 1,972 |
| TT2+ (Pregnant women) |  | 60 |  | 55 | 76 | NN Tetanus | 49 | 72 |
| Hib3 |  | 79 | 86 |  |  | Hib[2] | 6 | 3 |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 79 | 86 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

National EPI coverage surveys were conducted in 2001 and 2006. The titles of the surveys were: 1. National EPI coverage survey 2001 and 2. National EPI coverage survey 2006 respectively. The age group in both surveys were 12 -23 months and women with children of less than one year old children.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 2,937,283 | 3,085,983 | 3,163,133 | 3,242,211 | 3,323,266 |  |  |
| Total infants' deaths | 234,983 | 247,147 | 253,326 | 259,659 | 266,150 |  |  |
| Total surviving infants | 2,702,300 | 2,838,836 | 2,909,807 | 2,982,552 | 3,057,116 |  |  |
| Total pregnant women | 2,937,283 | 3,085,983 | 3,163,133 | 3,242,211 | 3,323,266 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 2,035,412 | 2,993,404 | 3,131,502 | 3,209,789 | 3,290,034 |  |  |
| BCG coverage (%)[1] | 69% | 97% | 99% | 99% | 99% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 2,320,177 | 2,611,729 | 2,764,316 | 2,863,250 | 2,934,831 |  |  |
| OPV3 coverage (%)[2] | 86% | 92% | 95% | 96% | 96% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 2,431,050 | 2,753,671 | 2,880,708 | 2,952,726 | 3,026,545 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 2,320,177 | 2,611,729 | 2,764,316 | 2,863,250 | 2,934,831 |  |  |
| DTP3 coverage (%)[2] | 86% | 92% | 95% | 96% | 96% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  | 2,753,671 | 2,880,708 | 2,952,726 | 3,026,545 |  |  |
| Target population vaccinated with last dose of Rotavirus |  | 2,611,729 | 2,764,316 | 2,863,250 | 2,934,831 |  |  |
| Rotavirus coverage (%)[2] | 0% | 92% | 95% | 96% | 96% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 2,193,833 | 2,441,399 | 2,589,727 | 2,684,297 | 2,751,404 |  |  |
| Measles coverage (%)[2] | 81% | 86% | 89% | 90% | 90% |  |  |
| Pregnant women vaccinated with TT+ |  | 2,684,805 | 2,846,820 | 2,917,990 | 2,990,940 |  |  |
| TT+ coverage (%)[4] | 0% | 87% | 90% | 90% | 90% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  | 2,441,399 | 2,589,727 | 2,684,297 | 2,751,404 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 5% | 5% | 4% | 3% | 3% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 20,443,638 | 131,274,335 | 124,152,020 | 127,275,928 | 131,404,229 |  |  |  |  |  |
| Traditional vaccines | 4,610,238 | 4,622,683 | 4,847,501 | 4,988,761 | 6,059,874 |  |  |  |  |  |
| New and underused vaccines | 15,833,400 | 126,651,652 | 119,304,519 | 122,287,167 | 125,344,355 |  |  |  |  |  |
| Injection supplies | 1,611,490 | 1,983,941 | 2,081,219 | 2,138,367 | 2,433,108 |  |  |  |  |  |
| Personnel | 615,039 | 639,281 | 652,067 | 665,108 | 678,410 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 29,673 | 30,266 | 30,872 | 31,489 | 32,119 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 585,366 | 609,015 | 621,195 | 633,619 | 646,291 |  |  |  |  |  |
| Transportation | 718,562 | 784,265 | 823,949 | 882,449 | 990,108 |  |  |  |  |  |
| Maintenance and overheads | 88,802 | 182,741 | 185,040 | 37,965 | 52,192 |  |  |  |  |  |
| Training | 298,808 | 386,981 | 438,140 | 469,248 | 488,206 |  |  |  |  |  |
| Social mobilisation and IEC | 15,000 | 97,007 | 109,831 | 117,629 | 122,381 |  |  |  |  |  |
| Disease surveillance | 2,789,177 | 3,004,015 | 3,070,223 | 3,256,893 | 3,421,691 |  |  |  |  |  |
| Program management | 7,971,231 | 8,620,935 | 8,828,565 | 9,022,855 | 9,210,764 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 34,551,747 | 146,973,501 | 140,341,054 | 143,866,442 | 148,801,089 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle |  | 130,000 |  |  |  |  |  |  |  |  |
| Cold chain equipment | 2,391,339 |  |  |  |  |  |  |  |  |  |
| Other capital equipment |  |  |  |  |  |  |  |  |  |  |
| Subtotal Capital Costs | 2,391,339 | 130,000 | 0 | 0 | 0 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 2,130,524 | 10,267,534 |  |  |  |  |  |  |  |  |
| Measles | 9,933,714 | 7,269,661 | 745,140 | 7,637,687 | 782,863 |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns | 1,190,572 |  |  |  |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 13,254,810 | 17,537,195 | 745,140 | 7,637,687 | 782,863 |  |  |  |  |  |
| GRAND TOTAL | 50,197,896 | 164,640,696 | 141,086,194 | 151,504,129 | 149,583,952 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
|  | GAVI | 18,074,422 | 126,814,146 | 119,643,055 | 121,661,178 | 123,845,047 |  |  |  |  |  |
|  | Government | 7,798,978 | 12,075,987 | 12,341,824 | 13,490,552 | 14,972,091 |  |  |  |  |  |
|  | UNICEF | 6,247,515 | 4,837,359 | 5,011,965 | 5,164,381 | 6,256,966 |  |  |  |  |  |
|  | WHO | 2,430,831 | 3,246,009 | 3,344,209 | 3,550,331 | 3,726,985 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
|  | Government | 1,750,000 | 130,000 |  |  |  |  |  |  |  |  |
|  | UNICEF | 641,339 |  |  |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
|  | Government | 2,250,000 | 2,552,037 | 261,584 | 2,681,234 | 274,827 |  |  |  |  |  |
|  | UNICEF | 6,160,447 | 2,358,812 | 241,778 | 2,478,227 | 254,018 |  |  |  |  |  |
|  | WHO | 4,844,363 | 12,626,346 | 241,778 | 2,478,227 | 254,018 |  |  |  |  |  |
| GRAND TOTAL |  | 50,197,895 | 164,640,696 | 141,086,193 | 151,504,130 | 149,583,952 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

A National cold chain inventory conducted with assistance from WHO in 2008 indicated that the available cold chain storage space at all levels (central, sub national, district and health facility) was 141,428 liters and that this was not adequate to support the introduction of Rota vaccine by 2012. Thus cold chain expansion work was done in 2010 and currently the positive cold chain storage space at central level has been expanded to 284,285 liters. By 2012, with the introduction of rota vaccine, the overall cold chain requirement will increase to 427,675 litres. Rotavirus vaccine can thus be still accommodated with the existing 284,285litres storage space given four consignments per year. Similarly, the currently available and the required positive temperature storage space at sub national level for 2011-2015 was computed and the analysis shows that it is adequate to accommodate rotavirus vaccines. All regions have adequate storage space for 3 months supply of vaccines. The assessment of cold chain storage space at health facility level from the inventory conducted in 2008 indicates that the introduction of the rotavirus vaccines by 2012 can be accommodated with the existing type of refrigerators at health facility level.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

In the process towards deciding on the introduction of rotavirus vaccine, the Federal Ministry of Health has undertaken a number of activities. In an attempt to document the burden of rotavirus disease through surveillance and monitoring, the Federal Ministry of Health in collaboration with WHO, has established two rotavirus sentinel surveillance sites since September 2007. According to the preliminary data of the ongoing rota virus surveillance being conducted at Black Lion hospital, out of 375 diarrheal stool specimens collected from hospitalized children of under 5 years of age with acute gastroenterities from September 2007 up to June 2009, 30%(106)of the acute gstroenteritis cases were found to be due to rotavirus. The Federal Ministry of Health of the Government of Ethiopia considered the burden of disease, reviewed the cold chain storage space, and decided to introduce rotavirus vaccine by 2012. The Government has also decided to construct a building and procured cold rooms in 2010 and upgraded the central cold chain store.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 380,548 | 405,416 | 416,120 | 427,675 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 284,285 | 284,285 | 284,285 | 284,285 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 2 | 2 | 2 | 2 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 4 | 4 | 4 | 4 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -189,148 | -182,931 | -180,255 | -177,366 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ |  |  |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The ultimate goal of the financial sustainability plan is self sufficiency; that is to be able to cover all costs related to immunization including the purchase of vaccines and required logistics, personnel and operational costs, etc. However, the country's overall health expenditure is still low and the rational way of achieving the financial sustainability will be mobilization and efficient use of domestic and supplementary external resources from other partners on a reliable basis to achieve the targeted goal of national immunization coverage. The FMOH has opened a budget line for vaccine procrument and with local EPI partners is currently procuring traditional vaccines (BCG, TT, OPV, measles) and injection materials. The Government has also committed itself to cofinance the pneumococcal and Rota vaccines and subsequently the government will increase the budget to cofinance other new vaccines and then fully cover the cost of vaccines in the long run.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Rota virus | Rota virus burden of disease and serotype hospital based surveillance study | June 2009 | 30% of diarrhael cases were found to be due to Rota virus. Major Rota virus sero types identified were G1(30%), G2(30%), G10(26%), G12(9%) and other 4%. |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| There was a delay in arrival of the new vaccine after training that required retraining and change in formulation of vaccine presentation | Ensure vaccine is available before conducting training activities |  |
| The budget for pre introduction activities especially training was not adequate | Ensure early planning of budget requirements and explore using other sources of budget |  |
| Under utilization of sub national cold rooms resulting in overstocking of central cold rooms | Develop proper vaccine distribution plan |  |
| Lack of adequate IEC materials like posters of leaflets on the new vaccine at operational level | Develop and distribute posters, leaflets, guidelines on the Rota vaccine prior to the introduction. |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Rotarix liquid oral vaccine 2-dose in single dose presentation

# 6.3.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 2,753,671 | 2,880,708 | 2,952,726 | 3,026,545 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 2,611,729 | 2,764,316 | 2,863,250 | 2,934,831 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 92.00% | 95.00% | 96.00% | 96.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 229,200 | 232,700 | 296,600 | 337,700 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,550 | 2,600 | 3,300 | 3,750 |  |  |  |  |
| Total value to be co-financed by country | $ | 1,446,000 | 1,223,500 | 1,248,000 | 1,279,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 6,999,200 | 5,883,600 | 5,942,100 | 6,056,900 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 77,700 | 65,325 | 65,975 | 67,250 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 44,150,000 | 30,935,000 | 25,003,000 | 22,942,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 3,085,983 | 0.30 | 926,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 1,902,883 | 926,000 |  |
| Social Mobilization, IEC and Advocacy | 373,306 |  |  |
| Cold Chain Equipment & Maintenance |  |  |  |
| Vehicles and Transportation | 340,186 |  |  |
| Programme Management | 278,446 |  |  |
| Surveillance and Monitoring |  |  |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Totals | 2,894,821 | 926,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

Vaccine will be procured and channelled through UNICEF

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

NA

- Please describe the introduction of the vaccines (refer to cMYP)

Capacity building: As the GAVI funds for the pre introduction activities is not adequate, Governmennt budget, WHO and UNICEF funds will be used to fill the budget gaps. Training of health workers, cold chain store keepers and EPI mangers on the burden of disease, mode of transmission and risk of infection, Rota vaccine presentation, handling of vaccine during storage and transportation, target group and schedule of vaccination, and route of administration and most importantly on the efficacy and safety of the vaccine and possible adverse events is important. Training will be conducted in a cascaded approach. As Ethiopia is a big country, use of pooled trainers is not a feasible option. But to standardize the training across the country, training materials will be prepared to be used uniformly in all training sessions. In addition, wall chart job aids with a revised schedule of immunization, on the job training and supervision after introduction of the vaccine will implemented. Updating of National EPI policy guideline, record keeping and reporting formats: The child immunization card, tally sheets, registration books, stock balance book, supervision checklists, and reporting formats, monitoring charts at all levels and vaccine requisition forms will be revised printed and distributed at least three months before the introduction of the Rota vaccines. It is also a government policy decison to provide immunization services on daily basis in all health facilities including health posts. Cold Storage Capacity: Cold chain spare parts will be procured and maintenance conducted to ensure the functionality of the cold chain at all levels. Vaccine distribution: Vaccine distribution will be conducted to ALL regions and from regions to zones, districts and health facilities one month before commencement of administration of the Rota vaccine. Waste Management: Training, sensitization and supervision will continue at all levels to improve waste management. Vaccine Wastage Monitoring: Use of vaccine stock balance books and monthly vaccine usage and wastage reporting will be strengthened through supervision and regular feedback to decrease vaccine wastage. AEFI monitoring: Data quality assessment and AEFI surveillance training will be conducted for all health workers working in EPI before the Rota vaccine introduction. Post introdcution AEFI (such as intussusceptions) surveillance using hospital based, sentinel surveillance sites, will be conducted based on a self controlled case series protocol previously used in other countries. Social mobilization and communication: • a media campaign which includes IEC material production will be implemented • Round table talks on TV and Radio afew weeks before introduction of Rotavirus vaccines. • Press conferences at federal level • Launching Ceremony in the presence of high level officials. • Production and broadcast of radio spot messages on the new vaccine to raise awareness among key policy and decision makers

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The same bank account used for the transfer of ISS funds will hold for the new vaccine introduction grant

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The co-financing required by the country for procuring vaccines will be transfered to UNICEF Supply Division after receipt of quotation for the required specification. The Federal Ministry of Health through the Pharmaceutical Fund Supply Agency (PFSA) will be responsible for the co-financing.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Program monitoring will be through the routine immunization monitoring system. There will be regular supportive supervision and review meetings and additional Data Quality Self Assessments will be regularly conducted integrated with supportive supervision to verify the accuracy of reported data and assess quality of immunization monitoring systems. Operational research will be conducted to assess behavioral determinants of vaccination uptake in poorly performing areas to develop messages based on identified gaps. In addition an impact study on sentinel sites to assses coverage and decline in isolation rate of Rota virus from cases with gastro enteritis will be conducted. Rota vaccine coverage will be included among the HMIS indicators.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted?   -

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? August  - 2009

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°3)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

- Upgrading of cold rooms at National level to expand cold chain storage space - Procurment and distribution of refrigerators to health posts. - Printing and distribution of standardised temperature monitoring chart for the health facility level. - Reinitiating stock management using SMT at national and regions levels. - One person trained on cold chain maintenance in each ditrict - Effective vaccine management training for cold store managers on vaccine management: stock management, importance of correct use and handling of diluents, vaccine wastage monitoring, contingency plan development, reception and distribution plan development, vaccine forecasting was conducted

- When is the next Effective Vaccine Management (EVM) Assessment planned?   - 2012

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

# Annexes

# Annex 1

# Annex 1.1 – Rotavirus 2-dose schedule

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 229,200 | 232,700 | 296,600 | 337,700 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,550 | 2,600 | 3,300 | 3,750 |  |  |  |  |
| Total value to be co-financed by the country | $ | 1,446,000 | 1,223,500 | 1,248,000 | 1,279,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 6,999,200 | 5,883,600 | 5,942,100 | 6,056,900 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 77,700 | 65,325 | 65,975 | 67,250 |  |  |  |  |
| Total value to be co-financed by the country | $ | 44,150,000 | 30,935,000 | 25,003,000 | 22,942,500 |  |  |  |  |

Table 1.1  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 2,838,836 | 2,909,807 | 2,982,552 | 3,057,116 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 2,611,729 | 2,764,316 | 2,863,250 | 2,934,831 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 92.00% | 95.00% | 96.00% | 96.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 2,753,671 | 2,880,708 | 2,952,726 | 3,026,545 |  |  |  |  |
| Number of doses per child |  | # | 2 | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | No | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 6.000 | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.17% |  |  | 3.80% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 2,753,671 | 87,310 | 2,666,361 | 2,880,708 | 109,579 | 2,771,129 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 5,507,342 | 174,620 | 5,332,722 | 5,761,416 | 219,157 | 5,542,259 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 5,782,710 | 183,351 | 5,599,359 | 6,049,487 | 230,115 | 5,819,372 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,445,678 | 45,838 | 1,399,840 | 66,695 | 2,537 | 64,158 |
| I | Total vaccine doses needed | F + G | 7,228,388 | 229,189 | 6,999,199 | 6,116,182 | 232,652 | 5,883,530 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 80,236 | 2,545 | 77,691 | 67,890 | 2,583 | 65,307 |
| N | Cost of vaccines needed | I * vaccine price per dose | 43,370,328 | 1,375,131 | 41,995,197 | 30,580,910 | 1,163,257 | 29,417,653 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 51,352 | 1,629 | 49,723 | 43,450 | 1,653 | 41,797 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 2,168,517 | 68,757 | 2,099,760 | 1,529,046 | 58,163 | 1,470,883 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 5,136 | 163 | 4,973 | 4,345 | 166 | 4,179 |
| T | Total fund needed | (N + O + P + Q + R + S) | 45,595,333 | 1,445,678 | 44,149,655 | 32,157,751 | 1,223,237 | 30,934,514 |
| U | Total country co-financing | I * country co-financing per dose | 1,445,678 |  |  | 1,223,237 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.17% |  |  | 3.80% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 4.75% |  |  | 5.28% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 2,952,726 | 140,345 | 2,812,381 | 3,026,545 | 159,805 | 2,866,740 |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 5,905,452 | 280,690 | 5,624,762 | 6,053,090 | 319,609 | 5,733,481 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 6,200,725 | 294,725 | 5,906,000 | 6,355,745 | 335,590 | 6,020,155 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 37,810 | 1,798 | 36,012 | 38,755 | 2,047 | 36,708 |
| I | Total vaccine doses needed | F + G | 6,238,535 | 296,522 | 5,942,013 | 6,394,500 | 337,636 | 6,056,864 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 69,248 | 3,292 | 65,956 | 70,979 | 3,748 | 67,231 |
| N | Cost of vaccines needed | I * vaccine price per dose | 24,954,140 | 1,186,086 | 23,768,054 | 23,020,200 | 1,215,488 | 21,804,712 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 44,319 | 2,107 | 42,212 | 45,427 | 2,399 | 43,028 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 1,247,707 | 59,305 | 1,188,402 | 1,151,010 | 60,775 | 1,090,235 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 4,432 | 211 | 4,221 | 4,543 | 240 | 4,303 |
| T | Total fund needed | (N + O + P + Q + R + S) | 26,250,598 | 1,247,707 | 25,002,891 | 24,221,180 | 1,278,900 | 22,942,280 |
| U | Total country co-financing | I * country co-financing per dose | 1,247,707 |  |  | 1,278,900 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 4.75% |  |  | 5.28% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rotavirus 2-dose schedule | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 5 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 6 | Yes |
| cMYP Costing tool for financial analysis |  | 7 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 4 | Yes |
| Improvement plan based on EVM |  | 9 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 8 |  |
| Banking details |  | 10, 11 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\In box\GAVI APR 2010\APR signitures\MOH Rota application signiture.pdf Date/Time: 16.05.2011 04:56:45 Size: 848 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\MOF Rota application signiture.pdf Date/Time: 16.05.2011 04:53:14 Size: 848 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\In box\GAVI APR 2010\APR signitures\ICC signiture-Rota application.pdf Date/Time: 13.05.2011 10:22:19 Size: 595 KB |  |  |  |
| 4 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\GAVI APR 2010\ICC\Last three ICC meeting Minutes.zip Date/Time: 25.04.2011 08:24:45 Size: 41 KB |  |  |  |
| 5 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\In box\GAVI APR 2010\APR signitures\main icc meeting endorsing RotaApplication.pdf Date/Time: 16.05.2011 03:11:41 Size: 971 KB |  |  |  |
| 6 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\Final CMYP\Ethiopia cMYP Final_Ma15_2011.doc Date/Time: 16.05.2011 05:01:19 Size: 2 MB |  |  |  |
| 7 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: C:\Documents and Settings\teklayk\Desktop\Final CMYP\cMYP_Costing_Tool_Vs(1).2.4_ Ethiopia_May15_2011.xls Date/Time: 16.05.2011 05:03:03 Size: 3 MB |  |  |  |
| 8 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Rota vaccine introduction plan proposal Ethiopoafinal_May15_21011.doc Date/Time: 17.05.2011 10:21:06 Size: 1 MB |  |  |  |
| 9 | File Type: Improvement plan based on EVM * File Desc: | File name: Logistic Plan of Action.doc Date/Time: 24.05.2011 03:37:44 Size: 356 KB |  |  |  |
| 10 | File Type: Banking details File Desc: | File name: Ethiopia Bank Account.pdf Date/Time: 15.06.2011 10:01:30 Size: 102 KB |  |  |  |
| 11 | File Type: Banking details File Desc: Letter from the Bank to GAVI - Bank account used for PCV & Rota | File name: Ethiopia LetterFromNationalBankToGAVI.pdf Date/Time: 15.06.2011 10:02:40 Size: 491 KB |  |  |  |