|  |  | [V1.4.1] |  |
| --- | --- | --- | --- |
| Gavi Application Form for Country Proposals For Support to: Preventive campaign support Submitted by The Government of Guinea-Bissau Date of submission: 25 January 2015 Deadline for submission: 25 January 2015 Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP) Start Year 2014 End Year 2017 Form updated in 2015 (To be used with Guidelines dated October 2014) Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet Enquiries to: proposals@gavi.org or representatives of a Gavi partner agency. Unless otherwise specified, the documents can be shared with Gavi partners, collaborators and the general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian. Note: Please ensure that the application has been received by Gavi on or before the day of the deadline. Gavi is unable to return submitted documents and attachments to the country. |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. GAVI Alliance will provide the necessary documents for the approved change, and the country's request will be duly amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purposes other than for the programmes described in this application, or any GAVI Alliance-approved amendment to this application. GAVI Alliance reserves the right to terminate its support to the Country for the programs described in this proposal if GAVI Alliance receives confirmation of misuse of the funds granted by GAVI Alliance. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of Gavi Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the Gavi Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage Gavi cash-based support. The Country confirms that it will take all responsibility for replenishing Gavi cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The languages of the arbitration will be English or French. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The Gavi Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

1. 1 Application specifications Please specify the type of GAVI support you would like to apply for. Type of Support Vaccine Start Year End Year Preferred second presentation[1] Preventive campaign support Meningococcal, 10 dose(s) per vial, LYOPHILIZED 2016 2017 [1] For a variety of reasons, GAVI may not be in a position to accommodate all countries’ first product preferences, and in such cases, GAVI will contact the country to explore alternative options. A country will not be obliged to accept its second or third preference; however, GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country.

2. Table of Contents 1. 1 Application specifications 2. Table of Contents 3. Executive Summary 4. Signatures 4.1. Signatures of the Government and National Coordinating Body 4.1.1 The Government and the Inter-Agency Coordinating Committee (ICC) for immunisation 4.1.2 National Coordinating Body/Inter-Agency Coordinating Committee for Immunisation 4.1.3 4.1.3. Signature Table for the Coordinating Committee for Immunisation 4.2. National Immunisation Technical Advisory Group NITAG 4.2.1 The NITAG Group for Immunisation 5. 5 Data on the immunisation program 5.1 Reference material 5.1.1 Lessons learned 5.1.2- Planning and budgeting of health services 5.1.3 Preparatory activities 5.1.4 Gender and equity 5.1.5 Data quality 5.2. 5.2 Baseline data and annual objectives (NVS routine immunisation) 5.3. Target for the preventive campaign(s) 5.3.1 Targets (Meningococcal A campaign) 6. 6 New and underused vaccines (routine NVS) 7. 7. NVS Preventive Campaigns 7.1. 7.1. Assessment of burden of relevant diseases related to the campaign (if available) 7.1.1 Epidemiology and disease burden for Meningococcal A 7.2 Demand for Meningococcal A, 10 dose(s) per vial, lyophilized, campaign support 7.2.1 Summary for Meningococcal A, campaign support 7.2.2 Allocation of support for the operating costs of the Meningococcal A campaign 7.2.3 MENINACONJUGATE vaccine introduction grant (VIG): 8. 8 Procurement and management 8.1 Procurement and management of routine vaccination with new or underused vaccines 8.2 Procurement and management for NVS preventive campaigns 8.2.1 Procurement and management for the Meningococcal A campaign, 10 dose(s) per vial, lyophilized 8.3. Product licensure 8.4 Vaccine Management (EVSM/EVM/VMA) 8.5 Waste management 9. Comments and recommendations from the national coordinating body (ICC/HSCC) 10. List of documents attached to this proposal 11. Appendices Annex 1 - NVS Routine Support Annex 2 - NVS Routine – Preferred Second Presentation Annex 3 - NVS Preventive campaign(s) Table Annex 3.1 C Summary table for Meningococcal A vaccine, 10 dose(s) per vial, lyophilized Table Annex 3.1 D Estimated numbers for Meningococcal A, 10 dose(s) per vial, lyophilized, associated injection safety material and related co-financing budget (page 1) Annex 4 Table Annex 4A: Commodities Cost Table Annex 4B: Freight cost as percentage of value Table Annex 4C: Low income - Country's minimum co-payment per dose of co-financed vaccine. Table Annex 4D: Wastage rates and factors Table Annex 4E: Vaccine maximum packed volumes 12. Banking form

3. Executive Summary Please provide a summary of your country's proposal, including the following the information:  For each specific request, NVS routine support or NVS campaign :  Duration of support  The total amount of funds requested  Characteristics of vaccine(s), if necessary, and the reason for the choice of the format  Month and year of planned introduction of the vaccine  Relevant baseline data, including:  DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form)  Birth cohort, targets and immunisation coverage by vaccines  Country preparedness  Summary of the EPI assessment report and progress report on the implementation of the planned improvements  The nature of stakeholders' participation in developing this proposal  Inter-Agency Coordinating Committee  Partners, including CSO involvement The African countries in the "meningitis belt" can be divided approximately into three groups as a function of the incidence of the disease: hyper-endemic countries, frontier countries with hyper-endemic zones and other countries at risk<?xml:namespace prefix = o /> Hyper-endemic countries: Burkina Faso, Ethiopia, Mali, Niger, the Northern states of Nigeria, Sudan and Chad. Frontier countries with hyper-endemic zones: Benin, Cameroon, Central African Republic, Côte d'Ivoire, People's Republic of Congo, Gambia, Ghana, Kenya, the other states of Nigeria, Uganda, Senegal and Togo. Other countries at risk without hyper-endemic zones: Burundi, Eritrea, Guinea, Guinea-Bissau, Mauritania, Rwanda and Tanzania. According to data from the National Institute of Public Health (INASA), Guinea-Bissau has not reported a single case of meningitis in the last 3 years (INASA). Taking into consideration the fact that recommendations call for conducting a preventive campaign of Meningococcus A immunisation, the country has decided to carry out a mass immunisation campaign from March 12 to 23, 2016. The execution of this activity will require a total of 1,425,641 doses of the vaccine and 1,415 AD syringes. For the execution of the planned campaigns, and including operating costs, the country is presenting a budget equivalent to USD 1,660,844.00. For this campaign, the Meningococcal A vaccine, 10 doses per vial, lyophilized, will be administered to individuals in age groups ranging from 1 to 29 years. This vaccine will be introduced into the routine immunisation in 2017 in the entire country. During the preventive mass campaign, plans call for the immunisation of 1,275,352 individuals in 2016, and for the mini make-up campaign, the immunisation of 63,991 children age one in 2017. Effective Vaccine Management (EVM) is supplying the tools necessary to monitor and evaluate the vaccine supply chains and to assist the country in improving the performance of the supply chain. An EVM assessment is identifying the strengths and weaknesses in nine areas of vaccine management on each of the four levels of the essential vaccines supply chains and is making recommendations to correct any deficiencies identified. The four levels of the supply chain are: Primary Level PR Sub-National Level SN Final Distribution Level LD Service Point Level SP Principal recommendations that will be used as a basis for the preparation of the EVM improvement plan prepared in October 2014 in Guinea-Bissau: Install the continuous temperature control system (Multilog) already available in the country, for the cold rooms Install the continuous temperature control system (Multilog) already available in the country, for the cold rooms Install air exhaust systems in every building that houses one or more cold rooms  Plan and create a budget for the construction/renovation of a building that can house the cold equipment, supplies and offices required for the next ten years that comply with the most recent standards Urgently supply equipment to protect the handlers who handle the vaccines in the cold room against the cold. On all levels, install a waste disposal system that meets the requirements of the WHO.  Systematically collect factual data too be used in projecting requirements for vaccines and supplies Two members of the IACC participated in the preparation of this proposal.

4. Signatures 4.1. Signatures of the Government and National Coordinating Body 4.1.1 The Government and the Inter-Agency Coordinating Committee (ICC) for immunisation The Government of Guinea-Bissau wishes to consolidate the existing partnership with GAVI to strengthen its national routine infant immunisation program and is specifically requesting GAVI support for: Meningococcal A, 10 doses per vial, lyophilized preventive campaigns The Government of Guinea-Bissau commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application. It should be noted that any request not signed by the Ministers of Health and Finance, or by their authorized representatives, will not be examined or recommended for approval by the Independent Examination Committee (IEC). These signatures appear in Documents Nos.: 1 and 2 in Section 10. Attachments Minister of Health (or delegated authority) Minister of Finance (or delegated authority) Name Dr Valentina Mendes Name Mr Geraldo João Martins Date Date Signature Signature This report has been compiled by (these persons may be contacted by the GAVI Secretariat if additional information related to this proposal is required): Full name Function Telephone E-mail Dr Eugenio Iala EPI Team +245 661 14 93 eugenioiala@yahoo.com.br Dr Mario Gomes tamy EPI Director +245 674 21 68 mariogomes61@yahoo.com.br Dr. Sidu Biai EPI WHO +245 666 61 00 biaisi@who.int Mr Jose Gomes Assistant Director +245 671 19 33 josegomes961@yahoo.com.br 4.1.2 National Coordinating Body/Inter-Agency Coordinating Committee for Immunisation Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, Health Sector Coordinating Committee (HSCC), or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the Gavi NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below. Profile of the ICC, HSCC, or equivalent committee Name of the committee ICC Year of constitution of the current committee 2001 Organisational structure (e.g., sub-committee, stand-alone) Technical committee Frequency of meetings Quarterly The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules are presented in the attached document (Document No.: 4) . Major functions and responsibilities of the ICC/HSCC: - Coordination of the planning and implementation of EPI activities; <?xml:namespace prefix = o /> - Endorsement of the planning documents and Proposals for the mobilisation of resources for the EPI; - Tracking and Evaluation of EPI activities; - Advocacy for the mobilization of resources; - Conduct advocacy with decision-makers to mobilize resources for the EPI Please describe the type of support offered by the different partners in the preparation of this request: The different parties have offered technical support in the preparation of this request. 4.1.3 4.1.3. Signature Table for the Coordinating Committee for Immunisation We, the undersigned members of the ICC, HSCC or equivalent committee [1] met on 23/01/2015 to examine this proposal.. At that meeting, we approved this proposal on the basis of the supporting documentation attached. The endorsed minutes of this meeting are attached as document number 5. The signatures confirm the request presented in Document 6 (please use the list of signatures in the following section). Please refer to Annex C of the ‘Gavi HSS and NVS General Guidelines’ for more information on ICCs. Function Title / Organisation Name Please sign below to indicate your attendance at the meeting during which the proposal was discussed. Please sign below to indicate your approval of the minutes of the meeting during which the proposal was discussed. Chair Minister/Ministry of Public Health Dr Valentina Mendes Secretary Ministry of Public Health Dr. Nicolau Quintino de Almeida Members WHO Representative Ayigan Kossi Akla UNICEF Representative Abubacar Sultan Representative/PLAN Guinea-Bissau Allassane Drabo President/Rotary Club Olívio Pereira Delegate/World Bank Carmem Pinto Pereira MInister/Ministry of Territorial Administration Doménico Sanca Minister/Ministry of National Education and Higher Instruction Maria Odete Costa Semedo Minister/Ministry of the Economy and Finance Geraldo João Martins President/Chamber of Commerce, Industry, Agriculture and Services Braima Camara President/Institut Femme et Enfant Ana Emília de Barros Sá AGUIBEF Programme Manager Sadna Na Bitã By submitting the proposal we confirm that a quorum was present. Yes The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER: 7) . 4.2. National Immunisation Technical Advisory Group NITAG Has a NITAG been established in your country? No In the absence of a NITAG, countries should clarify the role and functioning of the advisory group and describe plans to establish a NITAG. This document is attached as

5. 5 Data on the immunisation program 5.1 Reference material Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document. ▪ Please refer to the Comprehensive Multi-Year Plan for Immunisation (or equivalent plan), and attach a complete copy with an executive summary (DOCUMENT NUMBER 11). Please attach the cMYP costing tool (DOCUMENT NUMBER 12). ▪ Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 14 ▪ Please refer to the two most recent joint WHO/UNICEF reports on immunisation activities. ▪ Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate. ▪ Please refer to the attached risk assessments in the case of yellow fever and meningitis A mass preventive campaigns. Please use the most recent data available and specify the source and date. Figure Year Source Total population 1,692,376 2013 EPI (2013) Birth cohort 62,654 2013 cMYP 2013-2017 Infant Mortality Rate 63 2013 MICS 4 (2010) Surviving infants[1] 52,494 2013 cMYP 2013-2017 GNI per capita (US$) 3,792 % 2013 MoF Total Health Expenditure (THE) as a percentage of GDP 3 % 2013 MoF General government expenditure on health (GGHE) as % of General government expenditure 8 % 2013 MoF [3] Surviving infants = Infants surviving the first 12 months of life 5.1.1 Lessons learned Support for new routine vaccines Preventive campaign support If the campaigns with Meningococcus A vaccines have already been conducted in your country, please provide details on the lessons learned, in particular with regard to: storage capacity, additional protection against freezing, personnel training, the cold chain, logistics, coverage, wastage rate etc. and propose action items to correct any problems in future campaigns.. If they are included in the introduction plan or plan of action, please cite the sections only. Lessons Learned Action Points N/A 5.1.2- Planning and budgeting of health services Please provide some additional information on the planning and budgeting context in your country: For the country, the planning and budgeting cycle runs from the month of April to December, when it is approved by the National Assembly. Please indicate the name and date of the relevant planning document for health Plan National de Développement Sanitaire II 2013-2017 (National Plan for Healthcare Development II) 2013-2017. Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content etc)? Yes, the cMPY in place 2013-2017. Please indicate the national planning budgeting cycle for health The national planning budgeting cycle for health runs from January to December. Please indicate the national planning cycle for immunisation The national planning budgeting cycle for health runs from January to December. 5.1.3 Preparatory activities Please provide a summary of all the preparatory activities for the introduction of the vaccine(s) or the campaigns. If they are included in the introduction plan or plan of action, please cite the sections only. For the preparation of this proposal, the awareness-raising activities have been carried out among the decision-makers and a first generation of the plan of action for the campaign has been drafted. 5.1.4 Gender and equity Please describe any barriers to access, utilisation and delivery of immunisation services at district level (or equivalent) that are related to geographic, socio-economic and/or gender equity. Please describe actions taken to mitigate these barriers and highlight where these issues are addressed in the vaccine introduction plan(s). There are no inequities based on gender in the immunisation services on any level. Please examine whether questions of equity (socio-economic, geographic and gender-specific) factor have been taken into consideration in the process of preparing social mobilisation strategies, among other things, to improve immunisation coverage. Specify whether these issues are addressed in the vaccine introduction plan(s). The aspects of equity have been taken into consideration for the preparation of the strategic social mobilisation plan for routine immunisation and the campaigns. Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems. immunisation data are not disaggregated by gender. Is the country currently in a situation of fragility (e.g. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought or others)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities. Yes. In the last 5 years, the country has experienced political and military instability, resulting in frequent changes of government. In this context, the financing of immunisation activities has remained the responsibility of the Ministry's partners. If possible, please provide additional information and documents on the data relative to sub- national coverage, for example comparisons between urban and rural districts, or between districts with the highest and lowest coverage etc. immunisation coverage data comparing and urban and rural district, 2013 District<?xml:namespace prefix = o /> BCG % VPO3 % Penta3 % Measles % YFV % VAT2+ % SAB (Urban) 87 80 80 81 64 29 Oio (Rural) 92 91 91 76 59 21 Please describe what national surveys are routinely conducted in the country to assess gender and equity related barriers. Highlight whether this application includes any activities to assess gender and equity related barriers. 5.1.5 Data quality Please attach a data quality assessment (DQA), report if one has been completed within the previous 48 months (DOCUMENT NUMBER: 13). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER: 16 DOCUMENT NUMBER: 17). If DQA not available, please briefly describe plans to establish mechanisms for data quality assessment. the Program has not yet conducted a data quality assessment for this year; a tripartite validation of EPI data is planned. Please indicate what routine mechanisms to independently assess the quality of administrative data are in place, and if so what these mechanisms are and how they enable the country to track changes in data quality over time. The National Public Health Institute has implemented a systematic mechanism for the independent assessment of the quality of administrative data via an audit of the data on the basis of recording sources in healthcare institutions. Because the process has not yet been completed, the final report is not yet available. Please detail what household surveys have been conducted in recent years to independently assess immunisation coverage and equity, and describe any survey plans for the coming five year period. The only survey conducted among households in 2010 was the MICS4, although it should be noted that only immunisation coverage was taken into consideration, not equity.

5.2. 5.2 Baseline data and annual objectives (NVS routine immunisation) No routine NVS support is being requested

5.3. Target for the preventive campaign(s) 5.3.1 Targets (Meningococcal A campaign) Mini catch-up campaigns will be introduced at the same time as routine EPI. Gavi will support one-time mini catch-up campaigns with Meningococcal A conjugate vaccine targeting cohorts born between the initial mass campaign and introduction of routine infant vaccination in all 26 endemic countries in the African meningitis belt. The exact age range will depend on the specific country epidemiology and situation, although the target number to be reached should be included in table 5.3.1. The cohort for Meningococcus A via preventive mass immunisation campaigns is the population between the ages of 1 and 29. Table 5.3.1 Baseline NVS campaign figures for Meningococcus A Number Targets: preventative mass immunisation campaigns 2016 2017 Total target population 1,275,352 1,306,598 Wastage rate (%) for Meningococcus A (campaign) 10 10 Number Targets: mini catch-up campaigns 2016 2017 Total target population 63,768 65,330 Wastage rate (%) for Meningococcus A (campaign) 10 10

6. 6 New and underused vaccines (routine NVS) No routine NVS support is being requested

7. 7. NVS Preventive Campaigns 7.1. 7.1. Assessment of burden of relevant diseases related to the campaign (if available) Disease Title of the assessment Date Results Meningitis A N/A Please attach the Plan of Action for each campaign as Document No. 30.29 in Section 10. 7.1.1 Epidemiology and disease burden for Meningococcal A Please select at least one of the following information sources to document the results relative to the disease burden of Meningococcus A: Epidemiological information on the burden of the disease:  1 - Risk assessments  2 - Other The information sources for epidemiology and disease burden are the weekly notification database of the National Institute of Public Health (INASA) and JRF 2013.

7.2 Demand for Meningococcal A, 10 dose(s) per vial, lyophilized, campaign support 7.2.1 Summary for Meningococcal A, campaign support When does the country plan to organize a make-up immunisation campaign against MENINACONJUGATE? April 2017 When does the country plan to organize an immunisation campaign? March 2016 Please summarize the sections of the cMYP and/or of the plan for the introduction of Meningococcal A, 10 dose(s) per vial, lyophilized that relate to the introduction of Meningococcal A, 10 dose(s) per vial, lyophilized. Please describe the principal items that guided the decision-making process (data taken into consideration etc., and describe the social mobilization and micro-planning plans, in particular the strategies for unsafe areas or areas difficult to reach. If these items are included in the introduction plan or plan of action, please cite the sections only. The introduction of MenA is not yet part of the cMYP, although plans call for it to be included when this document is updated during the first quarter of 2015. Please summarise the cold chain capacity (at central and other levels) and readiness to accommodate new vaccines, taking into consideration training, cold chain and other logistic requirements. If cold chain expansion is required, state how it will be financed, and when it will be in place. Please describe how the surge capacity for campaigns will be managed. Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled. The Independent Review Committee (IRC) requires a certain level of assurance that the cold chain is ready or will be ready for the campaign, and evidence/plans need to be provided (if they are included in detail in the plan of action, please cite the section here). New Requirement: As approved by Gavi in June 2014 all future proposals (2015 and beyond) that include Gavi-financing for cold chain equipment intended for vaccine storage shall need to procure equipment pre-qualified by WHO under their Performance Quality and Safety (PQS) program. The purchase of non-PQS equipment will only be considered on an exceptional basis, with justification and advance agreement from GAVI. Please note that all Gavi-financed cold chain equipment needs to be WHO pre-qualified. The purchase of non-PQS equipment will only be considered on exceptional basis, with justification and advance agreement from Gavi. The central level: the central warehouse located in the offices of the EPI has a positive room with a net capacity of 4200 liters and a negative room with a capacity of 3300 liters. Three (3) refrigerators MK304, five (5) freezers (1 MF314, 1 MF304, 1 MF204, 1 MK304, 1 FCW300) are available to respond in part to emergencies. Nevertheless, a cold room will need to be purchased for the introduction of two new vaccines. <?xml:namespace prefix = o /> At the level of the health regions and areas, the capacity of the available cold chain is 3737 L. Taking into consideration the new vaccines, an additional volume is required; to make up for these gaps, the orders indicated below were issued in 2014: Via the GAVI HSS fund, to UNICEF and the WHO: UNICEF : 8 Dulas ZC 150-2 (Solar battery) and 1 Dulas ZC 65-2 (Solar battery) – Delivered to the country but not yet installed WHO: an order for 50 Zero Appliances ZLF100DC SDD and 5 Dometic TCW2043SDD was issued, and a cold room will be ordered in 2015.. The following items have been ordered via the GAVI RRF fund: UNICEF: 10 Dometic TCW40SDD Please describe any plans for expanding measles surveillance to include rubella and plans for the introduction of Congenital Rubella Syndrome (CRS) surveillance. The campaign activities will contribute to strengthening the routine immunisation services, especially in the following areas:<?xml:namespace prefix = o /> A. on the technical level The training activities will take into consideration not only the technical aspects relative to the MenA vaccine but also to the other vaccines. B. On the level of social mobilization in favor of immunisation: A public relations/social mobilization plan will be specially prepared to guide activities and to coordinate all of the planned measures. This plan will call on all the capabilities existing in the country in the area of communications: journalists, healthcare public relations specialists, civil society organizations operating in the healthcare sector, as well as state structures in charge of communications. The conventional approaches to public relations/mobilization that have proven effective in routine immunisation and mass immunisation campaigns will also be used. The goal is advocacy, social mobilization and community mobilization to change behavior. The strengthening of communications capabilities will also be used. A crisis communications system will also be implemented to respond to rumors and any particularly serious crises that occur as a result of the AEFI. The messages will be prepared both by public relations specialists and epidemiologists to ensure that they are consistent and will be accepted by the population. Pretests will also be conducted both with regard to the messages and the media via which these messages are communicated (posters, flags, T-shirts, possibly). Please produce the pertinent documents to support the relative estimates of the size of the target population of the campaign (DOCUMENT No.: 23). 7.2.2 Allocation of support for the operating costs of the Meningococcal A campaign Tableau 7.2.2: Calculation of the subsidy supporting the operating costs of the campaigns (mini-make-up campaigns and mass immunisation campaigns) Year of Meningococcal A support Total target population (Table 5.3) Gavi contribution per target person in US$ Total in US$ 2016 1,275,352 0.65 828,979 2017 1,306,598 0.65 849,289 [1] The Grant will be based on a maximum award of $0.65$ per target person- (synergies between mass campaigns, mini catch up campaigns and routine immunisation need to be highlighted. There will be common activities such as training relative to the new introductions). Please describe how the Introduction Grant will be used to facilitate the timely and effective implementation of immunisation campaigns for the target populations in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan). In the case of Guinea-Bissau, a campaign will be conducted before the introduction of the new vaccine. In the preparation process, the healthcare personnel will be trained in the vaccine, which should facilitate the introduction of Men A.

if the GAVI support does not cover all of the requirements, please describe the other sources of funding and the amounts projected, if available, to cover your requirements If support from GAVI does not cover all the requirements, plans call for the mobilization of state funds, although if that is not possible a request will be made to other partners of the Ministry of Health. Please complete the ‘Detailed budget for VIG / Operational costs’ template provided by Gavi and attach as a mandatory document in the Attachment section. VIG/operational costs template should detail or highlight activities for mini catch and comment on synergies across the VIGs). Detailed budget attached as Document No. 28. 7.2.3 Meningococcal A vaccine introduction grant (VIG): Has a Meningococcal A vaccine already been introduced into the national routine immunisation program? No Calculation of the vaccine introduction grant for Meningococcal A, 10 dose(s) per vial, lyophilized Please indicate in the tables below how the one-time Introduction grant [1] will be used to support the costs of vaccine introduction and costs inherent to the essential preparatory activities (refer to the cMYP). If GAVI support is insufficient to cover all the requirements, please indicate in the table below the additional amount required and who will supplement the total funding. Year of New Vaccine Introduction Birth cohort (from Table 5.1) Gavi contribution per target person in US$ Total in US$ 2016 62,654 0.80 100,000 [1] The Grant will be based on a maximum award of $0.80 per person in the birth cohort with a minimum starting grant award of $100,000 Please explain how the introduction grant provided by GAVI will be used to facilitate the timely and effective implementation of the activities before and during the introduction of the new vaccine (refer to the cMYP and to the vaccine introduction plan). This procedure will facilitate the timely and effective implementation of the activities before and at the time of the introduction of the vaccine, because the healthcare personnel involved in immunisation will be trained on the subject during preparation for the campaign.

8. 8 Procurement and management 8.1 Procurement and management of routine vaccination with new or underused vaccines No routine NVS support is being requested 8.2 Procurement and management for NVS preventive campaigns 8.2.1 Procurement and management for the Meningococcal A campaign, 10 dose(s) per vial, lyophilized a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF): The funds for the procurement of vaccines will be administered by UNICEF, via a request from the Ministry of Health b) Please describe the financial management procedures applicable to the operating support for preventive immunisation campaigns, including the procurement and related procedures. The financial management of the operational support will be provided by the WHO according to its procedures. c) Please indicate whether the campaign will be carried out in multiple phases. If so, please specify how these different phases will be organized. The campaign will be carried out in a single period all over the country d) Please specify how the coverage of the campaign, including the many make-up campaigns, will be tracked, reported and evaluated (please refer to the cMYP and/or to the plan for the introduction of the Meningococcal A, 10 dose(s) per vial, lyophilized campaign) The coverage of the campaign will be tracked, reported and evaluated in a post-campaign immunisation coverage survey. 8.3. Product licensure For each of the vaccine(s) requested, please state whether manufacturer registration and/or national vaccine licensure will be needed in addition to WHO prequalification and, if so, describe the procedure and its duration. In addition, state whether the country accepts the Expedited Procedure for national registration of WHO-prequalified vaccines. Note that the necessary time for licensure should be factored into the introduction timeline and reflected in the Vaccine Introduction Plan or Plan of Action. For each of the vaccine(s) requested, please provide the actual licensure status of the preferred presentation and of any alternative presentations, if required. Please describe local customs regulations, requirements for pre-delivery inspection, special documentation requirements that may potentially cause delays in receiving the vaccine. If such delays are anticipated, explain what steps are planned to handle these. Please provide information on NRA in the country, including status (e.g. whether it is WHO-certified). Please include points of contact with phone numbers and e-mail addresses. UNICEF will support the process by communicating licensing requirements to the vaccine manufacturers where relevant. 8.4 Vaccine Management (EVSM/EVM/VMA) It is mandatory for a country to conduct an assessment of effective vaccine management (EVM) before requesting support for the introduction of a new vaccine. The EVM a must have been conducted within the preceding 36 months. Please note that this assessment is recommended but not mandatory for requests for operational support to supplemental immunisation campaigns/activities (AVS). When was the EVM conducted? October 2014 Please attach the most recent EVM assessment report (DOCUMENT NUMBER : 25.26, 27) the corresponding EVM improvement plan (DOCUMENT NUMBER : 26) and the progress report on the EVM improvement plan (DOCUMENT NUMBER : 27). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation. If any of the above mandatory documents (EVM Assessment Report, EVM Improvement Plan, Progress on the EVM Improvement Plan) are not available, please provide justification and reference to additional documents such as PIE and External EPI Reviews. When is the next Effective Vaccine Management (EVM) Assessment planned? October 2017 The EVM assessment report is available. 8.5 Waste management Countries must have a detailed waste management and monitoring plan as appropriate for their immunisation activities. This should include details on sufficient availability of waste management supplies (including safety boxes), the safe handling, storage, transportation and disposal of immunisation waste, as part of a healthcare waste management strategy. Please describe the country’s waste management plan for immunisation activities (including campaigns). The injections during immunisation carry the risk of accidents for the health personnel and the community. These range from straightforward accidental benign accidental needle-sticks to infectious injections (transmission of germs) which are due to a number of reasons: lack of or non-availability of immunisation equipment (needles and syringes), negligent utilization of the equipment, lack of information on injection safety and disposal of the used material for example during the mass immunisation campaigns.<?xml:namespace prefix = o /> In an environment where the risks linked to injections are high and in an endeavor to protect both the service providers and users, the government of the Republic of Guinea - Bissau has an injection safety policy since 2002. Until 2002, in the routine EPI program, the syringes used for immunisation injections were syringes that can be reused after sterilization. The use of auto-disable syringes was introduced in 2002 and was made a standard practice in 2005. The essential elements of this policy are: the systematic use of auto-disable needles throughout the country and for all providers of health care services, in both the public and private sectors. This practice has been strengthened by the systematic use of lock boxes in all health care structures for the appropriate disposal of used syringes/needles and the installation of incinerators for the destruction of injection materials and supplies after use. In order to facilitate the implementation of this policy, training courses have been organized for all the health personnel and supplies are procured regularly. Injection safety and the disposal of medical waste from immunisation also form an integral part of the supervision. There is currently a functional incinerator in all the hospitals. Among the healthcare structures, there are those that do not have an operational incinerator, and in these cases the lock boxes must be kept in a room before being transported to healthcare centers and hospitals that do have an incinerator. Guinea-Bissau procures all products related to immunisation through UNICEF. therefore all the material and equipment supplied is prequalified by WHO.

9. Comments and recommendations from the national coordinating body (ICC/HSCC) Comments and Recommendations from the National Coordinating Body (ICC/HSCC) Following the presentation of the document by the Director of the EPI, here are the comments and recommendations from the ICC. - The need for advocacy on the part of the government with its partners for the success of this process - The involvement of the government in the process of preparation and implementation of this campaign - Raising the awareness of the population on the subject

10. List of documents attached to this proposal 10.1. List of documents attached to this proposal Document Number Document Section Mandatory File 1 MoH Signature (or delegated authority) of Proposal 4.1.1 Signature of the MoH.pdf Desc. file: Date/time 25/01/2015 05:15:18 Size: 990 KB 2 MoF Signature (or delegated authority) of Proposal 4.1.1 Signature of the MoH.pdf Desc. file: Date/time 25/01/2015 5:16:05 AM Size: 990 KB 3 MoH Signature (or delegated authority) of Proposal for assistance to the VPH 4.1.1 No file loaded 4 IACC Terms of Reference 4.1.2 IACC Terms of Reference.pdf Desc. file: Date/time 25/01/2015 5:18:42 AM Size: 85 KB 5 Minutes of ICC/HSCC meeting endorsing Proposal 4.1.3 Report from the IACC endorsing this document.pdf Desc. file: Date/time 25/01/2015 5:20:32 AM Size: 1 MB 6 Signatures of ICC or HSCC or equivalent in Proposal 4.1.3 Report from the IACC endorsing this document.pdf Desc. file: Date/time 25/01/2015 5:21:45 AM Size: 1 MB 7 Minutes of the three most recent IACC/HSCC meetings 4.1.3 Minutes IACC.pdf Desc. file: Date/time 25/01/2015 5:22:39 AM Size: 718 KB Minutes IACC April.pdf Desc. file: Date/time 25/01/2015 5:48:45 AM Size: 243 KB relatório Reuniao CCCSS, maio 2014.zip Desc. file: Date/time 25/01/2015 5:23:10 AM Size: 243 KB 8 A description of partner participation in preparing the application 4.1.3 No file loaded 9 Minutes of the meeting of the NITAG with specific recommendations on the introduction of the SVN??? or the campaign 4.2 No file loaded 10 Role and functioning of the advisory group, description of plans to establish a NITAG 4.2.1 ROL ET FONCTIONEMENT DU GTCV.pdf [ROLE AND FUNCTIONING OF THE GTCV.pdf] Desc. file: Date/time 25/01/2015 5:24:38 AM Size: 83 KB 11 comprehensive Multi Year Plan - cMYP 5.1 PPAC__GUB 08fev_2013 Vfinal.doc Desc. file: Date/time 25/01/2015 5:33:40 AM Size: 1 MB 12 cMYP Costing tool for financial analysis 5.1 cMYP_Costing_Tool_Fr-1.pdf [PPAC Costing TOol FR-1] Desc. file: Date/time 25/01/2015 5:34:38 AM Size: 22 KB 13 Monitoring and evaluation and surveillance (M&E) plan for the support requested, within the context of the country’s existing monitoring plan for the EPI programme 5.1.5 PLAN DE SUIVI ET EVALUATION.pdf [Monitoring and evaluation plan] Desc. file: Date/time 25/01/2015 5:35:15 AM Size: 83 KB 14 Vaccine introduction plan 5.1 PLAN DINTRODUCTIO DU VACCIN.pdf [Vaccine Introduction Plan] Desc. file: Date/time 25/01/2015 5:35:54 AM Size: 83 KB 15 Introduction Plan for the introduction of RCV / JE / Men A into the national programme 7.x.4 No file loaded 16 Data quality assessment (DQA) report 5.1.5 RAPPORT EVALUATION DE LA QUALITE DES DONNEES.pdf [Data quality assessment (DQA) report] Desc. file: Date/time 25/01/2015 5:36:54 AM Size: 83 KB 17 DQA improvement plan 5.1.5 No file loaded 19 HPV vaccine roadmap or strategy 6.1.1 No file loaded 20 Introduction Plan for the introduction of RCV into the national programme 7.x.4 No file loaded 21 Summary of the methodology of the assessment of the HPV vaccine 5.1.6 No file loaded 22 Evidence of commitment to fund purchase of RCV for use in the routine system in place of the first dose of MCV 7.x.3 No file loaded 23 Campaign target population documentation 7.x.1 LA POPULATION CIBLE EST BASE SUR LA POPULATION DE 2015.pdf [The target population is based on the 2015 population] Desc. file: Date/time 25/01/2015 5:37:36 AM Size: 84 KB 24 Roadmap or strategy for strengthening a comprehensive approach to pneumonia and/or diarrhoea prevention and treatment 6.x.6 No file loaded 25 EVM report 8.3 BIS GEV-2014-v02112014.pdf Desc. file: Date/time 25/01/2015 5:28:25 AM Size: 1 MB BIS GEV-2014-v02112014.pdf Desc. file: Date/time 25/01/2015 5:39:20 AM Size: 1 MB 26 Improvement plan based on EVM 8.3 Plan amelioration GEV.pdf [EVM Improvement Plan] Desc. file: Date/time 25/01/2015 5:40:02 AM Size: 312 KB 27 EVM improvement plan progress report 8.3 RAPPORT DE SITUATIO DA MELIORATION GEV.pdf [EVM IMPROVEMENT STATUS REPORT] Desc. file: Date/time 25/01/2015 5:41:24 AM Size: 83 KB 28 Detailed model budget for the grant for the introduction of a vaccine / operating costs 6.x,7.x.2 PLAN DINTRODUCTIO DU VACCIN.pdf [Vaccine Introduction Plan] Desc. file: Date/time 25/01/2015 5:42:11 AM Size: 83 KB 29 Risk assessment and consensus meeting report for Meningitis / Yellow Fever: (for yellow fever please include information required in the NVS guidelines on YF Risk Assessment process) 7.1 EVALUATION DES RISQUES.pdf [Risk Assessment] Desc. file: Date/time 25/01/2015 5:42:36 AM Size: 83 KB 30 Plan of Action for campaigns 7.1, 7.x.4 SIA Budget Templates20100614.pdf Desc. file: Date/time 25/01/2015 5:43:03 AM Size: 101 KB SIA Budget Templates20100614_Couch up SIA2017.pdf Desc. file: Date/time 25/01/2015 5:43:28 AM Size: 96 KB Other documents No file loaded

11. Appendices Annex 1 - NVS Routine Support No routine NVS support is being requested Annex 2 - NVS Routine – Preferred Second Presentation No NVS - routine immunisation - second preferred format requested this year Annex 3 - NVS Preventive campaign(s) Annex 3.1 - NVS preventive campaign(s) (Meningococcus A, 10 dose(s) per vial, lyophilized) Table Annex 3.1 C: Summary table for CAMPAIGN Meningococcal A, 10 dose(s) per vial, lyophilized Data from 2016 2017 Total target population Table 5.3.1 # 1,275,352 1,306,598 Number of doses per persons Parameter # 1 1 Vaccine wastage rates Table 5.3.1 # 10 10 Estimated vaccine wastage factor # 1.11 1.11 Number of doses per vial Parameter # 10 10 AD syringes required Parameter # Yes Yes Reconstitution syringes required Parameter # Yes Yes Safety boxes required Parameter # No No AD syringe price per unit Table Annexes 4A $ 0.0448 0.0448 Reconstitution syringe price per unit Table Annexes 4A $ 0.035 0.035 Safety box price per unit Table Annexes 4A $ 0.0054 0.0054 Freight cost as % of vaccines value Table Annexes 4B % 12.00 % 11.00 % Freight cost as % of devices value Parameter % 0 0

Table Annex 3.1 D: Estimated number of injection safety equipment associated with Meningococcal A, 10 dose(s) per vial, lyophilized, and corresponding co-funding budget (page 1) Formula Gavi 2016 2017 B Total target population Table 5.3.1 1,275,352 1,306,598 C Number of doses per persons Vaccine parameter (schedule) 1 1 D Number of doses needed B X C 1,275,352 1,306,598 E Estimated vaccine wastage factor 100 / (100 - Vaccine wastage rate) 1.11 1.11 F Number of doses needed including wastage D X E 1,415,641 1,450,324 G Vaccines buffer stock 0 0 0 I Total vaccine doses needed Round up((F + G) / Vaccine package size) * Vaccine package size 1,416,000 1,450,500 J Number of doses per vial immunisation parameter 10 10 K Number of AD syringes (+ 10% wastage) needed (D + G) x 1.11 1,415,641 1,450,324 L Reconstitution syringes (+ 10% wastage) needed (I / J) x 1.11 157,176 161,006 N Cost of vaccines needed I x * vaccine price per dose (g) 910,488 965,308 O Cost of AD syringes needed K x AD syringe price per unit (ca) 63,421 64,975 P Cost of reconstitution syringes needed L x reconstitution price per unit (cr) 5,502 5,636 Q Cost of safety boxes needed M x safety box price per unit (cs) 0 0 R Freight cost for vaccines needed N x freight cost as of % of vaccines value (fv) 106,528 109,080 S Freight cost for devices needed (O+P+Q) x freight cost as % of devices value (fd) 0 0 T Total fund needed (N+O+P+Q+R+S) 1,085,939 1,144,999 Note: There is no co-financing for NVS preventive campaigns

| Annex 4 Table Annex 4A: Commodities Cost Estimated prices of supply are not disclosed Table Annex 4B: Freight cost as percentage of value Vaccine Antigen Vaccine Type 2016 2017 Meningococcal, 10 dose(s) per vial, lyophilized HEPBHIB 23.80 % 11.70 % 11.30 % Table Annex 4C: Low income - Country's minimum co-payment per dose of co-financed vaccine. Vaccine product |  |
| --- | --- |

Table Annex 4D: Wastage rates and factors The table below presents the waste rates for the different vaccines (routine immunisation and campaigns) for 2016. Vaccine product dose(s) per vial Maximum Wastage rate* Benchmark Wastage Rate *** Yellow Fever, 10 dose(s) per vial, LYOPHILISED 10 40 % Yellow Fever, 5 dose(s) per vial, LYOPHILISED 5 10 % Meningococcal, 10 dose(s) per vial, lyophilized 10 10 % Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID 2 10 % Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID 1 5 % Rotavirus, 2-dose schedule 1 5 % Rotavirus, 3-dose schedule 1 5 % Measles, 2nd dose, 10 dose(s) per vial, LYOPHILISED 10 40 % DTP-HepB-Hib, 1 dose(s) per vial, LIQUID 1 5 % DTP-HepB-Hib, 10 dose(s) per vial, LIQUID 10 25 % 15 % DTP-HepB-Hib, 2 dose(s) per vial, lyophilized 2 10 % JE, 5 dose(s) per vial, LYOPHILISED 5 10 % HPV bivalent, 2 dose(s) per vial, LIQUID 2 10 % HPV quadrivalent, 1 dose(s) per vial, LIQUID 1 5 % MR, 10 dose(s) per vial, LYOPHILISED 10 15 % Observations: Sources WHO recommended wastage rates ** Source: *** Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat Note: HPV demonstration project wastage rates are the same as for the vaccine Table Annex 4E: Vaccine maximum packed volumes Please note that this table is used solely for reference and includes both the vaccines supported by GAVI as well as vaccines not supported. Vaccine product Designation Vaccine formulation Admin route No. Of doses in the schedule Presentation (doses/vial, prefilled) Packed volume vaccine (cm3/dose) Packed volume diluents (cm3/dose) BCG BCG lyophilized ID 1 20 1.2 0.7 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 20 2.5 Diphtheria-Tetanus-Pertussis DTP liquid IM 3 10 3 Diphtheria-Tetanus DT: liquid IM 3 10 3 Tetanus-Diphtheria Td liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 10 3 Tetanus Toxoid TT liquid IM 2 20 2.5 Tetanus Toxoid UniJect TT liquid IM 2 Uniject 12 Measles Measles lyophilized SC 1 1 26.1 20 Measles Measles lyophilized SC 1 2 13.1 13.1 Measles Measles lyophilized SC 1 5 5.2 7 Measles Measles lyophilized SC 1 10 3.5 4 Measles-Rubella lyophilized RR lyophilized SC 1 1 26.1 26.1 Measles-Rubella lyophilized RR lyophilized SC 1 2 13.1 13.1 Measles-Rubella lyophilized RR lyophilized SC 1 5 5.2 7 Measles-Rubella lyophilized RR lyophilized SC 1 10 2.5 4 Measles-Mumps-Rubella lyophilized MMR lyophilized SC 1 1 26.1 26.1 Measles-Mumps-Rubella lyophilized MMR lyophilized SC 1 2 13.1 13.1 Measles-Mumps-Rubella lyophilized MMR lyophilized SC 1 5 5.2 7 Measles-Mumps-Rubella lyophilized MMR lyophilized SC 1 10 3 4 Polio OPV liquid Oral 4 10 2 Polio OPV liquid Oral 4 20 1 Yellow fever YF lyophilized SC 1 5 6.5 7 Yellow fever YF lyophilized SC 1 10 2.5 3 Yellow fever YF lyophilized SC 1 20 1.5 2 Yellow fever YF lyophilized SC 1 50 0.7 1 DTP-HepB combined DTP-HepB liquid IM 3 1 9.7 DTP-HepB combined DTP-HepB liquid IM 3 2 6 DTP-HepB combined DTP-HepB liquid IM 3 10 3 Hepatitis B HepB liquid IM 3 1 18 Hepatitis B HepB liquid IM 3 2 13 Hepatitis B HepB liquid IM 3 6 4.5 Hepatitis B HepB liquid IM 3 10 4 Hepatitis B UniJect HepB liquid IM 3 Uniject 12 Hib liquid Hib_liq liquid IM 3 1 15 Hib liquid Hib_liq liquid IM 3 10 2.5 Hib freeze-dried Hib_lyo lyophilized IM 3 1 13 35 Hib freeze-dried Hib_lyo lyophilized IM 3 2 6 Hib freeze-dried Hib_lyo lyophilized IM 3 10 2.5 3 DTP liquid + Hib freeze-dried DTP+Hib liquid+lyop. IM 3 1 45 DTP-Hib combined liquid DTP+Hib liquid+lyop. IM 3 10 12 DTP-Hib combined liquid DTP+Hib liquid IM 3 1 32.3 DTP liquid + Hib freeze-dried DTP+Hib liquid IM 3 10 2.5 DTP liquid + Hib freeze-dried DTP-HepB-Hib liquid+lyop. IM 3 1 22 DTP-HepB-Hib liquid DTP-HepB-Hib liquid+lyop. IM 3 2 11 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 10 4.4 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 2 13.1 DTP-HepB-Hib liquid DTP-HepB-Hib liquid IM 3 1 19.2 Meningitis A/C MV_A/C lyophilized SC 1 10 2.5 4 Meningitis A/C MV_A/C lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/ MV_A/C/W/Y lyophilized SC 1 50 1.5 3 Meningococcal A/C/W/Y MV_A/C/W/Y lyophilized SC 1 10 2.5 4 Meningitis W135 MV_W135 lyophilized SC 1 10 2.5 4 Meningitis A conjugate Men_A lyophilized IM 1 10 2.6 4 Japanese Encephalitis JE_lyo lyophilized SC 1 5 2.5 2.9 Rota vaccine Rota_liq liquid Oral 2 1 17.1 Rota vaccine Rota_liq liquid Oral 3 1 45.9 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 1 11.5 Pneumo. conjugate vaccine 10-valent PCV-10 liquid IM 3 2 4.8 Pneumo. conjugate vaccine 13-valent PCV-13 liquid IM 3 1 12 Polio inactivated IPV liquid IM 3 PFS 107.4 Polio inactivated IPV liquid IM 3 10 2.5 Polio inactivated IPV liquid IM 3 1 15.7 Human Pappilomavirus vaccine HPV liquid IM 3 1 15 Human Pappilomavirus vaccine HPV liquid IM 3 2 5.7 Monovalent OPV-1 mOPV1 liquid Oral 20 1.5 Monovalent OPV-3 mOPV3 liquid Oral 20 1.5

12. Banking form In accordance with the decision on financial support made by the GAVI Alliance, the Government of Guinea-Bissau hereby requests that a payment be made via electronic bank transfer as detailed below: Name of Institution (Account Holder): Address: City Country: Telephone no.: Fax no.: Currency of the bank account: For credit to: Bank account's title: Bank account no.: Bank's name: Is the bank account exclusively to be used by this program? By who is the account audited? Signature of Government's authorizing official Seal Name: Title: Signature Dated: FINANCIAL INSTITUTION Bank's name: Branch Name: Address: City Country: Swift Code: Sort Code: ABA No.: Telephone No.: FAX No.: CORRESPONDENT BANK (in the United States) I certify that the account No. is held by at this banking institution The account must be signed jointly by at least 2 (number of signatories) of the following authorized signatories: 1 Name: Title: 2 Name: Title: 3 Name: Title: Name of bank's authorizing official Signature Dated: Seal: