GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Niger

Date of submission: 30.05.2011 14:15:53

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMS The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the program(s) described in the Country’s application. Any significant change from the approved program(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the program(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the program(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programs described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programs described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programs described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programs described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programs described in its application.

Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Pneumococcal (PCV13), 1 doses/vial, Liquid | 2012 | 2015 | Pneumococcal (PCV10), 2 doses/vial, Liquid |  |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 | Rotavirus 3-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunization

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunization

4.1.3. The Inter-Agency Coordinating Committee for Immunization

4.2. National Immunization Technical Advisory Group for Immunization

4.2.1. The NITAG Group for Immunization

5. Immunization Program Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunization coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunization budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 1.2 - Rotavirus 2-dose schedule

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.2  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

The Republic of Niger is asking for the support of the World Alliance for its backing in the introduction of  the new vaccines ‘Anti Pneumococcus and Anti-rotavirus’.  The total population at the end of 2009 is estimated at 14 340 660 inhabitants, of which 80 percent live in rural areas.

The infant mortality rate is 81 out of 1000 live births with a life expectancy of 57.2 years.  The proportion of the Government’s health expenses is 32.2% in relation to the total health budget.  The GDP is 162 815 francs CFA per head and yearly (344 USD), the economic growth rate is 3.9%.

The operational targets of the Expanded Program of Immunization and supplementary vaccinations for 2009 are, 797 004 for children surviving past the age of one year old (this target is the result of a consensus based on the number of children from 0-11 months regularly vaccinated on national vaccination days against poliomyelitis); expected births (pregnant women); 867251; children less than 5 years old 4 216 817; women of childbearing age 3 011 539.  The vaccination coverage estimated at the end of 2009 on the basis of administrative data are BCG 96%, DTC3-HepB3-Hib3: 93%, VPO3: 88%; VAR: 87%; VAA: 84% ; VAT2 +: 81%. The percentage of children of less than one year old who are routinely given extra vitamin A by EPI is estimated at 45%.  It is significant to note that the rate of gross coverage is as follows: BCG: 89%; Penta3 78% ;VAR 72%; VAA 71%; VAT2+ 82%.  The estimations of the WHO and UNICEF for a vaccine coverage gives Niger a rate of 71% for Penta3 and 73% for measles in 2009.

Despite these performances which are on the whole satisfactory, inequalities still exist between health districts.  In effect, 7% of health areas have not reached the 80% target recommended by GIVS.  This explains why the fixed objectives in the eradication/elimination and control of certain illnesses targeted by EPI have not been reached.

In Niger, the health services every year announce more than half a million cases of diarrhea of which 7% is due to dehydration.  A current study on morbidity and mortality linked to rota-virus carried out in Niamey and Maradi by EPICENTRE, shows that rota-virus is responsible for 20% of diarrhea with moderate and serious dehydration.  According to WHO, pneumonia affects   more than 1.6 million children each year and 800,00 die from it. More than 90% of these children live in developing countries, including Niger.  Pneumonia would be responsible of 16% of infantile  and juvenile deaths.

Taking into consideration strategic advice from the Global Immunization Vision and Strategy, and that given by GAVI, Niger has just drawn up its complete multi-year plan analysis for 2011-2015 with the aim of reaching by the end of 2015, a level of coverage by antigen of 90% to the national level and by 80% of each health area. This plan has a duration of five years (2011-2015) and a total amount of 312 092 489 USD of which 211 749 708 USD is destined for the purchase of new and under used vaccines.  It intends to achieve the Millennium Development Goals by reducing the morbidity and infantile mortality by two thirds as opposed to the situation before 2000.  It also hopes to introduce new vaccines, notably anti rota-virus, anti pneumococcal and vaccine for cervical cancer and that for meningitis A (MenAfri Vac).  The introduction of the pneumonia and anti rota-virus vaccines will commence respectively in 2012 and 2013.  The timescale for the introduction with the aid of the Global Alliance for Vaccines and Immunizations is 4 years for pneumococcal and 3 years for the Rotavirus. In a letter, dated 20 April 2011, GAVI informed Niger of its failing in co- financing with regards to the purchase of vaccines in 2010 totaling 189 000 000 francs CFA. The meeting of the Inter-Agency Coordination Committee on the 12 May makes recommendations to MSP that this situation cannot reoccur. These recommendations are: to appeal to the President of the Republic, to the National Assembly and to the Finance and Economic Minister to secure and make available over time the funds intended for the purchase of vaccines and consumables; to make available at the start of each year from UNICEF’s account a fund for the purchase of vaccines and consumables; to profit from opportunities from the Millennium Challenge Corporation, West African Health Organization, BID and several bilateral cooperation organizations and to submit their requests in the purchase of vaccines.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Niger would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunization program of the country, and specifically hereby requests for GAVI support for Pneumococcal (PCV13) 1 doses/vial Liquid , Rotavirus 2-dose schedule introduction.

The Government of Niger commits itself to developing national immunization services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of June.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) | Minister of Finance (or delegated authority) |
| --- | --- |
| Name | SOUMANA SANDA | Name | OUHOUMOUDOU MAHAMADOU |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr Abdoulaye Lado | Head of Immunization Divisions | 00227 20752071/ 0022796539575 | ablado19@hotmail.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunization

We the members of the ICC, HSCC, or equivalent committee[1] met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organization | Signature | Action |
| --- | --- | --- | --- |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Abdoulaye Lado | Title | Head of Immunization Divisions |
| --- | --- | --- | --- |
| Tel no | 0022796539575/ 0022720752071 |  |  |
| Fax no |  | Address | MINISTRY OF PUBLIC HEALTH BP NIAMEY NIGER |
| Email | ablado19@hptmail.com |  |  |

# The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners and NGOs) supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | INTER-AGENCY COORDINATION COMMITTEE ( ICC) |
| --- | --- |
| Year of constitution of the current committee | 2004 |
| Organizational structure (e.g., sub-committee, stand-alone) | ICC |
| Frequency of meetings | QUARTERLY |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | MINISTER OF PUBLIC HEALTH | SOUMANA SANDA |
| Secretary | HEAD OF EPI DIVISION | ABDOULAYE LADO |
| Members | Representative of WHO | MANZILA TARANDE | Action |
|  | Representative of l'UNICEF | GUIDO CORNALE |  |
|  | President, Red Cross Society Niger | ALI BANDIARE |  |
|  | President of Rotary Club | GASTON KABA |  |
|  | Representative of HKI | MARILY KNIERIEMEN |  |
|  | President ROASSIN | IDE DJERMAKOYE |  |

Major functions and responsibilities of the committee

To draw up and implement vaccination plans To give help evaluate and approve the EPI’s plans at all levels To help the national management of the Expanded Program of Immunization to maintain the clear and effective operation of the program. To support and encourage the exchange of information and of past information at all levels of the national health system and with its partners To assure the coordination of interventions of partners as regards to vaccination To coordinate the planning of all vaccination activities

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Appeal to the PTF and the government for the mobilization of resources in favour of the EPI. |
| --- | --- |
| 2. | Coordination of interventions of partners. |
| 3. | Follow up of the optimal use of resources of the program . |

# National Immunization Technical Advisory Group for Immunization

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | N/A | Title | N/A |
| --- | --- | --- | --- |
| Tel no | N/A |  |  |
| Fax no | N/A | Address | N/A |
| Email | N/A |  |  |

# The NITAG Group for Immunization

Profile of the NITAG

| Name of the NITAG | N/A |
| --- | --- |
| Year of constitution of the current NITAG | N/A |
| Organizational structure (e.g., sub-committee, stand-alone) | N/A |
| Frequency of meetings | N/A |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | N/A | N/A |
| Secretary | N/A | N/A |
| Members | N/A | N/A | Action |
|  | N/A | N/A |  |

Major functions and responsibilities of the NITAG

N/A

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | N/A |
| --- | --- |
| 2. | N/A |
| 3. | N/A |

# Immunization Program Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunization (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2009 (most recent; specify dates of data provided)

|  | Figure | Year | Source |
| --- | --- | --- | --- |
| Total population | 14,340,660 |  | 2009 | Projection made by cMYP based on the general census 2001 |
| Infant mortality rate (per 1000) | 81 |  | 2009 | JRF2010 |
| Surviving Infants[1] | 797,004 |  | 2009 | Données du consensus issues des JNV Polio |
| GNI per capita (US$) | 344 |  | 2009 | Outil du CMYP 2011-2015 Consensus data from NID Polio campaign of the cMYP 2011-2015 |
| Total Health Expenditure (THE) as a percentage of GDP | 5.90 | % | 2009 | PDS 2011-2015 |
| General government expenditure on health (GGHE) as % of General government expenditure | 31.22 | % | 2009 | cMYP2011-2015, table number 19 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The overall elaboration process of the PDS focuses on the objectives of the Strategy of Accelerated Development and Poverty Reduction and the WHO 2015, was carried out according to the Management for Results with the agreement of national experts, and was conducted in seven stages, setting up of various committees drawing up of strategic direction drawing up of the first draft of the PDS and implementation of the Framework of Medium Term Sectoral Expenditure drawing up of related documents; health cards, PDSD, PDSR PDRH.. finalization of the Strategic Plan 2011-2015 adoption of the plan by the government and the signing of COMPACT country. The document will be called PDS Strategic Plan 2011-2015. It should be noted that the complete multi year analysis, the Strategic Plan and the application formula are all aligned throughout the period.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

yes

Please indicate the national planning budgeting cycle for health

A strategic plan called PDS is planned over five years and, from which annual plans of action for each system level; (national, regional, and regional budgets) are worked out. The different regional budgets are incorporated and added to the budgets at central level to make a national budget which is examined and approved by the National Committee for Health and Safety.

Please indicate the national planning cycle for immunization

A strategic plan called PDS is planned over five years and, from which annual plans of action for each system level, (national, regional, and regional budgets) are worked out. The different regional budgets are incorporated and added to the budgets at central level to make a national budget which is examined and approved by the National Committee for Health and Safety. A national plan for vaccination extends from core level to the top. The integrated health centres draw up mini plans with the help of the community. The main points in these plans are implemented at each health district level and collectively give rise to an Action Plan for the health district. These plans are sent to central level which, in turn, draws up points leading to a National Action Plan. This long term strategy completes the Expanded Program of Vaccination and is referred to as the Strategic Plan PDS also of five year duration.

Please indicate if sex disaggregated data (SDD) is used in immunization routine reporting systems

NO

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

NO

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | Birth | Yes |  |  |
| VPO | Birth, 6,10,14 semaines | Yes |  |  |
| DTC-HepB-Hib | 6,10,14 weeks | Yes |  |  |
| Anti-measles | 9 months | Yes |  |  |
| Yellow fever | 9 months | Yes |  |  |
| VAT | 15- 49 years | Yes | Administered particularly to pregnant women. Few mass campaigns aim at both girls and women who can reproduce. |  |
| Vitamin A | 6- 11 months | Yes |  |

# Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2009 | 2010 | 2010 |  |  | 2009 | 2010 |
| BCG | 96 | 95 | 89 |  | Tuberculosis |  |  |
| DTP | DTP1 | 100 | 99 | 89 |  | Diphtheria | 0 | 0 |
|  | DTP3 | 93 | 92 | 78 |  | Pertussis | 1,354 | 30 |
| Polio 3 | 88 | 92 | 77 |  | Polio | 15 | 2 |
| Measles (first dose) | 87 | 89 | 72 |  | Measles | 801 | 372 |
| TT2+ (Pregnant women) | 81 | 85 | 82 |  | NN Tetanus | 14 | 13 |
| Hib3 | 93 | 92 | 78 |  | Hib[2] | 6 | 26 |
| Yellow Fever | 84 | 82 | 71 |  | Yellow fever | 0 | 0 |
| HepB3 | 93 | 92 | 78 |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) | 45 | 53 |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

National survey of vaccine coverage carried out in July 2010

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |
| --- | --- | --- |
|  | 2009 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 867,251 | 955,974 | 987,521 | 1,020,109 | 1,053,773 |  |  |
| Total infants' deaths | 70,247 | 77,434 | 79,989 | 82,629 | 85,356 |  |  |
| Total surviving infants | 797,004 | 878,540 | 907,532 | 937,480 | 968,417 |  |  |
| Total pregnant women | 867,251 | 955,974 | 987,521 | 1,020,109 | 1,053,773 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 832,561 | 879,496 | 918,391 | 958,903 | 1,001,084 |  |  |
| BCG coverage (%)[1] | 96% | 92% | 93% | 94% | 95% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 700,211 | 790,686 | 834,929 | 881,231 | 919,996 |  |  |
| OPV3 coverage (%)[2] | 88% | 90% | 92% | 94% | 95% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 799,887 | 878,540 | 907,532 | 937,480 | 968,417 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 741,781 | 790,686 | 834,929 | 881,231 | 919,996 |  |  |
| DTP3 coverage (%)[2] | 93% | 90% | 92% | 94% | 95% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Pneumococcal |  | 878,540 | 907,532 | 937,480 | 968,417 |  |  |
| Target population vaccinated with 3rd dose of Pneumococcal |  | 527,124 | 834,929 | 881,231 | 919,996 |  |  |
| Pneumococcal coverage (%)[2] | 0% | 60% | 92% | 94% | 95% |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  |  | 907,532 | 937,480 | 968,417 |  |  |
| Target population vaccinated with last dose of Rotavirus |  |  | 453,766 | 562,488 | 677,892 |  |  |
| Rotavirus coverage (%)[2] | 0% | 0% | 50% | 60% | 70% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 692,495 | 773,115 | 816,779 | 862,492 | 919,996 |  |  |
| Measles coverage (%)[2] | 87% | 88% | 90% | 92% | 95% |  |  |
| Pregnant women vaccinated with TT+ | 544,389 | 860,376 | 908,519 | 958,903 | 1,001,084 |  |  |
| TT+ coverage (%)[4] | 63% | 90% | 92% | 94% | 95% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months | 361,208 | 697,311 | 723,877 | 747,206 | 771,336 |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 7% | 10% | 8% | 6% | 5% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunization budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  | 2009 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| Vaccines (routine vaccines only) | 1,727,265 | 11,721,964 | 23,692,216 | 25,328,150 | 26,995,386 |  |  |  |  |
| Traditional vaccines | 732,829 | 1,001,309 | 1,054,929 | 1,111,989 | 1,165,283 |  |  |  |  |
| New and underused vaccines | 994,436 | 10,720,655 | 22,637,287 | 24,216,161 | 25,830,103 |  |  |  |  |
| Injection supplies | 585,767 | 713,478 | 809,525 | 1,560,211 | 1,618,547 |  |  |  |  |
| Personnel | 599,100 | 1,463,331 | 1,576,645 | 1,643,248 | 1,707,514 |  |  |  |  |
| Salaries of full-time NIP health workers (immunization specific) | 269,100 | 279,972 | 285,571 | 291,282 | 297,108 |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 330,000 | 1,183,359 | 1,291,074 | 1,351,966 | 1,410,406 |  |  |  |  |
| Transportation | 217,743 | 321,274 | 343,058 | 143,439 | 160,306 |  |  |  |  |
| Maintenance and overheads | 1,002,754 | 1,227,909 | 1,334,057 | 569,141 | 637,164 |  |  |  |  |
| Training | 214,264 | 653,235 | 666,300 | 679,626 | 693,218 |  |  |  |  |
| Social mobilization and IEC | 1,010,136 | 4,196,096 | 4,256,131 | 3,000,297 | 1,130,798 |  |  |  |  |
| Disease surveillance | 453,671 | 472,010 | 481,450 | 491,079 | 500,900 |  |  |  |  |
| Program management | 634,903 | 723,078 | 817,130 | 552,290 | 1,015,754 |  |  |  |  |
| Other | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Recurrent Costs | 6,445,603 | 21,492,375 | 33,976,512 | 33,967,481 | 34,459,587 |  |  |  |  |
| Routine Capital Costs |
| Vehicle | 690,820 | 730,278 | 308,016 | 423,036 | 308,204 |  |  |  |  |
| Cold chain equipment | 554,818 | 243,703 | 245,012 | 193,539 | 178,861 |  |  |  |  |
| Other capital equipment | 0 | 109,242 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Capital Costs | 1,245,638 | 1,083,223 | 553,028 | 616,575 | 487,065 |  |  |  |  |
| Campaigns |
| Polio | 9,403,364 | 4,002,332 | 4,169,359 | 4,343,774 | 4,525,920 |  |  |  |  |
| Measles | 0 | 0 | 0 | 3,266,849 | 0 |  |  |  |  |
| Yellow Fever | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| MNT campaigns | 2,747,551 | 1,412,054 | 1,487,894 | 1,567,880 | 1,652,239 |  |  |  |  |
| Other campaigns | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Subtotal Campaign Costs | 12,150,915 | 5,414,386 | 5,657,253 | 9,178,503 | 6,178,159 |  |  |  |  |
| GRAND TOTAL | 19,842,156 | 27,989,984 | 40,186,793 | 43,762,559 | 41,124,811 |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunization program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  | Estimated costs per annum in US$ (in thousand US$) |
| --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
|  |  | 2009 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Routine Recurrent Cost |
| current cost | national Government | 8,131 | 2,875 | 4,494 | 5,891 |  |  |  |  |  |  |
|  | Local Government | 0 | 0 | 0 | 2,938 |  |  |  |  |  |  |
|  | GAVI | 1,346 | 13,691 | 50,648 | 56,482 |  |  |  |  |  |  |
|  | OMS | 2,686 | 2,947 | 2,503 | 1,491 |  |  |  |  |  |  |
|  | UNICEF | 1,599 | 6,688 | 7,256 | 5,819 |  |  |  |  |  |  |
|  | JIKA | 359 | 0 | 600 | 77 |  |  |  |  |  |  |
|  | Common Fund | 0 | 1,082 | 0 | 474 |  |  |  |  |  |  |
|  | ROTARY | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | Red Cross | 0 | 40 | 40 | 40 |  |  |  |  |  |  |
|  | KOICA | 0 | 0 | 0 | 476 |  |  |  |  |  |  |
| Routine Capital Costs |  |
|  | national Government | 54 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | Local Government | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | GAVI | 1,196 | 565 | 500 | 0 |  |  |  |  |  |  |
|  | OMS | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | UNICEF | 276 | 1,025 | 1,094 | 233 |  |  |  |  |  |  |
|  | JIKA | 341 | 0 | 500 | 255 |  |  |  |  |  |  |
|  | Common Fund | 0 | 924 | 0 | 201 |  |  |  |  |  |  |
|  | ROTARY | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | Red Cross | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | KOICA | 0 | 0 | 658 | 279 |  |  |  |  |  |  |
| Campaigns |  |
|  | national Government | 0 | 0 | 0 | 1,041 |  |  |  |  |  |  |
|  | Local Government | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | GAVI | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | OMS | 9,419 | 4,106 | 4,233 | 6,432 |  |  |  |  |  |  |
|  | UNICEF | 2,626 | 3,543 | 3,749 | 4,147 |  |  |  |  |  |  |
|  | JIKA | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | Common Fund | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | ROTARY | 108 | 14 | 14 | 14 |  |  |  |  |  |  |
|  | Red Cross | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
|  | KOICA | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
| GRAND TOTAL | 28,141 | 37,500 | 76,289 | 86,290 |  |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

At central level, the country has two positive cold rooms available each with a total capacity of 90m3 and one 30m3 negative cold room. Each of these cold rooms is equipped with an emergency generator to ensure continual functioning even in the event of a power cut. At regional level, apart from the WHO/UNICEF approved freezers and refrigerators used to preserve vaccines, there is also a positive 30m3 cold room at Maradi, one positive 50m3 cold room at Zinder which serves as a secondary centre for re-supplying the regions of Zinder and Diffa and a 40m3 positive cold room at Tahoua which serves as a secondary depot for the regions of Tahoua and Agadez. From July 2011, thanks to the Korea International Cooperation Agency (KOICA) and UNICEF, six new positive cold rooms from KOICA have already been available at Niamey since February 2011. These cold rooms are set out as follows: Central level one 40m3 cold room Tillabrery region one 30m3 cold room Dosso region one 30m3 cold room Maradi region one 30m3 cold room UNICEF also plans, at the same time, to install a 30m3 cold room at Diffa and another 20m3 room at Agadez. Therefore, from July 2011, the central level will have a positive total capacity of 130m3, whilst seven of the eight regions (Agadez, Diffa, Dosso, Maradi, Tahoua, Tilabrery and Zinder) will each have at least one positive cold room with a capacity of 20m3 at Agadez to 50m3 at Zinder. Maradi will also have two positive cold rooms with a total capacity of 60m3. All of the health districts, the Integrated Health Centres and certain other places that have integrated vaccination are equipped with standard functional cold chain equipment. The provision of gas for this equipment is maintained by the partial collection of costs and from partners. The supply of vaccines from the regional depots is met every four months by the central store at Niamey by using three refrigerated vans, one of which is 5m3 and the other two each of 15m3, all of which are only three years old. The transport of injection materials and other equipment is carried out by using a 20 tonne lorry, also only three years old. The districts and the health centres each month supply the regional and district stores. The estimation of annual needs of positive storage capacity follows the yearly needs of traditional vaccines, new and under used vaccines already in existence within the program and of the pneumococcus vaccine due to be introduced in 2012 and the vaccine against the rota-virus due to be introduced in 2013.In determining these needs, targets are taken into consideration as well as the rate of loss, the packaging of each vaccine and the vaccine program contained in the complete multi-year plan analysis. The aims of the adopted vaccine coverage are those collated from unprocessed data of the coverage study carried out in July 2010 in children between 12 and 23 months. The table at figure 6.1 below shows that on the basis of two stocks per year, owing to the installation of a new cold room at Niamey as indicated previously, the introduction of the vaccine against pneumococcus in 2012 and against the rota-virus in 2013 will certainly have an impact upon the capacity of available stock, however, up until 2013, the country will have a reserve which will vary between 18 513 to 3470 liters of positive capacity. On the other hand, from 2014, if the available capacity remains the same, it will show a shortfall of 82 liters which, if nothing is done, will increase to 3 753 liters in 2015. This shortfall will continue to increase in the next few years with the increase of population size and the introduction of other vaccines. The gap of 81 liters predicted for 2014 could easily be made up by a refrigerator Vestfrost MK304, with an investment rising to 1 070 USD. The installation of a new cold room 40m3 is planned before the end of 2014 at a cost of 61 736 USD. The estimation of the storage capacity at regional level. This estimation is based upon the same principal as that of central level, with the difference that the supply is made every three months, that is four supplies each year. We predict that only Niamey will be in deficit from 2012. In reality, on the basis of a supply each quarter, the gap would be 747 liters from 2012. To close this gap the depot at Niamey needs to be supplied with seven Vestfrost MK304 refrigerators equivalent to an investment of 7 490 USD. Nevertheless, in 2012, this situation could be resolved by increasing the rate of supply. In effect, the three districts of the urban community of Niamey being at central level could be supplied monthly which would absorb this predicted gap. In the short term it would be possible to include a positive cold room in the three districts of the town.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Acute respiratory infections (ARI) like pneumococcal meningitis and meningococcal A, the viral diarrheal illnesses (rota-virus) and cervical cancer pose a health problem to Niger. In Niger the prevalence of diarrheal diseases is 22.2% in children according to a national study by the Nutrition and Survival of the Child by UNICEF carried out in May/June 2009. According to the national statistics, from 2007, the health services report on average 617 200 cases of simple diarrhea, 44200 with dehydration of which 271 resulted in deaths. According to a study in Niger by EPICENTRE in the Maradi and Niamey regions, one finds that the rota-virus is responsible for more than 20% of diarrhea with moderate and severe dehydration amongst children less than five years of age. With regards to pneumonia, in Niger the rates of infantile mortality and infantile juvenile mortality are amongst the highest in the world. Amongst the causes of this high mortality is pneumonia, according to the annual statistics of the Swiss Network for International Studies (2007), it represents 17% of cases of hospital mortality of children less than five years of age and 19% worldwide according to a report from the WHO; it figures only after Malaria (67%). The Epidemiology Research Group from the WHO has studied mortality in Niger in 2003 and has shown the distribution of mortality in children less than five years of age. This distribution shows that ARI represent the most with 25% of deaths. Four diseases represent 80% of immediate causes of infantile and juvenile mortality with 27% for pneumonia, 21% for diarrhea, 18% neonatal causes and 15% malaria. The official documents of the WHO indicate that interventions such as EPI and PLUS (vaccination, vitamin A supplements and de-worming) gives a confirmed effective safeguard in more than 80% for the first two and a good one for the latter intervention with a control of mortality of less than five years of 20%. The mortality rate in mothers is 648 out of 100 000 live births.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (liters or m3) Liters | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 37,260 | 67,346 | 74,449 | 81,792 |  |  |  |  |
| B | Existing net positive cold chain capacity (liters or m3) Liters | # | 37,143 | 37,143 | 37,143 | 37,143 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 2 | 2 | 3 | 3 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 2 | 2 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -18,513 | -3,470 | 82 | 3,753 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 1,070 | 61,736 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The implementation of these vaccine coverage objectives as set out in the 2011-2015 complete multi-year plan analysis is dependent upon the availability of financial, human and logistical resources which accompany the setting out of the EPI’s activities. The availability of the resources requires, along with releasing capital and eventually definite contributions, the mobilization of additional resources to make up the shortfall in the financing. To this effect, the financial viability strategy of the EPI should centre around the following three goals; mobilization of supplementary resources, improvement of the viability of resources, improvement of the effectiveness in using available resources With the aim of ensuring that resources are fully mobilized and on time, the following actions are carried out; Create a case for a reduction in the procedures for the release of resources allocated by the EPI at all levels in order to implement the whole of the resources to EPI activity; Make the members of the Inter-agency co-ordination committee aware of contributing on time to the budget of the complete multi-year plan analysis; Ensure a rigorous and transparent management of resources; Implement follow up procedures with regards to quality of use of allocated resources for vaccination; Maintaining vaccination budget procedures in the planning of grants of government funds (Medium Term Expenditure Frameworks) Improvement of the effectiveness of use of available resources, Optimizing the use of all available resources (human, material and logistical) to carry out or fulfil vaccination activities, To strengthen the capacity of key individuals at all levels of program operation, in planning, coordination, educational supervision and integrated monitoring; To reduce the level of waste of vaccines, To strengthen the use of open vial policy and of the Vaccine Vial Monitor by key players; Strengthen follow up on waste of vaccines, Strengthen program support communication by concentrating and redefining the actions of individuals in charge of the social mobilization in the community for the promotion of vaccination in general and the introduction of new vaccines in particular; Reduce the levels of loss by strengthening follow up of loss of sight by community links and other players of social mobilization.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| MENINGITE A Hib | Surveillance of bacterian meningitis in pediatric domanin 2002-2010 | 2011 | Net decrease in thenumber of Hib meningitis cases from 32 cases in 2002 to 2 cases in 2010 |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |
| --- | --- |
| 1) The delay in releasing of finance led to an accumulation of vaccine (2009-2010), the stock of vaccines against epidemics , and poliomyelitis, the breakdown of the cold room considerably reduced the storage capacity of vaccines at national level. 2) Malfunctioning of the positive cold rooms led to The freezing of the vaccines anti-tetanic and pentavalent. 3) Insufficient training of personnel at all Levels of the health pyramid (prevention, operation of the EPI and vaccination technique) | - Reprogramming of timescales of delivery times from initial - Dispatch of vaccines for epidemics to area districts (decentralization) -Replacement of broken parts of cold rooms -Strengthening of capacity of storage by using large capacity freezers - Recruitment of health persons into the program to reinforce the management capacity of CSI - Training of management personnel for the EPI under supervision |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

1. Vaccin anti-pneumonococcus(PCV13),1 dose/vial, liquid 2. vaccine antirotavirus 1 dose

# 6.3.1. Requested vaccine ( Pneumococcal (PCV13), 1 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce Pneumococcal (PCV13), 1 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% | 5% |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 878,540 | 907,532 | 937,480 | 968,417 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 527,124 | 834,929 | 881,231 | 919,996 |  |  |  |  |
| Immunization coverage with the third dose | Table 1 | # | 60.00% | 92.00% | 94.00% | 95.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 184,800 | 153,900 | 159,000 | 164,300 |  |  |  |  |
| Number of AD syringes | # | 197,300 | 162,800 | 168,200 | 173,700 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,200 | 1,825 | 1,875 | 1,950 |  |  |  |  |
| Total value to be co-financed by country | $ | 692,000 | 576,500 | 595,500 | 615,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 3,274,600 | 2,727,700 | 2,817,700 | 2,910,700 |  |  |  |  |
| Number of AD syringes | # | 3,496,300 | 2,884,700 | 2,979,900 | 3,078,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 38,825 | 32,025 | 33,100 | 34,175 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 12,265,500 | 10,215,000 | 10,552,000 | 10,900,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Pneumococcal (PCV13), 1 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 955,974 | 0.30 | 287,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Pneumococcal (PCV13), 1 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 653,235 | 90,000 |
| Social Mobilization, IEC and Advocacy | 4,196,096 | 10,000 |
| Cold Chain Equipment & Maintenance | 1,480,639 |  |
| Vehicles and Transportation | 1,051,552 |  |
| Program Management | 723,078 |  |
| Surveillance and Monitoring | 472,010 |  |
| Human Resources | 1,451,046 |  |
| Waste Management |  |  |
| Technical assistance |  |  |
| Autres cout capital | 109242 |  |  |
| Totals | 10,136,898 | 100,000 |

# 6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 907,532 | 937,480 | 968,417 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 453,766 | 562,488 | 677,892 |  |  |  |  |  |
| Immunization coverage with the third dose | Table 1 | # | 50.00% | 60.00% | 70.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 90,700 | 94,400 | 108,300 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,025 | 1,050 | 1,225 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 476,500 | 397,000 | 410,000 |  |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 2,291,700 | 1,890,200 | 1,941,700 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 25,450 | 21,000 | 21,575 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 12,049,500 | 7,953,500 | 7,355,000 |  |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 987,521 | 0.30 | 296,500 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |
| --- | --- | --- |
| Training | 666,300 | 90,000 |
| Social Mobilization, IEC and Advocacy | 4,256,131 | 10,000 |
| Cold Chain Equipment & Maintenance | 245,012 |  |
| Vehicles and Transportation | 651,074 |  |
| Program Management | 317,130 |  |
| Surveillance and Monitoring | 481,450 |  |
| Human Resources | 1,576,645 |  |
| Waste Management | 0 |  |
| Technical assistance | 0 |  |
| Totals | 8,193,742 | 100,000 |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

For the time being, the support management conforms to the rules of the national management budget. However, at the last meeting of the ICC on 12 May 2011, a recommendation was put to the Minister of Public Health to intervene to the Minister of Economy and Finance to secure this part of the funds directly from UNICEF/ Niger which would order the vaccines and consumables from the country’s profit.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunization commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

N/A

- Please describe the introduction of the vaccines (refer to cMYP)

The vaccines for pneumonia (PCV13) will be introduced from 2012 throughout the whole of the country. It will be administered to every child who is under one year old at the same time as the DTC6 HepB-Hib. It aims to vaccinate 60% of children and to attain the same objectives as DTC-HepB-Hib VPO from the second year. The vaccine is given in a single dose of liquid requiring 3 doses to protect the child. The vaccine against the rota-virus will be introduced from 2013 and will be administered in the same way throughout the country and under the same targets as DC-HepB-Hib. The vaccine chosen needs two doses to protect the child. It should be administered at 6 and at 10 weeks. The HPV vaccine will be introduced in 2014 and its introduction plan and submission will be the object of a request at the beginning of 2013.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

The aid asked for concerns the supply of vaccines and consumables, which are supplied directly by GAVI via UNICEF Copenhagen. The price for the introduction fees for the new pneumonia vaccine will be transferred from the common funds and managed according to the rules and procedures of fund management.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

According to the proposition made by the ICC on 12 May 2011, the shares will be directly transferred to UNICEF/Niger’s account by the Minister of Economy and Finance in line with the procedures of payment of national budget funds.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

The coverage of the new vaccine will be monitored and declared in three ways: Regulation of administrative cover (routine data) with actual computer use (SMT, DVD-MT) Study of vaccine coverage in line with sampling techniques in groups recommended by WHO; Annual surveys on nutrition and survival financed by UNICEF and organized by the Minister of Health, the National Statistic Institute and its partners.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? November  - 2007

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? May  - 2011

If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

The draft report of the GEV will be published in May 2011 and the final report will be available in June 2011. Nevertheless, an improvement plan has been drawn up at central level and will be combined into a plan of action which will take into account the main priorities. The main actions in the plan are: _the elaboration of a document of Normal Operating Procedures; _to review, calculate the required quantity and make available to the depots the management registers of stocks and delivery and order forms; _send clear instructions to all levels on the systematic use of management registers of stocks and order and delivery forms; _training of warehouse management, drivers of supply vehicles and warehouse personnel; _drawing up of emergency plans in the event of a breakdown of equipment of the CDF and transport; _drawing up of six monthly plans for preventative maintenance for buildings and equipment of the CDF (cold rooms, emergency generator, etc); _carry out a systematic study of temperatures for all cold rooms; _compile a temperature chart for all cold rooms; _acquire and make available at depots a continual temperature gauge to indicate freezing point; _equip health centers with waste disposal units that conform to the required standards; _build dry shops in certain regions and identifiable districts; _strengthen the storage capacities for the regions of Dosso and Niamey; _make the depot at Tillabery operational; _equip the depots at Niamey and Diffa with emergency generators; _acquire and make available tension stabilizers at the regional and district depots; _generalize the use of the SMT and DVD-MT.

When is the next Effective Vaccine Management (EVM) Assessment planned? November  - 2013

Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

1.The ICC has duly noted with satisfaction the urgency that the President of the Republic has given to improving the vaccine coverage, and has recommended that it be referred to the National Assembly and its counterpart of the Finance Economy to increase and make available financing for the vaccination program; 2. To secure a specific budget guideline for vaccinations and consumables; 3 To allocate directly at the start of every year, the share from the State and the co financers from UNICEF/Niger account for the purchase of vaccines and consumables; 4 Put the payment intended for the introduction of Pneumococcal vaccine into a common fund which will be managed according to regulations and procedures. For the administration plan, the ICC recommends to the Minister to take all necessary steps to develop the immunization program to a national level and strengthen the follow up mechanisms and control of use of resources and to review the law in the creation of the ICC to create a larger secretariat including the director in the fight against disease and the main points of the EPI WHO/UNICEF and Rotary. On the technical side, the ICC recommends that the meetings of the Core Group be formalized and made more regular, twice per month, particularly those referring to vaccination, to prepare technical dossiers for submission to ICC. The Core Group, having noted the existing opportunities with regards to vaccination, particularly the “Millennium Challenge” the Islamic Development Bank, the West African Health Organization, the United States Ambassadors and of France have recommended to the Minister for Public Health to uphold the cooperation network and elaborate and refer to these institutions for urgent aid.

# Annexes

# Annex 1

# Annex 1.1 – Pneumococcal (PCV13), 1 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 184,800 | 153,900 | 159,000 | 164,300 |  |  |  |  |
| Number of AD syringes | # | 197,300 | 162,800 | 168,200 | 173,700 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 2,200 | 1,825 | 1,875 | 1,950 |  |  |  |  |
| Total value to be co-financed by the country | $ | 692,000 | 576,500 | 595,500 | 615,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 3,274,600 | 2,727,700 | 2,817,700 | 2,910,700 |  |  |  |  |
| Number of AD syringes | # | 3,496,300 | 2,884,700 | 2,979,900 | 3,078,300 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 38,825 | 32,025 | 33,100 | 34,175 |  |  |  |  |
| Total value to be co-financed by the country | $ | 12,265,500 | 10,215,000 | 10,552,000 | 10,900,500 |  |  |  |  |

Table 1.1  C - Summary table for Pneumococcal (PCV13), 1 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 878,540 | 907,532 | 937,480 | 968,417 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 527,124 | 834,929 | 881,231 | 919,996 |  |  |  |  |
| Immunization coverage with the last dose | Table 1 | # | 60.00% | 92.00% | 94.00% | 95.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 878,540 | 907,532 | 937,480 | 968,417 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 3.500 | 3.500 | 3.500 | 3.500 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 878,540 | 46,911 | 831,629 | 907,532 | 48,468 | 859,064 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 2,635,620 | 140,732 | 2,494,888 | 2,722,596 | 145,403 | 2,577,193 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 2,767,401 | 147,769 | 2,619,632 | 2,858,726 | 152,673 | 2,706,053 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 691,851 | 36,943 | 654,908 | 22,832 | 1,220 | 21,612 |
| I | Total vaccine doses needed | F + G | 3,459,252 | 184,711 | 3,274,541 | 2,881,558 | 153,892 | 2,727,666 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 3,693,493 | 197,219 | 3,496,274 | 3,047,426 | 162,750 | 2,884,676 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 40,998 | 2,190 | 38,808 | 33,827 | 1,807 | 32,020 |
| N | Cost of vaccines needed | I * vaccine price per dose | 12,107,382 | 646,488 | 11,460,894 | 10,085,453 | 538,621 | 9,546,832 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 195,756 | 10,453 | 185,303 | 161,514 | 8,626 | 152,888 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 26,239 | 1,402 | 24,837 | 21,650 | 1,157 | 20,493 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 605,370 | 32,325 | 573,045 | 504,273 | 26,932 | 477,341 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 22,200 | 1,186 | 21,014 | 18,317 | 979 | 17,338 |
| T | Total fund needed | (N + O + P + Q + R + S) | 12,956,947 | 691,851 | 12,265,096 | 10,791,207 | 576,312 | 10,214,895 |
| U | Total country co-financing | I * country co-financing per dose | 691,851 |  |  | 576,312 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Pneumococcal (PCV13), 1 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 | 2015 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.34% |  |  | 5.34% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 937,480 | 50,067 | 887,413 | 968,417 | 51,720 | 916,697 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 2,812,440 | 150,201 | 2,662,239 | 2,905,251 | 155,158 | 2,750,093 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 2,953,062 | 157,711 | 2,795,351 | 3,050,514 | 162,915 | 2,887,599 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 23,584 | 1,260 | 22,324 | 24,363 | 1,302 | 23,061 |
| I | Total vaccine doses needed | F + G | 2,976,646 | 158,970 | 2,817,676 | 3,074,877 | 164,217 | 2,910,660 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 3,147,987 | 168,121 | 2,979,866 | 3,251,872 | 173,669 | 3,078,203 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 34,943 | 1,867 | 33,076 | 36,096 | 1,928 | 34,168 |
| N | Cost of vaccines needed | I * vaccine price per dose | 10,418,261 | 556,395 | 9,861,866 | 10,762,070 | 574,757 | 10,187,313 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 166,844 | 8,911 | 157,933 | 172,350 | 9,205 | 163,145 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 22,364 | 1,195 | 21,169 | 23,102 | 1,234 | 21,868 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 520,914 | 27,820 | 493,094 | 538,104 | 28,738 | 509,366 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 18,921 | 1,011 | 17,910 | 19,546 | 1,044 | 18,502 |
| T | Total fund needed | (N + O + P + Q + R + S) | 11,147,304 | 595,330 | 10,551,974 | 11,515,172 | 614,976 | 10,900,196 |
| U | Total country co-financing | I * country co-financing per dose | 595,330 |  |  | 614,976 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.34% |  |  | 5.34% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Rotavirus 2-dose schedule

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 90,700 | 94,400 | 108,300 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 1,025 | 1,050 | 1,225 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 476,500 | 397,000 | 410,000 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 2,291,700 | 1,890,200 | 1,941,700 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 25,450 | 21,000 | 21,575 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 12,049,500 | 7,953,500 | 7,355,000 |  |  |  |  |

Table 1.2  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 907,532 | 937,480 | 968,417 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 453,766 | 562,488 | 677,892 |  |  |  |  |
| Immunization coverage with the last dose | Table 1 | # |  | 50.00% | 60.00% | 70.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 907,532 | 937,480 | 968,417 |  |  |  |  |
| Number of doses per child |  | # |  | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # |  | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # |  | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 | 2014 |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.80% |  |  | 4.75% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 907,532 | 34,522 | 873,010 | 937,480 | 44,560 | 892,920 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 1,815,064 | 69,043 | 1,746,021 | 1,874,960 | 89,119 | 1,785,841 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 1,905,818 | 72,495 | 1,833,323 | 1,968,708 | 93,575 | 1,875,133 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 476,455 | 18,124 | 458,331 | 15,723 | 748 | 14,975 |
| I | Total vaccine doses needed | F + G | 2,382,273 | 90,619 | 2,291,654 | 1,984,431 | 94,322 | 1,890,109 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 26,444 | 1,006 | 25,438 | 22,028 | 1,048 | 20,980 |
| N | Cost of vaccines needed | I * vaccine price per dose | 11,911,365 | 453,093 | 11,458,272 | 7,937,724 | 377,286 | 7,560,438 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 16,925 | 644 | 16,281 | 14,098 | 671 | 13,427 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 595,569 | 22,655 | 572,914 | 396,887 | 18,865 | 378,022 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,693 | 65 | 1,628 | 1,410 | 68 | 1,342 |
| T | Total fund needed | (N + O + P + Q + R + S) | 12,525,552 | 476,456 | 12,049,096 | 8,350,119 | 396,887 | 7,953,232 |
| U | Total country co-financing | I * country co-financing per dose | 476,455 |  |  | 396,887 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.80% |  |  | 4.75% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |
| --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.28% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 968,417 | 51,134 | 917,283 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 1,936,834 | 102,267 | 1,834,567 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 2,033,676 | 107,380 | 1,926,296 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 16,242 | 858 | 15,384 |  |  |  |
| I | Total vaccine doses needed | F + G | 2,049,918 | 108,238 | 1,941,680 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 22,755 | 1,202 | 21,553 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 7,379,705 | 389,656 | 6,990,049 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 14,564 | 769 | 13,795 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 368,986 | 19,483 | 349,503 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,457 | 77 | 1,380 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 7,764,712 | 409,984 | 7,354,728 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 409,984 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.28% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ | 250’000 $ | 2’000’000 $ |
| --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pneumococcal(PCV13), 1 doses/vial, Liquid | 0.20 | 0.20 | 0.20 | 0.20 |  |  |  |
| Rotavirus 2-dose schedule |  | 0.20 | 0.20 | 0.20 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 10 | Yes |
| Improvement plan based on EVM |  | 7 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  |  |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 8, 9 |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name | New file | Actions |
| --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: signatuer du MSP soumission nouveau vaccins.docx Date/Time: 30.05.2011 11:12:26 Size: 96 KB |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: signatuer du MEF soumission nouveau vaccins.docx Date/Time: 30.05.2011 11:14:32 Size: 96 KB |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: signatures des membres de CCIA pour la soumission pour l'introduction des nouveaux vaccins.docx Date/Time: 30.05.2011 11:09:43 Size: 89 KB |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: réunion CCIA avalisant la soumission aux nouveaux vaccins 2010.docx Date/Time: 30.05.2011 11:11:14 Size: 220 KB |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: C:\Documents and Settings\nsanzabaganwac\Bureau\Documents amendés GAVI\PPAC_Niger_2011- 2015 VF Corrigée gill. MH et ZK.doc Date/Time: 28.05.2011 08:04:33 Size: 1 MB |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: C:\Documents and Settings\nsanzabaganwac\Bureau\Documents amendés GAVI\cMYP_Costing_Tool_Vs.2.5_FR VF Dosso.xls Date/Time: 28.05.2011 08:07:56 Size: 3 MB |  |  |
| 7 | File Type: Improvement plan based on EVM * File Desc: | File name: C:\Documents and Settings\nsanzabaganwac\Bureau\Documents amendés GAVI\Rapport Evaluation GEV_27_5_11.doc Date/Time: 28.05.2011 08:14:21 Size: 2 MB |  |  |
| 8 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: C:\Documents and Settings\nsanzabaganwac\Bureau\Documents amendés GAVI\Plan introduction PCV_Nig_11.doc Date/Time: 28.05.2011 08:09:50 Size: 1 MB |  |  |
| 9 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: C:\Documents and Settings\nsanzabaganwac\Bureau\Documents amendés GAVI\Plan Introduc_Rota_amd_26_11.doc Date/Time: 28.05.2011 08:11:15 Size: 815 KB |  |  |
| 10 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: G:\dossier annexe GAVI 2\Compte rendu réunion CCIA 2010.docx Date/Time: 30.05.2011 13:57:10 Size: 908 KB |  |  |

Banking Form

| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Niger hereby requests that a payment be made via electronic bank transfer as detailed below: |  |
| --- | --- |
| Name of Institution (Account Holder): |  |  |
| Address: |  |  |
| City Country: |  |  |
| Telephone no.: |  | Fax no.: |  |  |
| Currency of the bank account: |  |  |
| For credit to: |  |
| Bank account's title: |  |  |
| Bank account no.: |  |  |
| Bank's name: |  |  |

Is the bank account exclusively to be used by this program?

By who is the account audited?

Signature of Government’s authorizing official

| Name: |  | Seal |
| --- | --- | --- |
| Title: |  |  |
| Signature: |  |  |
| Date: |  |  |

| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| --- | --- |
| Bank Name: |  |  |  |
| Branch Name: |  |  |  |
| Address: |  |  |  |
| City Country: |  |  |  |
| Swift Code: |  |  |  |
| Sort Code: |  |  |  |
| ABA No.: |  |  |  |
| Telephone No.: |  |  |  |
| FAX No.: |  |  |  |

I certify that the account no is held by (Institution name) at this banking institution.

| The account is to be signed jointly by at least 0 (number of signatories) of the following authorized signatories: |
| --- |
| 1 |  |
|  | Name: |  |
|  | Title: |  |
| 2 |  |
|  | Name: |  |
|  | Title: |  |
| 3 |  |
|  | Name: |  |
|  | Title: |  |
| 4 |  |
|  | Name: |  |
|  | Title: |  |

Name of bank’s authorizing official

Signature:

Date:

Seal: