Expanded Program on Immunization

Ministry of Health, Government of Pakistan

PROPOSAL

for support to:

New and Under-Used Vaccines

(for Pentavalent  DPT-HepB-Hib) 1dose /vial all liquid vaccine

Under

Global Alliance for Vaccines and Immunization Phase-2

Submitted to GAVI by MOH Pakistan: April 2007

Re - submitted with clarifications: September 2007

## CONTENTS

|  |  | Page |
| --- | --- | --- |
|  | Executive Summary | 2 |
|  | Signatures of the Government and National Coordinating Bodies | 5 |
|  | National Coordinating body (National Health sector Coordination Committee (NHSCC) and National Interagency Coordination Committee for Immunization (NICC)) | 6 |
|  | 2.2 National Inter-Agency Coordinating Committee for Immunization | 8 |
|  | Immunization Programme Data | 9 |
|  | Immunization Fact Sheet | 9 |
|  | New and Under Used Vaccine Support (NVS) | 15 |
|  | First preference vaccines | 18 |
|  | Second preference vaccines | 20 |
|  | Procurement and Management of New and Under used vaccines | 21 |
|  | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | 23 |
|  | Documents required for each type of support | 24 |
|  | Annex 1 – Banking Form | 25 |

## Executive Summary

The Expanded Programme on Immunization Pakistan was started in 1978. It currently provides routine immunization services to children under 1 year of age and TT immunization to the pregnant women, besides conducting SIAs for Polio, Measles, and Tetanus, targeting different age groups. The surviving infants and pregnant women for 2006 are estimated to be 5,378,305 and 6,748,044 respectively.

Hepatitis B Vaccine (Monovalent) was introduced in routine EPI in a phased manner with GAVI support in 2001. Under the same GAVI support, it was switched to Tetravalent Combo (DPT-Hep B) in mid 2006.

During last two years a number of discussions and debates were held on the issue of inclusion of Hib Vaccine in routine EPI by all the EPI Pakistan stake holders i.e. MoH, MoP, NICC, NEAG. The high cost of this vaccine was often considered as a financial constraint for its introduction in the routine EPI. However, with the latest recommendation of WHO for inclusion of this vaccine in routine EPI schedule, increased evidence of Hib disease burden and the availability of the co-financing option under GAVI Phase-2, the EPI partners developed a consensus for introduction of Hib vaccine in routine EPI schedule from mid 2008.

Through this proposal GoP and NICC requests, GAVI alliance to consider support for  EPI Pakistan  under GAVI Phase-2 for provision of Pentavalent( DPT-Hep B-Hib) 1 Dose/ vial all liquid vaccine for 2008-2010 . However, 2 dose/vial lyophilized vaccine is also included in this proposal as second option.

There was a stagnation in the number of children reached with routine EPI antigens during 2004 and 2005. The BCG, DPT-3, HepB-3 and MCV1 coverage during 2005 was 89%, 72%, 73% and 77%.Much improvement has been made in 2006 whereby  the BCG, DPT-3,HepB-3 and MCV1 National administrative  coverage is reported to be 89%, 86%, 84% and 84% respectively. The TT2 reported coverage for pregnant women also increased from 46% in 2005 to 50% in 2006.

The basis of the proposal is the comprehensive multiyear plan of action (cMYP) 2005-2010. The population projections and the coverage targets in cMYP for 2007-2010 has been used in this proposals and are summarized below:

| Year | Total births | Surviving Infants | Planned % coverage of all Routine EPI antigens for 0-11 m | Pregnant Women | % coverage with TT2+ |
| --- | --- | --- | --- | --- | --- |
| 2007 | 6,013,023 | 5,531,981 | 85% | 6,013,023 | 70 |
| 2008 | 6,036,603 | 5,571,785 | 87% | 6,036,603 | 80 |
| 2009 | 6,093,175 | 5,624,001 | 90% | 6,093,175 | 85 |
| 2010 | 6,148,985 | 5,675,513 | 90% | 6,148,985 | 90 |

The number of Pentavalent  (DPT-HepB-Hib)  vaccine doses, associated injection safety supplies and the cost required each year is as following:

|  | 2008 | 2009 | 2010 | 2008-2010 |
| --- | --- | --- | --- | --- |
| No. of doses of Pentavalent (DPT-HepB-Hib) vaccine | 10,640,369 | 20,016,430 | 17,918,432 | 48,575,231 |
| No. of AD Syringes | 11,360,874 | 21,281,841 | 18,944,486 | 51,587,201 |
| No. of safety boxes | 126,106 | 236,228 | 210,284 | 572,618 |
| Total value(Vaccine, AD Syringes, Safety boxes) (US $) | 39,631,078 | 74,639,292 | 59,567,691 | 173,838,061 |
| GoP Co-financing Share (US $) | 3,192,111 | 6,004,929 | 5,375,529 | 14,572,569 |
| GAVI contribution (US $) | 36,438,968 | 68,634,363 | 54,192,162 | 159,265,493 |

The GoP agrees to provide the required funds as part of its co-financing share, given in the above table on regular basis as further described in the proposal.

Of the available two preparations of the Hib Vaccine being currently offered under GAVI-Phase 2 support EPI Pakistan will prefer all liquid preparation i.e. Pentavalent (DPT-Hep B-Hib) 1 dose/vial vaccine. The Pentavalent vaccine will be introduced country wide from 1st July 2008. A detailed plan for its introduction has been prepared and approved by the ICC. The plan takes into account the importance of reaching the laid down targets and improving the vaccine management with reduction in the vaccine wastage.

The original  proposal was developed by a working group of the EPI and key NICC members and was discussed in detail in joint NICC and NHSCC meeting  held on  16 th April 2007  at  National Institute of Health . Islamabad.

The revised version  i.e of September 2007 of this proposal   was prepared by Federal EPI Pakistan  in  the light of the  IRC comments conveyed vide GAVI decision letter dated 25 June 2007  in consultation with key EPI partners i.e WHO and UNICEF, thereby correcting certain figures

| Table 2.1a: Targets and budgets for the introduction of First Vaccine Presentation ( Pentavalent (DPT-HepB-Hib) 1 dose/via all liquid vaccine) . |
| --- |
| Total requirements |  | Base year (2007) | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 2011 | Year 5 2012 |
| National target for children to be immunized with 3rd dose of Pentavalent( DPT-HepB-Hib) vaccine | # | 0 | 2,423,726 | 5,061,601 | 5,107,962 |  |  |
| National Target for children to be immunized with 1st dose of Pentavalent( DPT-HepB-Hib) vaccine | # |  | 2,702,316 | 5,624,001 | 5,675,513 |  |  |
| Total number of vaccine doses required | # |  | 10,640,369 | 20,016,430 | 17,918,432 |  |  |
| Total number of AD syringes required | # |  | 11,360,874 | 21,281,841 | 18,944,486 |  |  |
| Total number of reconstitution syringes required | # |  | 0 | 0 | 0 |  |  |
| Total number of safety boxes required | # |  | 126,106 | 236,228 | 210,284 |  |  |
| Total budget | Price per vaccine dose | $ |  | 3.725 | 3.729 | 3.324 |  |  |
|  | Total funding required | $ |  | 39,631,078 | 74,639,292 | 59,567,691 |  |  |
| Country co-financing | Co-financing per dose | $ |  | 0.30 | 0.30 | 0.30 |  |  |
|  | Total country payment | $ |  | 3,192,,111 | 6,004,929 | 5,375,529 |  |  |
| GAVI Alliance support requested | GAVI payment per dose | $ |  | 3.425 | 3.429 | 3.024 |  |  |
|  | Total GAVI payment | $ |  | 36,438,968 | 68,634,363 | 54,192,162 |  |  |

| Table 2.1b: Targets and budgets for the introduction of Second Vaccine Presentation: Pentavalent (DPT-HepB-Hib) 2 dose/via lyophilized vaccine |
| --- |
| Total requirements |  | Base year | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 20… | Year 5 20… |
| National target for children to be immunized with 3rd dose of Pentavalent( DPT-HepB-Hib) vaccine | # | 0 | 2,423,726 | 5,061,601 | 5,107,962 |  |  |
| National Target for children to be immunized with 1st dose of Pentavalent( DPT-HepB-Hib) vaccine | # |  | 2,702,316 | 5,624,001 | 5,675,513 |  |  |
| Total number of vaccine doses required | # |  | 10,640,369 | 20,016,430 | 17,918,432 |  |  |
| Total number of AD syringes required | # |  | 11,360,874 | 21,281,841 | 18,944,486 |  |  |
| Total number of reconstitution syringes required | # |  | 0 | 0 | 0 |  |  |
| Total number of safety boxes required | # |  | 126,106 | 236,228 | 210,284 |  |  |
| Total budget | Price per vaccine dose * | $ |  | 3.2 | 2.9 | 2.65 |  |  |
|  | Total funding required | $ |  | 35,331,195 | 60,485,475 | 55,513,988 |  |  |
| Country co-financing | Co-financing per dose | $ |  | 0.30 | 0.30 | 0.30 |  |  |
|  | Total country payment | $ |  | 3,192,111 | 6,062,436 | 6,019,013 |  |  |
| GAVI Alliance support requested | GAVI payment per dose | $ |  | 2.9 | 2.6 | 2.35 |  |  |
|  | Total GAVI payment | $ |  | 32,139,084 | 54,423,039 | 49,494,975 |  |  |

Following the regulations of the internal budgeting and financing cycles the Government will normally release its portion of the funds in the month of October 2007. Payment of the procurement of the first year of co-financed support will be made around November 2007.

The Government agrees to use UNICEF Supply Division (Copenhagen) as its procurement agency for the purchase of the supply detailed in this application.  Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

2.1	National Coordinating body  (National Health sector Coordination Committee (NHSCC) and National Interagency Coordination Committee for Immunization (NICC)):

We, the members of the ICC met on the 16th April 2007. to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .01)

| SN | Agency/Organisation | Name & Designation |
| --- | --- | --- |
| 1 | Ministry of Health, Government of Pakistan | Mr. Mohammad Nasir Khan, Minister for Health |
| 2 |  | Mr. Khushnood Akhtar Lashari Secretary Health |
| 3 |  | Dr. Abdul Majid Rajput, DG Health |
| 4 |  | Maj Gen (Retd) Masood Anwar,Executive Director NIH/ NC EPI |
| 5 |  | DR Huma Qureshi, Executive Director Pakistan Medical Research Council (PMRC) |
| 6 |  | Dr. Rehan A. Hafiz, National Programme Manager, EPI |
| 7 |  | Dr. Altaf Hussain Bosan, Deputy National Programme Manager, EPI |
| 8 |  | Mr. Mazhar Nisar Sheikh, Health Education Advisor |
| 9 | Provincial Health Department | Dr. Muhammad Aslam Chaudhri, Director General Health Services (DGHS), Punjab |
| 10 |  | Dr. Ruhullah Jan, DGHSs office, NWFP, Peshawar |
| 11 |  | Dr. Muhammad Qurban, DGHSs, AJK, Muzaffarabad |
| 12 | WHO | Dr. Khalif Bile Mahmoud, WHO Country Representative |
| 13 |  | Dr. Ahmed Shadoul |
| 14 |  | Dr. Werner Bouhler |
| 15 |  | Ghiasuddin Baloch |
| 16 |  | Dr. Quamrul Hasan, STC |
| 17 | WHO EMRO | Mounir Farag |
| 18 | WHO HQ Geneva | Piva Paolo |
| 19 | Rotary International Paksitan | Mr. Abdul Haiy Khan,Chairman |
| 20 | Civil Society Organization | Dr. Sania Nishter, President Heartfile, Islamabad |
| 21 | Agha Khan University | Dr. Anita Zaidi, Assistant Professor |
| 22 | World Bank | Dr. Inamul Haq, Senior Consultant |
| 23 | UNICEF | Dr. Azhar Abid Raza, Project Officer MCHC |
| 24 | DFID | Jane Edmondson, Health and Population Advisor |
| 25 | JICA | Hiloyuki Nod, Programme Officer, JICA |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr. Rehan A Hafiz | Title: National Program Manager, EPI |
| --- | --- |
| Tel No: 00 92 51 9255101, 9255360, 9255370 | Address: Federal EPI, National Institute of Health, Park Road, Chack Shahzad, Islamabad, Pakistan |
| Fax No.: 00 92 51 9255086, 9255460 |  |
| Email: drrehan@mail.comsats.net.pk |  |

The GAVI Secretariat is unable to return documents and attachments.  Unless otherwise specified by the country, documents may be shared with the GAVI Alliance partners and collaborators.

## 2.2	The National Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).

The ICC are responsible for coordinating and guiding the use of the GAVI Alliance New and Under-Used Vaccine support, as well as all other immunization activities in the country.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

Name of the ICC: National Interagency Coordination Committee (NICC)

Date of constitution of the current ICC: 21ST February 2000

Organisational structure (e.g., sub-committee, stand-alone): Stand-alone

Frequency of meetings: Quarterly

Composition

| SN | Agency/Organisation | Name & Designation |
| --- | --- | --- |
| 1 | Ministry of Health | Mr. Mohammad Nasir Khan, Minister for Health |
| 2 |  | Mr. Khushnood Akhtar Lashari Secretary Health |
| 3 |  | Dr. Abdul Majid Rajput, DG Health |
| 4 |  | Dr. Rehan A. Hafiz, National Programme Manager, EPI |
| 5 |  | Dr. Altaf Hussain Bosan, Deputy National Programme Manager, EPI |
| 6 | Planning & Development Division | Dr. Muhammad Shafiquddin, Chief |
| 7 |  | Dr. Ali Asghar Abbasi, Deputy Chief |
| 8 | Provincial Health Department | Dr. Muhammad Aslam Chaudhri, Director General Health Services (DGHS), Punjab |
| 9 |  | Dr. Ruhullah Jan, DGHSs office, NWFP, Peshawar |
| 10 |  | Dr. Muhammad Qurban, DGHSs, AJK, Muzaffarabad |
| 11 | WHO | Dr. Khalif Bile Mahmoud, WHO Country Representative |
| 12 |  | Dr. Quamrul Hasan, STC |
| 13 | Rotary International Paksitan | Mr. Abdul Haiy Khan,Chairman |
| 14 | Civil Society Organization | Dr. Sania Nishter, President Heartfile, Islamabad |
| 15 | Agha Khan University | Dr. Anita Zaidi, Assistant Professor |
| 16 | World Bank | Dr. Inamul Haq, Senior Consultant |
| 17 | UNICEF | Dr. Azhar Abid Raza, Project Officer MCHC |
| 18 | DFID | Jane Edmondson, Health and Population Advisor |
| 19 | JICA | Hiloyuki Nod, Programme Officer, JICA |

Major functions and responsibilities of the ICC:

1. Coordinate support at national level from government and partner agencies to strengthen EPI and polio eradication activities in Pakistan.

2. Mobilize the national government and NGOs to eradicate polio and control other vaccine preventable diseases.

3. Assist Pakistan in becoming self-sufficient in its immunization programmes.

4. Establish a forum of exchange of information and dialogue on immunization programmes in the country and facilitate that dialogue by making data information sources readily available.

5. Ensure the availability of appropriate policies, advice and tools to the Pakistan government.

6. Assist the international and national in identifying and developing support for new disease control programmes when appropriate intervention tools such as new vaccines, become available.

7. Advise the government in specific areas related to EPI and Polio Eradication where partner agencies have specialized expertise.

8. Review progress towards polio eradication, improving routine EPI coverage, and plans for further strengthening of EPI.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1.  Regular   NICC meetings at least one in each quarter. Including at least one joint NICC and National Health Sector Coordination Committee meeting in six months.

2. Expansion of NICC to included further representatives from   reputable CSO and Research institutions

3. Active involvement of NICC or its sub committees in quarterly   EPI review   meetings being held at provincial headquarters.

## Immunization Program Data

Please complete the tables below, using data from available sources.  Please identify the source of the data, and the date. Where possible use the most recent data, and attach the source document.

  - Please refer to the Comprehensive Multi-Year Plan for Immunization (or equivalent plan), and attach a complete copy (with an executive summary) as DOCUMENT NUMBER   6.

  - Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms on Vaccine Preventable Diseases and attach them as DOCUMENT NUMBERS   5.

  - Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

Table 3.1: Basic facts for the year 2007… (most recent; specify dates of data provided and source)

Fact Sheet

|  | Figure | Date | Source |
| --- | --- | --- | --- |
| Total population (2007) | 168.432 million | 2007 | Federal EPI population projection based on 1998 Census and cMYP 2005-2010 |
| Infant mortality rate (per 1000) | 77 | 2007 | -do- |
| Surviving Infants* | 5,531,981 | 2007 | -do- |
| GNI per capita (US$) | 847 | 2005-2006 | Pakistan Economic Survey 2005-2006. Finance Division, Government of Pakistan |
| Percentage of GDP allocated to Health | 0.51 |  | -do- |
| Percentage of Government expenditure on Health | 27.7 |  | WHO EMRO – Country Profiles ( http://www.emro.who.int/emrinfo/index.asp) |

* Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country:

Please indicate the name and date of the relevant planning document for health

Medium Term Development Framework (MTDF)  2005-210 , Planning Commission , Government of Pakistan.

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content etc)?

Yes.  The cMYP was updated for the period 2005-2010 to be aligned with the MTDF.

Please indicate the national planning budgeting cycle for health

It is same as MTDF i.e. 2005-2010

Please indicate the national planning cycle for immunization

The current planning document ( PC-1) is for the period 2004-05 to 2008-09

Table 3.2: 	Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement (refer to cMYP pages or updated Multi-Year Plan)  -Page 9 of cMYP

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: | Comments |
| --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | At birth | x |  |  |
| OPV | 6 weeks,10 weeks,14 weeks | x |  |  |
| DPT | 6 weeks,10 weeks,14 weeks | x |  |  |
| HepB | 6 weeks,10 weeks,14 weeks | x |  |  |
| Tetra Valent (DPT-Hep B) | 6 weeks,10 weeks,14 weeks | X |  |  |
| MEASLES | 9 months | x |  |  |
| TT | Pregnant women | x |  |  |
| Vitamin A |  |  | x | Pilot campaign in this regards has been undertaken. Being implemented in selected districts and will be expanded to other districts in 2007. |

Table 3.3: Trends of routine immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form (Document No.5) on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) | Vaccine preventable disease burden |
| --- | --- |
| Vaccine | Reported | Survey | Disease | Number of reported cases |
|  | 2005 | 2006 | 2005 | 2006 |  | 2005 | 2006 |
| BCG | 89 | 86 | 82 | 77.7% | Tuberculosis* | 265 | 439 |
| DTP | DTP1 | 84 | 92 | 74.6% | 74.6% | Diphtheria | 23 | 42 |
|  | DTP3 | 72 | 83 | 64.5% | 64.5% | Pertussis | 133 | 313 |
| Polio 3 | 77 | 83 | 81 | 64.4% | Polio | 28 | 40 |
| Measles (first dose) | 77 | 82 | 78 | 62.6% | Measles | 2981 | 7641 |
| TT2+ (Pregnant women) | 46 | 50 |  | 62.5% | Neonatal Tetanus *** | 518 | 548 |
| Hib3 |  |  |  | ND | Hib *** |  |  |
| Yellow Fever |  |  |  | ND | Yellow fever |  |  |
| HepB3 | 73 | 82 | ND | 60.7% | Hepatitis B sero-prevalence* |  |  |
| Vit A supplement | Mothers (<6 weeks post-delivery) |  |  | ND | ND |  |  |  |
|  | Infants (>6 months) |  |  | ND | ND |  |  |  |

- If available ** If ‘total’ tetanus data only is available, please give it and note that this is the case *** Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, and the age groups the data refers to:

Table 3.4: Baseline and annual targets

| Number | Baseline and targets |
| --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program | Year 6 of Program |
|  | 2005 | 2006… | 2007… | 2008… | 2009… | 2010… | 2011… | 2012… | 2013 |
| Births | 5,688,724 | 5,814,384 | 6,013,023 | 6,036,603 | 6,093,175 | 6,148,985 | 6,203,964 | 6,258,041 | 6,311,139 |
| Infants’ deaths |  |  | 481,042 | 464,818 | 469,174 | 473,472 | 477,705 | 481,870 | 485,958 |
| Surviving infants | 5,262,070 | 5,378,305 | 5,531,981 | 5,571,785 | 5,624,001 | 5,675,513 | 5,726,259 | 5,776,171 | 5,825,181 |
| Pregnant women | 6,601,689 | 6,748,044 | 6,013,023 | 6,036,603 | 6,093,175 | 6,148,985 | 6,203,964 | 6,258,041 | 6,311,139 |
| Infants vaccinated with BCG | 5,044,017 | 5,198,860 | 5,111,070 | 5,251,845 | 5,483,858 | 5,534,087 | 5,707,647 | 5,882,559 | 6,058,693 |
| BCG coverage* | 89% | 89.4% | 85% | 87% | 90% | 90% | 92% | 94% | 96% |
| Infants vaccinated with OPV3 | 4,044,588 | 4,608,822 | 4,702,184 | 4,847,453 | 5,061,601 | 5,107,962 | 5,268,158 | 5,429,601 | 5,592,174 |
| OPV3 coverage** | 77% | 85.69% | 85% | 87% | 90% | 90% | 92% | 94% | 96% |
| Infants vaccinated with DTP3*** | 3,804,921 | 4,608,822 |  |  |  |  |  |  |  |
| DTP3 coverage** | 72% | 85.69% |  |  |  |  |  |  |  |
| Infants vaccinated with DTP1*** | 4,436,987 | 5,099,716 |  |  |  |  |  |  |  |
| Wastage rate in base-year and planned thereafter |  | 32 |  |  |  |  |  |  |  |
| Infants vaccinated with 3rd dose of Tetra(DPT-HepB) |  | 94,491 | 4,702,184 | 2,423,726 | - | - | - | - | - |
| Tetra (DTP-HepB) 3 coverage |  |  | 85% | 87% |  |  |  |  |  |
| Infants vaccinated with 1st dose of Tetra (DPT-HepB) |  |  | 5,255,382 | 2,702,316 |  |  |  |  |  |
| Tetra (DTP-HepB) 1 coverage |  |  | 95% | 97% |  |  |  |  |  |
| Wastage rate Tetra (DPT-HepB) |  |  | 20% | 20% |  |  |  |  |  |
| Infants vaccinated with 3rd dose of Penta (DPT-Hep B-Hib) 1dose/vial all liquid vaccine |  |  |  | 2,423,726 | 5,061,601 | 5,107,962 | 5,268,158 | 5,429,601 | 5,592,174 |
| Penta (DTP-HepB-Hib) 3 coverage |  |  |  | 87% | 90% | 90% | 92% | 94% | 96% |
| Infants vaccinated with 1st dose of Penta (DTP-HepB-Hib) |  |  |  | 2,702,316 | 5,624,001 | 5,675,513 | 5,726,259 | 5,776,171 | 5,825,181 |
| Penta (DTP-HepB-Hib) 1 coverage |  |  |  | 97% | 100% | 100% | 100% | 100% | 100% |
| Wastage1 rate in base-year and planned thereafter |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 |
| Infants vaccinated with Measles | 4,045,244 | 4,521,689 | 4,702,184 | 4,847,453 | 5,061,601 | 5,107,962 | 5,268,158 | 5,429,601 | 5,592,174 |
| Measles %age coverage** | 77% | 84% | 85% | 87% | 90% | 90% | 92% | 94% | 96% |
| Pregnant women vaccinated with TT2+ | 3,055,840 | 3,378,535 | 4,209,116 | 4,829,282 | 5,179,199 | 5,534,087 | 5,707,647 | 5,882,559 | 6,058,693 |
| TT2+ coverage**** | 46% | 50% | 70% | 80% | 85% | 90% | 92% | 94% | 96% |
| Vit A supplement | Mothers (< 6 weeks from delivery) |  |  |  |  |  |  |  |  |
| Infants (>6 months) |  |  |  |  |  |  |  |  |  |
| Annual DPT Drop out rate(DPT1-DPT3/DPT1)*100 |  |  | 10.5 | 10.3 | 10 | 10 | 8 | 6 | 4 |
| Annual Measles Drop out rate(for countries applying for YF) |  |  |  |  |  |  |  |  |  |

*  Number of infants vaccinated out  of total births

**  Number of infants vaccinated out of surviving infants

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with TT2+ out of total pregnant women

Table 3.5: Summary of current and future immunization budget

|  |  | Expenditures | Future Resource Requirements |
| --- | --- | --- | --- |
|  |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | Total 2006 - 2010 |
|  |  | US$ | US$ | US$ | US$ | US$ | US$ | US$ |
| Vaccines (routine vaccines only) | $8,524,565 | $20,112,314 | $22,213,312 | $53,091,406 | $80,225,305 | $65,475,742 | $241,118,079 |
| Traditional vaccines |  | $5,414,342 | $6,336,348 | $6,844,398 | $7,122,356 | $7,445,570 | $7,563,367 | $35,312,039 |
| New and underused vaccines | $3,110,223 | $13,775,966 | $15,368,913 | $45,969,051 | $72,779,735 | $57,912,374 | $205,806,039 |
| Injection supplies |  | $1,792,491 | $3,565,703 | $4,117,562 | $4,585,457 | $4,969,245 | $4,834,157 | $22,072,123 |
| Personnel |  | $25,117,889 | $25,620,247 | $26,140,492 | $26,663,302 | $27,196,568 | $27,740,500 | $133,361,109 |
| Salaries of full-time NIP health workers (immunization specific) | $19,270,859 | $19,656,276 | $20,049,402 | $20,450,390 | $20,859,398 | $21,276,586 | $102,292,052 |
| Per-diems for outreach vaccinators/mobile teams | $5,668,740 | $5,782,115 | $5,897,757 | $6,015,712 | $6,136,026 | $6,258,747 | $30,090,358 |
| Per-diems for supervision and monitoring | $178,290 | $181,856 | $193,333 | $197,200 | $201,144 | $205,167 | $978,700 |
| Transportation |  | $6,877,175 | $16,879,932 | $22,596,887 | $29,083,638 | $32,722,839 | $33,826,597 | $135,109,893 |
| Fixed site and vaccine delivery | $3,964,291 | $9,714,442 | $13,258,648 | $21,773,129 | $24,496,845 | $25,323,039 | $94,566,102 |
| Outreach activities |  | $2,912,884 | $7,165,491 | $9,338,240 | $7,310,509 | $8,225,994 | $8,503,558 | $40,543,791 |
| Maintenance and overhead | $3,910,257 | $9,521,360 | $10,673,854 | $11,585,246 | $12,324,973 | $15,083,891 | $59,189,324 |
| Cold chain maintenance and overheads | $2,965,990 | $8,539,494 | $9,653,129 | $10,518,360 | $11,213,116 | $13,990,300 | $53,914,398 |
| Maintenance of other capital equipment | $58,392 | $60,557 | $62,563 | $70,396 | $75,509 | $15,788 | $284,813 |
| Building overheads (electricity, water…) | $885,875 | $921,310 | $958,162 | $996,489 | $1,036,348 | $1,077,802 | $4,990,112 |
| Short-term training |  | $728,867 | $793,423 | $1,047,486 | $1,153,692 | $1,268,228 | $1,461,459 | $5,724,287 |
| IEC/social mobilization |  | $1,932,700 | $1,996,475 | $2,109,800 | $3,248,599 | $3,465,638 | $3,749,491 | $14,570,003 |
| Disease surveillance |  | $1,679,358 | $1,712,587 | $2,175,231 | $2,060,851 | $2,097,170 | $1,852,979 | $9,898,818 |
| Programme management |  | $964,710 | $1,132,005 | $1,824,070 | $1,935,661 | $2,026,309 | $2,122,122 | $9,040,168 |
| Other routine recurrent costs | $3,039,511 | $2,241,694 | $5,080,230 | $491,667 | $501,500 | $511,530 | $8,826,621 |
| Subtotal Recurrent Costs |  | $54,567,523 | $83,575,741 | $97,978,924 | $133,899,518 | $166,797,776 | $156,658,466 | $638,910,425 |
| Vehicles |  | $3,349,000 | $31,695,140 | $14,410,580 | $7,089,046 | $6,314,188 | $26,134,513 | $85,643,467 |
| Cold chain equipment |  | $2,939,995 | $20,756,448 | $2,896,758 | $2,275,121 | $1,780,005 | $21,078,905 | $48,787,235 |
| Other capital equipment |  | $34,500 | $5,440 | $4,335 | $35,904 | $20,205 | $17,665 | $83,550 |
| Subtotal Capital Costs |  | $6,323,495 | $52,457,028 | $17,311,673 | $9,400,071 | $8,114,398 | $47,231,083 | $134,514,252 |
| Polio |  | $62,771,400 | $99,086,071 | $74,762,471 | $55,537,292 | $56,727,985 |  | $286,113,818 |
| Vaccines |  | $25,011,896 | $35,241,953 | $26,252,471 | $19,251,812 | $19,410,918 |  | $100,157,153 |
| Other operational costs |  | $37,759,504 | $63,844,118 | $48,510,000 | $36,285,480 | $37,317,067 |  | $185,956,665 |
| Measles |  |  |  | $40,905,681 |  |  |  | $40,905,681 |
| Vaccines and supplies |  |  |  | $20,495,911 |  |  |  | $20,495,911 |
| Other operational costs |  |  |  | $20,409,770 |  |  |  | $20,409,770 |
| Yellow Fever |  |  |  |  |  |  |  |  |
| Vaccines and supplies |  |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |  |
| MNT campaigns |  | $1,909,327 | $459,885 | $7,091,316 |  |  |  | $7,551,201 |
| Vaccines and supplies |  | $1,164,327 | $279,885 | $4,282,236 |  |  |  | $4,562,121 |
| Other operational costs |  | $745,000 | $180,000 | $2,809,080 |  |  |  | $2,989,080 |
| Vaccines and supplies |  |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |  |
| Vaccines and supplies |  |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |  |
| Vaccines and supplies |  |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |  |
| Vaccines and supplies |  |  |  |  |  |  |  |  |
| Other operational costs |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs |  | $64,680,727 | $99,545,955 | $122,759,467 | $55,537,292 | $56,727,985 |  | $334,570,699 |
| Shared personnel costs | $28,386,411 | $28,954,139 | $29,533,222 | $30,123,887 | $30,726,364 | $31,340,892 | $150,678,504 |
| Shared transportation costs |  |  |  |  |  |  |  |
| Construction of new buildings |  |  |  |  |  |  |  |
| Subtotal Optional |  | $28,386,411 | $28,954,139 | $29,533,222 | $30,123,887 | $30,726,364 | $31,340,892 | $150,678,504 |
|  |  | $153,958,157 | $264,532,864 | $267,583,286 | $228,960,768 | $262,366,523 | $235,230,441 | $1,258,673,881 |
| Routine (Fixed Delivery) |  | $61,144,185 | $122,010,652 | $95,353,047 | $129,760,982 | $152,923,642 | $184,767,024 | $684,815,347 |
| Routine (Outreach Activities) | $28,133,244 | $42,976,257 | $49,470,772 | $43,662,494 | $52,714,896 | $50,463,416 | $239,287,835 |
| Campaigns |  | $64,680,727 | $99,545,955 | $122,759,467 | $55,537,292 | $56,727,985 |  | $334,570,699 |

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunization program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners.

Table 3.6: Summary of current and future financing and sources of funds

## New and Under-Used Vaccines (NVS)

Please give a summary of those aspects of the comprehensive multi-year immunization plan that refer to the introduction of new and under-used vaccines (refer to the cMYP or Multi-Year Plan).  Please outline the key points that informed the decision-making process (data considered etc):

The underlying principles of the Multi Year Immunization Strategic Plan (page 15)  includes ,” Extension of the scope of the present EPI “ . This also includes addition of the new vaccines (e.g. Hib, Rotavirus etc) with decisions taken based on disease burden and cost effectiveness studies”

About 24% of all childhood deaths (appx 500,000 in 2004)  in Pakistan are due to acute respiratory infections .  Based on the estimate that Hib is responsible for 4% of global childhood deaths, this will result in over 20,000 deaths from Hib alone in Pakistan. Therefore, introduction of Hib vaccine as recommended by WHO  and also as needed according to  estimated Hib burden disease in Pakistan can contribute significantly to achieving the Millennium Developmental Goal # 4 (MDG 4) of reducing child mortality by 2/3 by 2015 compared to 1990 levels.  Additionally Hib has also been shown to cause 20% of bacterial meningitis cases in children in surveillance sponsored by WHO-EMRO in Sindh. Hib Meningitis has devastating consequences (10% cases die and 40% are permanently disabled by damage to brain and deafness).

The financial contribution of GOP towards the cost of Pentavalent vaccine  would be around   US$ 14.573 millions, i.e.   approx 8.3%  of the total cost of US$ 173.838 million during the period 2008-10  of the GAVI Phase  2 Support.

After different discussions on various forums it was finally decided by the NICC, NHSCC, in its joint meeting held on 16 April 2007, to introduce Hib vaccine in routine immunization.  The joint meeting was also participated by the members from NEAG and the decision makers of MOH & MOP.

Please describe (or refer to the relevant section of the cMYP or Multi-Year Plan) how your country intends to move towards financial sustainability for the chosen new vaccines, how the co-financing payments will be met, and any other issues regarding financial sustainability that were considered:

The Government of Pakistan is committed to improve the health status of children of Pakistan and provides adequate resources to the immunization programme. This is evident from the fact that  under current Federal  EPI PC1  for ( 2004-05 to 2008-09) it has allocated Rs 11,484 million ( approx US$ 191 million.  This includes an amount of approx  US$ 25 million  for procurement of tetravalent vaccine ,in order to ensure  its availability , after  the end of GAVI support in 2007  .  The graph below depicts the Federal Government funding trend for EPI. It can be noted that  in the last year of the PC1 , because of the large amount allocated for the tetravalent  and then planned measles campaign  vaccine and  civil works  the budget increased to US$ 84 million from an annual average of US$ 26 million in last four years.

The GOP will ensure that the trend of  its  gradual overall contribution to the EPI Programme is kept in the coming years .  In addition it will follow the policy of exploring the other venues for financing of the EPI

As  GOP in consultation with  ICC and NHSCC  has decided to introduce Pentavalent vaccine (DPT-HepB-Hib)  in routine EPI schedule under GAVI phase 2 , it will be required to provide appx  US$ 3.192 million, US$ 6.005 million and US$ 5.376 million  for the year 2008,2009 & 2010.  Although the co financing level after 2010 will be higher than the current level, still the GOP is likely to bear this cost keeping in view the past trend on providing resources for the procurement of required vaccine.

The summary of the status of implementation of the strategies for financial sustainability as highlighted in cMYP  is as follows:

|  | Key Strategies | Implementation Status |
| --- | --- | --- |
|  | To reach the coverage targets for ensuring the projected resources from GOP | Much progress has been shown in 2006 , with increasing DPT3 coverage to 86% from 72% in 2005 |
|  | To secure GAVI and other partner funds | Pakistan is availing/plans to avail all the support available under different GAVI windows. IFFI funds have been secured for Measles campaign 2007 & 2008 Funds from other partners, UNICEF, WHO , JICA, Rotary International , USAID etc have been secured. |
|  | To have continuous and close liaison with Provincial Governments for reviewing the EPI progress and Federal and provincial district resource allocations | Provincial review meetings are being conducted on quarterly basis. |
|  | To be used as an advocacy tool. | Briefing and advocacy meetings are being held with different partners and with Provincial and District government. |
|  | To form the basis for strategic planning for the EPI programme at all levels. | Comprehensive plan has been developed at federal level where as district micro plan has been developed at district level. |
|  | To secure resources for EPI at district level from district government. | District government have been approached through provincial finance departments to secure the resource for EPI at district level from district government funds. |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation):

1. Pentavalent (DPT-HepB-Hib) all liquid 1dose/vial

Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hib Meningitis | Sentinel site surveillance for Hib meningitis in children in Karachi and Hyderabad. | 2003-04 | 20% bacterial meningitis is due to Hib Minimum detected rate 33/100,000 (infants < 1yr) |

If new or under-used vaccines have been already introduced, please give details of the lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc., and the action points to address them in the new plan:

Hepatitis B monovalent vaccine was introduced in 2001 in a phased manner in the country with GAVI support. In late 2006 it was switched to Tetravalent ( DPT-HepB ) vaccine. Following is the summary of the key lessons learnt in this regards as discussed in various EPI review meetings.

| Lessons Learnt under GAVI phase 1 , introduction of new vaccine | Action Points |
| --- | --- |
| 1. Storage Capacity: No issue of storage capacity was encountered at any level. | Though there was no issue regarding the storage capacity at any level with Hepatitis B (monovalent) and Tetra (DPT-HepB) vaccine, Federal EPI has prepared a report regarding the storage space required when switching to single dose Pentavalent vaccine. As per this report (attached) no storage capacity shortage is anticipated even after completely switching to pentavalent vaccine in 2009. A plan for gradual expansion as well as replenishment of cold chain equipment (PC1s)at all levels exist and is being implemented. |
| 2. Protection from accidental freezing: Occasional incidents of accidental freezing of Hepatitis B vaccine at one district EPI vaccine store level and a few health facilities level were reported during 2002/3. | The training material for vaccinators and supervisors adequately covers the topic of proper vaccine storage including prevention from freezing. All the vaccinators, (including LHWs and other paramedics providing immunization) are provided regular refresher trainings. The EPI check list for supervisors also includes a section on proper storage of vaccines. The District EPI Manager/Supervisors reinforce all the critical EPI issues including proper vaccine management during the monthly meetings with the immunization staff. |
| 3. Staff training : Training material for different level of immunization staff and training plan was prepared. There were some delays in training conductions in a few districts. Recording of the Heb B immunization on EPI instruments by some staff was not as per provided training. However this was rectified by supervisors and monthly vaccinators meetings at the district level. | The training material related to different aspects of Pentavalent (DPT-HepB-Hib) vaccine introduction will be developed. A training plan has been developed. |
| 4. Drop out rate | The strategies to reduce the drop out rate includes : Screening of the children attending the health facility for treatment or accompanying their parents for completion of the immunization. ( National EPI Policy strategy No. 5.4.3) Out reach team to encourage the parents of the target children within 3 KM radius of the Health Facility to get their children vaccinated from health facility rather to wait for the outreach team. ( National EPI Policy Strategy No. 5.1.4 & 5) Due and Defaulter lists to be made at each UC level and followed. LHWs where available to facilitate the vaccinator in preparation of the lists and follow up of defaulters. Continuous social mobilization for promotion of immunization. |
| 5. Wastage rate | The strategies to reduce the wastage rate include: Refresher trainings for vaccine management at all levels. Reinforcement of the multi dose vial policy. Provision of the option for health facilities to designate specific days for BCG and measles under National EPI Policy ( Strategy No. 7.2.7) Maintenance of Cold Chain. |

First Preference Vaccine

  - Please complete Table A.1 in Annex 1 (an excel spreadsheet), for the first vaccine required.

To fill out Table A.1, please update the figures in Table β and Table µ in Annex 1 with the most recent UNICEF Supply Division Prices and Charges on the UNICEF website.

Please refer to www.unicef.org/supply for the most recent GAVI Alliance Vaccine Product Selection Menu, and review the GAVI Alliance NVS Support Country Guidelines to identify the appropriate country category, and the minimum country co-financing level for each vaccine in each group.

Please indicate in the table below the required number of vaccine doses, the vaccine presentation, the

associated injection safety material required and safety boxes for the first vaccine required as per the calculation made in Annex 1.

| Table 4.1a : Material requirements for the introduction of Pentavalent (DPT-HepB-Hib) 1dose/vial all liquid vaccine .(vaccine presentation) |
| --- |
| Total requirements |  | Base year (2007) | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 2011 | Year 5 2012 |
| National target for children to be immunized with 3rd dose | # | 0 | 2,423,726 | 5,061,601 | 5,107,962 |  |  |
| National target of children to be immunized with 1st dose |  |  | 2,702,316 | 5,624,001 | 5,675,513 |  |  |
| Total number of vaccine doses required | # |  | 10,640,369 | 20,016,430 | 17,918,432 |  |  |
| Total number of AD syringes required | # |  | 11,360,874 | 21,281,841 | 18,944,486 |  |  |
| Total number of reconstitution syringes required | # |  | 0 | 0 | 0 |  |  |
| Total number of safety boxes required | # |  | 126,106 | 236,228 | 210,284 |  |  |

Please indicate in the table below the price per dose, the total funds required to meet the estimated demand, the country co-financing contribution, and the funds required from the GAVI Alliance according to the calculations made in the Annex 1 spreadsheet.

| Table 4.2a: Financial requirement for the introduction of Pentavalent (DPT-HepB-Hib) 1dose/vial all liquid vaccine .(vaccine presentation) |
| --- |
| Total budget | Price per vaccine dose * | $ | 3.725 | 3.728 | 3.324 |  |  |
|  | Total funding required | $ | 39,631,078 | 74,639,292 | 59,567,691 |  |  |
| Country co-financing | Co-financing per dose | $ | 0.30 | 0.30 | 0.30 |  |  |
|  | Total country payment | $ | 3,192,111 | 6,004,929 | 5,375,529 |  |  |
| GAVI Alliance support requested | GAVI payment per dose | $ | 3.425 | 3.428 | 3.024 |  |  |
|  | Total GAVI payment | $ | 36,438,968 | 68,634,363 | 54,192,162 |  |  |

* Total price pre dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc

GOP & NICC desires to be considered for the first preference.

  - Please fill out Table A.2 in Annex 1, for the second vaccine required, after updating Table β and Table µ in Annex 1 with the most recent UNICEF Supply Division Prices and Charges.

Please refer to www.unicef.org/supply for the most recent GAVI Alliance Vaccine Product Selection Menu, and review the GAVI Alliance NVS Support Country Guidelines to identify the appropriate country category, and the minimum country co-financing level for each vaccine in each group.

Please indicate in Table 4.1b below the required number of vaccine doses, the vaccine presentation, the associated injection safety material required and safety boxes for the first vaccine required as per the calculation made in Annex 1.

Second Preference Vaccine

| Table 4.1b : Material requirements for the introduction of Pentavalent (DPT-HepB-Hib) 2dose/vial lyophilized vaccine .(vaccine presentation) |
| --- |
| Total requirements |  | Base year (2007) | Year 1 (2008) | Year 2 (2009) | Year 3 (2010) | Year 4 2011 | Year 5 2012 |
| National target for children to be immunized with 3rd dose | # | 0 | 2,423,726 | 5,061,601 | 5,107,962 |  |  |
| National target of children to be immunized with 1st dose |  |  | 2,702,316 | 5,624,001 | 5,675,513 |  |  |
| Total number of vaccine doses required | # |  | 10,640,369 | 20,016,430 | 17,918,432 |  |  |
| Total number of AD syringes required | # |  | 11,360,874 | 21,281,841 | 18,944,486 |  |  |
| Total number of reconstitution syringes required | # |  | 0 | 0 | 0 |  |  |
| Total number of safety boxes required | # |  | 126,106 | 236,228 | 210,284 |  |  |

Please indicate in the table below the price per dose, the total funds required to meet the estimated demand, the country co-financing contribution, and the funds required from the GAVI Alliance according to the calculations made in the Annex 1 spreadsheet.

| Table 4.2b: Financial requirement for the introduction of Pentavalent (DPT-HepB-Hib) 2dose/vial lyophilized vaccine .(vaccine presentation) |
| --- |
| Total budget | Price per vaccine dose * | $ | 3.2 | 2.9 | 2.65 |  |  |
|  | Total funding required | $ | 35,331,195 | 60,485,475 | 55,513,988 |  |  |
| Country co-financing | Co-financing per dose | $ | 0.30 | 0.30 | 0.30 |  |  |
|  | Total country payment | $ | 3,192,111 | 6,062,436 | 6,019,013 |  |  |
| GAVI Alliance support requested | GAVI payment per dose | $ | 2.9 | 2.6 | 2.35 |  |  |
|  | Total GAVI payment | $ | 32,139,084 | 54,423,039 | 49,494,975 |  |  |

* Total price pre dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc

Procurement and Management of New and Under-Used Vaccines

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):

All the vaccines for EPI in the country are procured through UNICEF. GAVI alliance is requested to also provide Pentavalent (DPT-Hep B-Hib) 1 dose/vial all liquid vaccines as first preference and 2 dose/vial lyophilized vaccine as second preference, for which this proposal is being submitted, through UNICEF.

All the vaccine will be received at Federal EPI vaccine store NIH Islamabad, except that required for province of Sindh which will be received at provincial EPI vaccine store Sindh Karachi. Six month requirement of the vaccine along with the quantity required to be delivered at Islamabad and Karachi will be communicated to GAVI/Unicef according to the target date set by Unicef supply division.

The vaccine will be distributed to the sub national level according to the existing vaccine distribution system, which required a storage of six months supply at National level, three months supply at provincial level and one month supply at district and health facility level

The NICC will be regularly updated on the status of supply and distribution of the Pentavalent vaccine, besides other EPI activities.

b) If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document:

- That the functions of the National Regulatory Authority comply with WHO requirements for procurement of vaccines and supply of assured quality.

- That the delivery in country of the procured supply is in compliance with the co-financing plan.

- That acceptable procurement principles and processes are applied.

Procurement and delivery of the Pentavalent vaccine and associated injection safety supplies are requested through Unicef.

c) Please describe the introduction of the vaccines (refer to cMYP or updated Multi-Year Plan)

The Pentavalent vaccine will be introduced country wide from 1st July 2008. All the children requiring 1st dose of DPT containing vaccine will be provided with the 1st dose of Pentavalent vaccine and the three dose series completed.

Following activities as part of the introduction of Pentavalent vaccine to routine immunization schedule are planned (Document No.04)

- Submission of proposal to GAVI for Hib vaccine under GAVI phase-II NVS.

- Additional Vaccine Storage Capacity

- Designation of a Focal Person at all levels.

- Updating of ICC

- Revision of the related EPI Tools.

- Information and advocacy Seminar/material

- Briefing and Trainings.

- Mass Media Campaign

- Vaccine Arrival and Distribution

- Supervision, monitoring and evaluation

d) Please indicate how funds should be transferred to the country by the GAVI Alliance (if applicable)

The funds should be transferred to the WHO country office.

e) Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The MoH and Ministry of Finance will be responsible for making the payment of the co-financing share. The amount will be transferred to Unicef Pakistan by November each year.

e) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP or updated Multi-Year Plan)

1. The existing recording and reporting instruments will be updated, these instruments will have columns for both the Tetravalent (DPT-Hep B) and Pentavalent (DPT-Hep B-Hib) vaccine for the year 2008. This will allow to monitor the usage of these vaccines besides DPT coverage. Since Pentavalent vaccine will be introduced from 1st July 2008, it is expected that by the end of 2008 no more recording of Tetravalent vaccine would be required.

The column for the Tetravalent vaccine will be deleted later on.

2. The existing recording and reporting system will be followed. According to this system at each union council a permanent EPI register is maintained. All the immunizations given in the union council i.e. at static EPI centre, outreach  or mobile, given by any health worker including LHWs are recorded in this permanent register. Monthly immunization coverage report is generated at the UC level by the vaccinator from the permanent register. This is submitted to the district health office after desk analysis by the health facility in charge. At district level all these reports are compiled and a consolidated district coverage report is prepared. This report is submitted to the provincial level after its analysis during the monthly meeting at the district level. The reports of all the districts are compiled at provincial/areas EPI offices and a consolidated report is submitted by all the provinces/ areas to the Federal EPI Cell.  The reports from all the provinces/areas are consolidated after analysis at the Federal level, for onwards submission to the concerned quarters.

Review meetings are conducted quarterly at Federal and provincial/ areas level to discuss the observations, feedback/feed forward and to find out the required solutions for improvements and implementation of the programme.

If you are approved for new vaccines support, you will be entitled to receive a lump-sum of US$ 100,000 to facilitate the introduction of each new vaccine. If you wish to receive these funds, please submit the attached “Banking Form” (in Annex 2) along with this proposal, if you have not yet already done so for other types of support from the GAVI Alliance.

GoP and NICC requests that the funds for facilitating the introduction of new vaccine, currently approved as US $ 100,000 (One hundred thousand) for all countries be transferred through WHO Pakistan. These will be utilized to undertake the activities as highlighted in the plan of action (Document No.04) where there would be a funding gap. This expenditure will be authorized by ICC or its nominated subcommittee and will be according to the WHO administrative and financial rules.

Keeping in view the large birth cohort and seven provinces/ areas with a large number of subprovincial administrative units GAVI Alliance is requested to provide atleast US $ 500,000 (five hundrend thousand) for facilitating the introduction of the Pentavalent vaccine for routine EPI.

## Additional Comments and Recommendations from the Inter-Agency Coordinating Committee for Immunization (ICC) and other Health Sector Development Partners

National ICC   highly appreciates the role of GAVI in improving the immunization services in the country through provision of its support under different windows.

ICC takes note with pleasure that EPI has shown a significant improvement in DPT3 coverage last year i.e. 2006.

With decentralization taking its roots, the Districts are gradually taking increasing responsibility in ensuring that their target population receives maximum benefit of the immunization services.

The support offered by GAVI under Phase-2 for provision of Pentavalent vaccine with a minimal government contribution is highly appreciated by GoP and ICC. This will provide an opportunity to gradually absorb the price of this vaccine in the national budget. GoP has been providing all the funds required for EPI vaccines from early 90’s and will be able to provide the additional amounts required for Pentavalent vaccine when the GAVI support under Phase-2 comes to an end.

The introduction of the Hib Vaccine in routine immunization will substantially contribute toward the childhood morbidity and mortality reduction associated with Hib disease and this would be a big leap toward achieving MDGs.

## Documents Required

| Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- |
| Endorsed minutes of the National Coordinating Body meeting where the GAVI Alliance NVS proposal was endorsed | 1 | - |
| Endorsed minutes of the ICC meeting discussing the requested GAVI Alliance New and Under-Used Vaccine (NVS) support | 2 | - |
| Minutes of the three most recent ICC meetings | 3 | - |
| Plan for introduction of New Vaccine (if not already included in the cMYP or updated Multi-Year Plan) | 4 | 2008-2010 |
| WHO / UNICEF Joint Reporting Form (last two) | 5 | 2005-2006 |
| Comprehensive Multi-Year Plan (cMYP) or updated Multi-Year Plan | 6 | 2005-2010 |
| ICC work plan for the forthcoming 12 months | 7 | 2007-2008 |

* Please indicate the duration of the plan / assessment / document where appropriate

ANNEX 2: BANKING FORM

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  | Banking Form |
| --- | --- | --- |
| SECTION 1 (To be completed by payee) |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |
| Name of Institution: (Account Holder) | Ministry of Health, Government of Pakistan. |
| Address: |  |
|  | C Block, Pak. Secretariat Buildings Islamabad. |
| City – Country: | Islamabad—Pakistan. |
| Telephone No.: | 051-9255101 | Fax No.: | 051-9255086 |
| Amount in USD: | (To be filled in by GAVI Secretariat) | Currency of the bank account: | Pak. Rupees |
| For credit to: Bank account’s title | Government of Pakistan |
| Bank account No.: | Federal Government Account No. 1 (Non-Food) |
| At: Bank’s name | State Bank of Pakistan, Karachi |
| Is the bank account exclusively to be used by this program? | YES ( X ) NO ( ) |
| By whom is the account audited? | Auditor General of Pakistan |
| Signature of Government’s authorizing official: |
| Name: | Ministry of Health, Government of Pakistan. C Block, Pak. Secretariat Buildings Islamabad. Islamabad—Pakistan. Government of Pakistan Federal Government Account No. 1 (Non-Food) State Bank of Pakistan, Karachi | Seal: |
| Title: | Secretary to the Government of Pakistan Ministry of Health, Islamabad. |  |
| Signature: |  |  |
| Date: |  |  |

| SECTION 2 (To be completed by the Bank) |
| --- |
| FINANCIAL INSTITUTION | CORRESPONDENT BANK (In the United States) |
| Bank Name: |  |  |
| Branch Name: |  |  |
| Address: |  |  |
| City – Country: |  |  |
| Swift code: |  |  |
| Sort code: |  |  |
| ABA No.: |  |  |
| Telephone No.: |  |  |
| Fax No.: |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: | Name of bank’s authorizing official: |
| 1 Name: Title: |  | Signature: |  |
|  |  | Date: |  |
| 2 Name: Title: |  | Seal: |
| 3 Name: Title: |  |  |
| 4 Name: Title: |  |  |

COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)

### TO:    GAVI Alliance – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |
| --- |
|  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |
| Signature of UNICEF Representative: |
| Name |  |
| Signature |  |
| Date |  |

# Footnotes

WHO/ UNICEF   JRF for Jan-Dec 2006.

Ministry of Health.

Ministry of Planning

National Interagency Coordination Committee

National EPI Advisory Group

WHO position paper on Hib vaccine, Nov 2006.

Beginning 1st July 2008

WHO/UNICEF  JRF   for Jan- Dec 2005

Federal EPI Data and draft JRF for Jan-Dec 2006

Except for 2006  target population  which is based on the JRF 2005 and Draft JRF 2006.

As accurate factor of births with relation to pregnant women is not known ,  Total Pregnant women are estimated to be equal to total births . This approach is also used in cMYP.

Subject to approval of the proposal for NVS Support by GAVI under Phase-2.

National Health Sector Coordination Committee.

Including buffer stock.

Including injection supplies & freight etc.

Including injection supplies & freight etc.

Figures for 2005 & 2006 based on respective WHO/UNICEF JRF on Immunization. Figures for 2007-2013 based on cMYP .

WHO/UNICEF  Joint Reporting Form on Immunization  for the period January-December 2005

WHO/UNICEF  Joint Reporting Form on Immunization  for the period January-December 2006

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby : A = The number of doses distributed for use according to the supply  records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table (  after Table 7.1.

Federal EPI data

Federal EPI data

Including AD syringes, safety boxes and freight etc.

Selected from the two available options of  Pentavalent vaccine presentation i.e 1-dose/vial,liquid or in 2-dose/vial liquid + lyophilized , as conveyed through GAVI communication of March 2007  regarding , “ 2007 Update on support to countries from the GAVI Allliance”

# Text boxes

Total

GOP - Provincial

GOP - National

$ in million

Years

2009

2008

2007

2006

2005

2004

2003

100

80

60

40

20

0

Chart 10: GOP Financing trend for EPI