January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Islamic Republic of Afghanistan

Date of submission: …April 19, 2005…………… Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report √ Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

- Mechanism - GAVI fund is managing according to a mechanism that developed by National EPI office based on standard management tool for management of external grants and endorsed by ICC members. Different procedures (The ones that not existed in MoPH official documents) also developed to facilitate the management of the fund. - Based on ICC decision GAVI Fund Management Team established in MoPH and is functional. - Process of fund release is going through MoPH External Grant Management Unit according to the action plan, request of national EPI office and approval of His Excellency Minister of Public Health. - All action plans related to GAVI support or any change in the already endorsed action plans are presented to ICC for the endorsement. - ICC member kept inform on GAVI expenditures. - Internal Audit conducted and based on the finding of the audit necessary actions has been taken. Some of the dicision and out come of the audit are as follow: - Standard procedures and payment forms developed and distributed. - All extra expanses (out of micro-plan) reimbursed. - It was decided that payment should take place after submission of financial documents (not in advance for most of the activities). - Review of financial issues included in the agenda of Regional EPI Review and Planning Workshops. - Problems - Poor banking system in the country and poor management capacity of the fund by provincial EPI management teams (PEMT) is one of the reasons for centralized management of GAVI fund. - It was first time that national and provincial EPI teams took responsibility of the fund management. - Prolonged procurement procedures.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 ____519500_____

Remaining funds (carry over) from 2003 _519500___________

Note: Since the fund arrived late in year 2003 (National EPI office received information on arrival of fund by De Afghanistan Bank on 18th of October 2003), the use of the fund started in year 2004.

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 8800 | 8800 |  |  |  |
| Transportation (including purchase of one Vehicle) | 878 | 878 |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | 22401 | 5803 | 16598 |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach | 422121 |  |  | 422121 (Pulse Imm.) |  |
| Supervision | 707 | 530 | 177 |  |  |
| Monitoring and evaluation | 3412 | 3412 |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles | 23000 | 23000 |  |  |  |
| Cold chain equipment | 295438 |  |  | 295438 |  |
| Other; (Computers, Printers, Accessories and Mobil phones) | 76200 | 1917 | 46872 | 27411 |  |
| Total: | 852957 | 44340 | 63647 | 694624 |  |
| Remaining funds for next year: | 186043 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Major activities: - Introduction of pulse immunization as a strategy to reach under served villages. - Expansion of EPI centres to 871 in year 2004 (2003 figure was 780 centres) - Strengthening cold chain system: Remonstration of 7 regional cold rooms. Distribution of 60 set of cold chain (USAID fund) and ordering 125 set of cold chain (GAVI fund) - Training and Capacity Building: EPI review and planning workshop (national & Regional). Printing of EPI training manual, ToTs, MLM training course and Refresher training course for vaccinators (GAVI & WHO fund). Strengthening communication with provinces through Internet links and distribution of Cell phones. - Reporting: Provision of Computers, printers and other accessories for all provincial EPI team. - Problems - Restructuring and reforms of Health system: Hand over of EPI to Basic Package of Health Services implementers. Low experience of some BPHS implementers’ agencies regarding management of EPI programs. Un certainty of role and responsibilities of different stick holder in the context of BPHS at the provincial level.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

√

## If yes, please report on the degree of its implementation.

- Provision of standard reporting formats - Provision of 29 computers, printers and accessories. All provinces equipped at least with one set of computer. - Recruiting one data Clark and one EPI surveillance officer for national EPI office - Revision, printing and distribution of reporting documents (Registration books, tally sheets, Immunization cards and monthly report forms) - Monitoring of timeliness and completeness of the reports - Analysis of the data at the national level and feed back. - Improvement in the use of EPI monitoring chart. - Introduction of indicators on quality of registering and reporting in supportive supervision checklists - Use of Coverage data for planning during review workshops. - Inclusion of EPI reporting in the curriculum of EPI training courses for all categories of EPI staff. - Inclusion of EPI data quality assessment indicator in EPI supervisory checklist and conduction/planning for supportive supervision

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

NA

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

NA

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Afghanistan National Immunization Program will introduce Hepatitis-B vaccine in immunization schedule in year 2006 as the DPT-3 coverage rate reached to 54% in year 2003 and 66% in year 2004. - ICC requested WHO, Afghanistan to seek for a consultant to assess extend of the problem and support national EPI team in developing proposal to submit to GAVI secretariat. - WHO STC will arrived in March 2005 and the proposal drafted and endorsed by ICC and l will sub to GAVI secretariat till end of April year 2005 for review and approval.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

NA

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

- Afghanistan received the first trench of GAVI support for safety of immunization injection in January year 2004 (516000 US$).

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- Major Activities: - The national action plan revised and endorsed by ICC - Two Afghan national staff participated in a training course on surveillance of adverse events following immunization in South Africa (WHO support) - Development of field guide for surveillance of adverse event following immunization. - Introduction of AEFI surveillance in Regional Review and Planning Workshop for EPI MLM and NGO provincial senior staff - Investigation and proper response to two reported AEFI in year 2004 - 391 vaccinators have received training on injection safety, safe disposal of immunization wastes and reporting of AEFI during refresher training courses for vaccinators. - Safety of immunization injection and AEFI incorporated in all training packages for EPI staff. - Problems: - Need for support to introduce locally made incinerators

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Provision of syringes to EPI centres | 100% | 100% |  | 100% of vaccinators will follow safe immunization injection practices |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

- Policy, Management; 9025 - Planning and coordination: 17940 - Training on Safe immunization practices 26845 - Production of incinerators (locally made) and proper waste management; 243200 - Surveillance of AEFI: 22396 - Information, Education and Communication: 76514 - Supervision, monitoring and evaluation (assessments): 123580

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

FSP has been developed, endorsed by ICC members, signed by Ministers of Public Health and Finance and sent to GAVI/IRC for review.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 1186851 | 1215335 | 1244503 | 1274371 | 1304955 | 1336274 | 1368345 | 1401185 | 1434813 |
| Infants’ deaths | 183962 | 182300 | 186676 | 191156 | 195744 | 200441 | 205251 | 210178 | 215222 |
| Surviving infants | 1002889 | 1033035 | 1057827 | 1083215 | 1109211 | 1135833 | 1163093 | 1191007 | 1219591 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 801482 | 929732 | 1057827 | 1083215 | 1109211 | 1135833 | 1163093 | 1191007 | 1219591 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 662398 | 826428 | 952044 | 974894 | 998290 | 1022250 | 1046784 | 1071906 | 1097632 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* Hepatitis-B (new vaccine) | 0 | 0 | 634696 | 866572 | 998290 | 1135833 | 1163093 | 1191007 | 1219591 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of Hepatitis-B ( new vaccine) |  |  | 423130 | 649929 | 887369 | 1022250 | 1046784 | 1071906 | 1097632 |
| Wastage rate in 2004 and plan for 2005 beyond*** Hepatitis-B.. ( new vaccine) |  |  | 25 | 25 | 25 | 20 | 20 | 20 | 20 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 390903 | 850734 | 995602 | 1019497 | 1043964 | 1069019 | 1231510 | 1261066 | 1291331 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 774703 | 1093801 | 1244503 | 1274371 | 1304955 | 1336274 | 1368345 | 1401185 | 1434813 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 605909 | 774776 | 846262 | 866572 | 887369 | 908667 | 988629 | 1071906 | 1097632 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The target for EPI antigens for year 2005 and subsequent years revised based on the following facts: - Afghanistan national Immunization program has achieved the stated DPT-3 target for years 2003 (54%) 2004 (target 65% and achievement 66%) - Till end of year 2004 75% of Afghanistan total population covered by BPHS. Target for BPHS implementer agencies is to increase DPT-3 coverage in each district under BPHS to 80% till end of year 2005. - Revised National objective of the EPI program (according to national EPI policy) is to achieve at least 80% DPT-3 coverage till end of year 2005 and increase it 90% in subsequent years. In year 2004 a total number of 662398 children aged 0-11 months vaccinated with 3 doses of DPT. In year 2005 we have plan to vaccinate additional 164030 children with 3 doses of DPT.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

UNICEF country office is providing vaccine and injection supply both for routine and supplementary immunization according to the stated national coverage target.

Table 4: Estimated number of doses of Hepatitis vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 6-4

#### Table-6-5

#### Table6-6

#### Table 6-7

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The quantity is adjusted according to the new coverage target (Please see part 3-1 and justification for revision of baseline and targets).

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DPT-3 Coverage Rate 2003 | 55% | 54% |  |  |
| DPT-3 Coverage Rate, 2004 | 65% | 66% |  |  |
| DPT Dropout Rate 2003 | 16% | 18% |  |  |
| DPT-drop-our rate, 2004 | 13.5% | 17% |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | √ |  |
| Reporting Period (consistent with previous calendar year) | √ |  |
| Table 1 filled-in | √ |  |
| DQA reported on | √ |  |
| Reported on use of 100,000 US$ | NA |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) | NA |  |
| Table 2 filled-in | NA |  |
| New Vaccine Request completed | NA | Please refer to Afghanistan proposal (Hep-B) |
| Revised request for injection safety completed (where applicable) | √ |  |
| ICC minutes attached to the report | √ |  |
| Government signatures | √ |  |
| ICC endorsed | √ | April 17, 2005 |

6.  	Comments

ICC/RWG comments:

ICC members endorsed the Annual Progress Report and also highlighted the following points: - IEC related activities should be coordinated through IEC task force with in order to use optimally the available resources. - Safety of immunization activities has to be enhanced. Safety of immunization injections plan should be coordinated with similar programs through Infectious Diseases Control Task Force. - Quality of EPI data should be monitored regularly. National EPI office has to hire one qualify staff as data manager to facilitate the process.