Updated February 2004

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Azerbaijan

Date of submission: …………………………… Reporting period: 2004 ( Information provided in this report MUST refer to the previous calendar year ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report V Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with the GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during the previous calendar year

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for year… (indicate forthcoming year)

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Management of ISS Funds is carrying out at the Health Ministry level of and discussing in the ICC. No problems on using of ISS funds were registered. .

#### 1.1.2	Use of Immunization Services Support

In the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund contribution.

Funds received during the reporting year  260,494 USD (reward)

Remaining funds (carry over) from the previous year  0

Table 1 : Use of funds during reported calendar year 2004

| Area of Immunization Services Support | Total amount in US $ | Amount of funds |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization | 130,247 | 30,000 |  | 100,247 |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance (strengthening of the system through procurement of computers, provision of internet, development of software and training of the assigned staff) | 130,247 | 30,000 |  | 100,247 |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: | 260,494 | 60,000 |  | 200,494 |  |
| Remaining funds for next year: | 0 | 0 |  | 0 |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Creation of information systems of sanitary-epidemiological service. - Training of personnel of information systems. - Monitoring of using Vitamin A in the framework of EPI, analysis of results for discussing on the Board of Heath Ministry Problems: cold chain, liquidation of used injection materials in large cities, information service.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

V

YES                              NO

## If yes, please attach the plan and report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during the last year (for example, coverage surveys).

- Monitoring on EPI issues with submission of results’ analysis and problems to the Ministry of Health and UNICEF. - Analysis of immunization coverage in the whole country and insuring the immunization safety by results on 2003 for discussion on Board Meeting in 2004.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during the previous calendar year

Start of vaccinations with the new and under-used vaccine:           MONTH……October          YEAR…2001…………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Received vaccine against HB. in 2004: 2 doses- 100.460 10 doses – 280.800 Problems with receiving and distribution of HB vaccine are not registered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Maintenance of Immunization Programme in 2004 realized by funds of Republican Budget with exception of vaccine HB and MMR, and also syringes for coverage of routine immunization of children up to 1 year. - In the framework of “Programme for Elimination of Measles and Rubella” it is planned to strengthen immunization service in the field of provision for Immunization Safety

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Use of GAVI/VF support in amount of 100,000 USD is submitted in the report for 2002.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In framework of the injection safety support GAVI/VF provided medical goods (different syringes, safety boxes) for amount of 47,000 USD. No problems encountered

#### Progress of transition plan for safe injections and safe management of sharps waste.

Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

There are problems on safety utilization of used injection materials in big cities.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets (to 2013) | Achievements (to 2004) | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Providing with self-destructed syringes - Availability of containers for collection of used injection materials - Availability of destruction of used injection materials. - Provision with cold equipment. | 100% 100% 100% 100% | 53,2% 100% 70% 65% | Stage by stage provision Utilization of used injection materials in big cities. Stage by stage provision . |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No cash contribution has been received from the GAVI/VF for injection safety support

# 2.  	Financial sustainability

Inception Report :		Outline timetable and major steps taken towards improving financial sustainability and the development of a 		financial sustainability plan.

First Annual Progress Report : 	Submit completed financial sustainability plan by given deadline and describe assistance that will be needed

for financial sustainability planning.

Draft Financial Sustainability Plan (FSP) is submitted to GAVI Secretariat on January, 2004. FSP corrected with participation of Expert of Wold Bank was sent to GAVI Secretariat on 30 November, 2004.

Second Annual Progress Report :	Describe indicators selected for monitoring financial sustainability plans and include baseline and current values for each indicator. In the following table 2, specify the annual proportion of five year of GAVI/VF support for new vaccines that is planned to be spread-out to ten years and co-funded with other sources.

| Table 2 : Sources (planned) of financing of new vaccine ……HB……………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 |
| Proportion funded by GAVI/VF (%) | 100 | 100 | 100 | 100 | 100 | 80 | 70 | 60 | 50 | 50 |
| Proportion funded by the Government and other sources (%) | - | - | - | - | - | 20 | 30 | 40 | 50 | 50 |
| Total funding for …………. (new vaccine) * | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| * Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine |  |  |  |  |  |  |  |  |  |  |

Subsequent reports:	Summarize progress made against the financing strategy, actions and indicators section of the FSP; include successes, difficulties and responses to challenges encountered in achieving outlined strategies and actions. Report current values for indicators selected to monitor progress towards financial sustainability. Include funds received to date versus those expected for last year and the current year and actions taken in response to any difficulties.

Update the estimates on program costs and financing with a focus on the last year, the current year and the next 3 years. For the last year and current year, update the estimates of expected funding provided in the FSP tables with actual funds received since. For the next 3 years, update any changes in the costing and financing projections.  The updates should be reported using the same standardized tables and tools used for the development of the FSP (latest versions available on http://www.gaviftf.org under FSP guidelines and annexes. Highlight assistance needed from partners at local, regional and/or global level.

Table 2.2: Progress against major financial sustainability strategies and corresponding indicators.

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Current financing of EPI by internal source to total the total of financing of the programme | 64,6% vaccine and injection materials are fully procured by government. | Government completely fulfilled all duties on procurement of vaccines and injection materials | The problem of cold chain system is still exist | The government part for support to EPI increased to 15 % | In 2005 the part of government will increase up to 16,5% |  |
| 2. Total financing of EPI, execution in percentage to plan | 93,2% |  |  |  |  |  |
| 3. Purchase of vaccines on effective price | Cost of vaccines are in compliance with FSP |  |  |  |  |  |
| 4. Percentage of lost to decrease side | Delivery of HB and MMR vaccines in small-dose packing promoted decreasing of vaccines lost up to 5-10 percent |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year …………….. ( indicate forthcoming year )

Section 3 is related to the request for new and under used  vaccines and injection safety for the forthcoming year.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 113.388 | 116.035 | 116.975 | 117.922 | 118.878 | 119.841 | 120.811 | 121.790 | 122.776 |
| Infants’ deaths | 1.287 | 3.388 | 3.416 | 3.443 | 3.471 | 3.499 | 3.528 | 3.556 | 3.585 |
| Surviving infants | 112.101 | 112.647 | 113.559 | 114.479 | 115.406 | 116.341 | 117.284 | 118.234 | 119.1913 |
| Infants vaccinated / to be vaccinated with 1st dose of DTP (DTP1)* | 104.382 112.647 |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 3rd dose of DTP (DTP3)* | 102.886 112.647 |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 1st dose of …HB......... ( new vaccine) | 107.089 116.035 |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 3rd dose of …HB….… ( new vaccine) | 103.766 116.035 |  |  |  |  |  |  |  |  |
| Wastage rate of *** ………….. ( new vaccine) | 1.25 | 1.25 |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with BCG | 106.821 116.035 |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with Measles | 100.890 112.647 |  |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for the year …… (indicate forthcoming year)

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

Table 4: Estimated number of doses of …HB… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2006…… | Remarks |
| --- | --- | --- | --- | --- |
| A | Infants vaccinated / to be vaccinated with 1st dose of HB ( new vaccine) |  | *116.975 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a 10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 80 |  |
| C | Number of doses per child | 3 |  |  |
| D | Number of doses | A x B/100 x C | 280.740 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.33 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 373.384 |  |
| G | Vaccines buffer stock | F x 0.25 | 0 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 373.384 |  |
| J | Number of doses per vial | 10 doses double dose |  |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 311.621 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 41.445 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 3.919 |  |

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the year 2006-2007(indicate forthcoming year)

Table 6: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year …2006… | For year 2007…… |
| --- | --- | --- | --- | --- |
| A | Target of children for …DTP… vaccination (for TT : target of pregnant women) | # | 113.559 | 114.479 |
| B | Number of doses per child (for TT woman) | # | 3 | 3 |
| C | Number of …… doses | A x B | 340.677 | 343.437 |
| D | AD syringes (+10% wastage) | C x 1.11 | 378.152 | 381.215 |
| E | AD syringes buffer stock | D x 0.25 | 0 | 0 |
| F | Total AD syringes | D + E | 378.152 | 381.215 |
| G | Number of doses per vial | # | 10 doses | 10 doses |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G |  |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 4.198 | 4.231 |

: Estimated supplies for safety of vaccination for the next two years with MMR (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year …2006… | For year 2007…… |
| --- | --- | --- | --- | --- |
| A | Target of children for …MMR… vaccination (for TT : target of pregnant women) | # | 113.559 | 114.479 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 |
| C | Number of …… doses | A x B | 113.559 | 114.479 |
| D | AD syringes (+10% wastage) | C x 1.11 | 126.051 0 | 127.071 0 |
| E | AD syringes buffer stock | D x 0.25 | 0 | 0 |
| F | Total AD syringes | D + E | 126.051 | 127.071 |
| G | Number of doses per vial | # | 10 |  |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 20.168 | 17.790 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1.623 | 1.608 |

: Estimated supplies for safety of vaccination for the next two years with …BCG… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | Formula | For year …2006… | For year 2007…… |
| --- | --- | --- | --- | --- |
| A | Target of children for …BCG… vaccination (for TT : target of pregnant women) | # | 116.975 | 117.922 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 |
| C | Number of …… doses | A x B | 116.975 | 117.922 |
| D | AD syringes (+10% wastage) | C x 1.11 | 129.843 | 130.893 |
| E | AD syringes buffer stock | D x 0.25 | 0 | 0 |
| F | Total AD syringes | D + E | 129.843 | 130.893 |
| G | Number of doses per vial | # | 20 | 20 |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 |  |  |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 12.984 | 13.089 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1585 | 1598 |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Providing with self-destructed syringes - Availability of containers for collection of used injection materials - Availability of destruction of used injection materials. - Provision with cold equipment. | 100% 100% 100% 100% | 53,2% 100% 70% 65% | Stage by stage provision Utilization of used injection materials in big cities. Stage by stage provision . |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of  Azerbaijan

Signature:	……………………………………………/Dr Abbas Valibayov/

Title: Deputy Minister of Health of Azerbaijan

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.