January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: BHUTAN

Date of submission: 15May 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report   Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not applicable

#### 1.1.2	Use of Immunization Services Support (No ISS fund provided ` to Bhutan)

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004

Remaining funds (carry over) from 2003

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO



## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

No any studies conducted in 2004 for EPI coverage

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR: 2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

DPT-Hep.B combination vaccine were received in good condition as per the dates and quantities stated below 1. 10.12.2003 2003 DPT-Hep.B combination 6430 vials of 10 doses 2. 17.1.2.2004 DPT-Hep.B combination 2150 vials of 10 doses

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

1. In April 2004, a training workshop was conducted with support from WHO to strengthen vaccine management and implementation of open vial policy in NIP. Following that training workshop of District Medical Officers and District Health Supervisory Officers of all districts, the same persons held EPI Mid Level Management Training in their respective districts. More than 179 health workers have taken part in these training. 2. Surveillance for AFP, MNT and measles has been incorporated in the integrated reporting forms in addition the following activities has been conducted to improve and strengthen the immunization services - Open Vial Policy adopted in fixed clinic i,e. only in Hospital & Basic Health Unit - Rubella burden assessment conducted - Developed integrated surveillance guidelines for AFP, MNT, Measles& Rubella surveillance - Developed congenital rubella syndrome (CRS) surveillance guidelines

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Reported in 2003 Progress Report

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The following injection supplies were received during the reporting period: - AD Syringes 0.5 ml= 122,000 - Safety Box = 650 Nos - Reconstitute Syringes 2 ml for BCG = 1600 Nos. - BCG Syringes = 32,000 - Measles reconstitute Syringes = 5 ml = 47,000 Nos.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

At present, other than DTP-HepB vaccine, the rest of the EPI vaccines are supported by the Government of Japan through UNICEF. The current support agreement extends till 2007. UNICEF and the Government have already initiated work on negotiating future phases of support. With regards to DTP-HepB, the support from GAVI will last till 2007 as we were able to introduce the vaccine only from 2003. Further, it is our understanding that GAVI will continue some form of bridge financing for a few years beyond the current commitment of support for five year. Therefore, within the principle of bundled supply, we expect that the syringes and safety boxes will be supplied along with the vaccines.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| A national Policy on injection safety in EPI (including) disposal of injection associated waste is prepared Introduction of AD Syringes Percentage of Health facilities with one or more incidence of syringes incidence of stock out of AD /or safety boxes in a quarter Percentage of Health facilities, disposing off injection associated waste according to given procedure (Minimum 75% in 2003 and 100% in 2004 | Dec.2002 Dec.2003 - | The injection safety policy is incorporated in the national EPI policy and with EPI mid level management training manual has injection safety policy & practice All Mid Level manager health workers have been trained on it. AD Syringes introduced for all EPI vaccines No such assessment done However, Injection Saftey Assessment report is awaited. All the health facilities were practicing safe disposal of injection wastes | Fund shortage for training of Health workers on EPI policy. No constraint faced while introducing the AD Syringes Injection Safety, Waste Management Report awaited | October 2005 January 2004 March 2005 |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

As per the GAVI requirement, Financial Sustainability plan was submitted in November 2004. The FSP has been approved.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003 | 2005 | 2006 | 2007 | 2008 | 2009 | 210 | 211 | 212 | 213 |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  | 100% | 100% |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 14846 | 15,131 | 15,434 | 16204 | 16609 | 17024 | 17449 | 17885 | 18332 |
| Infants’ deaths | 898 | 915 | 933 | 980 | 1004 | 1029 | 1055 | 1082 | 1109 |
| Surviving infants | 13948 | 14216 | 15341 | 15224 | 15605 | 15995 | 16394 | 16803 | 17223 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 13,937 |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 13,355 |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) |  |  |  |  |  |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | - |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 13,803 |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 13086 |  |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Despite the small size of the population, the number of facilities required to deliver services are relatively huge due to the dispersed and scanty distribution of community settlements. Immunization services are delivered through a network of 29 hospitals, 172 Basic Health Units, and 440 outreach clinics per month .Therefore, annually 5280 Outreach sessions are conducted. Given the tiny birth cohort, at any ORCs the number of new births appearing for the first contact is just around 3 or less. Further, till 2004, Bhutan was not seriously implementing the WHO multi-dose open vial policy. Consequently, vaccine wastage for all antigens have been high for Bhutan due to these unavoidable circumstances. This problem was highlighted by WHO staff visiting to assess HepB introduction progress in 2003 (Report attached). Following that, we have conducted training in vaccine management, focusing on the open vial policy and the reduction of wastage. However, even the implementation of open vial policy is unlikely to have a significant reduction on vaccine wastage as it is still difficult to implement open vial policy for outreach services; it is being implemented in fixed health facilities such as hospitals and BHUs. In order to mininise vaccine wastage, it will be most ideal if Bhutan can be supplied with a combination of 2-dose and 10-dose vials. The 2-dose vials can be used for all outreach services and the 10-dose vials for all fixed facilities. Therefore, for 2006 supply request we have split the requirements into 2 and 10 dose vials, using 40% wastage for the 10-dose and 10% for the 2-dose vials.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Separate calculation has been made to estimate 2 and 10 dose vial requirement. We are request. 60% as 10 dose and 40% as 2 dose.

Informal contact through the RWG focal point in SEARO seems to indicate that it may be possible for UNICEF to mobilise the 2-dose supply for Bhutan, given the small quantity needed for the country.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fun

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Table 5 b: calculations for 2-dose vials

Remarks

In the above two tables, the calculations for the 10-dose and 2-dose vials needed are calculated using 40% wastage for the 10-dose vial and 10% wastage for the 2-dose vial. The total requirement should be the combined products of the two tables

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  | #### Formula | #### For 2006 | #### For 2007 |
| --- | --- | --- | --- | --- |
| #### A | #### Target if children for ………… Vaccination (for TT : target of pregnant women) 1 | #### # | #### 15434 | #### 16204 |
| #### B | #### Number of doses per child (for TT : target of pregnant women) | #### # |  |  |
| #### C | #### Number of ……….. doses | #### A x B |  |  |
| #### D | #### AD syringes (+10% wastage) | #### C x 1.11 |  |  |
| #### E | #### AD syringes buffer stock 2 | #### D x 0.25 |  |  |
| #### F | #### Total AD syringes | #### D + E |  |  |
| #### G | #### Number of doses per vial | #### # |  |  |
| #### H | #### Vaccine wastage factor 4 | #### Either 2 or 1.6 |  |  |
| #### I | #### Number of reconstitution syringes (+10% wastage)3 | #### Either 2 or 1.6 |  |  |
| #### J | #### Number of safety boxes (+10% of extra need) | #### (F + I) x1.11/100 |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Bhutan completes its three year support for injection safety supplies by end of 2005. Therefore, no calculations are included for 2006

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Percentage of DMO & DHSOs trained on Mid Level Management Training - National EPI Policy guidelines revised to include new vaccines - Percentage of Health workers trained on vaccine management injection safety use of new vaccine & revised policy | 41 Dec.2004 - | 100% 100% 179 Health Workers trained | - EPI, National Services manual has to be updated for the incorporation of the revised changes. |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 15.5.2005 |  |
| Reporting Period (consistent with previous calendar year) | January –December 2004 |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | - |  |
| Reported on use of 100,000 US$ | Filled |  |
| Injection Safety Reported on | - |  |
| FSP Reported on (progress against country FSP indicators) | - |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | - |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

Copy of the report sent to Regional Working Group, New Delhi

7.	Signatures

For the Government of …………BHUTAN……..…………………………………

Signature:	……………………………………………...……………...

Title:	………Offtg. Secretary………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Secretary Chairman |  | Planning Commission Royal Government of Bhutan | Director |  |
| Ministry of Health | Director, Department of Public Health, Vice Chairman |  | Youth Guidance and Counselling Division | Program Officer |  |
| Ministry of Health | Deputy Secretary Policy & Planning Division |  | Bhutan Broad casting Service | General Manager |  |
| Ministry of Finance | Director General, Department of Debt. Aid & Management |  | World Health Organization Country Office | Representative |  |
| Bhutan Chamber of Commerce & Industry | Offtg. Secretary General |  | JICA/JOCV | Resident Representative |  |
| UNICEF, Country Office | Project Officer, Health & Nutrition. |  |  |  |  |

~ End ~