January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: CUBA

Date of submission: 19 May 2006 Reporting period: 2005 ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

N/A

#### 1.1.2	Use of Immunization Services Support N/A

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 _______________

Remaining funds (carry over) from 2004 ________________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

## If yes, please report on the degree of its implementation.

N/A

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

N/A

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

N/A

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

N/A

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The country received conditional approval in July 13, 2005; pending clarification on the status of the National Regulations for the Management of Hazardous Wastes Public Health Care Institutions. In order to comply with WHO recommendations, they are being revised in collaboration with PAHO. The country received approval in September 19, 2005; a total of $US 436,000 for three years, $US 170,000 for 2006. On November 1, 2005, the country formally requested that the PAHO/WHO Office in Cuba manage these funds. The first transfer was made on January 4 of 2006. The country sent the first purchase order to the PAHO Revolving Fund in April and prepared a plan for distribution of supplies to provinces in May of 2006.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### The National Injection Safety Plan has been presented to the Ministerial Bureau.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. Approval of the National Regulations for the Management of Hazardous Solid Wastes for Public Health Care Institutions with 100% implementation in health care services. | Approval | Pending | Financial constraints have slowed down the approval process. |  |
| 2. Vaccination centers are adequate and basic furniture is available in 534 polyclinics and maternal hospitals where vaccination serves are provided. | 267 (50.0%) | Achieved in 100% of the country. |  |  |
| 3. 100% of healthcare establishments where regular schedule vaccine injection services are provided use AD syringes for BCG, DPT/HepB, Hib, DTP, MMR, and TT. | 90 hospitals 444 policlinics (100%) | Pending, except for BCG. |  |  |
| 4. 100% of polyclinics and hospitals where vaccine injection services are provided are supplied with needle destroyers before syringe elimination. |  | Was not approved as part of proposal for GAVI INS. |  |  |
| 5. 100% of polyclinics and hospitals where vaccine injection services are provided are supplied with safety boxes for the safe elimination of syringes and needles used in vaccination. | 90 hospitals 444 polyclinics (100%) | Arrival of supplies pending |  |  |
| 6. 100% of polyclinics and hospitals destroy safety boxes in safe manner by burring wastes at 1.5 meters of depth. | 90 hospitals 444 policlinics (100%) | Pending |  |  |
| 7. Train 100% of health personnel on norms for vaccination safety, with emphasis on injection safety.. | 100% | Achieved |  |  |
| 8. Incorporate injection safety component into curriculum of healthcare personnel training schools. |  | Achieved. It is expected that three courses will be carried out at provincial level. (4) |  |  |
| 9. Social communication strategy on injection safety formulated and implemented in 169 municipalities. | 84 municipalities (50%) | Pending |  | 100% of municipalities for 2007 |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

N/A

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

There is a commitment to guarantee sustainability after the end of GAVI support in 2008.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007 Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 127,200 | 120, 587 | 115,000 | 113,000 | 110,000 |  |  |  |  |
| Infants’ deaths | 736 | 746 | 649 | 632 | 616 |  |  |  |  |
| Surviving infants | 126,464 | 119 970 | 114,351 | 112,368 | 109,384 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DPT-HepB (DTP1 for 2004-2005)* | 112,929 | 44,425 | 110 400 | 110,120 | 107,196 |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DPT-HepB (DTP3 for 2004-2005)* | 112,047 | 101,185 | 109 250 | 110.120 | 107,196 |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 15 600 | 15 847 | 30 000 | 30 000 | 30,000 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 126,456 | 119,269 | 112,069 | 110,110 | 107, 196 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 126,100 | 124,787 | 112,069 | 110,110 | 107, 196 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Hib | 124 656 | 117,626 | 112,069 | 110,110 | 107, 196 |  |  |  |  |
| Newborns vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with HepB | 126,456 | 118,692 | 112,069 | 110,110 | 107, 196 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Yellow Fever | -- | -- | 20,000 | 20,000 | 18,000 |  |  |  |  |

* Indicate actual number of children vaccinated in 2004-2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- In 2004, due to a DTP vaccine shortage; DTP coverage rate was 89%, while that of HepB was 100%. Children with a pending DTP dose from 2004 were vaccinated during the first months of 2005, and therefore the DTP3 coverage was higher than that for HepB3 for this year. Tetravalent DTP-HepB vaccine was introduced in March of 2005, for vaccination of children born on January 2005; DTP and HepB vaccines were still used for children born in 2004. For the 2005 JRF, the number of vaccinated children reported for DTP3 corresponds to 6 months of 2005 (born January-June 2005), while the number reported for Hib3 corresponds to the children born in 1 year (born July 2004 – June 2005). Hib vaccination figures were double those of DTP-HepB in this year. - In 2005, the number of children to be immunized with BGC and the first dose of HepB was 120,587. There were 119,269 children (98.9%) immunized with BCG and 118,692 (98.4%) were immunized with the first dose of HepB; there was a difference of 577 children. Even though all the provinces reached 95% of coverage for both vaccines, not all reached 100%, which caused the differences of coverage. (For different causes, 1318 children were not vaccinated with BCG and 1895 children were not vaccinated with the dose of HepB given usually at birth. These were recovered subsequently in the vaccination services of primary and maternal-infant health care centers.) - There is no drop-out between BCG, DPT1, DPT3 and measles; the children that for some cause (disease, specific shortage of some vaccine, etc.) do not receive a specific vaccine at the corresponding moment are recovered subsequently as the cause is resolved. - Around 95% of the population over 15 years of age is immunized with TT vaccine; example of this is the very low occurrence of tetanus cases in the country. During the years 2004 and 2005, there were no cases reported; and to date of 2006, only 2 cases have occurred. For more than 15 years, there have been no tetanus cases in women of childbearing age; and since the year 1972, there is no neonatal tetanus. Around 95% of the population over 15 years of age is immunized with TT vaccine; example of this is the very low occurrence of tetanus cases in the country. During the years 2004 and 2005, there were no cases reported; and to date of 2006, only 2 cases have occurred. For more than 15 years, there have been no tetanus case in women of childbearing age; and since the year 1972, there is not neonatal tetanus. The use of the TT vaccine is not exclusive of the women of childbearing age; the official schedule initiates the protection against tetanus with 4 doses of DPT (2, 4, 6 and 18 months), 1 reactivation with DT at 6 years, 1 reactivation with TT at 14 years and 1 reactivation with TT every 10 years. Every year, there is need to vaccinate approximately 30,000 women in childbearing age with TT, according to their vaccination schedule. - Denominators and targets for upcoming years reflect the current birth rate tendencies. There are good statistical records of births (99.2% of births occur within the national healthcare system) and good vaccination registries at all centers where the services are provided.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

N/A

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG

Table 6: Estimated supplies for safety of vaccination for the next two years with MMR

Table 6: Estimated supplies for safety of vaccination for the next two years with DPT+HepB

Table 6: Estimated supplies for safety of vaccination for the next two years with Hib

Table 6: Estimated supplies for safety of vaccination for the next two years with HepB

Table 6: Estimated supplies for safety of vaccination for the next two years with tetanus toxoid

Table 6: Estimated supplies for safety of vaccination for the next two years with yellow fever

If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

The supplies have changed to reflect the needs according to revised demographic data.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of    Cuba

Signature: Dr. Miguel Angel Galindo

Title: EPI Manager, Ministry of Health

Date:  17 May 2006

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organization | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| UNICEF | Ms. Odalys Rodríguez Programs Officer | 17 May 2006 |  |  |  |
| PAHO/WHO | Dr. Lea Guido López PAHO/WHO Representative | 17 May 2006 |  |  |  |

~ End ~