15 May  2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: THE GAMBIA

Date of submission: 15th May 2006 Reporting period: Jan – Dec 2005( Information provided in this report MUST refer to the previous calendar year ) Third annual progress report Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with the GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during the previous calendar year 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for year 2006 (indicate forthcoming year)

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2006

  - Confirmed/revised request for injection safety support for the year 2006

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during the previous calendar year 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

ISS funds are jointly managed by the Department of State for Health and Social Welfare and Finance and Economic Affairs under a special account known as “below the line account” managed by the principal accountant of Department of State for Health. Funds are released upon the signatures of the director of Health Services and Permanent Secretary, Department of State For Health and Social Welfare for under the approval of the ICC. When proposals are made and signed by the above-mentioned authorities and submitted to the principal accountant it is acted upon without delay.

#### 1.1.2	Use of Immunization Services Support

In the past year, the following major areas of activities have been funded with the GAVI/Vaccine Fund contribution.

Funds received during the reporting year 2005 US $237,100.00

Remaining funds (carry over) from 2004  US $ 96, 888.00

Table 1 : Use of funds during reported calendar year 2005

| Area of Immunization Services Support | Total amount in US $ | Amount of funds |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Division | Health Facility |  |
| Vaccines |  |  |  |  |  |
| Injection supplies | 1,610 |  |  | 1,610 |  |
| Personnel | 17,886 | 7,886 | 10,000 |  |  |
| Transportation | 4,446 | 4,446 |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | 63,149 | 33,150 | 10,080 | 19,919 |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach | 18,536 | 3089 |  | 15,447 |  |
| Supervision | 2,250 | 1,543 | 7,07 |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles | 2,809 | 2,809 |  |  |  |
| Cold chain equipment | 15,427 |  |  | 15,427 |  |
| Other (Printing and stationery) | 23,980 | 19,650 | 2,400 | 1,930 |  |
| Total: | 150,093.00 | 72,573 | 23,187 | 54,333.5 |  |
| Remaining funds for next year: 2006 | 183,894.37 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Training of 6 (Six) Data Entry Clerks and six Divisional supervisors on vaccine data management, supported by WHO. Six supervision and monitoring visits to all health facilities in the six divisions. Developed, and distributed data collection and vaccine management tools to all health facilities countrywide.. Procurement of Access ladders and 100 vaccine carriers for the strengthening of the cold chain system at service delivery level. Validation of Two studies namely the wastage Rate Study and the injection safety Problems commonly encountered include lack of capacity due mainly to high staff attrition, lack of skills as a result of inadequate training, and problems of mobility to provide outreach services. .

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please attach the plan and report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during the last year (for example, coverage surveys).

The following studies/surveys were conducted in the year 2005: - Conduct an EPI evaluation survey supported by PHPNP Project - Validate safe injection study supported by WHO. See attached reports of Surveys/studies

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during the previous calendar year

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR: 1990/1997

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

The new and under-used vaccine have been introduced in The Gambia for a very long time after successfully carried out vaccines trails in The Gambia The Gambia received the following vaccines and quantities from GAVI in 2005. - DPT/Hib --- 98,000 doses , March 2005 98,000 doses in September 2005 - Hepatitis B --- 92,800 doses , March 2005 92, 800 doses, December 2005 - No problems were encountered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Major Activities expected to be undertaken to strengthen the new vaccine introduction are outline below:- - Training of National Staff in the field of community health - Increased monitoring and supervision of EPI activities at divisional and health facility levels. - Training of health staff on monitoring of vaccines - Procurement of six motor cycles to improve immunization services especially outreach EPI services - Coverage survey for the year 2005 - Award prizes to facilities with good monitoring indicators on Immunization and drop-out - Conduct National Immunization Days for Polio/Measles 2006 - Introduction of a 7 – valent pneumococcal vaccine - Installation of a cold room at Bansang (CRD) - Conducted a Vaccine Drop-Out Study - Support the training of the EPI store Hand on store management - Conduct the maintenance of the cold chain system country wide on a quarterly basis - Conduct the internal distribution of EPI Supplies to the divisions on a quarterly basis - Print and distribute vaccine tally booklets and ledgers to the H/facilities - EPI Programme Review and the development of a comprehensive Multi Year plan (cMYP) - Injection Safety assessment For major activities that have been undertaken please refer to page 5

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

See second annual report on details.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

The support for safe injection materials from GAVI ended in December 2004; as a result Government purchased the quantities needed for 2005 No problems encountered so far

#### Progress of transition plan for safe injections and safe management of sharps waste.

| No | Indicators | Targets | Achievements | Constraints | Updated Targets |
| --- | --- | --- | --- | --- | --- |
| 1 | No. of monitoring visits planed and conducted | Visit all health facilities and divisions quarterly Undertake 4 quarterly visits per annuam | 48 facilities visited monthly Four quarterly visits conducted, reaching 48 facilities | none | Visit 48 facilities and divisions quarterly |
| 2 | Vaccine Forecast and shipment plan timely finalised and sent to UNICEF | Adequate stocks of supplies available in all health facilities | The forecast sent and supplies received on time | Poor management and monitoring of injection safety materials in some facilities | Timely submission of forecast plan maintained |
| 3 | Number and type of health personnel trained on injection safety | Train at least two people from each health facility on injection safety | 190 staff including nurses, public health officers and divisional supervisors trained on injection safety | High staff turn over | All trained staff to practice injection safety More staff to be trained on injection safety and focal points identified |
| 4 | No. of facilities/personnel involved in the validation exercise | To reach all facilities | All facilities were visited and data analysed | None | Reports to be distributed to all levels of service delivery |
| 5 | No. of radio/TV spots on injection safety | No. of radio and TV spots developed and aired on injection safety | On-going, consultant and funds identified for development of plan | EPI team busy with FSP and EPI Communication Plan | Availability and use of TV and radio spots |
|  | No. of advocacy meetings held | 4 ICC meetings | 5 ICC meetings held | Low attendance of ICC members | 5 meetings held |
| 6 | Revised training modules on injection safety | Training modules included in pre-service curricula | 2 focal points from the training institutions trained | Limited staff trained on injection safety | All pre-service school trained on injection safety |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No cash was received.

# 2.  	Financial sustainability

Inception Report :			Outline timetable and major steps taken towards improving financial sustainability and the development of a 						financial sustainability plan.

Second Annual Progress Report :	Describe indicators selected for monitoring financial sustainability plans and include baseline and current values for each indicator. In the following table 2, specify the annual proportion of five year of GAVI/VF support for new vaccines that is planned to be spread-out to ten years and co-funded with other sources.

NOT APPLICABLE

| Table 2 : Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| Proportion funded by GAVI/VF (%) |  | NOT APPLICABLE |  |  |  |  |  |  |  |  |
| Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| Total funding for …………. (new vaccine) * |  |  |  |  |  |  |  |  |  |  |
| * Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine |  |  |  |  |  |  |  |  |  |  |

Subsequent reports:	Summarize progress made against the financing strategy, actions and indicators section of the FSP; include successes, difficulties and responses to challenges encountered in achieving outlined strategies and actions. Report current values for indicators selected to monitor progress towards financial sustainability. Include funds received to date versus those expected for last year and the current year and actions taken in response to any difficulties.

Update the estimates on program costs and financing with a focus on the last year, the current year and the next 3 years. For the last year and current year, update the estimates of expected funding provided in the FSP tables with actual funds received since. For the next 3 years, update any changes in the costing and financing projections.  The updates should be reported using the same standardized tables and tools used for the development of the FSP (latest versions available on http://www.gaviftf.org under FSP guidelines and annexes. Highlight assistance needed from partners at local, regional and/or global level.

# 3.  	Request for new and under-used vaccines for year 2007 ( indicate forthcoming year )

Section 3 is related to the request for new and under used  vaccines and injection safety for the year 2007.

- Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) approved with country application:  revised Table 4 of approved

application form.

DTP3 reported figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 10) .  Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 55,385 | 57,711 | 60,135 | 62,661 | 65,292 | 63948 | 66741 | 69673 |  |
| Infants’ deaths | 3,545 | 3,694 | 3,849 | 4,010 | 4,179 | 4729 | 4939 | 5158 |  |
| Surviving infants | 51,840 | 54,018 | 56,286 | 58,650 | 61,114 | 59219 | 61802 | 64515 |  |
| Infants vaccinated / to be vaccinated with 1st dose of DTP (DTP1)* | 38,569 | 40,513 | 48,689 | 51,525 | 58,591 | 60201 | 61802 | 64515 |  |
| Infants vaccinated / to be vaccinated with 3rd dose of DTP (DTP3)* | 38,569 | 40,513 | 45,080 | 47,726 | 56,884 | 56229 | 61802 | 64515 |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 1st dose of Hib ( new vaccine) | 38,569 | 40,513 | 48,689 | 51,525 | 58,591 | 60201 | 61802 | 64515 |  |
| Infants vaccinated / to be vaccinated with 3rd dose of Hib ( new vaccine) | 38,569 | 40,513 | 45,080 | 47,726 | 56,884 | 56229 | 61802 | 64515 |  |
| Wastage rate of *** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with 1st dose of Hep. B ( new vaccine) | 45,049 | 46,995 | 52,296 | 50,679 | 58,040 | 57479 | 66741 | 64515 |  |
| Infants vaccinated / to be vaccinated with 3rd dose of Hep. B ( new vaccine) | 45,049 | 46,995 | 46,478 | 44,967 | 54,721 | 56,402 | 61802 | 64515 |  |
| Wastage rate of *** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 41,816 | 45,015 | 42,352 | 42,043 | 46,027 | 45059 | 66741 | 69673 |  |
| Infants vaccinated / to be vaccinated with BCG | 41,816 | 45,015 | 52,675 | 50,653 | 57,353 | 65,381 | 66741 | 71,680 |  |
| Infants vaccinated / to be vaccinated with Measles | 47,538 | 49,696 | 46,850 | 41,161 | 53,206 | 51357 | 61802 | 66376 |  |
| Infants vaccinated/ to be vaccinated with Yellow Fever | 47,071 | 49,696 | 47,881 | 41,419 | 52,635 | 51383 | 61802 | 66376 |  |
| Infants vaccinated/ to be vaccinated with OPV3 | 47,589 | 49,588 | 39,666 | 56,982 | 56,236 | 57638 | 61802 | 66376 |  |

* Indicate actual number of children vaccinated in past years and updated targets

** Indicate actual wastage rate obtained in past years

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The number of children immunized with DPT and Hib, 51749 (95.8%), respectively exceeded the target set for 2001, 40513 (75%). Therefore the targets for the following years have been revised accordingly – from 45,029 to 54,035 for 2002; from 52,785 to 56,891 for 2003; from 58,058 to 59,892 for 2004; from 63,449 to 63,948 for 2005 from 65,691 to 66,741 for 2006; and from 68,451 to 69,673 for 2007.

3.2	Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division) for the year 2006 (indicate forthcoming year)

Please indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes.

Shipment Plan for 2006 sent to UNICEF supply division

Table 3: Estimated number of doses of DPT/Hib vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2007 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine (DPT/Hib) |  | 64515 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 193,545 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.18 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 228,383 |  |
| G | Vaccines buffer stock | F x 0.25 | 57,096 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 80,940 |  |
| I | Total vaccine doses requested | F + G - H | 204,539 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 188,368 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 22,704 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 2, 343 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

*Please report the same figure as in table 1.

|  |  | Formula | For year 2007 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine (Hep.B) |  | 64515 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 193545 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.18 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 228,383 |  |
| G | Vaccines buffer stock | F x 0.25 | 57096 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 60,200 |  |
| I | Total vaccine doses requested | F + G - H | 225,279 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 211,389 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 25,006 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 2,624 |  |

#### 3.3	Confirmed/revised request for injection safety support for the year  2006 (indicate forthcoming year)

Table 4: Estimated supplies for safety of vaccination for the next two years with DPT-Hib (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2006 | For year 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for DPT-Hib vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABLE |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of DPT-Hib doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2005 | For the year 2006 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for DPT-Hib |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 4: Estimated supplies for safety of vaccination for the next two years with Hep. B(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for Hep.B vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABLE |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of Hep. B doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2005 | For the year 2006 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for Hep. B |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 4: Estimated supplies for safety of vaccination for the next two years with TT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for TT vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABL:E |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of TT doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year … | For the year … |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for TT |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 4: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABLE |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of BCG doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2004 | For the year 2005 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for BCG |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 4: Estimated supplies for safety of vaccination for the next two years with Measles (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for Measles vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABLE |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of Measles doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2004 | For the year 2005 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for Measles |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Table 4: Estimated supplies for safety of vaccination for the next two years with Yellow fever (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

|  |  |  |  |  | Formula |  | For year 2005 | For year 2006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for Yellow fever vaccination (for TT : target of pregnant women) |  |  |  | # |  | NOT APPLICABLE |  |
| B | Number of doses per child (for TT woman) |  |  |  | # |  |  |  |
| C | Number of Yellow Fever doses |  |  |  | A x B |  |  |  |
| D | AD syringes (+10% wastage) |  |  |  | C x 1.11 |  |  |  |
| E | AD syringes buffer stock |  |  |  | D x 0.25 |  |  |  |
| F | Total AD syringes |  |  |  | D + E |  |  |  |
| G | Number of doses per vial |  |  |  | # |  |  |  |
| H | Vaccine wastage factor 4 |  |  |  | Either 2 or 1.6 |  |  |  |
| I | Number of reconstitution syringes (+10% wastage) |  |  |  | C x H x 1.11 / G |  |  |  |
| J | Number of safety boxes (+10% of extra need) |  |  |  | ( F + I ) x 1.11 / 100 |  |  |  |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |  |  |  |  |  |  |  |  |
| ITEM |  |  | For the year 2004 | For the year 2005 |  | Justification of changes from originally approved supply: |  |  |
| Total AD syringes |  | for Yellow fever |  |  |  |  |  |  |
|  |  | for other vaccines |  |  |  |  |  |  |
| Total of reconstitution syringes |  |  |  |  |  |  |  |  |
| Total of safety boxes |  |  |  |  |  |  |  |  |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | Yes |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | No |  |
| Reported on use of 100,000 US$ | No |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | No |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| World Health Organisation |  |  | Medical Research Council |  |  |
| Unicef – The Gambia |  |  | Catholic Relief Services |  |  |
| Action Aid The Gambia |  |  | Dept. of State for Finance- |  |  |
| Christain Children’s Fund |  |  | Rotary International |  |  |
| Gambia Red Cross Crescent |  |  |  |  |  |

~ End ~

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

GAVI will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women of Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births).

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Only for lyophilized vaccines. Write zero for other vaccines

4 Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.