May 2002

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

LESOTHO

Date of submission: 29 September 2002 Reporting period: 2001 ( previous calendar year ) ( Tick only one ) : Inception report X First annual progress report ( Financial sustainability plan attached ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report (

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds February,2002.

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

#### The fund was disbursed to the 19 Health Service Areas (H.S.As) and Central Level according to their micro-plans.

#### A new account was opened with the Ministry of Health & Social Welfare in accounts section for accountability.

#### The ICC was informed on the receipt of the fund and was involved in the disbursement. Activity reports and financial accountability has been done. A full report on the implementation of the funds will be discussed during the next ICC meeting.

#### Statement on use of GAVI/The Vaccine Fund immunization services support

Total received US$ 37,400

In the past year, the following major areas of activities have been funded with the GAVI/The Vaccine Fund contribution.

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |
| --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines | N/A | - | - |  |
| Injection supplies | N/A |  |  |  |
| Personnel | N/A |  |  |  |
| Transportation | N/A |  |  |  |
| Maintenance and overheads | N/A |  |  |  |
| Training | N/A |  |  |  |
| IEC / social mobilization |  |  |  |  |
| Monitoring and surveillance | US$ 3, 740 | 20% |  |  |
| Vehicles |  |  |  |  |
| Cold chain equipment |  |  |  |  |
| Conducting immunization accelerations | US$ 33, 660 | - | 80% | 80% |

#### Immunization Data Quality Audit (DQA)

#### Not yet done

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines  N/A

#### 1.2.2	Major activities

Please outline what major activities will be undertaken to prepare for new vaccine introduction.

- Training will be conducted for health workers on introduction of new vaccines the 2nd quarter 2003.

- Development of a training manual which incorporates new vaccines before March 2003

- Development of an operation manual on new vaccines before march 2003

- Intensified social mobilization which includes

a) Development of posters and leaflets on new vaccines

b) Media sensitisation

Because of the unavailability of the pentavalent (first choice), the monovalent Hep B vaccine is planned to be introduce in July 2003

#### Statement on use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine-

#### Not yet received

## 1.3 Injection safety

#### 1.3.1	Receipt of injection safety support

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

Not yet received

#### Progress of transition plan for safe injections and safe management of sharps waste.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

| Objectives | Indicators | Main achievements | Constraints | Targets for 2002 |
| --- | --- | --- | --- | --- |
| 1.To introduce AD syringes in routine and supplemental immunizations | -A proportion of facilities adequately and timely supplied with AD syringes -Proportion of facilities exclusively using AD syringes. | -Health workers have been briefed on introduction of AD syringes in routine and supplemental immunization activities. | -Few AD syringes as the support from GAVI has not yet arrived | -By July 03, all injections for vaccinations in Lesotho will be supplied with AD syringes - Prepare dry store for the storage of AD syringes |
| 2.To monitor management of waste disposal and sharps | -# of health facilities using safety boxes or sharps containers -# of Health Service Areas with functioning incinerators -# of health centres and health posts without incinerators, but with secured deep pits | -Distribution of a few safety boxes has been done and briefing on management of wastes and sharps has been done during the workshops | -Insufficient sharps disposals -Most of the health facilities don’t have incinerators, however they are using pits. | - By mid 03, all used syringes and needles will be disposed off immediately following use in a safety box or sharps containers - To complete training of health workers on safe injection and waste management by March, 03 |

#### Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

Not yet received

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  Financial sustainability

Inception Report:		Outline steps towards the development of a financial sustainability plan

First Annual Report: 	Submit completed financial sustainability plan

Subsequent Reports:	Summarize progress on financial sustainability

The government will continue to pay for recurrent and running costs like electricity for the national vaccine cold room It will also contribute an incremental annual budget percentage for vaccines and logistics Maintenance of cold chain vehicle to ensure proper transportation of vaccines

# 3.Request for new and under-used vaccines for year 2003

3.1    Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

NO CHANGE

| Table 1: Baseline and annual targets |
| --- |
| Number of | Baseline and targets |
|  | 2000 | 2001 | 2002 (65%) | 2003 (70%) | 2004 (75%) | 2005 (80%) | 2006 (85%) | 2007 (90%) |
| Births | 69.083 | 70.525 | 71.956 | 73.515 | 75.196 | 76.985 | 78.865 | 80.738 |
| Infants’ deaths | 5.112 | 5.219 | 5.328 | 5.440 | 5.565 | 5.697 | 5.836 | 5.975 |
| Surviving infants | 64.324 | 65.666 | 66.998 | 68.450 | 70.015 | 71.681 | 73.431 | 75.176 |
| Infants vaccinated with BCG* | 34.174 | 46.000 | 46.771 | 51.456 | 56.397 | 61.588 | 67.035 | 72.664 |
| Infants vaccinated with OPV3 ** | 36.293 | 41.799 | 43.549 | 47.915 | 52.511 | 57.345 | 62.416 | 67.658 |
| Infants vaccinated with DPT3** | 36.062 | 42.662 | 43.549 | 47.915 | 52.511 | 0 | 0 | 0 |
| Infants vaccinated with HepB** | N/A | N/A | N/A | 47.915 | 52.511 | 0 | 0 | 0 |
| Infants vaccinated with DPT-HepB+Hib** | N/A | N/A | N/A | 0 | 0 | 57.345 | 62.416 | 67.658 |
| Infants vaccinated with measles** | 30.970 | 36.908 | 43.549 | 47.915 | 52.511 | 57.345 | 62.416 | 67.658 |
| Pregnant women vaccinated with TT+ | 27.956 |  | 46.771 | 51.461 | 56.397 | 61.588 | 67.035 | 72.664 |
| Vit A for infants > 6 mths | 43.930 | 39.400 | 43.549 | 47.915 | 52.511 | 57.345 | 62.416 | 67.658 |

* Indicate target of children out of birth                              ** Indicate target of children out of surviving infants

If the request for supply for the coming years differs from previously approved plan:

Please indicate the reasons for those changes and, where relevant, the related modifications of targets of children to be vaccinated, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and indicate the date of the ICC meeting when the changes were endorsed. There are no changes in the plan

3.2	Confirmed request for new vaccine (to be shared with UNICEF Supply Division) for the year 2003  (indicate forthcoming year)

Table 2: Estimated number of doses of HepB  vaccine (specify for one presentation only): (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2003 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 47 916 | Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100% |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 143 748 |  |
| E | Estimated wastage factor | (See list in table 3) | 1,25 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 179 684 |  |
| G | Vaccines buffer stock | F x 0.25 | 44 921 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 224 605 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 209 422 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 0 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 2 325 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support

(If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference).

NO CHANGE

# Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

# Text boxes

Partnering with The Vaccine Fund