Partnering with The Vaccine Fund

GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION (GAVI)

AND

THE VACCINE FUND

PROGRESS REPORT

COUNTRY: KINGDOM OF LESOTHO

DATE OF SUBMISSION: 30 April 2005 REPORTING PERIOD: January to December 2004 SECOND ANNUAL PROGRESS REPORT

# Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Funds are used directly by the EPI programme, which submits requests to the Ministry of Health & Social Welfare accounting office where the money is kept under special account. Funds are disbursed directly to the Health Service Areas which are mandated to account on the activities undertaken. The Inter-Agency Coordinating Committee (ICC) is regularly informed whenever GAVI funds are available and are to be utilised. Due to funds being received in country by the Ministry Of Finance And Development Planning, there are periodic delays in informing the Ministry of Health & Social Welfare on the submission of requests

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

FUNDS RECEIVED DURING 2004:     NIL

REMAINING FUNDS (CARRY OVER) FROM 2003:  LESOTHO MALUTI 20,000.00

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | N/A |  |  |  |  |
| Injection supplies | N/A |  |  |  |  |
| Personnel | N/A |  |  |  |  |
| Transportation | N/A |  |  |  |  |
| Maintenance and overheads | N/A |  |  |  |  |
| Training | N/A |  |  |  |  |
| IEC / social mobilization | N/A |  |  |  |  |
| Outreach | N/A |  |  |  |  |
| Supervision | N/A |  |  |  |  |
| Monitoring and evaluation | N/A |  |  |  |  |
| Epidemiological surveillance | N/A |  |  |  |  |
| Vehicles | N/A |  |  |  |  |
| Cold chain equipment | Transporting to HSAs from central level (LSM20, 000) | $3,300 |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: | $3,300 | $3,300 |  |  |  |
| Remaining funds for next year: | NIL |  |  |  |  |

Funds were utilized for:

- Distribution of cold chain equipment to different HSAs

- Monitoring and supervision

- Collection of routine immunization data

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed. (NO FUNDS WERE RECEIVED IN 2004)

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Synchronized Polio National Immunization Days (NIDs) and vitamin A supplementation was conducted between the Republic of South Africa, The Kingdom of Swaziland and the Kingdom of Lesotho. As part of preparations, health workers partners and identified personnel in line Government of Lesotho Ministries i.e. Ministry of Education & Training, Ministry of Defence, Ministry of Agriculture & Food Security and the Ministry of Trade & Industry were trained in Polio and Vitamin A Administration and sensitized on the importance of immunizations and vitamin A. The first round was from 27/08/04 to 15/09/04 and the second round from 20/09/04 to 15/10/04.The estimated overall coverage was 77%. Problems encountered were related to inadequate financial resources for field work and unavailability of transportation in some remote areas.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

√

X

## YES                              NO

## If yes, please report on the degree of its implementation.

Recommendations from the DQA were incorporated into the Ministry of Health & Social Welfare’s Family Health Division’s child survival workplan. Specific implementation has been in the following areas: - Recording Practices - under five registers have been updated and are to be printed for distribution at health facilities - Printing and distribution of drop-out rate charts as well as training of health personnel on their use - Mounting of maps in EPI office Showing performance per HSA i.e. coverage, drop-out rate and population not immunized ii) Training - EPI officer trained in cold chain and vaccine management - Data manager training on disease surveillance - WHO-AFRO and CDC-Atlanta supported data management consultancy in early 2004 to train EPI personnel - November 2004 Integrated Disease Surveillance & Response (IDSR) updating training regional workshops - District public Health nurses equipped with computers. iii) Supervision - supervisory skills were imparted on District public Health nurses - supervisory and monitoring visits to HSAs have been intensified

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

- The Lesotho Demographic Health Survey which incorporated questions on vaccination history was conducted from September 2004 to January 2005. - Consultancy to Determine Values for Population-based denominators was undertaken in September 2004 under the European Union Support to the Health Sector Reforms (Project 8 ACP LSO 008)

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH: AUGUST      YEAR: 2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Vaccines were received on the 09/12/2004 and 11/12/2004 as follows: HEP B; 16, 770; HB35904; 07/07.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Development of manual on new vaccines (Hep-B) for health workers - Training of health workers on new(Hep-B) vaccine - Advocacy and social mobilization - Printing and distribution of IEC material on new vaccine - Revision of child booklet, under-five register and other reporting tools to include new vaccines. - Review and evaluation of a cold room temperature monitor - Relocation of EPI management unit to new premises close to cold room with infrastructural adjustment i.e. Renovations and partitioning - Strengthening of EPI unit with additional staff Problems encountered: - Large number of parents of children above the recommended age for Hep-B demanded immunization for their children - Health workers also demanded to be immunized - Health personnel often forgot to administer the vaccine routinely

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Utilization of $100, 000 was reported in the 2003 report.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Received Support: - 432, 000 AD syringes 0.5ml 231 - 60,800 BCG Syringes - 5,650 Safety Boxes - 6,100 Reconstituted BCG7,900 Reconstituted Measles No Problems encountered

#### 1.3.2	Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Recommendations from the 2003 Injection Safety Assessment are presently being implemented. Priority areas are safety disposal and social mobilization to demand safe injection.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No money was received in 2004 and the money received in previous years has been reported in the 2003 GAVI report.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial sustainability plan was developed and submitted in 2004. The major strategies are: To Mobilize additional resources; Improve reliability of its resources; Improve programme efficiency.

Subsequent Progress Reports: None 	 (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of Hepatitis B vaccine |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003** | 2004 | 2005 | 2006 | 2007 |  |  |  |  |  |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| C: Total funding (US$) | 171,206 | 172,559 | 170,065 | 1,336,871 | 1,098,599 |  |  |  |  |  |

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Mobilizing additional resources | Target additional resources from GOL through MTEF process | USD100, 000 has been pledged. | None to date | 0% | 7% | None |
| 2.Improved reliability of resources | Include programme costs and financing in MTEF | District Health Management Teams in the three pilot districts of the Health Sector Reforms have been introduced to program costing procedures | The transition from the Health Service Area concept which addressed 18 catchment areas to the 10 administrative districts concept under the new decentralized and local government structures has presented some challenges in costing | 30% | 0% | None |
| 3.Improved programme efficiency | In service capacity aimed at improving efficiency of service delivery | Performance ranking of districts developed | Implementation is being linked to the Health Sector decentralization process | 3 | 0 | None |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 63 494 | 72816 | 77411 | 77305 | 77192 | 77082 | 76973 | 76864 | 77880 |
| Infants’ deaths | 5080 | 5825 | 6193 | 6184 | 6175 | 6167 | 6158 | 6149 | 6230 |
| Surviving infants | 58,414 | 66961 | 71218 | 71116 | 71016 | 70915 | 70735 | 70714 | 71649 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 37 442 | 66990 | 71218 | 71116 | 71016 | 70915 | 70735 | 70714 | 71649 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 33 922 70% | 53592 80% | 56974 80% | 60449 85% | 60432 85% | 63824 90% | 63662 90% | 67178 95% | 68067 95% |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Hepatitis B | 37442 | 66990 | 71218 | 71116 | 71016 | 70915 | 70735 | 70714 | 71649 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of\ Hepatitis B | 28461 | 66990 | 71218 | 71116 | 71016 | 70915 | 70735 | 70714 | 71649 |
| Wastage rate in 2004 and plan for 2005 Hepatitis B | 30% | 30% | 25% | 25% | 25% | 20% | 20% | 15% | 15% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | N/D | 72816 | 77411 | 77305 | 77192 | 77082 | 76973 | 76864 | 77880 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 34 317 | 72816 | 77411 | 77301 | 77192 | 77082 | 76973 | 76864 | 77880 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 28 280 | 53592 | 56974 | 60449 | 60432 | 63824 | 63662 | 67178 | 68067 |

NB: Due to the change in the new program installed data for TT2 is not available

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Table 3 reflects data specific to children less than one year of age using data projected from the 1996 Lesotho Bureau of Statistics Census. Other sources may have different values due to the limitations encountered in reaching a consensus on the precise denominators in specified age groups. It is expected that the 2006 Lesotho Census will provide age-specific data that will differ from that listed in Table 3 therefore amendments to Table 3 will be reflected in subsequent reports.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No revised request for new vaccine was done.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

NOT APPLICABLE FOR THIS REPORT.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Estimated supplies for safety of vaccination for the next two years

Table 6.1 TT

|  | For 2006 | For 2007 |
| --- | --- | --- |
| Target | 77411 | 77305 |
| Number of doses per child | 154822 | 154610 |
| Number of doses | 11984925842 | 11952126050 |
| AD Syringes | 13303267685 | 13266859916 |
| AD Syringes buffer stock 2 | 3325816921 | 3316714979 |
| Total AD Syringes | 16629084606 | 16583574894 |
| Number of doses per vial | 10 | 10 |
| Vaccine wastage factor | 2 | 2 |
| Number of reconstitution syringes | 2660653537 | 2653371983 |
| Number of safety boxes | 214116093.4 | 213530110.3 |

Table 6.2 BCG

|  | For 2006 | For 2007 |
| --- | --- | --- |
| Target | 77411 | 77305 |
| Number of doses per child | 77411 | 77305 |
| Number of doses | 5992462921 | 5976063025 |
| AD Syringes | 6651633842 | 6633429958 |
| AD Syringes buffer stock 2 | 1662908461 | 1658357489 |
| Total AD Syringes | 8314542303 | 8291787447 |
| Number of doses per vial | 20 | 20 |
| Vaccine wastage factor | 2 | 2 |
| Number of reconstitution syringes | 665163384 | 663342995 |
| Number of safety boxes | 996747333 | 99401947 |

TABLE 6.3 MEASLES

|  | For 2006 | For 2007 |
| --- | --- | --- |
| Target | 77411 | 77305 |
| Number of doses per child | 77411 | 77305 |
| Number of doses | 5992462921 | 5976063025 |
| AD Syringes | 6651633842 | 6633429958 |
| AD Syringes buffer stock 2 | 1662908461 | 1658357489 |
| Total AD Syringes | 8314542303 | 8291787447 |
| Number of doses per vial | 10 | 10 |
| Vaccine wastage factor | 2 | 2 |
| Number of reconstitution syringes | 1330326768 | 1326689992 |
| Number of safety boxes | 107058047 | 106765055 |

Table 6.4 DPT

|  | For 2006 | For 2007 |
| --- | --- | --- |
| Target | 77411 | 77305 |
| Number of doses per child | 232233 | 231915 |
| Number of doses | 17977388763 | 17928189075 |
| AD Syringes | 19954901527 | 19900289873 |
| AD Syringes buffer stock 2 | 4989725382 | 4975072468 |
| Total AD Syringes | 24943626909 | 24875362342 |
| Number of doses per vial | 10 | 10 |
| Vaccine wastage factor | 2 | 2 |
| Number of reconstitution syringes | 3990980305 | 3980057975 |
| Number of safety boxes | 321174140 | 320295165 |

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NOT APPLICABLE

# Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| DPT Coverage | 75% | 83% (2004/2005 Lesotho Demographic Health Survey) | High attrition of trained staff | 85% |
| Drop–out rate | <5% | 8% | Misinformation among Health workers and caregivers between correlation of routine and NID vaccinations | 6% |
| Wastage rate | <10% |  | Policy on daily immunization also contributes to high wastage particularly in reference to the 20 dose BCG vial | <30% |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 10/05/05 |  |
| Reporting Period (consistent with previous calendar year) | 2004 |  |
| Table 1 filled-in | N/A |  |
| DQA reported on | 2004 |  |
| Reported on use of 100,000 US$ | 2003 |  |
| Injection Safety Reported on | 2003 |  |
| FSP Reported on (progress against country FSP indicators) | N/A | FSP was developed late 2004 |
| Table 2 filled-in | N/A |  |
| New Vaccine Request completed | N/A |  |
| Revised request for injection safety completed (where applicable) | N/A |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments:

ICC/RWG comments:

Consensus on the denominators for the targeted age groups is a prevailing challenge when planning immunization activities. The European Union supported exercise of September 2004 had some limitations in addressing this fundamental issue while working in collaboration with the Bureau of Statistics and the Ministry of Health. The upcoming 2006 Census will facilitate resolution of the population denominator issues. Lesotho’s ongoing Health Sector Reform is based on decentralization of services to 10 administrative districts from 18 Health Service Areas. Decentralization is being piloted in three of the 10 districts where health management teams are in place. When evaluating progress, interpretation of the baseline indicators for district-based activities should take into consideration that the decentralization process is phased hence only three districts being operational as set out by the Health Sector Reform process.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~