Annual Progress Report 2006

Submitted by

The Government of

MALAWI

to the

# Date of submission : 14th May 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of  Malawi………………..…………………………………

Ministry of Health:

Signature: ……………………………………

Title: Director of Preventive Health Services ……………………………………

Date: ……………………………………

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
|  | Ministry of Health |  |  |
|  | WHO |  |  |
|  | UNICEF |  |  |
|  | DFID |  |  |
|  | USAID |  |  |
|  | Norwegian Embassy |  |  |
|  | JICA |  |  |

Signatures Page for HSS   Not Applicable

For the Government of  ………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: …………………………………… | Title: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The HSCC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

First year of ISS Support : _________________

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If no, is there an intention to get them on-budget in the near future?

ISS Proposal submitted in January 2007 awaiting GAVI Board response

Provide an overview of ISS expenditure since the first year of ISS support in Table 1.

Table 1 : Statement of ISS funds expenditure

| Year | Type of disbursement (investment/reward) | Amount received | Total available | Amount spent | Balance taken to next year |
| --- | --- | --- | --- | --- | --- |
| 2000 |  |  |  |  |  |
| 2001 |  |  |  |  |  |
| 2002 |  |  |  |  |  |
| 2003 |  |  |  |  |  |
| 2004 |  |  |  |  |  |
| 2005 |  |  |  |  |  |
| 2006 |  |  |  |  |  |

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not Applicable

#### 1.1.2	Use of Immunization Services Support     Not Applicable

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 _______________

Remaining funds (carry over) from 2005 ________________

Balance to be carried over to 2007 __________________

Table 2: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Not Applicable

#### Immunization Data Quality Audit (DQA)

First DQA conducted in __________

Result of first DQA : Passed/Failed

If failed, second DQA conducted in _________

Result of second DQA : Passed/Failed

Next* DQA scheduled for _________

*If no DQA has been passed, when will the DQA be conducted

*If the DQA has been passed, the next DQA will be 5 years after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted

What were the major recommendations of the DQA ?

Not applicable but DQA planned for 2009

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared? Not applicable

YES                              NO

## If yes, please report on the degree of its implementation and attach the plan.

Not applicable

Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.    Not applicable

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

Multi indicator Cluster Survey (MICS) 2006

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

- The ICC met once - No Civil Society Organizations members in the ICC

1.2. GAVI Alliance New & Under-used Vaccines Support

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced (please include change in doses per vial and change in presentation, e.g. DTP + HepB mono to DTP-HepB):

| Vaccine | Vial size | Date |
| --- | --- | --- |
| DPT-HepB | 2 dose | Launched January 2002 |
| Hib | 2 dose | Launched January 2002 |

Please report on receipt of vaccines provided by the GAVI Alliance during 2006.

| Vaccine | Vials size | Doses | Date |
| --- | --- | --- | --- |
| DPT-HepB+Hib | 2 dose | 540,000 | 11/02/2006 |
| DPT-HepB+Hib | 2 dose | 540,000 | 29/05/2006 |
| DPT-HepB+Hib | 2 dose | 776,000 | 04/09/2006 |
| DPT-HepB+Hib | 2 dose | 686,600 | 27/12/2006 |

Please report on any problems encountered.

No problems encountered since introduction of new vaccines

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Activities for service strengthening: - District Health Management Teams (DHMT) conducted supervisory visits to health centres to monitor EPI activities. - Developed EPI Communication Plan - Conducted review meetings and follow up visits to RED implementing districts - Conducted district based briefings on EPI disease surveillance - Conducted integrated supportive supervisory visits to districts. - Finalised EPI Comprehensive Multi year Plan ( cMYP) - Finalised ISS Proposal development to GAVI Board - National dry store warehouse under construction - Adaptation of selected MLM modules - Development of draft HSS proposal to GAVI

#### Use of GAVI Alliance financial support (US$100,000) for the introduction of the new vaccine

These funds were received on :  2001___________

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

All the money was used up for: - Training health workers on introduction of new vaccines - Supervisory visits - Monitoring activities

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in  28th – 31st July 2003

Please summarize the major recommendations from the EVSM/VMA

- There is need for additional cold room capacity - There is need for additional dry goods warehousing - The existing cold room and freezer should be fitted with a voltage regulator/surge protector

Was an action plan prepared following the EVSM/VMA : Yes/No√

Please summarize main activities under the EVSM plan and the activities to address the recommendations.

EVSM plan was not available however the following activities are being implemented in line with the recommendations: - Construction of additional cold room not yet done but included in the cMYP and GAVI HSS proposal - Six forty –foot containers for dry stores were installed with KfW funding - National dry store warehouse is under construction with funding from UNICEF - Construction of 3 Regional vaccine/dry store facilities included in cMYP and GAVI HSS proposal

The next EVSM/VMA* will be conducted in: last quarter of 2007

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## Injection Safety

#### Receipt of injection safety support

When did injection safety support start: 2006

When did injection safety support end:  2008

Received in cash/ kind√

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Number | Date |
| --- | --- | --- |
| AD syringe BCG | 417,000 | 11/03/2006 |
| AD syringe BCG | 417,000 | August 2006 |
| AD syringe 0.5ml | 1,205,400 | 9/05/2006 |
| AD syringe 0.5ml | 1,206,100 | August 2006 |
| Reconstitution syringe 2ml | 89,600 | 11/03/2006 |
| Reconstitution syringe 2ml | 89,600 | August 2006 |
| Reconstitution syringe 5ml | 61,200 | 11/03/2006 |
| Reconstitution syringe 5ml | 61,200 | August 2006 |
| Safety boxes | 20,025 | 11/03/2006 |
| Safety boxes | 20,025 | August 2006 |

Please report on any problems encountered

All shipment of injection materials were received in good condition.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded

GAVI support for injection materials is up to 2008

#### Please report how sharp waste is being disposed of

Sharps are disposed off by use of incinerators and where there are no incinerators they are burnt and ashes thrown in a pit or buried

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Limited storage capacity for AD syringes in some health facilities

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

Not Applicable

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience. The purpose of Table 3 is to understand trends in overall immunization expenditure and financing context. Table 4 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed. The purpose of the questions related to Table 5 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting. Much of the information can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. Please report for the years till the end of your cMYP. Co-financing levels can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 3: Total Immunization Expenditures and Financing Trends |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | $10,239,118 | $10,408,641 | $10,704,030 | $11,155,405 | $11,661,365 |
| Injection supplies | $492,076 | $527,936 | $565,969 | $597,634 | $626,170 |
| Personnel | $398,369 | $406,337 | $414,463 | $422,753 | $431,208 |
| Other operational expenditures | $6,756,434 | $6,891,563 | $7,029,394 | $7,169,982 | $7,313,381 |
| Cold Chain equipment | $2,000,000 | $2,093,572 | $517,504 | $820,193 | $335,272 |
| Vehicles | $ | $ 31,212 | $ | $ | $ |
| Total Immunization Expenditures | $19,885,997 | $20,328,049 | $19,231,360 | $20,165,967 | $20,367,396 |
| Total Government Health Expenditures (GHE%THE) | 40.0% | 40.0% | 40.0% | 40.0% | 40.0% |
| Immunization Financing |  |  |  |  |  |
| Government (SWAP) | $1,929,698 | $1,992,817 | $ | $ | $ |
| GAVI | $8,555,458 | $9,245,661 | $9,485,810 | $9,875,035 | $10,307,010 |
| UNICEF | $275,550 | $ | $ | $ | $ |
| WHO | $58,160 | $40,000 | $ | $ | $ |
| World Bank | $ | $ | $ | $ | $ |
| Other (please specify) | $ | $ | $ | $ | $ |
| Total Financing (secured) | $10,818,866 | $11,278,478 | $9,485,810 | $9,875,035 | $10,307,010 |

| Table 4a: Country Vaccine Co-Financing |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine Please specify which vaccine ( DPT-HepB+Hib) |  |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total number of country co-financed doses | 298,994 | 129,803 | 133,174 | 138,639 |  | 144,704 |
| Total amount of country level co-financing | $ 9,555,458 | $ 9,679,792 | $9,931,217 | $ 10,338,718 |  | $ 10,790,977 |
| Of which by |  |  |  |  |  |  |
| Government | $ | $ | $ | $ |  | $ |
| Basket/Pooled Funding/SWAp | $ 1,000,000 | $ 434,131 | $ 445,407 | $ 463,683 |  | $ 483,967 |
| Other (GAVI) | $8,555,458 | $9,245,661 | $9,485,810 | $9,875,035 |  | $10,307,010 |
| Other (please specify) | $ | $ | $ | $ |  | $ |
| Total Co-Financing | $ 9,555,458 | $ 9,679,792 | $9,931,217 | $ 10,338,718 |  | $ 10,790,977 |

| Table 4b: Country Vaccine Co-Financing Not Applicable |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total number of country co-financed doses |  |  |  |  |  |  |
| Total amount of country level co-financing | $ | $ | $ | $ |  | $ |
| Of which by | $ | $ | $ | $ |  | $ |
| Government | $ | $ | $ | $ |  | $ |
| Basket/Pooled Funding/SWAp | $ | $ | $ | $ |  | $ |
| Other (please specify) | $ | $ | $ | $ |  | $ |
| Other (please specify) | $ | $ | $ | $ |  | $ |
| Other (please specify) | $ | $ | $ | $ |  | $ |
| Total Co-Financing | $ | $ | $ | $ |  | $ |

| Table 4c: Country Vaccine Co-Financing Not Applicable |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 |  | 2010 |
| Total number of country co-financed doses |  |  |  |  |  |  |
| Total amount of country level co-financing | $ | $ | $ | $ |  | $ |
| Of which by | $ | $ | $ | $ |  | $ |
| Government | $ | $ | $ | $ |  | $ |
| Basket/Pooled Funding/SWAp | $ | $ | $ | $ |  | $ |
| Other (please specify) | $ | $ | $ | $ |  | $ |
| Total Co-Financing | $ | $ | $ | $ |  | $ |

| Tables 5: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) |  | October 2005 |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 2: What mechanisms are currently used in your country for procuring vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- ICB |  |  |  |
| Government Procurement- Other | √ | All traditional vaccines and DPT-HepB+Hib | SWAp, GAVI |
| UNICEF | √ | All traditional vaccines and DPT-HepB+Hib | SWAp, GAVI |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | √ | DPT-HepB+Hib |  |
| National health sector plan | √ | DPT-HepB+Hib |  |
| National health budget | √ | DPT-HepB+Hib |  |
| Medium-term expenditure framework |  |  |  |
| SWAp | √ | DPT-HepB+Hib |  |
| cMYP Cost & Financing Analysis | √ | DPT-HepB+Hib |  |
| Annual immunization plan | √ | DPT-HepB+Hib |  |
| Other |  |  |  |
| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |  |  |
| 1. None |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |  |  |
| 1. No, the co-financing policy has placed Malawi in the poorest category and our co-financing amount will be reduced significantly from the initial projection of $1 million |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |

In table 6 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 6: Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Advocating for the maintenance of the share of funding for EPI to the Ministry of Health | Timely production of annual budget requirements for EPI to Planning Department. | Requirements for new and traditional vaccines are being processed. | MoH requires MOU for easy transactions of funds with World Bank. | 0 | 1st request to MoH successful. 2nd request to MoH in progress | Nil |
| 2.Capacity building in vaccine management especially on stock levels, storage space and MDVP | Training of health workers on vaccine management | Capacity building done | None | 0 | 100% | Nil |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (3.2.). Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Not Applicable

| Table 7 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 621,445 | 633,252 | 686,374 | 709,495 | 727,923 | 757,792 | 782,952 | 797,828 | 812,987 |
| Infants’ deaths | 64,630 | 59,654 | 48,480 | 50,113 | 51,415 | 53,524 | 55,301 | 56,352 | 57,423 |
| Surviving infants | 562,903 | 573,598 | 637,894 | 659,382 | 681,508 | 704,267 | 727,651 | 741,476 | 755,564 |
| Infants vaccinated in 2006 (JRF) / to be vaccinated 2007 and beyond with 1st dose of DTP (DTP1)* |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2006 (JRF) / to be vaccinated 2007 and beyond with 3rd dose of DTP (DTP3)* |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2006 (JRF) / to be vaccinated 2007 and beyond with 1st dose of DTP (DTP1)* DPT-HepB+Hib (new vaccine) | 595,995 | 616,943 | 602,685 | 695,305 | 713,365 | 742,636 | 775,122 | 789,850 | 804,857 |
| Infants vaccinated 2006 (JRF) / to be vaccinated 2007 and beyond with 3rd dose of DPT-HepB+Hib ( new vaccine) | 499,463 | 533,707 | 537,162 | 633,006 | 649,448 | 683,139 | 713,098 | 726,646 | 740,453 |
| Wastage rate in 2006 and plan for 2007 beyond*** DPT-HepB+Hib ( new vaccine) | 4 | 4 | 4 | 9 | 8 | 8 | 7 | 7 | 7 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 380,427 | 400,673 | 404,491 | 510,836 | 545,942 | 583,500 | 626,362 | 638,262 | 658,519 |
| Infants vaccinated / to be vaccinated with BCG | 605,848 | 616,943 | 625,225 | 709,495 | 727,923 | 757,792 | 782,952 | 797,828 | 812,987 |
| Infants vaccinated / to be vaccinated with Measles | 451,146 | 471,989 | 501,915 | 573,662 | 602,092 | 640,883 | 669,439 | 696,987 | 725,341 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

We would like to change to pre-mixed presentation of the pentavalent vaccine but not yet discussed with UNICEF Country Office

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 8 below. For calculations, please use same targets as in table 7.

Table 8.  Estimated number of doses of DPT-HepB+Hib vaccine.  (Please provide additional tables for additional vaccines and number them 8a, 8b, 8c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 2,969,382 | 3,091,222 | 3,226,454 |
| Doses to be supplied by GAVI | 2,836,207 | 2,952,583 | 3,081,742 |
| Doses to be procured by country | 133,174 | 138,639 | 144,704 |
| Co-pay in US$/dose | $0.20 | $0.20 | $0.20 |
| Total co-pay | $445,407 | $463,683 | $483,967 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 9a : Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 9a, 9b, 9c, etc. Please use same targets as in Table 7)

Table 9b : Estimated supplies for safety of vaccination for the next two years with Measles

#### Table 9c : Estimated supplies for safety of vaccination for the next two years with DPT-HepB+Hib

Table 9d: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

There is an increase in injection safety supplies because of the current population projections from National Statistical Office (NSO)

# 4. Health Systems Strengthening     Not Applicable

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

In case any change in disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 10.

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ?

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. Possible changes in the implementation plan and a request for changes in the disbursement schedule can be explained as well. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 11.

Please attach minutes of the HSCC meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

Are any Civil Society Organizations involved in the implementation of the HSS proposal and describe their participation?

| Table 10. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 11. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 12. Please update baseline indicators |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 14/05/2007 |  |
| Reporting Period (consistent with previous calendar year) | 22/04/2006 – 14/05-2007 |  |
| Government signatures | X |  |
| ICC endorsed | X |  |
| Table 1 filled-in | NA |  |
| DQA reported on | NA | Planned for 2009 |
| Reported on use of 100,000 US$ | √ |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) | √ |  |
| Table 2 filled-in | NA |  |
| New Vaccine Request completed | √ |  |
| Revised request for injection safety completed (where applicable) | √ |  |
| HSS reported on | NA |  |
| ICC minutes attached to the report | √ |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report | NA |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing