Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Nepal

Date of submission…5 July 2006 Reporting period: 2005 (15 July 2004- 14 July 2005). Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

ISS fund are channelled through government and expenditure are done as per government financial rules and regulation. Chid Health Division is responsible for all immunization activities in the country. Every year Child Health Division proposes the activities and required funds for coming year. It is then discussed in ICC meeting. The MoH & P and MoF after the consultation with Planning Commission give the final approval. The MoF releases funds as per rules and regulation. The office of the Auditor General carries out the audit of the expenditure. There are no major problems encountered in use of ISS fund.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 	1. First tranche of Reward Money of US$ 574,550

Remaining funds (carry over) from 2004 (before 14 July 2004) USD 1, 023,726

Table 1: Use of funds during 15 July 2004 – 14 July 2005:  Although we had balance of total USD 1,598,276, only 452,300 was allocated in given time period, because immunization activities were funded from other sources.  A total amount of USD 425,300 was allocated for the activities, out of which USD 323,798 (72%) was spent during given time period. This was mainly due to hiring of less number of immunization officers and fewer amounts were spent on social mobilization.

| Area of Immunization Services Support | Total amount in US $ | Amount of funds |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central USD | Region/State/Province | District USD |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 26,232.95 | 26,232.95 |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads | 13,116.49 | 13,116.49 |  |  |  |
| Training | 79,012.33 |  |  | 79,012.33 |  |
| IEC / social mobilization | 71,214.06 |  |  | 71,214.06 |  |
| Outreach |  |  |  |  |  |
| Supervision | 53,777.56 | 13,116.49 |  | 40,661.07 |  |
| Monitoring and evaluation | 104,218.26 |  |  | 104,218.26 |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles fuel & maintenance | 5,246.59 | 5,246.59 |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other 1) Computers and Printers 2) Printing Guidelines and Training manuals 3) Furniture 4) TA/DA for Vaccine movement (specify) | 39,349.43 32,791.18 1,311.64 26,029.51 | 39,349.43 32,791.18 1,311.64 |  | 26,029.51 |  |
| Total: | 452,300 | 131,164.77 |  | 321,135.23 |  |
| Remaining funds for next year: a) Remaining fund from previous years | USD 1023,726 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Major Activities: - Strengthening NIP and introducing new vaccine: - Orientation to District Health Officers, Public Health Officers and EPI supervisors of 24 district's of Mid Western and Far Western Development Region on introduction of tetravalent DPT-HepB - Revision, Printing and Distribution of immunization monitoring charts - Distribution of cold chain equipments (refrigerators, freezers and other equipments) to regional, district and peripheral health facilities. “Walk-in-cooler” and walk-in-freezers were installed at central and regional cold centres. These equipments were supported by JICA - Various trainings (MLM, repair and maintenance of cold chain equipments) were organized for health staff at different level - Districts micro-planning was completed in 35 districts - Review of immunization program was conducted in all 75 Districts. - Polio Eradication Initiatives - Conducted Responsive Mopping-up Activities (4 districts) and SNID (17) high-risk districts in response to the detection of wild poliovirus case in Siraha district. The coverage was >95%. - Data Quality Self Assessment (DQSA): - Guideline on DQSA in local language was developed, printed and distributed for use by district health offices - Financial Sustainability Plan (FSP): - FSP was developed, endorsed (by MoF, & ICC) and submitted to GAVI Board - Multi-year plan of action (2007-2011): - Initiated developing Multi-year plan of action based on the FSP. - National Measles Campaign - Conducted National Measles Campaign throughout the kingdom targeting all children between 9 months to under 15 years of age (9,423,866). The coverage was more than 95%. A single dose of OPV was integrated with measles campaign - School Immunization Program: - School immunization program with TT vaccine was piloted in 8 districts (coverage was > 92%) - JE vaccination program: - National policy and guideline was developed for JE immunization. - Problems encountered: - Vaccine stock out: - BCG Vaccine was stock out for 1 month in 16 districts - DPT Vaccine was stock out for 3 month in 35 districts.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

√

## If yes, please report on the degree of its implementation.

The recommendations made by DQA were implemented. No plan of action as such was developed. These recommendations were discussed in ICC meeting. and were were included in annual plan of immunization. - Supervision and Monitoring: Supervision and monitoring from centre to periphery was strengthened. Checklist were developed and used by the monitors. Frequency of supervision was increased and was integrated with other activities. The government and partners carried out the supervision and monitoring. - Data Quality: HMIS carried out data verification twice a year in all districts. DQAS has been adapted to local situation and implemented in 10 districts. - Data analysis: All districts were provided computers and training on data analysis

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

None

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:  November 11, 2002

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Hepatitis B and DPT-HepB vaccine received in 2005/2006 FY Vaccine/Devices; Delivery Date; Quantity in doses.. DTP-Hep B (10 dose vial); May-05; 870,000. DTP-Hep B (10 dose vial); Feb 2006; 70,0000.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Orientation of health workers on introduction of DPT-HepB vaccine. - FSP developed, endorsed by government - First draft of cMYP 2007- 2011 developed - Revision, printing and distribution of immunization monitoring tools (chart) and vaccine management reporting tools. - Micro planning in 35 districts. - After 4 years of no wild poliovirus, a case of wild poliovirus was detected. Because of this a number of responsive activities were carried out. This resulted in diversion from other routine activities.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

| NA |  |
| --- | --- |

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Nepal received the following lots of AD syringes, reconstitution syringes and safety boxes in 2005: Vaccine/Devices; Delivery Date; Quantity in pieces.. BCG Syringes (AD); 05-Apr-05; 258,900. AD Syringes; 16-Apr-05; 751,200. Reconstitution Syringes 2.0 ml (BCG); 05-Apr-05; 25,900. Reconstitution Syringes 5.0 ml (Measles); 05-Apr-05; 38,800. Safety Boxes; 14-Apr-05; 11,950.

#### Progress of transition plan for safe injections and safe management of sharps waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

There was no major problem encountered during introduction of AD syringes. Now ADS are used for all injectable antigens throughout the country. Mostly sharp waste management is done by collection in safety box, burn and bury method. Some hospitals have constructed incinerators for waste management. There is a problem of waste disposal in majority of the municipalities.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Numbers of districts with DPT-HepB introduction in routine immunization Number of districts using ADS for all injectiable antigens in routine immunization Number of trained Health Workers on use of safe injection practice & wastage disposable (use of Safety Boxes) | 24 districts Through out the country (75 districts) All Health Workers (Vaccinators) | 100% 100% 100% | None None Most of the health facilities are not routinely reporting AEFI cases. AEFI are reported regularly from 31 sentinel sites |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/the Vaccine Fund injection safety support in the past year:

Not applicable

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

FSP was developed by MoH&P, endorsed by MoF and ICC members, and submitted to GAVI board on Feb 25, 2005

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine DPT-HepB (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2002..** | 2003.. | 2004. | 2005.. | 2006.. | 2007.. | 2008. | 2089 | 2010. | 2011. |
| A: Proportion funded by GAVI/VF (%)*** | 0 | 0 | 0 | 20% | 100% | 100% | 99% | 98% | 95% | 95% |
| 0 B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 0 | 1% | 2% | 5% | 5% |
| C: Total funding for …………. (new vaccine) |  |  |  | 315802 | 3,515,210 | 3,594,299 | 3,757,862 | 3,842,496 | 3,928,881 | 4,017,271 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

NB: Country will apply for GAVI II on 2006

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| Domestic resourcing for immunization services 7% of total National budget to be allocated for Health by year 2008/09 | . Advocacy to increase government commitment ongoing | Government has allocated USD 1,219,403 (FY 2004/05) (of which 20% is funded by pool funding assistance of DFID and the World Bank via Nepal Health Sector Program) |  | Total EPI budget USD 1,232,819 ( 2003/04) Total MoH Patners GAVI |  |  |
| 2) External resourcing for immunization Additional resourcing from GAVI/ Vaccine Fund explored Support from SWAP pool fund Project grants from bilateral agencies like, JICA, and USAID, Ongoing support from multilateral agencies like WHO, UNICEF, World Bank, etc. | MOH&P plans to submit request for GAVI II support Ministry of Health plans to use SWAP money for vaccine procurement, operation as well as logistic management. WHO/UNICEF continues to support immunization. | 8,000 US$ 2.8 million USD |  |  | 0 350,000 USD |  |
| 3) Improved Program Management Effective Cold Chain Management | Cold chain equipment was supplied to all districts, which was supported by JICA. | 326 new health facilities received cold chain equipment and 212 old cold chains equipment were replaced with new equipments. | Distribution and transportation of cold chain equipment has been slow and difficult, especially in mountain districts. Significant problem encountered in Zero Appliances equipments | 1 Central and 6 regional cold rooms with total of 8 walk in cold rooms and 75 district cold rooms with at least 3 freezers, ice liner and freezes. |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2003/04 | 2004/05 | 2005/06 | 2006/07 | 2007/08 |  | 2008/09 |  | 2009/010 | 2010/011 |  | 2011/012 |  |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Births | 831,864 | 850,747 | 870,057 | 889,810 | 910,008 |  | 930,666 |  | 951,792 | 973,398 |  | 995,494 |  |
| Infants’ deaths | 53,406 | 54,618 | 55,858 | 57,126 | 58,423 |  | 59,749 |  | 61,105 | 62,492 |  | 63,911 |  |
| Surviving infants | 778,458 | 796,129 | 814,199 | 832,684 | 851,586 |  | 870,917 |  | 890,687 | 910,906 |  | 931,583 |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 688,763 | 688,781 | 635,056 |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 652,640 | 657,811 | 588,583 |  |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of -HepB* …......... (new vaccine) | 174,872 | 215,505 | 460,758 |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of HepB ( new vaccine) | 125,275 | 196,596 ** | 398,751 |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP-HepB* …......... (new vaccine) |  |  |  | 724,671 | 740,839 |  | 755,954 |  | 771,028 | 786,150 |  | 801,323 |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DPT-HepB ( new vaccine) |  |  |  | 675,369 | 687,377 |  | 701,401 |  | 715,387 | 729,418 |  | 743,495 |  |
| Wastage rate in 2005 and plan for 2005 beyond*** ………….. ( new vaccine) | *** | 25% | 21% | 15% | 15% |  | 15% |  | 15% | 15% |  | 15% |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2006 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 685,924 | 756,832 | 413,029 | 409,625 | 501,578 | 596,843 |  | 695,485 |  |  | 753,214 |  | 797,521 |
| Infants vaccinated in 2006 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 734,365 | 701,853 | 679,584 | 712,477 | 740,839 | 755,954 |  | 771,028 |  |  | 786,150 |  | 801,323 |
| Infants vaccinated in 2006 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 606,834 | 622,613 | 582,818 | 638,261 | 641,552 | 670,227 |  | 715,387 |  |  | 745,627 |  | 784,801 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Fiscal Year in Nepal is July 15 to July 14 (Example FY 2005 is from July 15 2005 to July 14 2006)

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

| Number of |  | Targets |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2003/04 | 2004/05 | 2005/06 |  | 2006/07 | 2007/08 | 2008/09 |  | 2009/010 | 2010/011 | 2011/012 |  |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Births |  |  |  |  | *793,249 |  | **812,632 |  | 829,212 | 845,746 | 862,334 | 878,977 |  |
| Infants’ deaths |  |  |  |  | 51,085 |  | 48,880 |  | 49,877 | 50,872 | 51,870 | 52,871 |  |
| Surviving infants |  |  |  |  | 742,164 |  | 763,752 |  | 779,334 | 794,874 | 810,464 | 826,106 |  |
| Pregnant Women |  |  |  |  | 819,249 |  | 835,964 |  | 852,633 | 869,356 | 886,134 | 886,134 |  |
|  | Fiscal Year in Nepal is July 15 to July 14 (Example FY 2005 is from July 15 2004 to July 14 2005) * Management Division officially provides target Population. **Target Population from 2007/08 on ward is projected by EPI program therefore subject to change upon official projection by Management division. |  |  |  |  |  |  |  |  |  |  |  |  |

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of DPT-HepB  vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6: Estimated supplies for safety of vaccination for the next two years with TT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Note: Target population is based on Table 3, for TT BCG and Measles

|  |  | Formula | For year 2007 (2007/08) | For year 2008 (2008/09) |
| --- | --- | --- | --- | --- |
| A | Target for TT pregnant women | # | 501,578 | 596,843 |
| B | Number of doses per Pregnant woman | # | 2 | 2 |
| C | Number of TT doses | A x B | 1003156 | 1193686 |
| D | AD syringes (+10% wastage) | C x 1.11 | 1113503 | 1324991 |
| E | AD syringes buffer stock 2 | D x 0.25 | 278376 | 331248 |
| F | Total AD syringes | D + E | 1391879 | 1656239 |
| G | Number of doses per vial | # | 10 | 10 |
| H | Vaccine wastage factor 4 | Either 2 or 1.6 | 1.6 | 2 |
| I | Number of reconstitution syringes (+10% wastage) 3 | C x H X 1.11/G | 178161 | 211999 |
| J | Number of safety boxes (+10% of extra need) | (F + I) x 1.11/100 | 17427.44 | 20737 |

Table 6.1 : Estimated supplies for safety of vaccination for the next two years with BCG

Table 6.2: Estimated supplies for safety of vaccination for the next two years with Measles

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

According to Multi Year Plan of Action Nepal had set the following indicators and targets

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 1. Number of districts with coverage more than 80% or above for all antigen 2. Number of wild poliovirus cases 3. Number of districts with NT cases <1/1000 LB. 4. Number of districts with routine measles coverage more than 90% 5. Number of districts with HepB introduced into routine immunization | 1. All 75 districts will have coverage of at least 80% for all routine antigens 2. zero cases of wild poliovirus 3. All 75 districts with NT cases <1/1000 LB. 4. 75 districts 5.75 districts | 1. 31 districts have coverage 80% for all routine antigens 2. zero cases 3. 100% 4. 9 districts 5. 100% | 1. All planed EPI sessions were not conducted due to Nation measles campaign. 2. Vaccine stock out 3. conflict situation 4. Due to conflict situation and campaign 5. None | 1. Achieve and sustain routine coverage of 90% in all 75 districts for all antigens by FY 2010/11. |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 5, July 2006 |  |
| Reporting Period (consistent with previous calendar year) | Completed |  |
| Table 1 filled-in | Completed |  |
| DQA reported on | Completed |  |
| Reported on use of 100,000 US$ | Completed |  |
| Injection Safety Reported on | Completed |  |
| FSP Reported on (progress against country FSP indicators) | Completed |  |
| Table 2 filled-in | Completed |  |
| New Vaccine Request completed | Completed |  |
| Revised request for injection safety completed (where applicable) | Completed |  |
| ICC minutes attached to the report | Completed |  |
| Government signatures | Completed |  |
| ICC endorsed | Completed |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of Government of Nepal,

Signature:	……………………………………………...……………...

Dr. M.B.Bista

Title:	Director General, Dept. of Health Services, Ministry of Health ………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~