Annual Progress Report 2006

Submitted by

The Government of

NICARAGUA

to the

# Date of submission: May 2006

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of …NICARAGUA……………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Minister | Title: …………………………………… |
| Signature: … Minister Maritza Cuan Machado … | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organization | Signature | Date |
| --- | --- | --- | --- |
| Dr. Alejandro Solís Director, Planning and Development | Ministry of Health |  |  |
| Dr. Omar Malespín Director, Immunization Program | Ministry of Health |  |  |
| Dr. Debora Comino Representative | UNICEF |  |  |
| Dr. Ivette Sandino Health Officer | UNICEF |  |  |
| Dr. Socorro Gross Representative | PAHO / WHO |  |  |
| Dr. Cristina Pedreira Consultant, EPI | PAHO / WHO |  |  |
| Dr. Enrique Solís President | Nicaraguan Pediatric Society |  |  |
| Dr. Alfonso Matus President | National Committee on Immunization Practices |  |  |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date Received |
| --- | --- | --- |
| AD Syringes 0.1CC 27G x 3/8 | 221,600 | 13/11/2006 |
| AD Syringes 1/2CC 25G x 5/8 | 232,800 | 07/09/2006 |
| Reconstitution Syringes 5CC 22G x 1 1/4 | 682,300 | 11/10/2006 |
| Safety Boxes E12/08 | 24,725 | 20/10/2006 |

Please report on any problems encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

Although the EPI personnel has prior experience in the use of AD syringes, the EPI has programmed training of vaccinators for the use of these syringes for the beginning of the year 2007, and then introduction into its routine program. During 2006, injection safety was part of training that took place at all levels of care prior to the National Health Days and the introduction of the rotavirus vaccine.

#### Please report how sharps waste is being disposed of.

For waste disposal, the Ministry of Health, through the National Immunization Program, recommends the utilization of safety boxes. Currently, all the vaccination posts have this resource. For the final disposal of sharps, the Ministry of Health recommends incineration, wherever available. During the past year, 5 incinerators were installed in different points of the country - Matagalpa, Managua, Chinandega, *Grenada, *León - with the support of the Government of Japan. Furthermore, the country has incinerators in some of the principal hospitals of Managua that are also used to this end. Where no resources are available for incineration, the program recommends burning, however, some health services mix vaccination program wastes with the common refuse and others bury them. Currently, a project is being developed with the support of GAVI, with the objective of guaranteeing an adequate destination to the hospital solid wastes, which represent 0.14% of the total daily waste production at national level. This percentage is consistent in Managua, which was chosen as pilot site for the initial development of the project, as location of the main referral hospitals of the country. The immunization program’s wastes, which will be included in this project, correspond to approximately 1-2% of the total hospital solid wastes.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

#### See above.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

To date, $432,000 have been received. The expenditures total $269,815.06. The current balance is of $162,184.94. This balance includes the recent deposit of $131mil for the last year of INS support..

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Based on the population census conducted in 2005, the birth projections from 2007 on were reduced.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 148,652 | 149,709 | 136,159 | 138,473 | 140827 | 143,221 | 145,656 | 148,132 | 150,650 |
| Infants’ deaths | 2046 | 2085 | 1,136 | 1155 | 1,174 | 1,194 | 1,215 | 1,235 | 1,256 |
| Surviving infants | 146,606 | 147,624 | 135,023 | 137,318 | 139,653 | 142,027 | 144.441 | 146,897 | 149,394 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 136,581 | 139,905 | 132,074 | 134,319 | 136,602 | 138,924 | 141,286 | 143,688 | 146,131 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 128,151 | 130,550 | 129,351. | 131,550 | 133,789 | 136,060 | 138,373 | 140,425 | 143,117 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of…….… ( new vaccine) |  |  |  |  |  |  |  |  |  |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 127,736 | 132,973 | ND |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with BCG | 152,278 | 150,443 | 136,159 | 138,473 | 140827 | 143,221 | 145,656 | 148,132 | 150,650 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 140,997 | 144,610 | 133,435 | 135,704 | 138,010 | 140,357 | 142,743 | 145,169 | 147,637 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with PAHO Revolving Fund)      for 2008

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

#### Table 8a: Estimated supplies for safety of vaccination for the next two years with BCG

Table 8b: Estimated supplies for safety of vaccination for the next two years with Pentavalent (DTP-HepB-Hib)

Table 8c: Estimated supplies for safety of vaccination for the next two years with MMR

Table 8: Estimated supplies for safety of vaccination for the next two years with dT

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 25May07 |  |
| Reporting Period (consistent with previous calendar year) | 2006 |  |
| Government signatures | x |  |
| ICC endorsed | x |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on | x |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) | x |  |
| HSS reported on |  |  |
| ICC minutes attached to the report |  |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~