Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: NIGERIA

Date of submission: 15TH MAY 2006 Reporting period: January 1st to December 31st 2005 ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report   Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Nigeria’s ISS fund received for 2005 was credited into the NPI/GAVI domiciliary account at the Union Bank of Nigeria, as was applicable in previous years. Conversion into Naira was carried out using the prevailing Central Bank of Nigeria exchange rate when required. The GAVI Award Review Committee at its meeting of Feb 2005 reviewed State proposals from the 36 States and the Federal Capital Territory and forwarded its recommendations and approvals to the ICC for ratification. The GARC recommendations and the ICC approval were thereafter forwarded to the GAVI Secretariat for necessary funding. Following the receipt of the GAVI funds on the 26th of June 2005, approved amounts were disbursed through States and LGAs GAVI accounts accordingly. The existing mechanism for the management of the ISS fund has worked effectively in a transparent manner. Delays in assessment of the fund was experienced in some States due to inability of the States and Local Government Areas (LGAs) to open State and LGAs GAVI account with the required signatories, payment of the pre-requisite 10% counterpart fund and submission of State work plan prior to release of funds.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities was  funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 			Year 2005 		$5,533,982.70

Remaining funds (carry over) from 	Year 2004		   $300,429.24

TOTAL FUNDS 							$5,834,411.94

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | -- |  |  |  |  |
| Injection supplies (Measles campaign in the North) | 2,513,316.53 |  | 2,513,316.53 |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | 402,971.28 | 126,896.55 | 17,254.67 | 258,820.06 |  |
| IEC / social mobilization | 140,778.5 |  | 117,324.8 | 23,453.7 |  |
| Outreach (LIDs) | 75,012.043 |  | 75,012.043 |  |  |
| Supervision | 147,566.6 |  | 147,566.6 |  |  |
| Monitoring and evaluation | 907,091.9 |  | 53,518.4 | 853,573.5 |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other Consultants | 109,139.96 | 109,139.96 |  |  |  |
| Total: | 4,295,876.813 | 236,036.51 | 2,923,993.043 | 1,135,847.26 |  |
| Remaining funds for next year: | 1,538,535.127 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed. Minutes of the ICC meeting of February 14th 2005 is attached

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Activities that strengthened routine immunization in year 2005: -Some of the components of Reaching Every Ward was adopted and implemented in Year 2005, these included ward microplanning, re-validation of microplans, as well as the establishment of State  LGA monitoring of all immunization activities. -The State monthly meetings of NPI Managers and DSN Officers was a strength in the Year 2005, which provided a forum for review of ward, LGA and state data on coverage, DSN reports, wastage rates, vaccine stock and drop out rates. Necessary feedback was provided to appropriate operational levels for actions. -Cascaded capacity building for health workers, particularly training of immunization service providers. -Revision of NPI Service Delivery Modules and Trainers guides for immunization service providers. - Harmonized training for PEI, Measles and RI in the last quarter of the year for the northern states -Continued implementation of the cold chain rehabilitation plan for cold chain systems at state, LGA and health facilities, which achieved a 70% level of implementation as at December 2005. - Some states conducted accelerated Multi-antigen campaigns (Local Immunization Days) to boost routine immunization coverages in targeted wards and LGAs identified to have less than 50% DPT3 coverage as indicated by DSN reports and administrative data. -Revised Immunization cards, Registers, data reporting and monitoring tools were printed and distributed within the year to all health facilities nationwide for improved data management systems. -Streamlining of intensified social mobilization efforts to increase community awareness on immunization Problems encountered: -Sustained and regular provision of immunization services at both public and private Health facilities and outreach services to hard to reach settlements due to lack of regular imprest funding for immunization services at LGA and State levels. -Inadequate utilization of public health facilities in some wards of the country due to the weak existing PHC systems. -Weak data management system at Health facility levels and in some LGAs and States, which affect completeness and timeliness of immunization data reporting and collation. -delayed access of GAVI funds due to payment of counterpart funds and submission of LGA work plans -Weak capacity of States especially at the Local Government level

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.



## YES                              NO

## If yes, please report on the degree of its implementation.

The following recommendations have been implemented to strengthening data management system in the country 1. Identification and listing of all Health facilities at the lowest health service delivery level i.e. the ward level. 2. NPI and partners in collaboration with the States and LGAs have revised the data recording tools namely Child Immunization cards, tally booklets and registers, Health facility, LGA and State summary forms. 3. Production and distribution of standard data reporting forms have been concluded to all Levels. 4. Ward /LGA microplan/demographic information is available for the country. 5. There is standard data management software for uniform data management in the country. 6. A simplified reporting format has been adopted at National, State, LGA and Health facility level in order to capture pertinent immunization data. 7. Refresher Trainings for health personnel on data management is an on going process, which is cascaded from National to Zones to States, LGAs and ward levels. 8. The country has a standard guideline for the preparation of monthly/quarterly reports, also utilization of monthly tally sheets and data from supportive supervision are in place to ensure data verification at all levels. 9.Monthly review meetings at State and Quarterly meetings at Zonal level Plans to strengthen Data Management systems -Continued collation and analysis of the monthly immunization returns at the state monthly review meetings. -Supportive supervision visits to States, LGAs and Health facility levels to assess performance..

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC. ICC minutes of April 26th 2005  is attached

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

The planned coverage survey for 2005 could not be carried out but it has been scheduled for 2006

## GAVI/Vaccine Fund New & Under-used Vaccines Support  NA (NOT APPLICABLE)

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

NA (GAVI support to Nigeria which was on Yellow Fever commenced in January 2004 but was discontinued in Jan 2005 because YF Vaccines are fully provided by the Federal Government) No funds was released

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

NA

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine NA

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

NA

## Injection Safety NA

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

NA( The ICC has approved that a fresh application for Injection Safety support be submitted for 2006)

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

NA

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution) NA

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

NA

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine …………………… (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

# 3.  	Request for new and under-used vaccines for year 2006 NA

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2004 | 2005 | 2006 | 2007 | 2008 |
| DENOMINATORS |  |  |  |  |  |
| Births | 5,806,814 | 5,978,411 | 6,155,077 |  |  |
| Infants’ deaths | 609,715 | 677,676 | 649,230 |  |  |
| Surviving infants | 5,197,099 | 5,300,735 | 5,505,847 |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 1,553,787 | 2,372,809 | 3,854,093 (70%) |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 1,179,389 | 1,988,452 (37.5%) | 3,578800 (65%) |  |  |
| NEW VACCINES ** |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…….… ( new vaccine) |  |  |  |  |  |
| Wastage rate in 2005 and plan for 2006 beyond*** ………….. ( new vaccine) |  |  |  |  |  |
| INJECTION SAFETY**** NA |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

NA

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007 NA (A fresh application for INS )

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Adherence to safe injection practises | 100% use of AD syringes by 2006 | Use of one disposable syringe per child. | Availability of funds No INS support | 100% supply of bundled vaccines |
| Increased Immunization coverage | DPT3 COVERAGE OF 65% | Achieved a DPT3 coverage of 37.5% | Weak PHC Systems | DPT3 coverage of 65% by Dec 2006 |
| Availability of vaccines at all Health facilities | 100% | Introduction of the Private Sector Vaccine distribution in some pilot states | Lack of ownership at the Local Government level. Delay in release of budgetary allocation for vaccine procurement | Introduction of the Push push push system of vaccine distribution Change in procurement timing to cover the 1st quarter that appropriation bill is delayed (Done in 4th quarter of preceeding year) |
| Measles campaign in the Northern States | At least 95% coverage | >95% coverage recorded |  | Second dose campaign in the Southern States in October 2006 |
| Improvement in DATA management | Timely and complete reporting at all level | About 72% of Health facilities reported completely and timely as against the 54% recorded in 2004 DATA reporting tools supplied to the Health facilities | Lack of mechanism for tracking non reporting Health facilities. Verification process of data | At least 90 % of Health facilities should report completely and timely by Dec 2006 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ | NA |  |
| Injection Safety Reported on | NA |  |
| FSP Reported on (progress against country FSP indicators) | NA |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed | NA |  |
| Revised request for injection safety completed (where applicable) | NA |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

Nigeria’s Inter-Agency Coordinating Committee (ICC) has received regular progress reports on the implementation of the GAVI supported activities in the country. The ICC notes that: 􀂾 Out of the current 30 approved state proposals, 17 states received their State and LGA level funding in Year 2005 􀂾 Taraba, Zamfara and Katsina States who met the funding requirement in December 2005 had their funds transferred early 2006 􀂾 To further strengthen RI services for 2006, 31 states proposals reviewed by the GARC at its meetings of 7th and 8th March 2006 were approved for funding by the ICC. The GARC and ICC approved budgets have been forwarded to GAVI Secretariat for further actions. 􀂾 The ICC has approved a waiver of the 10% counterpart funds by States for Year 2006 to ease accessibility of GAVI funds. 􀂾 The ICC also approved that Nigeria should re-apply for the GAVI Injection Safety support (INS) 􀂾 The ICC further approved the funding of the procurement of Injection materials and safety boxes for the May/June IPDs, as well as the Southern states measles campaign from Nigeria’s ISS fund 􀂾 GAVI DQA which was scheduled for the last quarter of 2005 was not conducted due the tight schedule of activities for that period. The DQA is now scheduled for June – September 2006 and the POA for improving DATA management based on recommendation from last GAVI DQA team has been approved by the ICC and circulated nationwide. Nigeria’s DPT3 data by LGAs has been submitted to the audit firm responsible for the conduct of the DQA in Nigeria.

7.	Signatures

For the Government of  NIGERIA

Signature:	………………………………………………….

Title: HONOURABLE MINISTER OF HEALTH

Date: …..MAY 2006.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| NATIONAL PROGRAMME ON IMMUNIZATION (NPI) | DR EDUGIE ABEBE mni Interim Coordinator/Chief Executive (ICCE) NPI |  |  |  |  |
| WHO | DR M BELHOCINE W.R NIGERIA |  |  |  |  |
| UNICEF | A ABAI UNICEF REP. NIGERIA |  |  |  |  |

~ End ~