January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Papua New Guinea

Date of submission: 23 May 2006 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report √ First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2006

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The ISS Fund was supposed to have been received in late March 2006, however nothing was received and some planned activities under GAVI support (ISS) are gradually implemented with current government funding for NIP. This funding support will be used in such areas as microplanning at district /facility level, technical supervision, IEC activities and materials. This will be reported in the Second Annual Activity Report 2006. A copy of the Implementation Plan is attached for your information. The National Department of Health (NDOH) holds all funds in a common basket call HSIP which is a SWAP approach mechanism, including funding from Vaccine Funds in a separate bank account with the (NIP) being responsible to request for funds based on its approved Annual Activity Plan including few components of the province and district plans. The NIP last year has developed its AAP based on the multi-year plan and with collaboration with the EPI Technical Committee (EPI/TC) and other stakeholders like the Child Health Advisory Committee (CHTAC) and the Paediatric Society. The NIP will provide accounting of funds to the EPITC and the ICC with support from HSIP secretariat.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2006 Nil (still coming) _______________

Remaining funds (carry over) from 2005 Nil ________________

Table 1: Use of funds during 2006

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision | 20,119 | 4,062 |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other /FHSCs & EPI Officers National Meeting for GAVI briefing 15-17 March 2006 | 54,857 | 23,130 |  |  |  |
| Total: | 74,976 | 27,192 |  |  |  |
| Remaining funds for this year: | 47,784 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

NIP held a national workshop for all Provincial Family Health Coordinators including Provincial EPI Officers on the 15TH to 17TH March 2006. The main purpose of this workshop was to brief them on the approval of ISS and the conditional approval for new vaccine. Secondly its was to prepare them to do district and facility microplans to implement ISS as of 2006. Provinces were asked to make budget estimates to access financial support from ISS and the current national budget. Supervisory visits were carried out by national staff with support from WHO consultant to assess cold chain and vaccine management, including monitoring of immunization coverage both at province and some district facilities. NIP is currently implementing Annual Activity Plan based on its multi-year plan. Though the ISS fund has not come through, NIP is using funds from its recurrent government fund to initiate some activities under GAVI which needed to be implemented. The government is fully committed towards immunization program in the country and has year-marked funds to implement the EPI multi-year plan. The NIP is only encountering manpower shortage to fully support the planning and implementing of GAVI in the provinces.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

√

## YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

NIP is currently preparation microplanning guidelines to be used in the districts and health facilities. Most provinces have submitted their planning budget estimates and are being analysed before funds are disburse to the provinces. Other stakeholders such as Health Promotion Branch and Inservice Training Unit of the Department of Health are being involved to developing appropriate IEC materials. It is anticipated that the process of conducting microplanning and the introduction of new vaccine will be done province by province because of the manpower capacity at the national level.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

| Financing of new vaccines and other incremental costs (extracted from response to GAVI document) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financing of new vaccine costs | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| New Vaccine costs | 0 | 1155000 | 2532916 | 2601252 | 2833630 | 2760545 | 2848883 | 2940047 | 3034129 | 3131221 |
|  |  |  |  |  |  |  |  |  | Bridge financing period |  |
| GAVI financing (%) | 0 | 100 | 80 | 80 | 75 | 75 | 75 | 70 | 65 | 60 |
| Govt and other donors financing (%) | 0 | 0 | 20 | 20 | 25 | 25 | 25 | 30 | 35 | 40 |
| Govt financing (US$) | 0 | 0 | 506583 | 520250 | 708408 | 690136 | 712221 | 882014 | 1061945 | 1252488 |
| One time training program costs | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| GAVI ISS or new vaccine support (%) | 80 | 80 |  |  |  |  |  |  |  |  |
| Govt and other donors (%) | 20 | 20 |  |  |  |  |  |  |  |  |
| One time IEC program |  |  |  |  |  |  |  |  |  |  |
| Govt financing (US$) | 20000 | 20000 |  |  |  |  |  |  |  |  |
| One time IEC program | 100000 | 100000 |  |  |  |  |  |  |  |  |
| GAVI ISS or new vaccine support (%) | 80 | 80 |  |  |  |  |  |  |  |  |
| Govt and other donors (%) | 20 | 20 |  |  |  |  |  |  |  |  |
| One time IEC program |  |  |  |  |  |  |  |  |  |  |
| Govt financing (US$) | 20000 | 20000 |  |  |  |  |  |  |  |  |

Under the previous response for GAVI condition, a situational analysis was done and mentioned inline with the above table that the government is able to

co-finance the introduction  of new vaccine from 2007.  This is because it is currently paying 100% of its vaccine cost. And as indicated in the above table

the declining phase of GAVI support over the period.

After the introduction of DTP-Hib-HpB in 2007 there is a need to review the previous Financial Sustainability Plan (FSP) which was developed and

approved by  ICC and forwarded to GAVI Secretariat last year.  NIP did not receive adequate feedback regarding this FSP.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine DTP-Hib-HepB (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2006** | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| A: Proportion funded by GAVI/VF (%)*** | 0 | 100 | 80 | 80 | 75 | 75 | 75 | 70 | 65 | 60 |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 20 | 20 | 25 | 25 | 25 | 30 | 35 | 40 |
| C: Total funding for …………. (new vaccine) | 0 | 1,155,000 | 2,532,916 | 2,601,252 | 2,833,630 | 2,760,545 | 2,848,883 | 2,940,047 | 3,034,129 | 3,131,221 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 184,633 | 190,541 | 196,639 | 202,931 | 209,425 | 216,126 | 223,042 | 230,180 | 237,546 |
| Infants’ deaths | 11,117 | 12,194 | 12,587 | 12,988 | 13,403 | 13,832 | 14,274 | 14,732 | 14,253 |
| Surviving infants | 172,816 | 178,347 | 184,052 | 189,943 | 196,022 | 202,294 | 208,768 | 215,448 | 223,293 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 139,981 | 151,595 | 156,4460 | 170,949 | 176,419 | 192,180 | 204,592 | 211,139 | 217,896 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 107,146 | 115,925 | 129,838 | 151,955 | 166,618 | 182,065 | 198,329 | 204,676 | 212,128 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 0 | 0 | 0 | 75,977 | 176,420 | 192,179 | 204,593 | 211,139 | 218,827 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | 0 | 0 | 0 | 75,977 | 166,619 | 182,065 | 198,330 | 204,676 | 212,128 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 0 | 0 | 30 | 25 | 25 | 20 | 20 | 15 | 15 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * |  |  |  |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There hasn’t been any changes to the data provided in approved plan.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of …… vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~