January 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: SIERRA LEONE

Date of submission: 5th May 2006 Reporting period: January - December 2005 (Information provided in this report must refer to 2005 activities). ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report √ Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

;[

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Upon receipt of funds from GAVI secretariat, the Hon. Minister of Health and Sanitation who is the chairperson of the ICC will mandate the Technical Committee (EPI Manager, UNICEF Focal person and WHO/ EPI Consultant) to allocate fund to EPI activities not funded .The draft allocation is presented at an ICC meeting for approval. Upon approval, funds are requested on quarterly basis using the revised form devised by the Ministry of Finance for the utilization and management of funds. Funds released are liquidated before the release of funds for other activities. There was no problem in the release of the funds.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 USD 268,750

Remaining funds (carry over) from 2004 ___USD 605.26

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel | 18,000 | 18,000 |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads | 27,305.55 | 7,387.20 |  | 19,918.35 |  |
| Training | 25,000 | 5,000 |  | 20,000 |  |
| IEC / social mobilization | - | - |  | - |  |
| Outreach | 51,785.72 | - |  | 51,785.72 |  |
| Supervision | 5,857.15 | 5,857.15 |  | - |  |
| Monitoring and evaluation | - | - |  | - |  |
| Vehicles | 56,071.43 | 56,071.43 |  | - |  |
| Cold chain equipment | 20,585.98 | - |  | 20,585.98 |  |
| Other …………. (Specify) |  |  |  |  |  |
| 1. Fuel for cold chain | 35,603 | 2,092.5 |  | 33,510.5 |  |
| 2. Servicing of Distr. Cold chain | 26,645.42 | - |  | 26,645.42 |  |
| Total: | 266,854.25 | 94,408.28 |  | 172,445.97 |  |
| Remaining funds for next year: | 2,501.01 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Major Activities - Supervision visits to all districts and selected PHUs -(GAVI/GOSL) - Training of Trainers on integrated child survival initiatives in all 13 districts- (UNICEF) - Training PHU staff on EPI in 4 districts – (GAVI) - Conduction of outreach activities in all 13 districts–(GOSL) - Support to outreach services in all 13 districts- (GAVI) - Advocacy meetings at national and district levels with District Chairmen, Chief Administrators and Paramount chiefs –(GOSL & WHO) - Planning and review meetings of District Healthy Management Teams (DHMTs) in all 13 districts -(UNICEF) - Expansion of health facilities on-going -(GOSL and NGOs & other partners) - District and national micro planning for National Immunization Days (NIDs)- (WHO) - Implementation of NIDs- (GOSL, WHO and UNICEF) - Distribution and installation of solar equipment (procured by ECHO) to districts -(GAVI) - Maintenance of cold chain equipment at all levels -(GAVI) - Procurement of fuel for running of cold chain at all levels (GAVI) - Procurement of generators for 2 districts in support of cold chain (GAVI) - Procurement of vehicle and motor bikes –(GAVI) - Revision of EPI Health workers manual- (UNICEF) - EPI programme review (Desk review) -(WHO and GAVI) - Development of draft multi year plan- (MOH&S & GAVI) - Submission of application for new vaccine introduction -(GOSL, WHO, UNICEF and GAVI) Problems related to multi year plan - Limited public-private partnership in EPI service delivery - Inadequate transport - Limited support to social mobilization - Inventory system for solar spare parts yet to be established

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

√

## If yes, please report on the degree of its implementation.

The recommendations were discussed and plan of action developed to address them. The plan identified three key responsible areas to implement the recommendations, vis-à-vis the district, central and partner agencies. District oriented recommendations were factored into district plans for implementation. Those for Central level were after deliberations with WHO and UNICEF technical staff also factored into central level plan. See document 6 of new vaccine application. The implementation of said plan has been on-going since January 2005. See attached plan.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

None

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH JANUARY YEAR 2002

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

- In addition, a total of 180,000 doses of Yellow Fever vaccine was received in 2005. No problem was encountered on receipt of vaccine.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Yellow Fever vaccine was introduced since 2002/2003 and major activities under taken have been reported on in the previous reports.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

- The proportion of USD 100,000 was received prior to the introduction of Yellow Fever vaccine in 2002, report regarding the utilization of this fund has also been provided in previous progress reports.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

- A total of 233,100 BCG syringes and needles were received in 2005

#### Progress of transition plan for safe injections and safe management of sharps waste

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- Materials for the construction of demorfort incinerators not available in country - Inadequate vehicles for distribution of injection materials from national to district, and district to health facilities - Unavailability of funds for the procurement of AD needles and syringes

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Number of functioning incinerators - No. of health workers trained - Number of meetings held at district level - Number of PHUs with injection equipment | 90 to be constructed in major health facilities by the end of 2005 846 health workers to be trained 156 meetings to be held in all 13 districts 846 PHUs to received injection safety equipment | 26 incinerators constructed with local materials. 280 health workers trained 130 meetings held in all 13 districts 846 PHUs receiving injection equipment on quarterly basis | -Resources (materials & funds) -Inadequate Funds -Transportation cost for PHU staff to venue -Vehicles from central to district and district to PHUs | 64 to be constructed by the end of 2006 566 health workers to be trained 156 meetings to be held 846 PHUs to be supplied with injection safety equipment |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

No cash contribution received for injection safety support.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

A revised final draft of the Financial Sustainability Plan was submitted in December 2004.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five-year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five-year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for yellow fever  (under used  vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Yellow Fever (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 100% | 100% | 100% | 100% | 100% |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| C: Total funding for yellow fever (under used vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. |  |  |  |  |  |  |
| 2. |  |  |  |  |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

Sierra Leone has submitted Financial Sustainability Plan in December 2004, approved in 2005 but yet to be implemented

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |
| Births | 229,088 | 207,117 | 211,259 | 215,484 | 219,794 | 224,190 | 228,674 | 233,248 |
| Infants’ deaths | 38,945 | 35,209 | 35,914 | 36,632 | 37,365 | 38,112 | 38,875 | 39,652 |
| Surviving infants | 190,143 | 171,908 | 175,345 | 178,852 | 182,429 | 186,078 | 189,799 | 139,596 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 176,750 | 113,459 | 124,495 | 143,082 | 145,943 | 148,863 | 151,839 | 154,877 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 145,878 | 113,459 | 124,495 | 143,082 | 145,943 | 148,863 | 151,839 | 154,877 |
| NEW VACCINES ** Yellow Fever |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Yellow Fever..... (new vaccine) | 145,784 | 125,493 | 133,262 | 141,293 | 147,768 | 154,445 | 161,329 | 168,429 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of…….… ( new vaccine) | NA | NA | NA | NA | NA | NA | NA | NA |
| Wastage rate in 2005 and plan for 2006 & beyond*** ……………… ( new vaccine) | 36% | 30% | 25% | 20% | 15% | 15% | 15% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 188,826 | 130,484 | 141,455 | 150,839 | 160,450 | 170,384 | 180,652 | 188,931 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 188,422 | 169,836 | 177,458 | 185,316 | 193,419 | 201,771 | 208,093 | 214588 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 153,184 | 125,493 | 133,262 | 141,293 | 147,767 | 154,445 | 161,329 | 168,429 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- There are changes in population for2006 and beyond because we are now using December 2004 census figures which was finalized in January, 2006.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for the year 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Approval for new /underused vaccines planned for 2007 has been granted by GAVI secretariat with estimated quantities required to be supplied. Preferred delivery plan has been shared with UNICEF supply division.

Table 4a: Estimated number of doses of Yellow Fever vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

| NO. |  | FORMULA | FOR 2007 |
| --- | --- | --- | --- |
| A | Infant vaccinated/to be vaccinated with 1st dose of Yellow fever (new vaccine)* |  | 133,262 |
| B | Percentage of vaccines requested from the vaccine fund taking into consideration the financial sustainability | % | 100 |
| C | Number of doses per child |  | 1 |
| D | Number of doses | A X B X C | 133,262 |
| E | Estimated wastage factor | (See list in table 3) | 1.33 |
| F | Number of doses (incl. Wastage) | A X C X E X B/100 | 177,238 |
| G | Vaccines buffer stock | F X 0.25 | 0 |
| H | Anticipated vaccines in stock at start of year 2007 |  | 44,309 |
| I | Total vaccine doses requested | F + G-H | 132,929 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | (D + G-H)X 1.11 | 98,738 |
| L | Reconstitution syringes (+10% wastage) | 1/J X 1.11 | 14,755 |
| M | Total safety boxes (+10% of extra need) | (K+L)/100 X 1.11 | 1,260 |

*Please report the same figure as in table 3.

Table 5a: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Table 4b: Estimated number of doses of Pentavalent vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

| NO. |  | FORMULA | FOR 2007 |
| --- | --- | --- | --- |
| A | Infant vaccinated/to be vaccinated with 1st dose of pentavalent (new vaccine)* |  | 133,262 |
| B | Percentage of vaccines requested from the vaccine fund taking into consideration the financial sustainability | % | % |
| C | Number of doses per child |  | 3 |
| D | Number of doses | A X B X C | 399,786 |
| E | Estimated wastage factor | (See list in table 3) | 1.11 |
| F | Number of doses (incl. Wastage) | A X C X E X B/100 | 443,763 |
| G | Vaccines buffer stock | F X 0.25 | 110,941 |
| H | Anticipated vaccines in stock at start of year 2007 |  | 0 |
| I | Total vaccine doses requested | F + G-H | 554,704 |
| J | Number of doses per vial |  | 2 |
| K | Number of AD syringes (+10% wastage) | (D + G-H)X 1.11 | 522,931 |
| L | Reconstitution syringes (+10% wastage) | 1/J X 1.11 | 0 |
| M | Total safety boxes (+10% of extra need) | (K+L)/100 X 1.11 | 522,931 |

Table 5b: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Number of health workers trained | 1,692 health workers to be trained | 280 health workers trained | - | 1,412 health workers to be trained in 2006 |
| - Number of PHUs with injection materials | 711 PHUs to received injection materials | 711 PHUs supported with injection materials | Vehicles for distribution of materials (Trucks) | 846 PHUs to be rehabilitated and supplied with injection materials |
| - Number of ICC meetings | 4 ICC meetings to be held | 4 ICC meetings held | None | 5 ICC meetings to be held |
| - Number of sensitisation meetings at district and community levels | 180 meetings to be conducted | 180 meetings conducted at district, chiefdom/zonal levels during NIDs | Inadequate support for social mobilization for Routine EPI services | 720 meetings to be conducted |
| - Number of supervision visits conducted | -Four supervision visits to be carried out to district and selected PHUs | -Four supervision visit conducted to district and PHUs | -Inadequate availability of transport | - Four supervision to be conducted |
| Number of PHUs supported for outreach services | 711 PHUs to be supported | 703 PHUs given performance incentives for outreach services | - | -846 and more PHUs to have performance incentives |
| - Number coordinating meetings at district level | 12 coordinating meetings to be held | 10 meetings held at district level | - | -12 coordinating meetings to be held |
| - Number of PHUs with solar equipment | 692 PHUs to have solar equipment | 486 PHUs with solar equipment | -Lack of spare part to carry out maintenance | -206 PHUs to have solar equipment |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  | 5th May 2006 |
| Reporting Period (consistent with previous calendar year) |  | January-December 2005 |
| Table 1 filled-in |  |  |
| DQA reported on |  | Work plan for implementation of recommendations attached |
| Reported on use of 100,000 US$ |  | Report previously submitted |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  | FSP approved awaiting implementation |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  | Request completed |
| Revised request for injection safety completed (where applicable) |  | Only for new vaccine |
| ICC minutes attached to the report |  | Minutes attached |
| Government signatures |  | Document signed by Government and ICC Members |
| ICC endorsed |  | ICC endorsed report on 3rd May 2006 |

6.  	Comments

ICC/RWG comments:

ICC has reviewed report and approved for submission to GAVI .

7.	Signatures

For the Government of Sierra Leone      Abator Thomas (Mrs)

Signature:	……………………………………………

Title: HON. MINISTER OF HEALTH AND SANITATION.

Date:	………………………………………….…

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| WHO | DR FELICITAS ZAWAIRA |  |  |  |  |
| UNICEF | MR. GEERT CAPPELAERE |  |  |  |  |
| ROTARY | MR. S.H.O.T MACAULEY |  |  |  |  |
| CHRISTIAN CHILDREN FUND | MR DANIEL KAINDANEH |  |  |  |  |
| SIERRA LEONE REDCROSS | DR. M.A.S. JALLOH |  |  |  |  |

~ End ~

THE FOLLOWING CLARIFICATIONS WERE RECEIVED FROM SIERRA LEONE REGARDING APR 2005

SIERRA LEONE GOVERNMENT

 240427						   	Office of the Minister of

Fax 235036                                                                               	Health and Sanitation

Email minhs@sierratel.sl                                              		Youyi Building

Abator_t@yahoo.com.uk				Brookfields

Freetown

MIN//0061							8thAugust 2006

Dr. Lob-Levyt

Executive Secretary

GAVI Alliance Secretariat

C/o UNICEF, Palasis des Nations

CH-1211 Geneva 10-Switzerland

Visitors: 5-7 Avenue dela paix

Dear Dr. Lob-Levyt,

# CLEARIFICATION  ON ANNUAL PROGRESS REPORT 2005

I wish on behalf of the Government of Sierra Leone and the |Ministry of Health and Sanitation hereby submit clarification on Annual Progress Report 2005 as it was mentioned in your letter dated 17th July 2005 with code No. SLE-2006.03(XCXX)M.

i	UPDATED TARGETS AND VACCINE REQUIREMENT

(PENTAVALENT 2007 – 2011 SIERRA LEONE

| Number | 2007 | 2008 | 2009 | 2010 | 2011 |
| --- | --- | --- | --- | --- | --- |
| Denominators |  |  |  |  |  |
| Births | 211,259 | 215,484 | 219,7,94 | 224,190 | 228,674 |
| Infants’ deaths | 35,194 | 36,632 | 37,365 | 38,112 | 38,875 |
| Surviving Infants | 175,345 | 178,852 | 182429 | 186,078 | 189,799 |
| Coverage Targets | 84% | 86% | 88% | 90% | 92% |
| Infants to be vaccinated in 2007 and beyond with first dose of pentavalent vaccine | 147,290 | 153,813 | 160,538 | 167,470 | 174,615 |
| Infants to be vaccinate in 2007 and beyond with third dose pentavalent vaccine | 147,290 | 153,813 | 160,538 | 167,470 | 174,615 |
| Vaccine requirement in 2007 and beyond | 613,095 | 512,197 | 534,592 | 557,675 | 581,468 |

Note: The buffer stock of 25% is included to the annual request for the first year of introduction (2007).

ii	CONCERNS

- The population used in 2005 was based on the projection from 1985 census figures

- The country conducted Population Census in December 2004 and the final result was released in January 2006.  The result of this new population figures are now being used to estimate target for immunization

- Some factors that contributed to high immunization figures in 2005 include: -

a.	Refugee population in camps and environs.

b.	Incentives given to districts for outreach activities might have motivated health workers to intensify their activities especially in districts sharing boundaries with neighbouring countries.

In conclusion, taking into consideration a country with prolonged interval of census (20 years) and emerging from conflict situation, your global experience in this matter is highly solicited for our guidance.

I thank you very much for your usual assistance and continued support to the children and women of Sierra Leone.

Yours sincerely,

ABATOR THOMAS (MS)

MINISTER OF HEALTH AND SANITATION

Revised Table 4b: Estimated number of doses of Pentavalent vaccine (specify for one presentation only):

Please

repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

| NO. |  | FORMULA | FOR 2007 |
| --- | --- | --- | --- |
| A | Infant vaccinated/to be vaccinated with 1st dose of pentavalent (new vaccine)* |  | 147,290 |
| B | Percentage of vaccines requested from the vaccine fund taking into consideration the financial sustainability | % | 100 |
| C | Number of doses per child |  | 3 |
| D | Number of doses | A X B X C | 441,870 |
| E | Estimated wastage factor | (See list in table 3) | 1.11 |
| F | Number of doses (incl. Wastage) | A X C X E X B/100 | 490,476 |
| G | Vaccines buffer stock | F X 0.25 | 122,619 |
| H | Anticipated vaccines in stock at start of year 2007 |  | 0 |
| I | Total vaccine doses requested | F + G-H | 613,095 |
| J | Number of doses per vial |  | 2 |
| K | Number of AD syringes (+10% wastage) | (D + G-H)X 1.11 | 626,583 |
| L | Reconstitution syringes (+10% wastage) | 1/J X 1.11 | 340,268 |
| M | Total safety boxes (+10% of extra need) | (K+L)/100 X 1.11 | 10,732 |