Annual Progress Report 2006

Submitted by

The Government of

Sierra Leone

to the

# Date of submission: 10th May, 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of …Sierra Leone……………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Hon.Dep. Minister of Health and Sanitation | Title: Hon. Minister of Finance |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr. Felicitas Zawaira | WHO |  |  |
| Mr. Geert Cappelaere | UNICEF |  |  |
| Mr. Daniel Kaindaneh | Christian Childrens’ Fund |  |  |
| Mr. M. A. S Jalloh | Sierra Leone Red Cross |  |  |

Signatures Page for HSS  (Not applicable)

For the Government of Sierra Leone  - Not applicable

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Not applicable |  |  |  |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Yes. The Ministry of Health and Sanitation conducts annual review and planning workshop for its three-year rolling plan every year. Activities identified for the next three years are costed, and a budget prepared. Budget for the first year of the plan is disaggregated to indicate the sources of funding and the existing gap in funds for the activities. The Directorates’ of Planning and Financial Resources will then compile all the activity plans of various units and divisions to produce a three-year rolling plan for the Ministry. The Ministry of Health and Sanitation’s request to the Ministry of Finance for GOSL fund allocation takes into consideration other partners including GAVI funding support, as would have been highlighted in its rolling plan budget.

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Upon receipt of funds from GAVI secretariat, the Hon. Minister of Health and Sanitation who is the chairperson of the ICC will mandate the Technical Committee to allocate fund to EPI activities not funded .The draft allocation is presented at an ICC meeting for approval. Upon approval, funds are requested /released by the MOHS based on time line of activities. There was no problem in the release of approved funds.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 _431,440 USD

Remaining funds (carry over) from 2005 _2,501.01 USD

Balance to be carried over to 2007 ___117,366.01 USD

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation | 3,000 | 3,000 |  |  |  |
| Maintenance and overheads | 27,000 | 17,000 |  | 10,000 |  |
| Training | 20,000 |  |  | 20,000 |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach | 71,000 |  |  | 71,000 |  |
| Supervision | 18,000 | 10,000 |  | 8,000 |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles | 65,000 |  |  | 65,000 |  |
| Cold chain equipment | 11,575 | 11,575 |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| 1. Fuel for cold chain | 20,000 | 5,000 |  | 15,000 |  |
| 2. Servicing of Distr. Cold chain | 21,000 |  |  | 21,000 |  |
| 3. Introduction of New vaccine | 60,000 | 18,465 |  | 41,535 |  |
| Total: | 316,575 | 65,040 |  | 251,535 |  |
| Remaining funds for next year: | 117,366.01 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

Major Activities - Supervision visits to all districts and selected PHUs -(GAVI, GOSL) - Training of Trainers on integrated child survival initiatives in all 13 districts- (UNICEF) - Training PHU staff on improving immunization coverage in 3 districts – (GOSL,GAVI) - Conduction of outreach activities in all 13 districts–(GOSL) - Support to outreach services in all 13 districts- (GAVI) - Planning and review meetings of District Healthy Management Teams (DHMTs) in all 13 districts -(UNICEF) - Expansion of health facilities on-going -(GOSL, NGOs & other development partners) - District and national micro planning for integrated Measles- malaria campaign (WHO ,UNICEF, GOSL) - Implementation of integrated Measles- Malaria campaign (WHO, UNICEF, GOSL, LDS, AWARE WAHO, VESTAGUARD) - Distribution and Installation of solar equipment (procured by ECHO) to districts (GOSL, UNICEF) - Training of solar cold chain technicians (UNICEF) - Maintenance of cold chain equipment at all levels -(GAVI) - Procurement of fuel for running of cold chain at all levels (GOSL, GAVI) - Procurement of generator to national office(GAVI) - Development of field guide for new vaccine introduction (GOSL, WHO) - Training of Health workers for new vaccine introduction (GAVI) - Development of comprehensive multi year plan- for EPI (GAVI, UNICEF, WHO, GOSL) - Development and Submission of GAVI HSS country proposal (GOSL,UNICEF, WHO) - Distribution of vaccines and other supplies to districts (GOSL, GAVI) - Orientation of DHMTs on the RED approach ( WHO, GOSL) Problems related to multi year plan. - Inadequate transport - Limited support to social mobilization - Limited human resource

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for ____2009

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA?

DQA recommendations have been communicated to secretariat in previous APR. Plans are underway to further strengthen the system using integrated Tools

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

x

## If yes, please report on the degree of its implementation and attach the plan.

Implementation of the recommendations has been reported on in the previous report

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

Not Applicable

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

5 times Civil Society Organizations are not currently represented in the ICC

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| DPT+HepB+Hib | 1 | 282,200 | 15th January, 2007 | 18th Dec. 2006 |
| Yellow fever | 10 | 203,100 | 2002 | 12th Jan. 2006 |

Yellow fever was introduced in 2002 and no change in vial in 2006

Please report on any problems encountered.

No problem was encountered on receipt of both vaccines

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Major Activities: - Distribution and installation of solar equipments to cover all districts. - Construction of incinerators/ digging of pits for waste disposal - Review of EPI data recording and reporting tools - Review of IEC materials to include key messages on pentavalent - Development of field guide for pentavalent vaccine introduction - Training of health workers on pentavalent vaccine - Conduction of press briefing on pentavalent - National launching on pentavalent introduction into routine immunization - Withdrawal of DPT from the field - Conduction of regular supportive supervision - Monitoring of vaccine coverage Problems: - Inadequate transportation - Limited human resource

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on : No funds received this time as support had been received for introduction of yellow fever in 2002

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Utilization of USD 100,000 has been provided in previous reports

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in __(Not yet done)

Please summarize the major recommendations from the EVSM/VMA

Not yet done

Was an action plan prepared following the EVSM/VMA : Yes/No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

The next EVSM/VMA* will be conducted in : ___2008

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |

Please report on any problems encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

#### GAVI INS to Sierra Leone ended in December 2004. In 2006, Government through UNICEF procured injection safety supplies that will last up to 2008. Government is very much committed to continue with the provision of injection safety supplies

#### Please report how sharps waste is being disposed of.

#### Injection wastes including sharp waste are disposed of through: - Incineration for facilities that have incinerators. - Burning and burying in facilities that do not have incinerators as yet.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

#### Materials for construction of Demorfort incinerator are not available locally. - Inadequate vehicles for the distribution of injection materials from national to district, and district to health facilities

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

Not Applicable. INS ended in December 2004.

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

.

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | 482,500 | 2,805,011 | 2,350,535 | 8,008,982 | 2,756,637 |
| Injection supplies | 712,102 | 282,918 | 312,071 | 327,259 | 343,374 |
| Personnel | 199,000 | 816,112 | 908,941 | 1,087,064 | 1,173,233 |
| Other operational expenditures | 1,089,159 | 3,379,645 | 2,096,548 | 4,883,033 | 2,220,503 |
| Cold Chain equipment | 839,746 | 300,818 | 474,506 | 278,482 | 416,103 |
| Vehicles | 182,876 | 186,150 | - | 161,304 | 97,960 |
| Other | 661,201 | 3,037,807 | 2,643,621 | 2,864,643 | 2,748,878 |
| Total Immunization Expenditures | 4,481,587 | 10,808,461 | 8,786,038 | 17,610,766 | 9,756,688 |
| Total Government Health Expenditures | 9,256,552 | 15,543,832 | 18,657,412 | 21,829,143 | 24,854,160 |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) | 1,950,877 | 3,650,939 | 3,706,075 | 4,260,057 | 4,448,931 |
| GAVI | 318,000 | 2,556,248 | 1,951,202 | 7,415,901 | 1,720,645 |
| UNICEF | 2,032,610 | 1,678,317 | 1,024,224 | 1,900,241 | 1,821,735 |
| WHO | 183,100 | 736,151 | 320,331 | 994,431 | 427,835 |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing | 4,484,587 | 8,621,655 | 7,001,832 | 14,570,630 | 8,419,146 |

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine : DTP-HepB-Hib (Pentavalent) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country | NA | 0 | 33,207 | 37,300 | 0 |
| Total co-financing by country | NA | 0 | 112,109 | 114,800 | 0 |
| Of which by |  |  |  |  |  |
| Government |  | 0 | 112,109 | 114,800 | 0 |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  | 2,299,500 | 2,523,264 | 2,355,527 | 2,412,061 |

| Table 3b: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3c: Country Vaccine Co-Financing in US$ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF | X | Tetanus Toxoid, BCG, Measles, OPV | UNICEF |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) GAVI | X | Pentavalent, Yellow Fever | GAVI |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) | Co-Financing payment starts in 2008 | - | - |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | X | Pentavalent |  |
| National health sector plan |  |  |  |
| National health budget | X | Pentavalent |  |
| Medium-term expenditure framework | X | Pentavalent |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis | X | Pentavalent |  |
| Annual immunization plan | X | Pentavalent |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |
| --- | --- |
| 1. Activities for mobilization of resources for co-financing payment not fully undertaken yet |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |
| 1. Limited number of manufacturers thus leading to sustained high vaccine prices |  |
| 2. Vaccine demand out-weighing supply |  |
| 3. Regional instability especially within the Mano-River basin |  |
| 4. National economic growth not sustained |  |
| 5. Non receipt of anticipated aid flow |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There are changes (slight modifications) in the figures of the final Census report document released in 2007. These changes have subsequently affected our targets for 2007 and beyond.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 229,088 | 207,117 | 213,728 | 218,858 | 224,111 | 229,490 | 234,998 | 240,638 | 246,413 |
| Infants’ deaths | 38,945 | 35,209 | 24,579 | 25,169 | 25,773 | 26,392 | 27,024 | 27,673 | 28,337 |
| Surviving infants | 190,143 | 171,908 | 189,149 | 193,689 | 198,338 | 203,098 | 207,972 | 212,964 | 218,076 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 176,7501 | 174,454 | - | - | - | - | - | - | - |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 145,875 | 164,312 | - | - | - | - | - | - | - |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of Yellow fever* | 145,784 | 148,322 | 174,017 | 184,001 | 188,421 | 192,943 | 197,573 | 202,316 | 213714 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of Yellow fever | NA | NA | NA | NA | NA | NA | NA | NA | NA |
| Wastage rate till 2006 and plan for 2007 beyond*** Yellow fever | 36% | 30% | 25% | 20% | 15% | 15% | 15% | 15% | 15% |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of Pentavalent* | - | - | 107,258 | 189,815 | 194,371 | 199,036 | 203,813 | 208,705 | 213,714 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of Pentavalent | - | - | 158,885 | 166,573 | 174,538 | 182,788 | 191,334 | 202.316 | 207,171 |
| Wastage rate till 2006 and plan for 2007 beyond*** Pentavalent | - | - | 10% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 188,826 | 198,312 | 170,982 | 181,652 | 190,494 | 222,605 | 209,148 | 216,574 | 221,772 |
| Infants vaccinated / to be vaccinated with BCG | 188,422 | 178,679 | 190,218 | 201,349 | 212,906 | 222,605 | 230,294 | 235,825 | 241,485 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 153,184 | 155,408 | 174,017 | 184,001 | 188,421 | 192,943 | 197,573 | 202,316 | 213714 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of pentavalent vaccine.

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 747,397 | 765,336 | 783,704 |
| Doses to be funded by GAVI | 714,189 | 728,036 | 783,704 |
| Doses to be funded by country | 33,207 | 37,300 | 0 |
| Country co-pay in US$/dose* | 112,109 | 114,800 | 0 |
| Total co-pay | 2,523,264 | 2,355,527 | 2,412,063 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Not Applicable.  Country injection safety support ended in December, 2004.

Table 8a: Estimated supplies for safety of vaccination for the next two years with BCG vaccine

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |
| --- | --- | --- | --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 10/05/07 |  |
| Reporting Period (consistent with previous calendar year) | Jan-Dec, 2006 |  |
| Government signatures | X |  |
| ICC endorsed | X |  |
| ISS reported on | X |  |
| DQA reported on |  | Previous Report |
| Reported on use of 100,000 US$ |  | “ |
| Injection Safety Reported on |  | Sup. Ended 2004 |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached | X |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report | X |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

We the members of the ICC met on the 4th of May, 2007, and discussed the Annual Progress Report for 2006. We are in agreement with its content and therefore unanimously endorsed it.

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing