January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: UNITED REPUBLIC OF TANZANIA

Date of submission: 13th APRIL, 2006…………………………… Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The country conducted mass measles campaign on 30th to 31st July to 1st Aug 2005. Prior to the campaign there were several planning activities. The late inclusion of vitamin A, deworming & net distribution which necessitated several coordination meetings, which occupied most of the time and caused delay in implementation of some of the planned activities. Strike in Muhimbili National Hospital, which stared early November, and ended in early January 2006, caused the Ministry of Health to paralysed most of its activities and caused delay in implementation of planned activities. Low performing districts were encouraged to identify problems, and suggest how they will improve and raise immunization coverage in their districts. Problems identified include: hard to reach areas; areas with high dropout rates; areas with high number of unreached children; poor data management; unreliable transport in some districts; inadequate supervision. Lack of spare parts/service of cold chain equipments. Lack of reliable transport in 12 municipal councils. Lack of supportive supervision by regional EPI focal person and absence of stand-by generator at central level were also among the problems identified. Facilitation of supportive supervision at the districts level by the Regional supervisor. Vehicles for 7 districts were procured. Engine boats for 10 districts procured. Problems with safety issues were identified. Data management especially timeliness of reporting EPI routine data. DQSA/ injection safety training in a CASCADE manner was planned to address it. Workshop by Bureau Statistics on was conducted - to solve target population problem. Based on the above problems plans were prepared and then presented to the ICC for comments. The plans were then sent to WHO for disbursement of funds.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005    2,306,000US$

Remaining funds (carry over) from 2004 1,860,186US$

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 5,541, 875 |  |  | 5,541, 875 |  |
| Injection supplies | 163793 |  |  | 163,793 |  |
| Personnel | 5238 | 4259 | 979 |  |  |
| Transportation | 15533 | 3943 |  | 11590 |  |
| Maintenance and overheads | 30190 | 15696 | 13771 | 723 |  |
| Training | 12195 | 1169 |  | 11026 |  |
| IEC / social mobilization | 6026 | 1774 |  | 4252 |  |
| Outreach | 2910 |  |  | 2910 |  |
| Supervision | 106580 |  | 104315 | 2265 |  |
| Monitoring and evaluation | 22487 | 20340 | 861 | 1286 |  |
| Epidemiological surveillance | 37629 | 19621 | 15390 | 2618 |  |
| Vehicles | 225439 |  | 4450 | 220989 |  |
| Cold chain equipment | 2249 |  |  | 2249 |  |
| Other …………. (specify) | 163793 |  |  |  |  |
| Total: | 6172144. | 66,802 | 139766.00 | 5,965,576.00 |  |
| Remaining funds for next year: | 3,688,232 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

NB:Support shown above include both public and private HFs. All HFs providing immunization service are fully supported

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Multiyear plan started in January while MTEF starts in July. The plan is to synchronize multiyear plan with MTEF.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

V

## If yes, please report on the degree of its implementation.

There was no DQA conducted during reporting period. Most of the recommended activities had been in cooperated in the Council Comprehensive Health Plans. Most of the recommendations have been implemented at Health facility and District level. Data management training under the existing Health Management has been conducted for Regional Health Management Teams. Monitoring of timeliness and completeness of reporting has been introduced in collaboration with the IDSR. During annual EPI meeting more emphasis was done on proper data management and reporting. Data Quality Self assessment training was conducted for ToTs and the regional focal persons were trained. The plan is to cascade to the district and health facility levels. Other opportunities were effectively used to improve immunization data quality through supervision and distribution of Vaccines by district t cold chain officers to health facilities. The data management activities have been incorporated into EPI 5 years strategic plan. DQSA training is also included.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

Post integrated measles campaign survey

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:	 JANUARY     YEAR 2002

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

100 percent of DPT-HB vaccine supported by GAVI was available in the country timely. We did not experience any problems in delivery the vaccine. Schedule: 06/01/2005 – 797,500 doses of DPT-HB vaccines, 02/03/2005 – 1,212,000 doses of DPT-HB vaccines, 25/05/2005 – 1,212,000 doses of DPT-HB vaccines and 19/08/2005 1,212,000 doses of DPT-HB vaccines doses of DPTHB. .

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

The major activities undertaken includes Support of Annual EPI evaluation meeting, support of hard to reach area procurement of vehicles and engine boats, support of integrated measles campaign and injection safety practices training. Support regional level supportive supervision. Due to strike at Muhimbili National Hospital which lead to paralysis of some of MoH activities and caused delay in Implementation of Several planning meetings due to late inclusion of several interventions during integrated measles campaign affects the implementation of some activities.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Though Tanzania was eligible for receiving the 100,000 US D support for vaccine introduction, we haven’t received the fund despite o several reminders..

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Tanzania Mainland has received injection safety funds. The support ended December 2004. Injection safety training which was integrated with DQS training for ToT’s which was conducted and the plan is to cascade to the health facility level. The fund will also support construction of incinerators in districts. However, Zanzibar received injection safety materials and didn’t encounter any problem. (Zanzibar to update).

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

All ADs for other antigens apart from DPT-HepB vaccine are procured by the Government and advocacy is for the Government to take over after the GAVI support for ADs for DPT-HepB vaccine. Districts are encouraged to support and construct low cost incinerators at District levels and at health facilities level all sharps should be burnt and buried.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Adequacy of supplies Adoption of safe injection practices by Health Workers. Injections Waste disposal Adverse Event Following Immunization | 100% AD syringes & safety boxes in all immunization services 90% of service providers adopt injection safety practices. Train 100% health workers on injection waste disposal Non existence of cases of AEFI due to poor injection safety practices | 100% 80% 75% 80% | No problem encounted for the reporting period. Inadequate training to Health Workers Non availability of Ideal low cost incinerators construction materials locally. Few incinerators were constructed. Weak AEFI reporting system Inadequate training to Health Workers on AEFI | 100% 85% 80% 85% |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Tanzania Mainland received injection safety support fund (489,000 US$), implementation of the identified activities is currently on board. The delay in implementation of the planned activities was contributed by the late synchronisation of some interventions with Integrated measles mass campaign and strike of Muhimbili National Hospital doctors

# Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan.

Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major

strategies for improving financial sustainability.

Tanzania participated in the orientation workshop in Nairobi in which participants from MOH (EPI and planning), MOF, WHO and UNICEF attended. A National workshop was held in July 2002 to put up a Financial Sustainability Plan. In August 2002, an economist was hired by WHO as a local consultant to further work on this document for both Mainland and Zanzibar. External Consultants joined the local consultant in November 2002 to complete the Document for presentation to GAVI Reviewers indicated some areas for improvement The Financial Sustainability Plan, sub-working group incorporated the comments and finalized the second revised financial Sustainability Plan. Financial Sustainability plan strategies were also developed. Another external consultant came to fine tune the second draft in September 2003 A second submission was made in December 2003. Comments from second revision received are being incorporated. Revision of FSP strategies and revision of costing has started. Revision of FSP document was done when preparing the multiyear plan (2006 – 2010).

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine ……DPT-HepB (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003.. | 2004.. | 2005.. | 2006.. | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| A: Proportion funded by GAVI/VF (%)*** | 97% | 80% | 41% | 41% | 70% | 0% | 0% | 0% | 0% | 0% |
| B: Proportion funded by the Government and other sources (%) | 3% | 20% | 59% | 59% | 30% | 15% | 15% | 15% | 15% | 20% |
| C: Total funding for DPT Hep B (new vaccine) | 4.97Mil | 6.2 Mil. | 6.5Mil | 7.0Mil | 7.5Mil | 8.0Ml | 8.0Ml | 8.0Ml | 8.0Ml | 8.0Ml |

- Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and

under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| Mobilize additional local Govt resources | Sensitisation meeting to CHMTs and Health Coordinators of PMO-RALG | EPI activities are priority at the district level | Reliabity of the allocated resources | Data not compiled from districts | Data not compiled from districts | To be able to capture district level expenditures on EPI |
| Expansion of ICC | Other partners encouraged to join ICC. | One member joined ICC | Poor attendance of ICC members | Not Applicable | Not Applicable | To use the opportunity of EPI membership in Maternal and Child Survival Partnership |
| Reduce vaccine wastage | Refresher training on reducing wastage rate was done to Health workers | Wastage rate reduced | Weak monitoring system | 15% | 10% | Daily sessions to be encouraged Improving vaccines wastage reporting system |
| Increase vaccination offered through static units | 10 remote HFs will be supported to deliver immunization services | Items to be supported identified | Many HFs are constructed & demand support | 0 | 10 HFs will be supported | No change proposed to this strategy |
| Preparation of advocacy documents | Develop the brief / flyer highlighting key FSP messages | EPI FSP quoted in different forums | Competing priorities & good EPI performance made local partners and some decision leaders to focus other program. | Non existing brief/flyer highlighting FSP | Existence of a flyer | Conduct advocacy meetings |
| Mobilize additional Govt resources | Advocacy done to decision makers | Govt resources increased | Competing priorities | 5.4 ml. US$ (2004/05) | 10.3 ml. US$ (2005/06) | Establish evidence ( impact, opportunistic cost etc ) and present to decision makers and partners especially for measles second dose and Hib vaccines. |
|  | Meetings with top Ministry of Health officials regarding Govt, Policy and Planning | Meeting done | Lack of local evidence | One meeting conducted | Three meetings conducted | No change proposed to this strategy |
|  | Meeting with key Government ministries Presidents office, planning and privatization, state house, prime ministers office |  |  |  |  | No change proposed to this strategy |
|  | Presentation of FSP information memorandum to cabinet | Not done |  | NA | NA | No change proposed to this strategy |
| ## Increase reliability of public resources | Identify and highlight funding gap in the present planning cycle for the Govt (Medium Term Expenditure Framework) | EPI gap identified & presented in Health sector review meetings | None | Exact EPI gap is known | Exact EPI gap is known | No change proposed to this strategy |
|  | Ensure program funding needs are included in the MTEF | Program needs are included in the MTEF | Competing priorities allocation is not 100% | Not all activities were included in the MTEF | All activities are included in the MTEF | No change proposed to this strategy |
|  | Advocate for protection/ring fencing of the bulk of program funds from Govt (particularly for vaccine purchases) | EPI funds are protected no reallocation. All vaccines in exception of DPT-Hep B are procured by government | Several request for reallocation by other program | Reallocation of funds for other activities apart from vaccines | Rear reallocation | No change proposed to this strategy |
| Use of performance standards by centre for districts | Agreement on indicators to measure districts performance against each other | Indicators identified | Identifying one district from 119 districts | Reward prepared for best district | Continuation of rewarding best performing districts | No change proposed to this strategy |
|  | Information on performance of districts reported in regular ICC meetings | District performance is shared to all ICC members | Poor monthly reporting | 4 times a year | 4 times a year | No change proposed to this strategy |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 1,356,054 | 1,432,259 | 1,532,851 | 1,621,791 | 1,668,864 | 1,717,305 | 1,767,151 | 1,818,444 | 1,871,225 |
| Births | 1,498,830 | 1,534,675 | 1,645,407 | 1,740,855 | 1,791,385 | 1,843,382 | 1,896,889 | 1,951,949 | 2,008,606 |
| Infants’ deaths | 177,179 | 102,416 | 112,556 | 119,064 | 122,521 | 126,078 | 129,738 | 133,505 | 137,381 |
| Surviving infants | 1,356,054 | 1,432,259 | 1,532,851 | 1,621,791 | 1,668,864 | 1,717,305 | 1,767,151 | 1,818,444 | 1,871,225 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* |  |  |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* …......... (new vaccine) | 1,355,922 | 1,361,714 | 1,472,462 | 1,557,546 | 1,602,347 | 1,648,440 | 1,695,862 | 1,744,651 | 1,794,847 |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of…….… ( new vaccine) | 1,282,278 | 1,286,274 | 1,440,146 | 1,523,423 | 1,567,258 | 1,612,356 | 1,658,754 | 1,706,492 | 1,755,606 |
| Wastage rate in 2004 and plan for 2005 beyond*** ………….. ( new vaccine) | 15% | 6% | 10% | 10% | 10% | 10% | 10% | 10% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 1,192,270 | 1,247,668 | 1,404,546 | 1,485,491 | 1,528,168 | 1,572,085 | 1,617,247 | 1,663,721 | 1,711,534 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 1,369,596 | 1,413,855 | 1,591,565 | 1,682,542 | 1,730,286 | 1,779,405 | 1,829,936 | 1,881,924 | 1,935,407 |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 1,275,352 | 1,307,953 | 1,443,564 | 1,526,910 | 1,570,814 | 1,615,983 | 1,662,454 | 1,710,265 | 1,759,456 |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Following the 2002 census data, the problem of target population exists. EPI, National Bureau of statistics and HMIS conducted a workshop to deliberate on the issue and the inputs in this workshop will assist Bureau of statistics to come up with projections of different age group for immunizations.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if

UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Table 4: Estimated number of doses of DPT-HepB…… vaccine (specify for one presentation only): Please repeat this table for any other vaccine

presentation requested from GAVI/The Vaccine Fund
*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine

BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NA

# Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

* See 1.3.2

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | √ |  |
| Reporting Period (consistent with previous calendar year) | √ |  |
| Table 1 filled-in | √ |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) | √ |  |
| Table 2 filled-in | √ |  |
| New Vaccine Request completed | √ |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report | √ |  |
| Government signatures | √ |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~