January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY:

Date of submission: May 27, 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report X Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

N/A

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004 _______________

Remaining funds (carry over) from 2003 ________________

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

X

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH: January YEAR: 2004

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

First consignment of HepB vaccine from GAVI was received in February 2004. Total number of doses – 764,872. Vaccine presentation: in single-dose vials – 202,600; in 10-dose vials – 562,272. Manufacturer – LG Life Sciences Ltd., South Korea. Second consignment of HepB vaccine was received in August 2004. Total number of doses – 225,000. Vaccine presentation: in single-dose vials – 77,500; in 10-dose vials – 147,500. Manufacturer - Shantha Biotechnics Pvt.Ltd., India Total number of doses received in 2004 – 989,872. Supplier – UNICEF Supply Division. Also in two consignments (in March and September) arrived equipment for safe injections, i.e. auto-disable syringes – 4,700,100 and safety boxes – 48,175. In 2004 Ukraine received support worth of US$549,668.88 and €14,666.40 (vaccines and syringes). The Ministry of Health of Ukraine has authorized "Ukrvaccina" State Company to be a consignee of vaccines and injection equipment. Both consignments of vaccine were distributed throughout Ukraine to immunize newborns. The supplies were delivered to immunization sites by special vehicles of "Ukrvaccina" State Company.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

All activities to this effect were conducted in 2003. No related activities were implemented in 2004.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

As of 1st January 2005 the funds had not been used due to the acting legislation, which does not protect incoming money against taxation. It took some time to develop a mechanism for opening a protected earmarked account. The funds were received on 23rd Feb'04 and are currently kept at the Kyiv Branch of "Black Sea Bank for Development and Reconstruction" Joint Stock Bank. Ukraine's Cabinet of Ministers issued a special resolution recognizing the above funds as humanitarian aid. During 2005 some funds (US$36,045.71) were used to purchase cold chain equipment. Also planned is the purchase of some office equipment (computers and printers) for mid-level managers of immunization program to improve efficiency of monitoring of HepB immunization coverage within target groups, vaccine flow and wastage during immunization, etc.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In 2004 Ukraine received from GAVI 4,700,100 auto-disable syringes (or 46.5% of all syringes used to vaccinate children and adolescents in 2004) and 48,175 safety boxes.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### Since its independence, Ukraine developed a system to collect and dispose used disposable syringes. In 1993 the MoH Ukraine issued order #223 dated 22nd Oct'93 "About collection, decontamination and delivery of used disposable plastic items". Significant share of used disposable syringes (both made locally and imported) after chemical decontamination were accumulated in health care settings (HCS) (in special premises). All HCS nominated a person in charge of decontamination, collection and storage of such equipment. Usually, they were senior nurses of departments and chief nurses of HCS. The system took care of all syringes used in the somatic departments and for vaccinations. After decontamination disassembled syringes (with needle separated) are delivered by HCS to respective companies for recycling. As reimbursement the HCS were either paid or got the good produced by the company (plastic buckets for cleaning, bed pans, etc). Having got support from GAVI (vaccine and AD syringes) Ukraine faced the problem of their utilization due to metal plates inside syringes. WHO recommendations for the disposal of such syringes through burning in high-temperature incinerators, open burning, or burial could hardly be followed for the following reasons: - HCS have no incinerators; - in large cities burning of the used syringes in high-temperature furnaces should be paid for; - open burning of used syringes is prohibited by law. MoH ordered to accumulate used syringes in HCS until strategic decision is made on the method of their disposal. In the circumstances, therefore, the necessity of revision of existing waste disposal system became apparent and a new system had to be tested in terms of increasing immunization injection safety and utilization of used syringes.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Adequate supply of syringes and needles at HCS level - Disposal of used injection equipment | 100% supply of AD syringes to HCS 100% supply of safety boxes to HCS for EPI | 100% of AD syringes supplied to HCS 100% of safety boxes supplied to HCS for EPI | Other age groups are immunized using regular disposable syringes Regular disposable syringes are subject to chemical decontamination | Insure safe collection and decontamination of used syringes |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

In 2004 the WHO pilot project on recycling AD syringes was conducted in Kyiv City and Khmelnitsk Oblast. Involved in the project were 25 immunization units of the health care settings of these sites, as well as two companies dealing with the recycling of plastic materials. The project's objective was as follows: - After each injection, made in the immunization unit to vaccinate a child, a needle was separate from the syringe (AD or conventional) using special needle cutter. Separated needles were placed in a container fixed to cutter. Immediately after needle separation, plastic syringes were taken into special polyethylene bags, which were placed in pedal-operated bucket. Full containers and bags were taken to a premise with restricted access. Autoclaving (using autoclaves of HCS) was chosen as decontamination method. Decontaminated syringes were delivered to recycling companies mainly by company vehicles. Needle cutters, containers for used needles, bags for used syringes, pedal-operated buckets, test indicators (to control temperature during autoclaving, and funds to develop technology for separating metal inserts from plastic during its recycling were supplied by WHO EURO. Results of pilot project are as follows: - Health workers admitted increased safety; - Real time saving; - No significant technical problems; - No additional funds are needed to introduce new system. Based on project findings the MoH is currently working on regulatory documentation on injection safety and safe disposal of injection equipment.

# 2.  	Financial sustainability

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Ukraine's delegation attended a workshop organized by the World Bank, WHO EURO and UNICEF on restructuring national health care systems and financial sustainability (23-28 August 2004, Budapest, Hungary).

Delegation included Yuri Vitrenko, Chief, Department for Human Development, MoE; Maria Vovk, Deputy Chief, Dept. of Economics and Finance, MoH; Nina Borisenko, Deputy Director General, "Ukrvaccina" State Company; Svitlana Gheraimovich, Chief Economist, MoF; O. Stelmakh, Chief Specialist, Department for Prevention of Infectious Diseases and Immunization, Dept. for State Sanitary Surveillance, MoH.

Upon return to Kyiv all members joined intergovernmental working group to develop FSP. Each member was responsible for certain section of FSP.

In October 2004 the World Bank consultants (Santiago Conneho, David Gzirishvili and Victor Galaida) worked with MoH Ukraine to help Ukraine's specialists at the initial stages of FSP development within the framework of the WB technical support to Ukraine's Government.

At its meeting on 22nd Oct'04 the Inter-Agency Coordinating Committee reviewed the draft FSP prepared by Ukraine's specialists with technical support of the WB mission. Victor Galaida served as WB Consultant to help complete the FSP. It was submitted to GAVI Secretariat in late March 2004.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for HepB vaccine for each new vaccine.

| Table 2.1: Sources (planned) of financing of new HepB vaccine |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 100 | 80 | 60 | 60 | 50 | 50 |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 20 | 40 | 40 | 50 | 50 |  |  |  |
| C: Total funding for HepB vaccine | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1.Optimizing centralized procurement (achieving most favorable ration between price and quality of vaccines and equipment to be purchased) | - Identify WHO pre-qualified vaccines, which are included in the immunization schedule, but not registered in Ukraine (List V-N-W) - Written report on comparative characterization of vaccines in the list V-R and list V-N-U |  |  |  |  |  |
| 2. Developing efficient system of financial incentives for regional and local authorities to maintain an adequate infrastructure of immunization services at health facility level. | - Making national inventory of cold chain equipment and assessing the quality control system to check its reliability - Recognize financing the purchase of cold chain equipment using fund of local and state budgets as a component part of the national and regional immunization programs. |  |  |  |  |  |
| 3. Improving an information system of NIP (monitoring of infrastructure and operation of immunization services as a whole: vaccine flow, cold chain reliability, adequate staffing, other resources) | Analyze existing system of NIP management and identify information needs of this system, develop recommendations for system development |  |  |  |  |  |
| 4. Improving criteria for introduction of new vaccines in immunization schedule of Ukraine's NIP. | Introduce pharmaco-economic analysis in taking a decision about expansion of NIP (introduction of new vaccines) |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 13). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 427,259 | 439,000 | 439, 000 | 439,000 | 439,000 | 439,000 | 439,000 |  |  |
| Infants’ deaths | 4,026 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 |  |  |
| Surviving infants | 423,233 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 407,669 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 404,053 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of HepB vaccine* | 424,663 | 439,000 | 439,000 | 439,000 | 439,000 | 439,000 | 439,000 |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of HepB vaccine | 400,944 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 | 435,000 |  |  |
| Wastage rate in 2004 and plan for 2005 beyond of HepB vaccine *** | 1.13 | 1,15 | 1,15 | 1,15 | 1,15 | 1,15 | 1,15 |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 411 286 | 439 000 | 439 000 | 439 000 | 439 000 | 439 000 | 439 000 |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 399 202 | 435 000 | 435 000 | 435 000 | 435 000 | 435 000 | 435 000 |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

By the time country proposal was submitted to GAVI there was a decline in the birth rate. During four recent years there was a steady increase of birth rate after a prolonged period of decline. Therefore, the figures of target groups differ from those presented in the country proposal and subsequent reports. According to MoH's Center for Medical Statistics an increase of birth rate will continue in 2005 (by 2.7%) and the size of the target group will increase to 439,000 newborns. Due to unstable demographic dynamics of birth rate, long-term forecasts may be inaccurate. Therefore, the same target group was used for 2006-2010. Updated figures will be included in subsequent annual reports.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

In view of birth rate increase an increased number of doses of HepB vaccine are requested for 2006. UNICEF Supply Division confirmed availability of the sufficient quantity of vaccine for 2006.

Table 4: Estimated number of doses of HepB vaccine in single-dose vials

|  |  | Formula | For 2006 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of HepB vaccine* |  | 131,700 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 60 |
| C | Number of doses per child | 3 | 3 |
| D | Number of doses | A x B/100 x C | 237,060 |
| E | Estimated wastage factor | (see Table 3) | 1.05 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 248,913 |
| G | Vaccines buffer stock | F x 0.25 | 62,228 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | 27,380* |
| I | Total vaccine doses requested | F + G - H | 283,761 |
| J | Number of doses per vial |  | 1 |
| K | Number of AD syringes (+10% wastage) | ( D + G – H ) x 1,11 | 301,818 |
| L | Reconstitution syringes(+10% wastage) | I / J x 1,11 |  |
| M | Total safety boxes (+10% of extra need) | ( K + L) / 100 x 1,11 | 3,350 |

*Please report the same figure as in table 3.

Table 4.1: Estimated number of doses of HepB vaccine in ten-dose vials

|  |  | Formula | For 2006 |
| --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of HepB vaccine* |  | 307,300 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | % | 60 |
| C | Number of doses per child | 3 | 3 |
| D | Number of doses | A x B/100 x C | 553,140 |
| E | Estimated wastage factor | (see Table 3) | 1.18 |
| F | Number of doses (incl. Wastage) | A x C x E x B/100 | 652,705 |
| G | Vaccines buffer stock | F x 0.25 | 163,176 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | 91,378** |
| I | Total vaccine doses requested | F + G - H | 724,503 |
| J | Number of doses per vial |  | 10 |
| K | Number of AD syringes (+10% wastage) | ( D + G – H ) x 1,11 | 693,681 |
| L | Reconstitution syringes(+10% wastage) | I / J x 1,11 | N/A |
| M | Total safety boxes (+10% of extra need) | ( K + L) / 100 x 1,11 | 7,700 |

*Please report the same figure as in table 3.

**Original forecast for 2004 was 388,000 births. By the end of 2004 there were 427,259 live newborns. Due to an increase of 						birth rate by the end of 2004, there was no leftover vaccine. A reserve stock (25%) for the second VF year was not 						calculated.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG vaccine

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | # | 439 000 | No support |
| B | Number of doses per child | # | 1 |  |
| C | Number of BCG doses | A x B | 439 000 |  |
| D | AD syringes (+10% wastage) | C x 1,11 | 487 290 |  |
| E | AD syringes buffer stock1 | D x 0,25 | 121 823 |  |
| F | Total AD syringes | D + E | 609 113 |  |
| G | Number of doses per vial | # | 20 |  |
| H | Vaccine wastage factor2 | 2 | 2 |  |
| I | Number of reconstitution syringes (+10% wastage) 3 | C x H x 1,11 / G | 48 729 |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1,11 / 100 | 7 302 |  |

1 The buffer stock for vaccines and AD syringes is set at 25%.  This is added to the first stock of doses required to introduce the vaccination in any given geographic area.  Write zero for other years.

2 Standard wastage factor will be used for calculation of reconstitution syringes.  It will be 2 for BCG, 1.6 for measles and YF

3 Only for lyophilized vaccines.  Write zero for other vaccines.

Table 7: Estimated supplies for safety of vaccination for the next two years with DTP vaccine

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Target of children for DTP vaccination | # | 435,000 | No support |
| B | Number of doses per child | # | 3 |  |
| C | Number of DTP doses | A x B | 1,305,000 |  |
| D | AD syringes (+10% wastage) | C x 1,11 | 1,448,550 |  |
| E | AD syringes buffer stock1 | D x 0,25 | 362,138 |  |
| F | Total AD syringes | D + E | 1,810,688 |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor2 | 2 |  |  |
| I | Number of reconstitution syringes (+10% wastage)3 | C x H x 1,11 / G | 0 |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1,11 / 100 | 20,100 |  |

1 The buffer stock for vaccines and AD syringes is set at 25%.  This is added to the first stock of doses required to introduce the vaccination in any given geographic area.  Write zero for other years.

2 Standard wastage factor will be used for calculation of reconstitution syringes.  It will be 2 for BCG, 1.6 for measles and YF

3 Only for lyophilized vaccines.  Write zero for other vaccines.

Table 8: Estimated supplies for safety of vaccination for the next two years with MMR vaccine

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Target of children for MMR vaccination | # | 435,000 | No support |
| B | Number of doses per child | # | 1 |  |
| C | Number of MMR doses | A x B | 435,000 |  |
| D | AD syringes (+10% wastage) | C x 1,11 | 482,850 |  |
| E | AD syringes buffer stock1 | D x 0,25 | 120,713 |  |
| F | Total AD syringes | D + E | 603,563 |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor2 | 2 |  |  |
| I | Number of reconstitution syringes (+10% wastage) – single-dose vials3 | C x H x 1,11 / G | 152,098 |  |
| I+ | Number of reconstitution syringes (+10% wastage) – ten-dose vials3 | C x H x 1,11 / G | 54,080 |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1,11 / 100 | 9,000 |  |

1 The buffer stock for vaccines and AD syringes is set at 25%.  This is added to the first stock of doses required to introduce the vaccination in any given geographic area.  Write zero for other years.

2 Standard wastage factor will be used for calculation of reconstitution syringes.  It will be 2 for BCG, 1.6 for measles and YF

3 Only for lyophilized vaccines.  Write zero for other vaccines.

Table 9: Estimated supplies for safety of vaccination for the next two years with IPV vaccine

|  |  | Formula | For 2006 | For 2007 |
| --- | --- | --- | --- | --- |
| A | Target of children for IPV vaccination | # | 435,000 | No support |
| B | Number of doses per child | # | 1 |  |
| C | Number of IPV doses | A x B | 435,000 |  |
| D | AD syringes (+10% wastage) | C x 1,11 | 482,850 |  |
| E | AD syringes buffer stock1 | D x 0,25 | 120,713 |  |
| F | Total AD syringes | D + E | 603,563 |  |
| G | Number of doses per vial | # |  |  |
| H | Vaccine wastage factor2 | 2 |  |  |
| I | Number of reconstitution syringes (+10% wastage)3 | C x H x 1,11 / G | 0 |  |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1,11 / 100 | 6,700 |  |

1 The buffer stock for vaccines and AD syringes is set at 25%.  This is added to the first stock of doses required to introduce the vaccination in any given geographic area.  Write zero for other years.

2 Standard wastage factor will be used for calculation of reconstitution syringes.  It will be 2 for BCG, 1.6 for measles and YF

3 Only for lyophilized vaccines.  Write zero for other vaccines.

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

During four recent years there was a steady increase of birth rate after a prolonged period of decline. According to MoH's Center for Medical Statistics, an increase of birth rate will continue in 2005 (by 2.7%) and the size of the target group will increase to 439,000 newborns. A request submitted in 2003 was based on 2001population forecasts, with due account of a tendency towards birth rate decrease.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage of children under 1 year with HepB3 immunization at the national level | Over 95% coverage of children under 1 year with HepB1 by 2005 | In 2004 coverage of children under 1 year with HepB was 94.7% | Limited capacity to advance skills of managers at the rayon level |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 15th May 2005 |  |
| Reporting Period (consistent with previous calendar year) | 1st Jan'04 - 30th Dec'04 |  |
| Table 1 filled-in | N/A |  |
| DQA reported on | No DQA made |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

RWG reviewed the draft report. All comments and remarks were included into the final version.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
|  |  | . | MoE Ukraine | Vitrenko Yu.M. Chief, Department for Human Development |  |
| MoH Ukraine | Mukharskaya L.M. Deputy Chief State Medical Doctor of Ukraine, Deputy Chairman of ICC | . | National Red Cross Committee of Ukraine | Khabarova A.M. Executive Director |  |
| MoH Ukraine | Karamushka L.I. Director, Dept. of Economics and Finance | . | World Bank Office in Ukraine | Beh О.А Consultant, Sector of Human Development |  |
| MoH Ukraine | Kuznetsov A.V. Director-General, "Ukrvaccina" State Company | . | РАТН | David Mercer Program Manager |  |
| MoH Ukraine | Moiseenko R.A. Chief, Dept. of Mother and Child Health |  | USAID | Radziyevskaya E.E. Health Project Manager |  |
| Inst. of Epidemiology and Infectious Diseases AMS Ukraine | Selnikova O.P. Director, Inst. of Epidemiology and Infectious Diseases | . | UNICEF | Sherstyuk Е.N. Project Coordinator |  |
| MoF Ukraine | Didenko S.A. Chief, Dept. of Budget Health Programs & Social Security | . | USAID | Tim Clary Senior Health Advisor |  |
| WHO Office in Ukraine | Subbotin Yu.V. WHO Liaison Officer |  | MoH Ukraine | Stelmakh О.М. Chief Specialist, Department for Prevention of Infectious Diseases and Immunization, Dept. for State Sanitary Surveillance, ICC Secretary |  |

~ End ~