January 2005

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: THE SOCIALIST REPUBLIC OF VIETNAM

Date of submission: May 2005 Reporting period: 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report x  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

Nationally, 1,435,080 children under 1 year old were vaccinated with 3 HBV doses in 2004. (94.2% of total targeted).

In the provinces receiving vaccine supplied by GAVI, a total of 1,192,786 children under 1 year old (94.0% of the target population) were vaccinated with 3 HBV doses. Coverage with HBV1 reached 96.8%, of which 69.6% was given during the first three days of life and HBV2 coverage was 94.3%. A total of 242,294 children (95% of the target population) received three doses of locally produced hepatitis B vaccine. Coverage levels were: HBV1: 96.5% and  HBV2: 96.4%.

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

None received

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new vaccine:           MONTH: January           YEAR  2002

Total number of hepatitis B vaccine received for 2004

| Vaccine/Devices | Quantities in doses/pcs | Delivery date |
| --- | --- | --- |
| HepB (1 dose/vial) | 1,243,800 | 10, 12 Jan. 2004 and 23, 25 Jun. 2004 |
| Hep B (2 doses/vial) | 2,920,780 | 11, 12 Feb. 2004 and 30 Jun. 2004 |

Number of Hepatitis B vaccine doses received for 2005

| Vaccine/Devices | Quantities in doses/pcs | Delivery date |
| --- | --- | --- |
| HepB (1 dose/vial) | 7,00,000 | 1 Dec.2004 and 20,22 Dec. 2004 |
| Hep B (2 doses/vial) | 1,300,000 | 4 Jan. 2005 |

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

All Hep B vaccine vials received had a VVM attached. 200 inner boxes were contained in foam box. They should be put in an individual carton box. The GAVI supplied vaccine is being used in 83% of the total target population; the remaining use locally produced vaccine.AD syringes 0.5ml and safety boxes were supply enough for administration of HepB vaccine. According to the letter on 30 July 2004, US$ 307,000 will be received in cash in lieu of AD syringes (4,058,000) and safety boxes (45,050) required for HepB vaccination in 2005. The fund was sent to MOH in October 2004. However, National EPI only know about that in March 2005. Please note that for purchase locally produced AD syringes and safety boxes we need the letter from GAVI to MOH to inform about this fund will be used for purchase of locally produced AD syringes and safety boxes instead of received injection equipment as was asked in the application form in 2001.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

In the year 2004, the second year Hepatitis B vaccine is used for children under 1 year old nation-wide. 83% of target population used GAVI – supported vaccine. The remaining using locally produced vaccine. The coverage in provinces using GAVI – Hep B vaccine was 94 % of 1,268,370 children for Hep B 3, 96,8 % for HepB 1 and 69,6 % were vaccinated HepB 1 within 3 days after birth. Nationally, 94,2 % of 1,523,465 children were vaccinated with HepB3, 96,8 % were vaccinated with HepB 1 and 59,5 % were vaccinated with HepB 1 within 3 days after birth. With the support from WHO, in August 2004, an assessment on the introduction of Hepatitis B birth dosing at commune health centre was carried out in 4 provinces used GAVI vaccine. The conclusion of this assessment: 1. Health system tried to be innovative to reach to all newborns. In all districts visited, hepatitis B birth-dosing was reflected in the annual EPI plan of action. 2. Major operational constraints in providing the timely birth-dose were followings: - Location of the vaccine storage. - Policies on vaccine storage and their interpretations (Both policy on the administrative levels where vaccines should be stored and policy on out-of-cold chain storage and use of hepatitis B vaccine with VVM). - Proportion of community delivery and hesitance to deliver at health facility. - Network of village health workers. - Relations with private obstetrics practices. - Relations with large hospitals. 3. The incremental operational cost of hepatitis B vaccine birth-dosing comprised fuel cost and travel allowances both for collecting vaccines and home outreach immunization for infants born at home, and electricity cost in case vaccines were stored at CHCs. 4. It was considered feasible to apply timeliness requirement of within 24 hours rather than 72 hours despite the perceived difficulty in achieving birth-dosing within 24 hours for deliveries outside public health facilities.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Total fund for injection safety for 2005 was US$1,023,000. This fund was informed to National EPI in March 2005. A contract for safe injection equipment between National EPI and Mediplast (local manufacturer) will be signed in April 2005. Safe injection equipment will be received in quarters 2 – 3, 2005.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### The EPI produces only a small part of medical waste. A national policy on medical waste management is in development, but is not yet ratified. The use of safety boxes is now available for EPI but not include therapeutic services. With support from PATH, a demonstration of a needle remover device in Huong Khe district, Ha Tinh Province in 2005 will be conducted. The overall goal of the demonstration is to demonstrate the use of a needle remover device at commune level. The devices will be used for all syringes used in both the immunization program and for therapeutic services. This will enable the Vietnam NEPI to explore an alternative method for managing injection waste at commune level that may be more effective and appropriate than current practices.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| 100 % of Provinces with adequate access to appropriate disposal system, including exchange mechanism for new and used injection equipment where this is feasible, and local disposal in remote locations | By the end of 2004 | Some provinces and districts received industrial incinerators to destroy medical waste. Other provinces and districts that are not equipped with industrial incinerators yet, and are destroying the medical waste by building various types of local prototype incinerators | The EPI produces only a small part of medical waste, but it is difficult, and probably not appropriate to separate this out. A national policy on medical waste management is in development, but is not yet ratified. Pilot activities are in progress. However, the use of safety boxes is now almost universal in Viet Nam. | By the end of 2008 (acknowledging that this target is difficult for the EPI to set) |
| 100 % of Districts with 100% AD use for all EPI vaccines and safe disposal practices | By the end of 2003 | 100% AD syringes usde in routine EPI except syringes used for BCG. | AD syringes used for BCG is not available | 2004 (it is already 2005!!)(not include syringes used for BCG) |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Total fund for injection safety for 2004 was 1,300,780 USD (including 119,800 USD for 0.5 ml AD syringes and safety boxes was used for Hep B vaccination. This fund was received in November 2003. Safe injection equipment was distributed in 2004 as follow: -BCG syringes 0,1 ml: 2,236,400 pieces -AD syringes 0,5 ml: 15,880,200 pieces -Re-constitution syringes 5ml: 581,600 pieces - Safety boxes 5 l: 234,750 pieces

# 2.  	Financial sustainability

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of Hepatitis B vaccine (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 |
| A: Proportion funded by GAVI/VF (%)*** | 81 | 87 | 83 | 83 | 83 | 41 | 0 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 19 | 13 | 17 | 17 | 17 | 659 | 100 | 100 | 100 | 100 |
| C: Total funding for Hepatitis B vaccine (USD) | 1,888,873 | 2,824,637 | 2,062,189 | 2,080,507 | 2,105,473 | (to be modifie2,128,782d) | 2,156,307 | 2,182,183 | 2,208,369 | 2,234,870 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Enhancing Government Funding for EPI (central level) | -Featuring FSP in ICC agenda with participation of MOF and MPI. |  | -No full compliance to interim agreement of 10% annual increment of EPI budget (MOF interprets it as average increase rate, not every year.) | -No FSP at the beginning of 2003 -2003 EPI budget was 98 billion VND (6,130,000 USD). | -FSP completed and being revised. -2005 EPI budget is 110 bilionVND, which is 10-% increase from 2003 level. | No change, but rather reiterate the basic agreement of 10% annual increase of EPI budget. |
| 2. Budget shifting at the national and province levels | -According to the SWB research, action plan was made and fund secured to facilitate amendment of Circular 51 stipulating remuneration for local EPI staff. |  | -Due to financial decentralization, EPI system does not have control over provincial budget allocation. |  | National health expenditure has not been officially available to date, it is not possible to indicate. |  |
| 3. Additional resourcing from GAVI/ Vaccine Fund | -ICC started to discuss GAVI phase II proposal. |  |  | -No existence of concrete proposal in 2003. | -Proposal development in progress (but waiting for GAVI announcement) |  |
| 4. Project grants from bilateral or multilateral agencies | -JE expansion was proposed to ADB’s Mekong Region Communicable Diseases Control Project | -ADB basically agreed to finance JE expansion. | -Technical and long-term policy issues (which vaccine to use?, universal coverage or high-risk approach?) still under discussion. | -No grant from bilateral or multilateral agency was discussed in context of FSP in 2003. | -So far, JICA and ADB have committed their funding on the basis of FSP. |  |
| 5. Reduce vaccine wastage (modified from “enhanced training to reduce vaccine wastage) | -Nationwide cold-chain training in 2004. -Cold chain inventory development in early 2005. | -Hepatitis B vaccine wastage support from GAVIwas 10% (it was 12% in 2003) |  | -No district received cold-chain training in 2003. -No cold-chain inventory in 2003. | -250 districts received cold-chain training in 2004. -Cold chain survey conducted and inventory being established. |  |
| 6. Cold chain management |  |  |  |  |  | This strategy is largely redundant with above therefore should be deleted. |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births |  |  |  |  |  |  |  |  |  |
| Infants’ deaths |  |  |  |  |  |  |  |  |  |
| Surviving infants | 1,523,462 | 1,545,475 | 1,567,657 | 1,594,187 | 1,616,070 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 1,395,670 | 1,483,656 | 1,505,911 | 1,528,499 | 1,551,427 |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 1,465,548 | 1,468,201 | 1,490,224 | 1,512,578 | 1,535,266 |  |  |  |  |
| Hep B VACCINE |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Hep B (GAVI) | 1,228,128 | 1,218,607 | 1,236,886 | 756,289 |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of Hep B (GAVI) | 1,192,786 | 1,154,470 | 1,171,787 | 716,484 |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of Hep B Local) | 246,054 | 249,594 | 253,338 | 756,289 | 1,535,266 |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of Hep B (Local) | 242,294 | 236,458 | 240,005 | 716,484 | 1,454,463 |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** of Hep B (GAVI) | 12% | 10% | 8% | 8% |  |  |  |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** of Hep B (Local) | 18% | 18% | 18% | 18% | 15% |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 (90%) | 1,386,217 | 1,390,928 | 1,411,791 | 1,432,968 | 1,454,463 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * (96%) | 1,456,280 | 1,499,111 | 1,521,597 | 1,544,421 | 1,567,588 |  |  |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * (96%) | 1,479,514 | 1,468,201 | 1,490,224 | 1,512,578 | 1,535,266 |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The figure for 2004 survising infants os based on reports of real counts from provinces. It is diffrent from the figure reported in the 2nd APR (1,522,635). This modification was also made on JRF 2004 with footnote of explanations. Hep B vaccines support from GAVI will be continued until the end of June 2007 (letter from GAVI dated30 July 2004 stated that 756,289 children will received 1st dose of Hep B and 716,484 children will receive 3rd dose of Hep B instead of 0 in Second annual progress report in 2004. Infants will receive locally-produced Hep B vaccine from August 2007.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Please note that case making in every shipping box with following address of EPI: VIEN VE SINH DICH TE TRUNG UONG (NIHE) 1 YERSIN, HANOI, VIET NAM HANG VIEN TRO KHONG DUOC BAN

Table 4: Estimated number of doses of Hepatitis B  vaccine in 1 dose vial (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

Table 4: Estimated number of doses of Hepatitis B  vaccine in 2 dose vials(specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Shipment of Hep B vaccine 2006:

| Vaccine | Indicate delivery date | Quantity in doses |
| --- | --- | --- |
| Hep B (1 dose/vial) | November 2005 May 2006 | 700,000 723,846 |
| Hep B (2 doses/vial) | December 2005 June 2006 | 1,400,000 1,408,851 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6a: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### Table 6b: Estimated supplies for safety of vaccination for the next two years with DPT

Table 6c: Estimated supplies for safety of vaccination for the next two years with measles

#### Table 6d: Estimated supplies for safety of vaccination for the next two years with TT

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| HBV3 coverage | 85% | 94.2% (includes GAVI and local vaccine) (GAVI 94%, local 95%) | The rate of HBV3 in 35 of 667 districts below 80% | No change |
| Drop out rate HBV3 | <10% | 1.5% for local, and 2.9% for GAVI vaccine | Late introduction of GAVI vaccine compare with local | No change |
| Wastage rate of HepB vaccine and other EPI vaccines. | 20% for HepB vaccine. For OPV, DTP and measles vaccines, allowed wastage rates are 33%. | Wastage rate of HepB for GAVI vaccine was 10% and local vaccine, 15%. This reflects the fact that local vaccine is being used in more remote areas where wastage reduction is more difficult. Wastage rates for OPV, DPT and measles vaccines were 35%. | Wastage rates for other vaccines were 35%. Supply of local vaccines in 20-dose vials limits capacity to reduce wastage | 10% for HepB |
| DPT3 coverage |  90% | 96.2% | The fund from government purchase of 6.5million doses of DPT include 5.5 million doses local production (70% requirement). DPT will be in short supply for 2005 if supply from UNICEF have problem. | No change |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  | May 2005 |
| Reporting Period (consistent with previous calendar year) |  | Jan to Dec 2004 |
| Table 1 filled-in |  | Yes |
| DQA reported on |  | N/A |
| Reported on use of 100,000 US$ |  | N/A |
| Injection Safety Reported on |  | Yes |
| FSP Reported on (progress against country FSP indicators) |  | Yes (2004) |
| Table 2 filled-in |  | Yes |
| New Vaccine Request completed |  | Yes |
| Revised request for injection safety completed (where applicable) |  | Yes |
| ICC minutes attached to the report |  | Yes |
| Government signatures |  | Yes |
| ICC endorsed |  | Yes |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |

~ End ~