Revision 3

August 2001

The Government of

The Lao People's Democratic Republic

Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Executive Summary

# The Vaccine Fund approved Lao PDR’s application for introduction of hepatitis B vaccine in the first round.  The Government of Lao PDR is now applying for Immunisation Services Sub-Account (ISS) and for Injection Safety support.

For the ISS, the baseline reported number of children (under one year old) who received DTP3 in 2000 was 101,515 (49%), and targets are for 188,306 (80%) in 2003, increasing to 209,068 (90%) by 2005.  These coverage targets are as previously submitted to GAVI.  They are challenging, but as an additional 55,552 were reported to have received DTP3 aged over one year, the major challenge will be to increase timeliness of delivery.

Improving coverage will require these actions:

- Strengthen the planning and monitoring capacity at province and district level.

- Increase supervision to reduce drop-out and improve programme quality.

- Pilot a register of children for follow-up and for a more accurate denominator than current 4% estimate.

- Increase sites offering monthly immunization

- Increase number of rounds of immunization to at least six rounds a year for at least 60% of districts.

A study is planned for early 2002 to identify the costs and strategies to reach increasing levels of coverage up to the 95% required for measles control.

For Injection Safety support, the national policy, strategic plan (2001-2005) and a 2002 workplan are submitted. To build on existing plans, the Government of Lao PDR requests the injection safety support as safe injection materials (%) and a cash grant (%). The funds will be used for injection safety activities proposed in the 2002 workplan to enable introduction of AD syringes for all EPI vaccines by 2003, in addition to those being funded by partners.

The Government of Lao PDR is committed to continuing use of ADs and safe disposal, beyond the three years of Vaccine Fund support.

# Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of Lao PDR commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests the Alliance and its partners to contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature:	…………………………………………...Dr. PoneMek DARALOY

Title:	…………Minister of Health………………………………...

Date:	………September 25, 2001…………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal does not imply any financial (or legal) commitment on the part of the partner agency or individual:

| Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- |
| WHO | Dr. G. Deodato Representative |  |
| UNICEF | Ms. I. Zalitis Representative |  |
| Ausaid | Ms. Penny Bond First Secretary of Australian Embassy |  |
| Department of Hygiene and Prevention, MOH | Dr. Bounlay PH. Deputy Director |  |
| Department of General Education, MOE | Mr. Kongphachanh Deputy Director |  |
| Depart. of Women Development and Interest Central LWU | Mrs. Khammanh General Director |  |
| Secretariat of the National Commission for Mother and Child | Ms. Khantharasy S. Head of Division |  |

In case the GAVI Secretariat have queries on this submission, please contact :

Name : Dr Somthana Douangmala,

National EPI manager, Deputy Director of MCH centre.

National Centre for Mother and Child Health, MOH, Vientiane

Tel.No. : 856 21 350027…  		   Fax No. :… 856 21 350067..

E-mail :……… somthdml@laotel.com

Alternative address :

Name : Dr Bouavanh Senesathith		Title/Address : Director of MCH centre.

Tel.No. : 856 21 214038.   	Fax No. : 856 21 214037

E-mail :……………………………                         ……………………………….

- Immunization-related fact sheet

In previous application

# Profile of the Inter Agency Co-ordinating Committee (ICC)

In previous application

# Immunization services assessment(s)

In previous application

# Multi-Year Immunization Plan

In previous application.

Baseline data for year 2000 on DTP3 numbers are:

under one year olds: 	101,515 (49%)

over one year olds:	 55,552 (27%)

Targets are as previously submitted:

| Table 4 : Annual targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| Infant Population | 211,273 | 216,344 | 221,536 | 226,853 | 232,297 |
| BCG Coverage (%) | 80 | 80 | 85 | 90 | 90 |
| Infants vaccinated | 169,019 | 173,075 | 188,306 | 204,168 | 209,068 |
| OPV Coverage Targets (%) | 80 | 80 | 85 | 90 | 90 |
| Infants vaccinated | 169,019 | 173,075 | 188,306 | 204,168 | 209,068 |
| DTP-Hep B3 Coverage (%) | 80 | 80 | 85 | 90 | 90 |
| Target Pop. (phased introd.) | 3,156 | 62,559 | 221,536 | 226,853 | 232,297 |
| Infants vaccinated | 2,525 | 50,047 | 188,306 | 204,168 | 209,068 |
| DTP3 Coverage Targets (%) | 80 | 80 | 85 | 90 | 90 |
| Target Pop. (phased withdrawal) | 208,117 | 153,785 | 0 | 0 | 0 |
| Infants vaccinated | 166,494 | 123,028 | 0 | 0 | 0 |
| Measles Coverage (%) | 80 | 80 | 85 | 90 | 90 |
| Infants vaccinated | 169,019 | 173,075 | 188,306 | 204,168 | 209,068 |
| TT for PW Coverage (%) | 40 | 40 | 40 | 50 | 60 |
| TT for CBAW Coverage (%) | 30 | 30 | 30 | 35 | 35 |
| Women vaccinated | 369,728 | 378,602 | 387,688 | 470,720 | 505,247 |

Summary of major action points for improving immunization coverage:

- Strengthen the planning and monitoring capacity at province and district level.

- Increase supervision to reduce drop-out and improve programme quality..

- Pilot a register of children for follow-up and for a more accurate denominator than current 4% estimate.

- Increase sites offering monthly immunization

- Increase number of rounds of immunization to at least six rounds a year for at least 60% of districts.

# Injection safety

7.1	Summary of the injection safety strategy for immunization

The target is to have 100% of immunization injections given with AD syringes that are properly disposed of in safety boxes and effectively incinerated by 2005.

A phased introduction during 2002 and 2003, by province, is planned in line with availability of incinerators in each province and following on from the immunization campaigns that are planned and where ADs will be used.  The specific objectives of the 2002 workplan are to:

- phased introduction of ADs for EPI vaccines in provinces introducing Hepatitis B vaccine.

- establishing adequate incineration facilities for provinces introducing Hepatitis B vaccine.

- piloting and establishing an ‘exchange strategy’ for used injection materials.

- increasing health worker knowledge and practice on safe injection and disposal.

- increasing community awareness of the importance of safe injection and disposal.

| - Attached are copies of national policy, Strategic Plan of Action for 2001-2005 to improve Injection Safety for EPI vaccines, and 2002 Workplan | Document numbers 1-3. |
| --- | --- |

7.2	Injection safety equipment

The following tables calculate the amount of supplies requested for injection safety:

| Table 6.1 : Estimated supplies for BCG Vaccine |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2002 | 2003 | 2004 | 2005 |
| Target no. of children | 173,075 | 188,306 | 204,168 | 209,068 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 173,075 | 188,306 | 204,168 | 209,068 |
| AD syringes (+10%) | 192,113 | 209,019 | 226,626 | 232,065 |
| AD syringes buffer (25%) | 48,028 | 4,226 | 4,402 | 1,360 |
| Total AD syringes | 240,142 | 213,246 | 231,028 | 233,425 |
| Doses per vial | 20 | 20 | 20 | 20 |
| Wastage factor | 4.0 | 4.0 | 4.0 | 4.0 |
| Effective doses per vial | 5.0 | 5.0 | 5.0 | 5.0 |
| Reconst.syringe | 38,423 | 41,804 | 45,325 | 46,413 |
| Safety boxes (+10%) | 3,092 | 2,831 | 3,068 | 3,106 |
| Table 6.2 : Estimated supplies for Measles Vaccine |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 |
| Target no. of children | 173,075 | 188,306 | 204,168 | 209,068 |
| Doses per child | 1 | 1 | 1 | 1 |
| Total no. of doses | 173,075 | 188,306 | 204,168 | 209,068 |
| AD syringes (+10%) | 192,113 | 209,019 | 226,626 | 232,065 |
| AD syringes buffer (25%) | 48,028 | 4,226 | 4,402 | 1,360 |
| Total AD syringes | 240,142 | 213,246 | 231,028 | 233,425 |
| Doses per vial | 10 | 10 | 10 | 10 |
| Wastage factor | 2.0 | 2.0 | 2.0 | 2.0 |
| Effective doses per vial | 5.0 | 5.0 | 5.0 | 5.0 |
| Reconst.syringe | 38,423 | 41,804 | 45,325 | 46,413 |
| Safety boxes (+10%) | 3,092 | 2,831 | 3,068 | 3,106 |
| Table 6.3 : Estimated supplies for DPT Vaccine |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 |
| Target no. of children | 123,028 | 0 | 0 | 0 |
| Doses per child | 3 | 3 | 3 |  |
| Total no. of doses | 369,084 | 0 | 0 | 0 |
| AD syringes (+10%) | 409,683 | 0 | 0 | 0 |
| AD syringes buffer (25%) | 102,421 | 0 | 0 | 0 |
| Total AD syringes | 512,103 | 0 | 0 | 0 |
| Safety boxes (+10%) | 5,684 | 0 | 0 | 0 |
| Table 6.4 : Estimated supplies for DTP-HepB Vaccine |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 |
| Target no. of children | 50,047 | 188,306 | 204,168 | 209,068 |
| Doses per child | 3 | 3 | 3 | 3 |
| Total no. of doses | 150,142 | 564,917 | 612,503 | 627,203 |
| AD syringes (+10%) | 166,657 | 627,058 | 679,878 | 696,195 |
| AD syringes buffer (25%) | 41,664 | 12,679 | 13,205 | 4,079 |
| Total AD syringes | 208,321 | 639,737 | 693,083 | 700,274 |
| Safety boxes (+10%) | 2,312 | 7,101 | 7,693 | 7,773 |
| Note: buffer stock adjusted for cohorts switching from DTP |  |  |  |  |
| Table 6.5 : Estimated supplies for TT Vaccine |  |  |  |  |
|  | 2002 | 2003 | 2004 | 2005 |
| Target no. of women | 369,728 | 378,602 | 387,688 | 470,720 |
| Doses per woman | 2 | 2 | 2 | 2 |
| Total no. of doses | 739,456 | 757,203 | 775,376 | 941,439 |
| AD syringes (+10%) | 820,797 | 840,496 | 860,668 | 1,044,998 |
| AD syringes buffer (25%) | 205,199 | 4,925 | 5,043 | 46,083 |
| Total AD syringes | 1,025,996 | 845,420 | 865,710 | 1,091,080 |
| No. Of safety box (+10%) | 11,389 | 9,384 | 9,609 | 12,111 |
| Table 6.6 : Summary of total injection safety supplies (incl. DTP-HepB) |  |  |  |  |
| ITEM | 2002 | 2003 | 2004 | 2005 |
| Total AD syringe (BCG) | 240,142 | 213,246 | 231,028 | 233,425 |
| Total AD syringes (all other) | 1,986,562 | 1,698,403 | 1,789,821 | 2,024,779 |
| Total Reconst. Syringes | 76,845 | 83,608 | 90,650 | 92,826 |
| Total Safety boxes | 25,569 | 22,147 | 23,438 | 26,096 |
| Table 6.7 : Costs of total injection safety supplies (incl. DTP-HepB) |  |  |  |  |
| ITEM | 2002 | 2003 | 2004 | 2005 |
| Total AD syringe (BCG) | $16,330 | $14,501 | $15,710 | $15,873 |
| Total AD syringes (all other) | $135,086 | $115,491 | $121,708 | $137,685 |
| Reconst. Syringes | $3,458 | $3,762 | $4,079 | $4,177 |
| Safety boxes | $14,319 | $12,403 | $13,125 | $14,614 |
| UNICEF service charge (6%) | $10,272 | $8,890 | $9,398 | $10,461 |
| TOTAL | $179,464 | $155,047 | $164,020 | $182,810 |

In 2002, the ADs will be progressively implemented as incinerators become operational in each province (see 2002 workplan), as each province introduces DTP-HepB vaccine.  The phasing is shown in Table 7.1:  As a result of the phasing only 42% of the annual need will be required in 2002.  The remaining support is requested in the forms of funds to enable implementation of the 2002 workplan (Table 7.2).

| Table 7.1. AD introduction start, by province, in 2002 |  |  |  |
| --- | --- | --- | --- |
| Province | % of total | Start | Adjusted |
|  | population | month | Usage |
| Khammouane | 6.0% | Jan | 6.0% |
| Vientiane M | 11.5% | May | 7.7% |
| Lunge Prabang | 8.0% | Jun | 4.7% |
| Champasack | 10.9% | Oct | 2.7% |
| Houaphanh | 5.4% | Nov | 0.9% |
| Vientiane P | 6.2% | Nov | 1.0% |
| Sayaboury | 6.4% | Nov | 1.1% |
| Phongsaly | 3.3% | Dec | 0.3% |
| Xiengkhouang | 4.4% | Dec | 0.4% |
| Oudomxay | 4.6% | Dec | 0.4% |
| Total | 66.7% |  | 25.1% |
| Total 2002 need (adjusted for buffer stock) |  |  | 42% |
| Note: remaining 8 provinces will have ADs introduced in 2003 |  |  |  |

| Activity | Time (2002) | Source | Budget |
| --- | --- | --- | --- |
| Incinerator/Disposal |  |  |  |
| Install and build housing structure for auto-combustion incinerators in 7 provinces introducing Hepatitis B vaccine. | Jan-Dec | WHO/ AusAID | $78,000 |
| Training of provincial focal persons on incinerator use | Jan-Dec | WHO | $7,000 |
| Autodisable syringes and safety boxes |  |  |  |
| Evaluate Khamouane pilot introduction of ADs. | Mar | Fund | $7,000 |
| ADs and safety boxes into routine EPI in 10 provinces | May-Dec | Fund | (below) |
| Pilot ‘exchange strategy’ | Jan-Mar | WHO | $3,000 |
| Implement ‘exchange strategy’. | May-Dec | Fund | $8,000 |
| Practice |  |  |  |
| Supervision/Training of health worker practice and incineration (including transport) - in each province | Jan-Dec | Fund | $90,000 |
| Community awareness |  |  |  |
| Development and dissemination of IEC materials | Jun-Dec | UNICEF | $15,000 |
| Media campaign | Oct-Dec | UNICEF | $25,000 |
|  |  | TOTAL | $233,000 |
|  |  | Fund | $105,000 |
|  |  | Partners | $128,000 |

# New and under-used vaccines

No new application

# Strategic directions to mobilise additional resources for immunization

In previous application.

# Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above the Government of Lao PDR considering that its reported DTP3 coverage for 2000 (for children under one year) was 49% corresponding to 101,515 children vaccinated with DTP3, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund.

- Support for Immunization Services                       YES

- Support for New and Under-used vaccines                                 NO

- Support for Injection Safety                                  YES

10.1	SUPPORT FOR IMMUNIZATION SERVICES

GAVI and the Vaccine Fund are requested to fund the strategies for strengthening immunization services in year 2002 according to the number of additional children (as compared to the baseline) that are targeted to be immunized with DTP3 as presented in table 4, namely 67,504 children (DTP + DTP-HepB for 2002 increase over 2001). Funds will also be requested for following years as estimated in table 4.

- The Government takes full responsibility to manage the in-country transfer of funds.

(In case an alternative mechanism is necessary please describe it and the reasons for it:)

- Operational mechanism that is followed for safeguarding transparency, standards of accounting, long-term sustainability and empowerment of the government in using the funds:

The mechanism for receiving the funds are still being finalised with details to be sent to GAVI before the end of October.  The funds will be sent to the Ministry of Health Bank Account and then immediately transferred to a new EPI Bank Account.

It is planned to establish a bank account for the EPI that will have a full-time accountant to manage the funds and ensure that disbursements are in line with the plan for these funds.  The EPI will have the management responsibility with periodic reporting to the ICC on the status and use of the funds.  The account will be monitored by the Ministry of Health Planning and Finance Department and with an annual independent external audit.

- Countries requesting immunization services support should submit the “Banking Details” form (Annex 3) with their proposal

  - SUPPORT FOR NEW AND UNDER-USED VACCINES

N/a

  - SUPPORT FOR INJECTION SAFETY

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing:

The amount of supplies listed in table 8  (42% of 2002 need)

The equivalent amount of funds (remaining 58%)

| Table 8: Summary of support requested from GAVI and the Vaccine Fund |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM | 2002 | 2003 | 2004 | 2005 |
| Total AD syringe (BCG) | 100,255 | Tba | 0 | 0 |
| Total AD syringes (all other) | 829,353 | Tba | 0 | 0 |
| Total Reconst. Syringes | 32,081 | Tba | 0 | 0 |
| Total Safety boxes | 10,675 | Tba | 0 | 0 |
| Cash | $104,541 | Tba | tba | 0 |
| tba - request for 2003 to be advised by September 2002 with 2003 workplan |  |  |  |  |

# Additional comments and recommendations from the ICC

ANNEX  1

Summary of documentation

Document 1: National policy on injection safety

Document 2:  Strategic Plan of Action for 2001-2005 to improve Injection Safety for EPI vaccines

Document 3: 2002 Workplan to improve Injection Safety for EPI vaccines

ANNEX  2

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Details |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on support to immunization services made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , the Government of Lao PDR hereby requests that a payment be made, via electronic bank transfer, as detailed below : |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution : (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address : |  |  |  |  |  |  |  |  |  |  |
| #### City – Country : |  |  |  |  |  |  |  |  |  |  |
| Telephone No. : |  |  |  | Fax No. : |  |  |  |  |  |  |
| #### Amount in USD : |  | ( To be filled in by GAVI Secretariat ) |  |  | Currency of the bank account : |  |  |  |  |  |
| For credit to : Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No. : |  |  |  |  |  |  |  |  |  |  |
| At : Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited ? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official : |  |  |  |  |  |  |  |  |  |  |
| #### Name : |  |  |  |  |  |  |  |  | Seal : |  |
| #### Title : |  |  |  |  |  |  |  |  |  |  |
| #### Signature : |  |  |  |  |  |  |  |  |  |  |
| Date : |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 ( To be completed by the Bank ) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name : |  |  |  |  |  |
| Branch Name : |  |  |  |  |  |
| Address : |  |  |  |  |  |
| City – Country : |  |  |  |  |  |
| Swift code : |  |  |  |  |  |
| Sort code : |  |  |  |  |  |
| ABA No. : |  |  |  |  |  |
| Telephone No : |  |  |  |  |  |
| Fax No : |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories : |  |  | Name of bank’s authorizing official : |  |  |
| 1 Name : Title : |  |  | Signature : |  |  |
|  |  |  | Date: |  |  |
| 2 Name : Title : |  |  | Seal: |  |  |
| 3 Name : Title : |  |  |  |  |  |
| 4 Name : Title : |  |  |  |  |  |

COVERING LETTER

(To be completed by UNICEF representative on a letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Tore Godal

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials : |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of UNICEF Representative : |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |