The Government of

THE REPUBLIC OF GHANA

Proposal for support submitted

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Global Fund for Children’s Vaccines

(The Fund)

This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF; Palais des Nations; 1211 Geneva 10; Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.ch or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

# Signatures of the Government

The Government of  The Republic of Ghana commits itself to develop the national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document, and to annually review districts performance on immunization through a transparent monitoring system. The Government hereby requests the Alliance and its partners to contribute to the unmet needs for financing, material and technical assistance required in accordance with the plan.

Signature:  Dr Moses Adibo

Title:    Deputy Minister of Health

Date:	…………………………………………...

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached :

| Agency/Organization | Name/Title | Signature |
| --- | --- | --- |

Signed this day of : _____________/2000

In case the GAVI Secretariat have queries on this submission, please contact :

Name :  Dr Mercy Essel Ahun	Title/Address : EPI Programme Manager

Tel.No. :  233-24-325118   		            Disease Control Unit

Fax No  233-21-667980 		           P. O. Box KB 493

E-mail : meahun@hotmail.com               Korle-Bu, Accra, GHANA

- Immunization-related fact sheet

| Basic facts: (1998 or most recent; specify dates of data provided) |  |  |  |
| --- | --- | --- | --- |
| Population | 19,483,980 (1999) | GNP per capita | $US390.00 ( 1999) |
| Infants 0-11 months | 779,359 (1999) | Infant mortality rate | 67/ 1000 (1998) |
| Percentage of GDP allocated to Health | 5.6% (1999) | Percentage of Government expenditure for Health Care | 8.4% (1999) |

| Health system development status |  |
| --- | --- |
| Please find attached background documentation on: |  |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number 2 |
| - Status of the ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies and practices on private sector participation, as it relates to immunization | Document number 4 |

| ### Immunization coverage trends As per annual reporting to UNICEF/WHO |  |  |  |  | Vaccine preventable disease burden As per annual reporting to UNICEF/WHO |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine | Reported % |  | Survey % |  | Disease | Reported cases |  | Estimated cases/deaths |  |
|  | 1998 | 1999 | 1998 (DHS) | 1999 |  | 1998 | 1999 | 1998 | 1999 |
| BCG | 77.4 | 84.5 | 87.8 | NA | Diphtheria | 0 | 0 | 0 | 0 |
| DTP3 | 68.0 | 73.0 | 72.2 | NA | Pertussis | 796 | 749 | 796/1 | 496/1 |
| OPV3 | 69.0 | 73.4 | 72.2 | NA | Polio | 22 | 3 | 22/0 | 3/0 |
| Measles | 67.0 | 71.4 | 72.6 | NA | Measles | 23064 | 15987 | 23064/4 | 15987/2 |
| TT2+ Pregnant Women | 58.3 | 57.7 | 51.6 | NA | NN Tetanus | 100 | 78 | 100/26 | 66/17 |
| Hib | NA | NA | NA | NA | Hib | NA | NA | NA | NA |
| Yellow Fever | 41.0 | 64.0 | 38.9 | NA | Yellow fever | 0 | 0 | 0 | 0 |
| Hep B | NA | NA | NA | NA | Hep B seroprevalence (if available) | 5-20% |  |  |  |

# Profile of the Inter Agency Coordinating Committee (ICC)

(Various agencies and partners supporting immunization services in the country are coordinated and organized through an inter-agency coordinating mechanism which is referred to in this document as ICC)

- Name of the ICC…Inter Agency  Coordinating Committee

- Date of constitution of the current ICC   2 years ago

- Organizational structure (e.g., sub-committee, stand alone)  stand alone

- Frequency of meetings   Quarterly

- Composition :

| Function | Title / Organization | Name |
| --- | --- | --- |
| Chair | Director, Public Health Division/MOH | Dr Sam Bugri |
| Secretary | Programme Manager General EPI/MOH | Dr Mercy Essel Ahun |
| Members | - Deputy Director General/ Ghana Health Service - Deputy Director (Public Health) Disease Control & Surveillance/MOH - Deputy Director (Public Health) Family Health/MOH - Head, Disease Control/MOH - DPC/WHO - Health Officer/UNICEF - Child Health Adviser/USAID - Health Officer/JICA - Health Officer/DFID - Health officer/Rotary - Rep., Paediatric Society of Ghana - Director, Noguchi Memorial Institute for Medical Research | Dr Sam Adjei Dr George Amofah Dr Henrietta Odoi – Agyarko Dr Samuel Sackey Dr Fenella Avokey Dr Victor Ankrah Dr Bob Pond Mr Matthew Dally Dr Victor Bampoe Mr Robert Atta Dr Onike Rodrigues Prof David Ofori-Adjei |

- Major functions and responsibilities :

- Provide technical support, policy direction and review and endorse EPI Action Plans, including those for routine services, diseases control and surveillance - Mobilise resources and assist the EPI Programme in enhancing transparency and accountability - Encourage information sharing with the implementing levels and with partners outside the country

- The following diagram shows the ICC functional relationships with other institutions in health sector :

SEE ATTACHED

Find attached the following documents :

| - Terms of reference of the ICC | Document number…5……. |
| --- | --- |
| - Minutes of the three most recent ICC meetings or of any meetings in which partners participated that concerned improving and expanding the national immunization program | Document number……6……. |

# Immunization services assessment

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

- Assessments, reviews and studies of immunization services for current reference :

| Title of the assessment | Main participating agencies | Dates |
| --- | --- | --- |
| Improving Child Health Services in Ghana : Assessments of Nutrition, EPI, and Community – Level Programs | MOH, USAID, BASICS, LINKAGES, UNICEF, WHO | June 8 – 26 1998 |

- The following are the three major problems identified in the assessments :

- Inadequate cold chain equipment at health facilities - Little familiarity with the use of local data for monitoring, evaluation and planning at the district or sub-district level - Low priority given to seeking vaccination services by care givers in spite of high awareness of immunisations

- The following are the three major recommendations in the assessments :

- Continue efforts to increase the number of subdistrict health facilities equipped with cold chain equipment and trained personnel to provide immunisation services - Develop approaches to increase the use of data at the district and subdistrict levels for planning, monitoring and evaluating immunisation services - Design and implement targeted communication efforts to increase utilisation of immunisation services by caretakers

- Find attached a complete copy (with an executive summary) of :

| - the most recent assessment report on the status of immunization services | Document number….7. |
| --- | --- |
| - a list of the recommendations of the assessment report with remarks on the status of their implementation i.e. included in workplan, implemented, not implemented, in progress…. | Document number…8.. |

- The following components or areas of immunization services are yet to be reviewed (or studied). They will be assessed on the following dates.

| ##### Title of the assessment | Year | USD |
| --- | --- | --- |
| Cold chain and Logistics Survey | 2001 | 30,000 |

# Multi-Year Immunization Plan

Based upon the recommendations of the assessment of immunization services, the Government has developed (or updated) the multi-year immunization plan or adjusted the health sector plan.

| - Please find attached a complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number…9…. |
| --- | --- |

- As per 1999 annual report to UNICEF/WHO

| 1999 |  |
| --- | --- |
| Children vaccinated with DTP3 | 567197 |
| Used doses of DTP | 2,235,850 |

- Estimated annual targets (Projected from 1984 census)

|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- |
| Children planned to be vaccinated with DTP3 | 594028 | 620117 | 647237 | 675426 | 704723 | 735171 |
| Doses of DTP planned to be used | 2784507 | 2906798 | 3009652 | 3115402 | 3224108 | 3308269 |

# New and under-used vaccines

Find below a summary of those aspects of the plan, mentioned in section five,  that refer to introduction of new and under-used vaccines.

- Assessment of burden of relevant diseases (if available):

| Disease | Title of the assessment | Date | Results |
| --- | --- | --- | --- |
| Hepatitis B infection | Seroepidemiological Survey of hepatitis B and C virus infection in Ghanaian chidren | 1993 | 15.8% HbsAg carriage |
| Hepatitis B infection | Hepatitis B viral markers in pregnant women | 1994 | 6.4% HbsAg carriage 18% HbeAg carriage |

- (If monovalent vaccine is requested) Hereunder is the rationale for the choice of monovalent vaccine :

NOT APPLICABLE

- Planning for hepB vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 826,822 (75%) | 851,627 (76%) | 877,176 (77%) | 903,491 (78%) | 930,596 (79%) |
| Total vaccine doses required | 2,906,798 | 3,009,652 | 3,115,402 | 3,224,108 | 3,308,269 |
| Preferred vial size(s) | 10 | 10 | 10 | 10 | 10 |
| Estimated wastage rate | 25% | 24% | 23% | 21% | 20% |
| % of vaccines requested from the Fund | 95 | 94 | 93 | 91 | 90 |
| AD syringes | 2,906,798 | 3,009,652 | 3,115,402 | 3,224,106 | 3,308,269 |

- Planning for Hib vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group |  |  |  |  |  |
| Total vaccine doses required |  |  |  |  |  |
| Preferred vial size(s) |  |  |  |  |  |
| Estimated wastage rate |  |  |  |  |  |
| % of vaccines requested from the Fund |  |  |  |  |  |
| AD syringes |  |  |  |  |  |

- Planning for yellow fever vaccinations :

|  | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- |
| Target group | 826822 (64%) | 851627 (65%) | 877176 (68%) | 903491 (70%) | 930596 (72%) |
| Total vaccine doses required | 826823 | 858015 | 917088 | 964476 | 1005045 |
| Preferred vial size(s) | 10 | 10 | 10 | 10 | 10 |
| Estimated wastage rate | 25% | 24% | 23% | 22% | 20% |
| % of vaccines requested from the Fund | 96* | 95 | 94 | 93 | 92 |
| AD syringes | 826822 | 858015 | 917088 | 964476 | 1005045 |

| - Find attached the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate page and paragraphs) | Document number…10… |
| --- | --- |

# Unmet needs requiring additional resources

| - Tables of expenditure for 1999 and resource needs (other than new vaccines) detailing the sources of funds for each line item and for each year are attached in Annex 1. | Document number .11…. |
| --- | --- |

- Find below a list of financial sustainability strategies and of current/projected financing mechanisms for immunization including agreements made with other agencies (i.e.: Vaccine Independence Initiative). The relevant documents are attached.

(USD ,000)

| Strategy title / Line item | Partner1 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Document number |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine Stabilisation fund/ procurement of vaccines | UNICEF | 54.661 |  | 485.436 |  | 513.743 |  |  |  | 12 |
| Government commitment |  |  | 80 | 500 | 550 | 580 | 600 | 650 | 700 |  |
| Other donors |  | 800 | 750 | 900 |  |  |  |  |  |  |
| Specify contributions in USD made by each partner sharing the strategy (Government, name of donor…) |  |  |  |  |  |  |  |  |  |  |

| - We summarize hereunder the support to immunization generated from the poverty reduction strategies (including the use of funds freed by debt relief), of which relevant pages are attached. | Document number…… |
| --- | --- |

NOT APPLICABLE

# Preferred channel of funds

(Only for countries seeking support from the immunization services sub-account)

- From the immunization services sub-account, funds will be transferred to the country through the following channel or system (tick only one) :

| Directly to the Government |  | Through a partner agency |  | Through an independent third party |  |
| --- | --- | --- | --- | --- | --- |

- In the following box we describe how the mechanism will operate and how it will address transparency, standards of accounting, long-term sustainability and empowerment of the government.

The funds should be preferrably transferred to the Ghana Health Service (GHS) .The EPI Programme will then submit estimates on budget items to the ICC. The agreed budget will be submitted through the Director, Public Health to the Director General of the Ghana Health Service. Funds will be released to the programme through the Financial Controller of the Ghana Health Service. This will ensure that the funds can be monitored both by the ICC and the GHS Ssystems. At its quarterly meetings , the ICC will monitor progress on use of funds. Quarterly reports and financial returns will be discussed at ICC meetings and copies of such reports submitted to the Director General and the ICC. The accounts will be audited both through the GHS accounting system and any other external auditing systems.

# Country concerns

The following are the ICC’s concerns and recommendations while submitting this proposal :

The concerns of the ICC are mainly on the financial sustainability of the current EPI and this initiative ; given the downturn of the economy globally, it is unlikely that Ghana will be self sufficient in vaccine procurement within the next five to ten years.The ICC expects that support from GAVI and other traditional partners will continue well beyond the stipulated five years of assistance. The ICC while noting other operational costs borne by the Ghana Health Service, will encourage government to gradually increase contributions for procurement of vaccines and injection safety materials. The ICC notes the insreases in immunisation coverage over recent years and commits itself to consistently work on reviewing immunisation coverage regularly and monitoring key indicators.

ANNEX 1

#### Statement of financing and of unmet needs for immunization (USD ,000)

Table 1

| Expenditure in 1999 from different sources |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | Private sector | DDFID | USAID | Japan Embassy | WHO | UNICEF | Total Expend-iture in 1999 |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 80 |  |  | 646,484 |  |  |  |  | 727 |
| 1.2 | - Procurement of injection materials & safety boxes |  |  |  | 473,707 |  |  |  |  | 473,707 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  | 110,121 |  | 878.693 |  |  | 989 |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  |  | 5 |
| 2.3 | Procurement & installation of subnational cold store |  |  |  | 104,207 |  |  |  |  | 104,207 |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  |  |  |  |  |  |  |  |
| 3.2 | - Training |  |  |  |  | 80 |  |  |  | 80 |
| 3.3 | - Printing of road to Health cards, tally sheets | 103,163 |  |  |  |  |  |  | 10.675 | 114 |
| 3.4 | - Surveillance |  |  |  |  |  |  | 215 |  | 215 |
| 3.5 | - District EPI surveys |  |  |  |  | 16.4 |  |  |  | 16,4 |
| 3.6 | - Mini Mass Campaigns |  |  |  |  | 21.8 |  |  |  | 21,8 |
| 3.7 | - National Immunisation Days |  |  |  |  |  |  |  |  |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  |  |  |  |  |  |  |  |
| 3.9 | - Operational Research |  |  |  |  |  |  |  |  |  |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 76,571 |  |  |  |  |  |  |  | 76,571 |
| 4.2 | - Administration* | 18,105 |  |  |  |  |  |  |  | 18,105 |
| 4.3 | - Invest ment | 91,651 |  |  |  |  |  |  |  | 91,651 |
| Total expenditure in 1999 |  | 186,516 |  |  | 1335 | 119 | 878,693 | 215 | 10,675 | 189,075 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible.(Basket funding represents funds sent to the 10 regions) 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 2

| Budget for 1999 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 80 |  |  | 690 |  |  |  | 770 |  |
| 1.2 | Procurement of injection safety materials |  |  |  | 160 |  |  |  | 160 |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 110 | 683.1 |  | 794 |  |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  | 5 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  | 110 |  |  |  | 110 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  |  |  |  |  |  |  | 5 |
| 3.2 | - Training |  |  |  |  |  |  | 80 | 80 |  |
| 3.3 | - Printing of Road to Health Carda, tally sheets | 103.2 |  |  |  |  |  |  | 103,2 |  |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 185 | 185 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 19 |  |  | 19 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 22 |  |  | 22 |  |
| 3.7 | - National Immunisation Days |  |  |  |  |  | 749 | 2600 | 3349 |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 1579 |  |  |  |  | 1579 |  |
| 3.9 | - Operational Research |  |  |  |  |  |  |  |  |  |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 63,050 |  |  |  |  |  |  | 63,050 |  |
| 4.2 | - Administration** | 32,980 |  |  |  |  |  |  | 32,980 |  |
| 4.3 | - Investment | 93,705 |  |  |  |  |  |  | 93,705 |  |
| Total commitment |  | 189,924 |  | 1579 | 960 | 151 | 1433 | 2865 | 196,912 | 5 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 3

| Budget for 2000 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 80 |  |  | 690 |  |  |  | 770 |  |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 160 |  |  |  | 160 |  |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 110 | 683.1 |  | 793 | 662.327 |
| 2.2 | - Maintenance of cold chain equipment | 5 |  | 20 |  |  |  |  | 25 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  | 110 |  |  |  | 110 |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials | 10 |  |  |  |  |  |  | 10 | 100 |
| 3.2 | - Training | 10 |  |  |  | 10 |  |  | 20 | 200 |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 103.2 |  |  |  |  |  |  | 103,2 | 300 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 185 | 185 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 25 |  |  | 25 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 29 |  |  | 29 |  |
| 3.7 | - National Immunisation Days |  |  |  |  | 200 | 1013 | 880 | 2093 |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  |  |  |  | 400 |  | 400 |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 25 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 89.167 |  |  |  |  |  |  | 89,167 |  |
| 4.2 | - Administration** | 36.981 |  |  |  |  |  |  | 36,981 |  |
| 4.3 | - Investment | 97.190 |  |  |  |  |  |  | 97,190 |  |
| Total commitment |  | 432 |  | 20 | 960 | 374 | 2096 | 1065 | 4947 | 164,327 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 4

| Budget for 2001 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 100 |  |  | 950 |  |  |  | 1050 | 2821,459 |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 179 |  |  |  | 179 | 281,522 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 500 | 683.1 |  | 1184 | 662,327 |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  | 5 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials | 5 |  |  |  |  |  |  | 5 | 10 |
| 3.2 | - Training |  |  |  |  |  |  |  |  | 200 |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 103.2 |  |  |  |  |  |  | 103.2 | 300 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 255 | 255 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 30 |  |  | 30 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 32 |  |  | 32 |  |
| 3.7 | - National Immunisation Days |  |  |  |  |  |  | 2000 | 2000 |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 524 |  |  |  |  | 524 |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 50 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 95,315 |  |  |  |  |  |  | 95,315 |  |
| 4.2 | - Administration** | 38,812 |  |  |  |  |  |  | 38,812 |  |
| 4.3 | - Investment | 99,156 |  |  |  |  |  |  | 99,156 |  |
| Total commitment |  | 147 |  | 524 | 1129 | 562 | 683,1 | 2255 | 5601 | 4621,014 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible.(basket Funding represents funds sent to regions) 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 5

| Budget for 2002 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 120 |  |  | 924 |  |  |  | 1044 | 3074 |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 176 |  |  |  | 176 | 292,633 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 500 | 213 |  | 713 | 568,766 |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  | 5 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  |  |  |  |  |  |  | 5 |
| 3.2 | - Training |  |  |  |  |  |  |  |  |  |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 103.2 |  |  |  |  |  |  | 103,2 | 105 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 265 | 265 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 26 |  |  | 26 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 39 |  |  | 39 |  |
| 3.7 | - National Immunisation Days |  |  |  |  |  |  | 2000 | 2000 |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 590 |  |  |  |  | 590 |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 50 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 101,352 |  |  |  |  |  |  | 101,352 |  |
| 4.2 | - Administration** | 41,678 |  |  |  |  |  |  | 41,678 |  |
| 4.3 | - Investment | 98,178 |  |  |  |  |  |  | 98,178 |  |
| Total commitment |  | 470 |  | 590 | 1100 | 565 | 263 | 2265 | 5203 | 4615,075 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 6

| Budget for 2003 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 80 |  |  | 690 |  |  |  | 770 | 3189 |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 160 |  |  |  | 160 | 206,706 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  |  | 683.1 |  | 683,1 |  |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  | 5 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  |  |  |  |  |  |  | 5 |
| 3.2 | - Training |  |  |  |  |  |  |  |  |  |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 103.2 |  |  |  |  |  |  | 103,2 | 106 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 185 | 185 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 43 |  |  | 43 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 37 |  |  | 37 |  |
| 3.7 | - National Immunisation Days |  |  |  |  |  |  | 500 | 500 |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 500 |  |  |  |  | 500 |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 50 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 121,908 |  |  |  |  |  |  | 121,908 |  |
| 4.2 | - Administration** | 45,243 |  |  |  |  |  |  | 45,243 |  |
| 4.3 | - Investment | 93,704 |  |  |  |  |  |  | 93,704 |  |
| Total commitment |  | 94,060 |  | 500 | 850 | 80 | 683,1 | 685 | 96,859 | 185 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 7

| Budget for 2004 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 80 |  |  | 690 |  |  |  | 770 | 6207 |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 160 |  |  |  | 160 | 241.119 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 500 | 1100 |  | 1600 |  |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  | 5 |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  |  |  |  |  |  |  | 5 |
| 3.2 | - Training |  |  |  |  |  |  |  |  |  |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 1120 |  |  |  |  |  |  | 1120 | 107 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 215 | 215 |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 51 |  |  | 51 |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 56 |  |  | 56 |  |
| 3.7 | - National Immunisation Days |  |  |  |  |  |  |  |  |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 500 |  |  |  |  | 500 |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 50 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 121,5 |  |  |  |  |  |  | 121,5 |  |
| 4.2 | - Administration** | 56,908 |  |  |  |  |  |  | 56,908 |  |
| 4.3 | - Investment | 121,9 |  |  |  |  |  |  | 121,9 |  |
| Total commitment |  | 58,357 |  | 500 | 850 | 607 | 1100 | 215 | 61629 | 164 |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

Table 8

| Budget for 2005 (Fill in a similar table for subsequent years) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Contributions committed by partners |  |  |  |  |  |  | Total projected needs | Unmet needs |
| Ref. # | Category / Line item | Central Govern-ment | Local Govern-ment | UNICEF | DFID | USAID | Japan Embassy | WHO |  |  |
| 1. | Vaccines, AD syringes… |  |  |  |  |  |  |  |  |  |
| 1.1 | - Procurement of vaccines | 150 |  |  | 950 |  |  |  |  | 3395 |
| 1.2 | - Projection of injection materials & safety boxes |  |  |  | 215 |  |  |  |  | 251,262 |
| 2. | Equipment (cold chain, spare parts, sterilization…) |  |  |  |  |  |  |  |  |  |
| 2.1 | - Cold Chain Equipment |  |  |  |  | 500 | 1178 |  |  |  |
| 2.2 | - Maintenance of cold chain equipment | 5 |  |  |  |  |  |  |  |  |
| 2.3 P | Procurement & installation of subnational cold store |  |  |  |  |  |  |  |  |  |
| 3. | Other item immunization specific |  |  |  |  |  |  |  |  |  |
| 3.1 | - Production of education materials |  |  | 5 |  |  |  |  |  | 5 |
| 3.2 | - Training |  |  | 10 |  |  |  |  |  |  |
| 3.4 | - Printing of Road to Health Carda, tally sheets | 1045 |  |  |  |  |  |  |  | 108 |
| 3.4 | - AFP Surveillance |  |  |  |  |  |  | 225 |  |  |
| 3.5 | - District EPI Surveys |  |  |  |  | 57 |  |  |  |  |
| 3.6 | - MiniMass Campaighns |  |  |  |  | 43 |  |  |  |  |
| 3.7 | - National Immunisation Days | B |  |  |  |  |  | 500 |  |  |
| 3.8 | - Neonatal Tetanus Elimination |  |  | 450 |  |  |  |  |  |  |
| 3.10 | - Operational Research |  |  |  |  |  |  |  |  | 50 |
| 4.0 | - Basket Funding |  |  |  |  |  |  |  |  |  |
| 4.1 | - Service* | 154,908 |  |  |  |  |  |  |  |  |
| 4.2 | - Administration** | 67,356 |  |  |  |  |  |  |  |  |
| 4.3 | - Investment | 101,765 |  |  |  |  |  |  |  |  |
| Total commitment |  |  |  |  |  |  |  |  |  |  |
| 1 If basket funding or a similar aggregated funding approach is used, please describe the total funding amounts, and/or detail partner contributions as fully as possible. 2 Please use the electronic version of the document and insert as many columns for partner contributions as are necessary for your submission 3 Please use the electronic version of the document to insert as many line items as necessary for your submission |  |  |  |  |  |  |  |  |  |  |

ANNEX 2

Summary of documentation requested

| Background information on Health System Development status |  |
| --- | --- |
| - Overall government health policies and strategies | Document number 1 |
| - Structure of the government health services at central, provincial and peripheral levels and how it relates to immunization services (with an organizational chart) | Document number 2 |
| - Ongoing or planned health reforms (e.g. decentralization, integration of functions, changes in financing) as it impacts on immunization services | Document number 3 |
| - Government policies on private sector participation, as it relates to Immunization. | Document number 4 |
| Profile of the Inter Agency Coordinating Committee (ICC) |  |
| - Terms of reference of the ICC | Document number 5 |
| - Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines | Document number 6 |
| Immunization Services Assessment |  |
| - Most recent, national assessment report on the status of immunization services | Document number 7 |
| - Summary of the recommendations of the assessment report with remarks on the status of implementation of each recommendation. | Document number 8 |
| Multi-Year Immunization Plan |  |
| - Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan. | Document number 9 |
| - Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs) | Document number 10 |
| Unmet needs requiring additional resources |  |
| - Tables of expenditure for 1999 and resource needs (Annex 1) | Document number 11 |
| - Agreement made with other agencies as sustainability strategy (i.e.: VII) | Document number 12 |
| - The priority given to immunization in the poverty reduction strategies for the use of funds freed by debt relief (for countries targeted in the HIPC initiative) | Document number…… |

Please submit hard copy documents with an additional electronic copy wherever possible