[image: image1.png]THE GLOBAL ALLIANCE FOR
VACCINES & IMMUNIZATION



[image: image2.png]THE GLOBAL ALLIANCE FOR
VACCINES & IMMUNIZATION




10
*** Valid for proposals submitted in 2002 ***


Revision 4 





     
August 2002

The Government of

	INDIA


Proposal for support submitted to the

Global Alliance for Vaccines and Immunization (GAVI)

and the Vaccine Fund


This document is accompanied by an electronic copy on diskette for your convenience. Please return a copy of the diskette with the original, signed hard-copy of the document to

GAVI Secretariat; c/o UNICEF, Palais des Nations, 1211 Geneva 10, Switzerland.

Enquiries please to: Dr Tore Godal, tgodal@unicef.org or representatives of a GAVI partner agency.  All documents and attachments must be submitted in English or French.

1. Executive Summary

GOVERNMENT OF INDIA

PROPOSAL FOR SUPPORT TO THE GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION AND THE GLOBAL FUND FOR CHILDREN’S VACCINES

PROJECT FOR SUSTANINING & IMPROVING THE COVERAGE OF 

HEPATITIS-B VACCINE IN THE EXISTING CITIES AND DISTRICTS AND 

INTRODUCTION OF AUTO-DISABLE SYRINGES 

IN IMMUNISATION PROGRAMME IN INDIA

 CONTINUATION OF HEPATITIS-B VACCINE IN THE EXISTING CITIES AND DISTRICTS:

India adopts a Five Year cycle of Planning and the Tenth Five Year Plan (2002- 2007) is currently underway. The World Health Organization had recommended the introduction of Hepatitis-B vaccine in the National Immunization Programs by 1997. The Ministry of Health & Family Welfare (MoHFW), Government of India (GOI) had recommended the pilot project of Hepatitis-B Immunization in the selected Cities and District before considering its expansion into Universal Immunization Program (UIP) during the Ninth Five Year plan. The pilot project of Hepatitis-B vaccination was introduced in the year 2002 with assistance from GAVI in 15 metropolitan cities and 33 districts of the country.  The introduction of Hepatitis-B vaccine was not considered until the year 2002, not only because of resource constraints but also due to the fact that the State Governments and the field staff were pre-occupied with activities related to the eradication of poliomyelitis.  

The various assessments of immunization services have clearly shown the areas where districts where routine immunization services need considerable strengthening. To address these needs expeditiously, in 1999-2000, the Government of India negotiated a large Immunization Strengthening Project of US $ 159 million, with the World Bank for an International Development Assistance (IDA) credit of US $ 143 million to cover costs for polio eradication, strengthening of routine immunization and new initiatives. The Immunization Strengthening Project, which became effective in 2000, addresses the critical program deficiencies such as weak management, supervision, logistics and demand generation for immunization services. In addition to the nation-wide support for mid-level manager training, cold chain strengthening and program monitoring being provided under the project, specific focus is being given to improve routine immunization services in eight low performing states under the ongoing RCH program. UNICEF-supported Border District Cluster program, which is being implemented in selected States, also gives high priority to strengthen routine immunization, in addition to other special State initiatives.

To oversee the activities related to Immunization Services, the Government has assigned an officer of the Assistant Commissioner level dedicated to routine immunisation work. The Government of India has also constituted a Technical Advisory Committee to advise Government on strengthening immunization services. In the area of capacity building at the State and District levels, initiatives that have already started are: State / District level assessment of the cold chain; assessment of injection safety in a representative sample of states and; Mid-level Immunization Managers’ training.

According to available scientific studies, the carrier-rate of Hepatitis-B in India has been estimated to be in the range of 2-10%. India is thus grouped under the intermediate zone of Hepatitis-B prevalence.

In view of these developments, the Government of India decided in November 2001 to launch a phased introduction of the Hepatitis-B vaccine in its National program. This phasing was essentially proposed to assess the operational feasibility of introducing a new antigen in the National program along with improved injection safety measures. To begin with, the project has been initiated in slum populations of 15 metropolitan cities (which are at high risk for Hepatitis-B) and districts that have been evaluated to have a high coverage (more than 80%) with currently used vaccines. A similar approach was used when India introduced the Universal Immunization Program in 1985.  The initial phase of the project has been conducted over a two-year period ending in December 2004. The Hepatitis-B vaccine is being administered along with the three doses of primary DPT vaccination in the above stated areas under the phase I of the project. For the present, the Monovalent Hepatitis-B vaccine is being used. When the combined DPT-Hepatitis-B vaccine becomes more easily available, the Government of India may consider the transition to the combination vaccine in the existing 33 districts and 15 cities.

Progress Achieved in the existing Hepatitis B Project Areas: The Hepatitis B vaccination was launched by the Prime Minister of India on June 10, 2002. After completing the trainings, immunization with Hepatitis-B Vaccine was started in Hyderabad city by Nov. 2002.  11 other cities started Hepatitis-B immunization by March 03. Of the remaining three cities Hepatitis B immunization started in two cities in last quarter of year 2003. The late start by some cities was due to their preoccupation in Polio eradication. The city of Patna in the State of Bihar was the last city to complete the trainings in the month of March’2004 because of preoccupation with other programmes such as polio eradication. However, they are yet to start immunizing children with Hepatitis-B vaccine. In addition to the 32 districts already selected for Hepatitis B project, an additional district (the Union Territory of Andaman & Nicobar Islands) was added under the project after consulting the ICC (Inter-Agency Coordinating Committee), due to the high prevalence rate of Hepatitis B infection in that district. Implementation of Hepatitis B vaccination is now being carried out in all the 33 Project Districts. The immunization coverage achieved so far, the constraints observed & targets are summarized in the table below:

	Indicators
	Targets
	Achievements

	- Hepatitis B Coverage in year 2003.

Achieving Injection Safety

Training


	1.62 Million (A)
To introduce AD syringes in all Project Areas

To conduct a national assessment of Injection Safety

Train  master trainers and trainers from each city /district

Who would complete all further trainings 
	0.88 Million (54.32%) (B)
Initiated in 14 Cities (out of 15) & 33 districts (out of 33 districts).

Achieved in 98% introduction target in all the Project Cities & Districts.

A national assessment of injection practices was completed in the year 2003 (enclosed).

All the trainings were completed as scheduled. 100% staff involved in the project were trained. 


	                     Constraints
Poor infrastructure in city slums.

Lack of monitoring & feed back.

General decrease in routine immunization coverage rates in some districts impacting the Hepatitis-B vaccine coverage as well.
	                 Updated targets
80% Coverage targeted in year 2005.

(The Immunization Coverage by Hepatitis B vaccine by March 2004 has reached 62%)

- Improving monitoring & feed back of immunization coverage & vaccine logistics.

- To cover all the non slum infants of the city also. This will help to ensure equity among all the population and  improve the coverage in cities by reducing various logistical problems like demarcation of slums etc.


Notes for Table : 

A: The data are reproduced as targets set for year 2003, under Executive Summary, page 5 of the Revised

     Proposal submitted to GAVI for Hepatitis B Project in Nov. 2001. 

B: The data are based on the compilation of the Progress Reports Received by Govt. of India from states     implementing the Hepatitis B Project.
After this initial project, the Government of India has decided to improve & consolidate the Hepatitis-B vaccine in existing project area of 15 metropolitan cities and 33 districts before considering any further expansion. Towards this end, the Government of India is proposing through this document the second application to GAVI - the Vaccine Fund to mobilize resources required for continuation of the existing 33 districts and expanding Hepatitis B vaccination to cover the entire city as against the slum areas proposed in the earlier application in the selected 15 cities. 

Introduction of AD syringe in Universal Immunisation Programme

Injection Safety is assuming grave public health importance in India. The Government of India in collaboration with INCLEN (Indian Network of Clinical Epidemiologists) conducted a Nation-wide study on injection safety. The study has revealed that the injection safety is being compromised by the injection giver to the extent of 60.5% for all injections given in both curative and immunisation sector. In immunisation sector the unsafe injection is to the tune of 73.9% of this half is due to use of un-sterile syringe and needle. In view of compromises in injection safety and recommendations by WHO, UNICEF and UNFPAI to use AD syringes in all immunisation by 2003, Government of India is planning to introduce auto-disable (AD) syringes at all immunisation clinics under the Universal Immunization Program (UIP) all over the country. As regard the disposal of used AD syringes, a policy is being formulated as per the existing rules of the country under “Bio-Medical Waster (Management and Handling) rules 1998” and as amended thereafter. Under the said rule the needle has to be separated from the syringe and both the syringe and needle have to be disinfected. After disinfection both syringe and needle have to be recycled and where recycling is not possible or viable as in rural setup then the same have to be disposed off in a land fill. 

In view of the above, the Government of India is now approaching the Global Alliance for Vaccine and Immunization (GAVI) and the Global Fund for Children’s Vaccines for providing support for auto-disable syringes in the second phase in the entire country covering all the districts from year 2005 to 2007.

The Table stated below depicts the requirement of AD syringes and other logistics for introduction of AD syringe in the second phase of the project. 

	
	ITEM
	2005
	2006
	2007
	

	A
	Total AD syringes
	for BCG (in million)
	 30.34
	30.92
	31.52
	

	
	
	for other vaccines

(in million)
	283
	288
	294
	

	 B
	Total  of reconstitution  syringes 
	7.58
	7.73
	7.88
	

	 C
	Total of safety boxes Nil
	Will be disposed in conformity with national regulations  (Annexure 7)


Current Application:

In this second phase of project the Government of India is examining options for domestic procurement of the vaccine and syringes for ensuring sustainability of the program. Currently, in India some manufacturers are manufacturing  AD Syringes.

The details of the Project have been discussed in several meetings of the Inter-agency Coordinating Committee. Inputs given by members of the ICC in the above stated meetings have been incorporated in the proposal. The Proposal for the Project has been accorded approval by the Government of India. 

In this proposal, the Government of India (GoI) is applying for Introduction of New and Under-used Vaccines & Injection Safety sub-account. As mentioned earlier, the Government of India has already undertaken a detailed assessment of its immunization program and received credit from the IDA for strengthening immunization services and addressing the key program gaps. Hence, the Government of India is not seeking assistance under Strengthening Immunization Services Sub-account.

It may be worth mentioning here that the assistance received from GAVI for introduction of Hepatitis B vaccination in the country through the Pilot Project has immensely helped to identify the strategic priorities of the immunization program. Therefore unless the crucial weaknesses of the immunization system are addressed the reach and impact of basic immunization services as well as the new vaccines will remain limited. With these considerations in mind the Govt. of India and the members of ICC agreed to utilize the assistance from GAVI as seed money for value addition to the existing immunization services. Hence the present proposal has been developed with increased focus on:

· Continuation and Strengthening of the implementation of Hepatitis B vaccination in the existing project areas and using the lessons learnt for improvements

· Utilizing the results of study carried out on injection safety across the country, to expand the introduction of AD syringes beyond the project area of Hepatitis B vaccination to cover all the districts of the country.

· The final disposal of immunization waste will be handled in conformity with the national regulations for pollution control. 

Estimated number of doses of Hepatitis B vaccine

(Specify one table for each presentation of any vaccine and number it 7.2, 7.3,)
	
	
	Formula
	2003
	2004
	2005
	2006
	2007

	A
	Number of children to receive new vaccine 

	#
	0.55
	1.62
	2.59 *
	2.64
	2.69

	B
	Percentage of vaccines requested from The Vaccine Fund 
	%
	100
	100
	100
	100
	100

	C
	Number of doses per child 
	#
	3
	3
	3
	3
	3

	D
	Number of doses 
	A x B/100 x C
	1.65
	4.86
	7.77
	7.91
	8.07

	E
	Estimated wastage factor 
 
	see list in table (
	25
	25
	25
	25
	25

	F
	Number of doses ( incl. wastage)
	 A x C x E x B/100
	2.19
	6.46
	10.33
	10.52
	10.73

	G
	Vaccines buffer stock 

	F x 0.25
	0.55
	1.61
	0.00
	0.00
	0.00

	H
	Total vaccine doses requested
	F + G
	2.74
	8.07
	10.33
	10.52
	10.73

	I
	Number of doses per vial
	#
	10.00
	10.00
	10.00
	10.00
	10.00

	J
	Number of AD syringes (+ 10% wastage) 

	(D + G) x 1.11
	Given seperately
	Given seperately
	Given seperately
	Given seperately
	Given seperately


* Notes for the Table: In consultation with ICC the Govt. of India has planned to cover all the non slum infants of the city also from year 2004. This will help to ensure equity among all the infants & to improve the coverage of infants by expanding the provision of Hepatitis B vaccination from health care facilities in the non slum areas also. The target of 2.59 million infants in year 2005 has been reached by adding  number of non slum infants in 15 project cities that is target of 0.94 million to the existing target of 1.61 million infants in 33 districts & slum infants in 15 project cities. The factor of population increase at 1.016 has also been applied to the target. The targets for year 2006 & 2007 have been derived by applying the factor of population increase to the no. of target infants for year 2005. The population increase factor has been taken as 1.016 upto year 2006 & 1.015 there after in line with the population tables published by the office of Registrar General of India. The situation of supply overshooting the demand will be prevented by reviewing the immunization coverage each year & modifying the procurement request for next year accordingly.
2. Signatures of the Government and the Inter-Agency Co-ordinating Committee

The Government of India commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document. Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

Signature: 

Title: Deputy Commissioner (Child Health), Department of Family Welfare,

          Ministry of Family Welfare, Government of India.

Date:                September, 2004.

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

We, the undersigned members of the Inter-Agency Coordinating Committee endorse this proposal on the basis of the supporting documentation which is attached. Signatures for endorsement of this proposal do not imply any financial (or legal) commitment on the part of the partner agency or individual:

	Agency/Organisation
	Name/Title
	Date              Signature

	DFID
	Dr. Joanna Reid

Senior Health Advisor
	

	EUROPEAN COMMISSION
	Dr. Karan Singh

Programme Advisor
	

	Gates Children’s Vaccine Programme at PATH
	Dr. Raj Kumar

Project Manager
	

	UNICEF


	Dr. Ms. Erma Manoncourt

Incharge -Country Representative
	

	USAID


	Dr. Meri Sinnitte

Director PHN
	

	WHO, INDIA


	Dr. Salim Habayeb

WHO Representative to India
	

	WORLD BANK


	Dr. G.V.N. Ramana

Senior Public Health Specialist
	


In case the GAVI Secretariat has queries on this submission, please contact:

Name: Dr. D.C. Jain       Title/Address: Deputy Commissioner (Training/Child Health),  

Tel. No.: 91-11-23019791    Department of Family Welfare, 
Fax No.: 91-11-23019791   Ministry of Health & Family Welfare, Government of India,                                         

E-mail:                         Room No. 307, D wing, Nirman Bhavan,

                                        Maulana Azad Road, New Delhi - 110001

Alternative address:

Name: Dr. Pradeep Haldar     
Title/Address: Assistant Commissioner (UIP),  

Tel. No.: 91-11-23019728       
Department of Family Welfare, 

Fax No. 91-11-23019728       
Ministry of Health & Family Welfare, Government of India,         

E-mail:



pradeephaldar@yahoo.co.in                     

 



Room No. 106, D wing, Nirman Bhavan,

                                               
Maulana Azad Road, New Delhi - 110001

2. Immunization-related fact sheet

	Table 1: Basic facts (For the year 2001 or most recent; specify dates of data provided)

	Population as on March 2001¹
	1012 million
	GNP per capita
	US$ 450 

	Surviving Infants * 
	24.57 million
	Infant mortality rate² 
	70 / 1000

	Percentage of GDP allocated to Health³
	4.9
	Percentage of Government expenditure for Health Care 4
	5.3


· Surviving infants = Infants surviving the first 12 months of life

1 Technical Committee on Population Projections (Planning Commission)

2 Registrar General of India

3 World Health Report 2002 (WHO)

4 World Development Indicators 2000 (The World Bank)

	Table 2: Trends of immunization coverage and disease burden by 12 months of age (as per annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

	Trends of immunization coverage (in percentage)
	Vaccine preventable disease burden

	Vaccine
	Reported
	Survey
	Disease
	Number of reported cases*

	
	2002  A 
	2003 
	2003B 
	Age group
	 2002 B
	Age group
	
	 2001
	2002

	BCG
	98.1
	100
	81
	12-23 months
	81
	12-23 months
	Tuberculosis
	823964
	N.A.

	DTP


	DTP1
	N.A.
	
	N.A.
	
	N.A.
	
	Diphtheria
	5472
	7449

	
	DTP3
	92.9
	91
	70
	
	70
	
	Pertussis
	34673
	28746

	OPV3
	93.2
	92.3
	70
	
	70
	
	Polio
	268
	1600

	Measles
	88.8
	85.5
	67
	
	67
	
	Measles
	51780
	38927

	TT2+  (Pregnant women)
	80.6
	77.8
	N.A.
	
	NA
	
	NN Tetanus
	1718
	1390

	Hib3 
	NA
	NA
	NA
	
	NA
	
	Hib
	NA
	NA

	Yellow Fever
	NA
	NA
	NA
	
	NA
	
	Yellow fever
	NA
	NA

	HepB3  
	NA
	NA
	NA
	
	NA
	
	hepB seroprevalence  (if available)
	NA
	NA

	 Vit A supplementation  


	Mothers                               ( < 6 weeks after delivery )
	NA
	NA
	NA
	
	NA
	
	
	
	

	
	Infants              ( > 6 months)
	NA
	NA
	35E
	
	NA
	
	
	
	


	The best official estimate: Indicate the best official estimate of coverage among infants as reported in WHO/UNICEF Joint reporting form. Provide explanatory comments on why these are the best estimates: 

A. Government of India’s Reported Immunization Coverage(data from State Governments under RCH compiled by GoI) attached as Enclosure 2.1.
B. The data is  reproduced from WHO-UNICEF Review of National Immunization Coverage, 1980-2003, June 2004 enclosed as Enclosure 2.  
Also attached is a partial evaluated coverage report of Govt. of India’s RCH-CES,2002. The survey covers 50% of India’s districts.  Enclosure 2.2
* The No. of reported cases for VPD has been reproduced from the data available from Central Bureau of Health Intelligence, Government of India.  ………………………………………………………………………………………………………………………


· Summary of health system development status relevant to immunization:

The responsibility of the Government of India in terms of health care is divided between the Center, states and union territories, which are 35 in number. Health is a State subject, according to Article 47 of the Indian Constitution. The States, therefore, have the prime responsibility of “raising the level of nutrition and the standard of living of its people and the improvement of public health…”

Health services in the urban areas are provided by local bodies like the Municipal Corporations, as well as by private practitioners / institutions. The rural health services are managed through a network of Community and Primary Health Centers and Sub-Centers, each catering to a defined population and area.

The Government of India  is responsible for the planning of health services and programs, providing funding for key components of the program, technical and material support to national programs on communicable disease control, as well as health promotional activities such as family welfare and immunization, etc. The bulk of the expenditure on public health programs is borne by the Government of India, through its own resources, with some funding raised through multilateral and bilateral agencies.

All preventive and health promotional services provided to the general population through government hospitals, health centers and sub-centers are free.

The Family Welfare Program in India, which is the umbrella program for immunization services, has undergone important changes in recent years. The scope of services provided by the program has increased consistently over the years. At the time of initiation of the program in 1952, it was primarily a clinic-based family planning program. After subsequent integration with the Maternal and Child Health (MCH) Program, the activities broadened significantly, to include a variety of services to mothers and children, including antenatal, delivery and post-natal care, immunization, and counselling on maternal and child health and nutrition. In later years, specific emphasis was given to reducing maternal and child mortality through a focus on treatment of childhood diarrhoea, ARI, neonatal care and strengthening of emergency obstetric care. In 1994, subsequent to the International Conference on Population and Development (ICPD), the program was further reoriented to respond to client needs and came to be called the Reproductive and Child Health Program (RCH) which is entering its second phase this year. 

There has been a tradition of very close coordination of the MOH with professional bodies and private associations such as the Indian Academy of Pediatrics, the Indian Medical Association, at both the national and regional levels and private sector health institutions. In the last decade, the GOI has also initiated programs in collaboration with professional associations of private industry, e.g. for the involvement of industrial organizations in health messages to their workforce, such as family planning, HIV/AIDS awareness and maternal and child health camps. 

Multi Year Strategic Plan for Immunization (MYP 2004-09):

Government of India is aware of wide variations in immunization coverage levels across the country and is consciously looking at addressing various systemic issues in under performing states which are pulling down the immunization coverage levels.  The Govt. has also constituted a National Technical Advisory Group (NTAGI) comprising of national immunization administrators and well-known experts from academic institutions, partner agencies and NGOs etc. active in immunization.  This body has submitted its report to the Govt. in late 2003 based on which a Multi Year Strategic Plan for immunization (MYP 2004-09) has been prepared.  This document has been validated by experts from national/international partner/donor agencies and is ready for implementation.  

The MYP has also been extensively discussed with various state governments during various national deliberations with necessary adaptations to suit the state specific requirements.  A copy of the MYP is attached.   

The MYP is a part of the umbrella Reproductive and Child Health (RCH)-II program which is a sectoral approach to reproductive and child health including immunization.

The Government is also working on a National Immunization Policy, first draft of which is prepared for discussions at various forums (attached).

National EPI Review (August 25 – Sept.9, 2004):

Another step in this direction which demonstrates GoI’s seriousness in strengthening the routine immunization levels in the country is the National EPI Review carried out in six most under performing states viz. Bihar, Jharkhand, Madhya Pradesh, Rajasthan, Orissa and Uttar Pradesh.   This review was a qualitative study with the objective of identifying and addressing state specific barriers to immunization in each of these states. In all, 57 immunization professionals from GoI, academic institutions, national and international partner agencies, divided into 13 teams, participated in this review lasting two weeks.  Each team visited a district, starting with district headquarters upto the Health Sub Centre / Out Reach levels which is the last immunization service delivery point. 

One of the common observations of these thirteen teams was  lack of supervision/monitoring at all levels and the present system of sterilizing / using glass syringes is cumbersome and needs urgent replacement so as not to compromise injection safety and to maximize the time available to ANM (Auxiliary Nurse Midwife – the injection provider).  

The final review report is under compilation.

Therefore, the current focus areas for Government of India for strengthening UIP are as under:-

· Continuing focus on Polio Eradication Program. 

· Replacement of aging Cold Chain with CFC free equipment  
· Focus on Injection Safety under Universal Immunization Program (UIP).

· Strengthening Programme Management for UIP 

· Training of Mid level managers in child health with focus on managing immunization services.

	Attached are the relevant section(s) of strategies for health system development: 

1. Multi Year Strategic Plan for Immunization (2004-09) 

2. Draft National Immunization Policy

3. Organogram 

	Document number: 3
Document number: 3.1

Document  3.2


3. Profile of the Inter Agency Co-ordinating Committee (ICC) 

Various agencies and partners (including NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency co-ordinating mechanism which is referred to in this document as ICC.
· Name of the ICC : 


Inter Agency Coordinating Committee

· Date of constitution of the current ICC:
1995

· Organizational structure (e.g., sub-committee, stand-alone): ICC with Working Group for GAVI assisted Hepatitis B vaccination Project in India as stated below:
· Frequency of meetings: Quarterly but more frequently when required.

· Composition:

	Function


	Title / Organization
	Name

	Chair


	Secretary Ministry of Family Welfare, Government of India
	Mr. Prasanna Hota

	Secretary


	WHO representative to India
	Dr. Salim Habayeb

	Ministry of Health & Family Welfare, Government of India
	Joint Secretary, Family Welfare,

Deputy Commissioner (CH),

Assistant Commissioner (UIP),

 
	Mr. S.S. Brar,

Dr. D.C. Jain

Dr. Pradeep Haldar

	DFID
	Senior Health Advisor

Health Advisor
	Mrs .Joanna Reid 

Dr. Ranjana Kumar 



	EUROPEAN COMMISSION
	Programme Advisor
	Dr. Karan B. Singh

	Children’s Vaccine Programme at PATH
	Project Manager

Project Administrator
	Dr. Rajkumar 

Mr. K. A. Balaji

	UNICEF


	Country Representative

Chief, Health Section

Project Officer Health

Project Officer Immunization
	Dr. Erma Manoncourt 

Dr. Marzio Babille

Dr. K. Suresh

Dr. Hussain Yusuf 

	USAID


	Director PHN
	Dr. Meri Sinnitte 

	WHO, INDIA


	WHO Representative to India

National Professional Officer-

Hepatitis B
	Dr. Salim Habayeb

Dr. R.K. Pal



	WORLD BANK


	Lead Health Specialist

Senior Public Health Specialist

Public Health Specialist
	Dr. Peter Heywood

Dr. G.V.N. Ramana

Dr .J .S. Kang

	WHO SEARO


	Regional Advisor, Vaccines & Other Biologicals

Medical Officer – VAB

Technical Officer- VAB
	Dr. Brent Burkholder

Dr. Pem Namgyal

Mr. Stephan Guichard

	WHO, NPSP 
	Medical Officer- Epidemiology
	Dr. J. Wenger


· Major functions and responsibilities of the ICC: 
Annexed as Document No. 4
· Three major strategies to enhance the ICC’s role and functions in the next 12 months:

· Strengthen Working Group Mechanism 

· Injection Safety Focus

· To continue focus on strengthening implementation of Hepatitis-B immunization in the existing project areas.

· Three main indicators (in addition to DTP3 coverage) that are chosen by the ICC to monitor implementation of this proposal:

· Usage of  A D Syringes  

· Hepatitis B Coverage in existing project areas.

· DPT1 Coverage

Attached are the supporting documents:

	· Terms of reference of the ICC
	        Document number 4.

	· ICC’s workplan for the next 12 months
	        Document number 4.1.

	· Minutes of the three most recent ICC meetings or of any other meetings in which partners participated that concerned improving and expanding the national immunization program 
	        Document number 4.2.


4.  Immunization services assessment(s)

Reference is made to the most recent assessments of the immunization system that have been completed within the three years prior to the submission of this proposal.

· Assessments, reviews and studies of immunisation services for current reference:

	Title of the assessment
	Main participating agencies
	Dates
	Enclosed as enclosure No.

	Sixth World Bank Review Mission, for India Immunization Strengthening Project.  
	World Bank, WHO, IDA, 
	June 9 – 17, 2003
	5

	Proposed Reproductive & Child Health Second Phase Program for India, Draft Aide-Memoire of the Identification Mission. 
	World Bank, WHO, IDA, DFID, UNICEF
	July 16 – 26, 2003
	5.1

	Observations of RCH- survey Phase I & II, relevant to Immunization. 
	Department of Family Welfare, Ministry of Health & Family Welfare, Government of India.
	1998-99
	5.2

	Observations of National Family Health Survey – NFHS II, relevant to Immunization.
	Same as above.
	1998-99
	5.3.

	Recommendations of National Technical Advisory Group.
	Department of Family Welfare, Ministry of Health & Family Welfare, Government of India.
	July,2003
	5.4


National EPI Review (August 25 – Sept.9, 2004):

Towards this end, a National EPI Review has also been commissioned by GoI, which was carried out in six most under performing states viz. Bihar, Jharkhand, Madhya Pradesh, Rajasthan, Orissa and Uttar Pradesh.   This review was a qualitative study with the objective of identifying and addressing state specific barriers to immunization in each of these states. In all, 57 immunization professionals from GoI, academic institutions, national and international partner agencies, divided into 13 teams, participated in this review lasting two weeks.  Each team visited a district, starting with district headquarters upto the Health Sub Centre / Out Reach levels which is the last immunization service delivery point. 

One of the common observations of these thirteen teams was  lack of supervision/monitoring at all levels and the present system of sterilizing / using glass syringes is cumbersome and needs urgent replacement so as not to compromise injection safety and to maximize the time available to ANM (Auxiliary Nurse Midwife – the injection provider).  

The final review report is under compilation.

· The three major strengths identified in the assessments:

Self-Sufficiency:  India finances over 95% of routine immunization services, including operating costs, vaccines, and other costs.  This level of financing reflects the sustained commitment to immunization on part of the government. 

Established Infrastructure:  The immunization infrastructure is established in all states. However, some states maintain reliable coverage over 85% while others fluctuate around 40% or below, reflecting the diversity in the strength of the infrastructure.  Eight of 35 states have particularly weak systems.  
There is also a reinforcement of Government commitment to Routine Immunization by way of establishment of National Technical Advisory Group on Immunization and preparation of a Multi Year Plan for Immunization (2004-09)    

Polio Eradication:  National Immunization Day has wide reach.  The success towards polio eradication is largely due to improved surveillance, micro-planning, logistics, and IEC/social mobilization.  Strong commitment and close coordination between national and state governments and partners
· The three major problems identified in the assessments:

Decline in Coverage:  While routine data suggests an overall increase in coverage through much of the 1990’s, surveys indicate that there has been a decline in all states (excepting Tamil Nadu and Goa) over the past 3 plus years.

Chronic Low Performing Areas:  A subset of states and districts has chronically low levels of coverage, far below national targets. Also, drop-out rates are estimated at 17% from highest to lowest coverage antigen (BCG to measles as shown in Table 2), according to coverage surveys.  
Injection Safety Issues:  the present system of sterilizing / using glass syringes is cumbersome and needs urgent replacement so as not to compromise injection safety and to maximize the time available to ANM (Auxiliary Nurse Midwife – the injection provider).  Also the National Assessment on Injection Safety carried out by IN-CLEN for GoI highlights the high prevalence of unsafe injections in the country, calling for immediate attention of the government.
· The three major recommendations in the assessments:

Polio Eradication: Complete polio eradication activities, while phasing in new initiatives for appropriate regions.

Improving Program Management to address declining coverage & increasing dropouts:
Human Resources & System strengthening:  Strengthen essential immunization related activities within the integrated Reproductive and Child Health system.

· Management Strengthening:  Supervision and monitoring, planning, institutional review mechanisms (e.g. quarterly meetings), demand creation/social mobilization, stock management, cold chain, and financing.

· Field Staff Strengthening: Training on technical issues, planning, surveillance, stock management, social mobilization, etc; Fill staff vacancies.

Physical Resource Strengthening:  Strengthen essential physical resources within the integrated Reproductive and Child Health system, particularly cold chain maintenance and replacement, and staff mobility to reach session sites.  Also focus on injection safety issues and rolling out of AD syringes.
Low Performing Districts and States:  Intensify focus on immunization within integrated health services in low-performing states and districts. 

· Attached are  complete copies (with an executive summary) of:

	· the most recent assessment reports on the status of immunization services
	Document numbers 5 to 5.4 as stated above.

	· A list of the recommendations of the assessment reports with remarks on the status of their implementation i.e. included in work-plan, implemented, not implemented, in progress….   
	Summarized above. 


5. Components or areas of immunization services that are yet to
     be reviewed (or studied). 
	Component or area
	Month/Year

	· Assessment of Cold Chain & Vaccine Wastage Rates (on the basis of DPT 3) & how to avoid shortages was to be conducted by WHO-SEARO, but could not be initiated.        

· The Study on assessment of Injection Safety has been completed. The preliminary findings of the study are enclosed as enclosure 6
	Pending

October 2003

Enclosure number 6


6. Multi-Year Immunization Plan

The Govt. of India has developed a Multi Year Strategic Plan for Immunization (2004-09), the details of which are given under Section.3.  A copy of the plan document is also attached vide Document No. 3.  An executive summary of the plan is given below:
This medium term plan addresses the geographic and social inequities in immunization coverage rates. It aims to increase awareness of all stakeholders about immunization strengthening and strengthening management roles at each of three specific levels; Centre, State/Union Territory and district. The plan aims to strengthen the immunization infrastructure within the broader RCH programme as well as inter sectoral linkages.

Medium term goals and strategies

The medium term plan envisions six goals, each with its own set of objectives and strategies. The six goals and their respective objectives with strategies to achieve these objectives are summarized below: 

Goal 1: Districts will provide efficient and safe immunization services to all infants and pregnant women

To achieve this goal the following objectives have been planned.
Objectives:

· To ensure regular quality immunization sessions are planned and held
· To ensure adequate trained staff are empowered to provide essential quality immunization services

· To keep an annually upgraded inventory of cold chain according to the levels of the network, allowing for new equipment, substitution, replacement, spare parts, fuel and others in order to maintain a functional status of 90%

· To ensure an efficient vaccine and injection equipment management and logistics system to forecast and deliver adequate supplies of vaccines in a timely manner

· To ensure the implementation of safe injection practices and waste disposal
To achieve the above objectives following strategies will be adopted:

Strategies:

Coordination between National and State level; Printing and supply of National Operational Guideline; Strengthening of supervision; Prioritisation of poorly performing districts; Prioritisation of under served populations within districts; Proper Micro Planning; Filling up of staff vacancies; Strengthening training for all categories of staff; Assessment of Cold Chain status, Procurement, installation and proper inventory management of Cold Chain equipment; Maintenance and repairs of Cold Chain equipment; Timely supply of vaccines; Ensuring quality control of vaccines; Phased introduction of AD syringes. 

Goal 2: Contribute to global polio eradication, measles mortality reduction and neonatal tetanus elimination

Objectives:
· To achieve polio eradication certification by 2007

· To eliminate neonatal tetanus (NNT) by 2009

· To reduce measles mortality by two-thirds by 2010, compared to 2000 estimates 

· To achieve and maintain a level of 70% coverage with two doses of vitamin A supplementation to children under three

Strategies:

Strengthening routine immunization; Supplementary immunization campaigns; AFP surveillance, Strengthening service delivery; Increase reporting and action on cases; Data analysis; Targeted SIAs; Strengthening surveillance and Measles case management.
Goal 3: The UIP will have sufficient and sustainable funding with established adequate, accountable and efficient fund flows

Objectives:
· To ensure adequate and reliable financial resources at national, state and local levels for the UIP to achieve goals and objectives

· To ensure political commitment for adequate annual funding at all levels

Strategies:

Strengthening of National financial planning; Partnership building (strengthening ICC), 

Goal 4: Sustain demand and reduced social barriers to access immunization services

Objectives:

· To ensure widespread support by all families and communities and to ensure that all eligible children and pregnant women are immunized

· To ensure high level political and administrative support for immunization as the key public good

Strategies:

Coverage with print, electronic and other mass media; Improve interpersonal communication 

Goal 5: Accelerated introduction of licensed new and under utilized vaccines against diseases with significant mortality and morbidity in India

Objectives:

· To ensure institutional mechanisms are in place to adequately obtain, review and utilize information for deciding on introduction of new and under utilized vaccines

· To review need for MMR or MR vaccine in India’s immunization programme

· To review need for introduction of Japanese encephalitis (JE) vaccine in selected states

· To review need for a phased introduction of Hepatitis B vaccine

Strategies: 

Improve coordination between MoHFW and research institutes, NRA and development partners; Disease burden analysis; Disease surveillance

Goal 6: To monitor and use accurate, complete and timely data on vaccine preventable diseases, AEFIs and antigen coverage and drop out rates by district

Objectives:

· To institutionalize surveillance for vaccine-preventable diseases and early detection of any outbreaks

· To strengthen vaccine quality and injection safety by developing a monitoring system for reporting and responding to adverse events following immunization (AEFI) by 2009

· To establish an effective, efficient, complete and timely immunization recording and local area monitoring system by 2009

Strategies: 

Introduction of software database system; Increase accuracy and use of data at local levels; Private sector and community involvement; Laboratory confirmation and strengthened linkages with surveillance, AEFI and NRA; Strengthen monitoring system at local level; Decentralization of monitoring to strengthen local use of information for action; Use of data at different levels; Use of surveys;  Linkages with the private sector. 

Attachments:

	· Multi Year Strategic Plan for the Universal Immunization Programme 2004-2009
	Already attached as Document number 3



	Technical support required for implementation of the immunization plan (expert consultants, training curricula, managerial tools…)
This component is not applicable here as India is not receiving assistance under the Immunization Support.

	Type of technical support
	Period for the support
	Desired from which agency

	N.A.
	N.A.
	N.A.

	
	
	

	Table 3: Schedule of vaccinations with traditional and new vaccines, and with Vit A supplementation

	Vaccine (do not use trade name)
	Ages of administration                (by routine immunization services)
	Indicate by an “x” if given in:
	Comments

	
	
	Entire country
	Only part of the country
	

	BCG
	Birth
	X
	
	

	OPV
	Birth, 6, 10 & 14 weeks
	X
	
	

	DPT
	6, 10 & 14 weeks
	X
	
	

	HBV
	6, 10 & 14 weeks
	
	X
	

	Measles
	9 Months
	X
	
	

	Vitamin A
	9 Months – 3 Years
	X
	
	1st dose is given with Measles vaccination. 2nd dose is given with DPT booster vaccination.


· Summary of major action points and timeframe for improving immunization coverage

The strategic plan drawn up by the Government of India to cover the remaining years of the Tenth Plan Period (2002-2007) has been conceptualised in terms of support to the polio eradication activities aimed at achieving zero polio incidence and certification. Maintaining the polio-free status after achieving zero polio incidences will require also a very high level of coverage of OPV under the routine immunization program.

This translates into the fact that the routine program has not only to achieve high immunization coverage levels, but also sustain it. Strengthening routine immunization would not only help in polio eradication but also in sustaining high coverage levels for other antigens included in the Universal Immunization Program of the country. 

While planning for the strengthening of the routine immunization, lessons learnt in polio eradication on disease surveillance, capacity building, micro planning, mapping of hard to reach villages, use of alternate service delivery mechanisms, social mobilization using locally available resources with decentralization of planning and implementation, will be applied in routine immunization activities, so that high levels of OPV and routine immunization coverage are not only achieved but sustained. 

A comprehensive multi-year plan is being developed under the RCH II project of Govt. of India including the introduction of newer vaccines such as Hepatitis-B, improving injection safety and the strategies for sustained strengthening of Immunization systems uniformly throughout the country. 

	Number of

	
	 2001

Baseline
	 2005
	 2006
	 2007

	Births
	24.75
	27.336
	27.863
	28.401

	Infants’ deaths
	1.56
	1.45
	1.48
	1.28

	Surviving infants
	23.19
	25.89
	26.39
	27.12

	Pregnant women
	26.00
	32.190
	32.815
	33.449

	Infants vaccinated with BCG* 
	19.58
	27.336
	27.863
	28.401

	Infants vaccinated with OPV3** 
	17.79
	27.336
	27.863
	28.401

	Infants vaccinated with DTP3** 
	16.63
	27.336
	27.863
	28.401

	Target Infants to be vaccinated with**: Hepatitis B
	
	2.59
	2.64
	2.69

	Infants vaccinated with Measles** 
	14.89
	27.336
	27.863
	28.401

	Pregnant women vaccinated with TT+ 
	17.37
	32.190
	32.815
	33.449

	Vit A supplementation
	Mothers (< 6 weeks from delivery)
	
	
	
	

	
	Infants (> 6 months)
	8.12
	27.336
	27.863
	28.401


1. The Population of the country, Birth Rate & Infant Mortality Rate projected for year 2002 to 2016 by the office of Registrar General of India have been used (Reference SRS Bulletin Oct. 2002 & Projection tables enclosed as Encl. 6.1) as basis for calculating no. of births & Infant deaths stated in the above table. The above figures for different states of the country are reconciled with the state Governments & the reconciled figures have been used as the final figures in the above table. 

2. The no. of Infants vaccinated with BCG, OPV3, DPT3 & Measles in year 2001 has been derived by multiplying the no. of surviving infants in column 2 of the above table,  with the vaccination coverage data of 79.1, 76.7,71.7 & 64.2% respectively. Thereafter, every year the target no. of Infant to be vaccinated for each vaccine has been considered same as the number of births. 
3. To arrive at the number of Pregnant women vaccinated with 2 doses of Tetanus Toxoid in year 2001 & the target numbers for year 2005 to 2008 same approach has been followed as in case of Point No. 2, except using the no. of pregnant women in place of the no. of surviving infants. The data for baseline coverage by 2 doses of TT has been reproduced from NFHS-II Survey, 1998-99. (Enclosed as enclosure 5.3 ).

 4. To arrive at the number of infants above the age of 6 months having received at least one dose of Vit. A supplementation in year 2001 & the target numbers for year 2005 to 2008 same approach has been followed as in case of Point No. 2. The data for coverage by Vitamin A has been reproduced from RCH-II Survey, 1998-99. (Enclosed as enclosure 5.2). 

5. The target of 2.59 million infants in year 2005 has been reached by adding number of non slum infants in 15 project cities that is target of 0.94 million non slum infants has been added to the existing target of 1.61 million infants in 33 districts & slum infants in 15 project cities. The factor of population increase at 1.016 has also been applied to the target. The targets for year 2006 & 2007 have been derived by applying the factor of population increase to the no. of target infants for year 2005. The population increase factor has been taken as 1.016 upto year 2006 & 1.015 there after in line with the population tables published by the office of Registrar General of India. 
7. Summary of major action points and timeframe for reduction of vaccine wastage:

If maximum allowance of wastage rates cannot be achieved immediately, the proposal has to provide a rationale for a higher rate: 

· Implementation of computerized Vaccine Logistics Systems 

· Building systems for assessment of wastage at district level

· Strict maintenance of cold chain

· Implementing the open vial policy

	Table 5: Estimate of annual DTP wastage and drop out rates

	
	Actual rates and targets

	
	 2001
	 2002
	 2003
	 2004
	 2005
	 2006
	 2007
	 2008

	Wastage rate 

	
	
	30 A
	25.00
	25.00
	25.00
	20.00
	20.00

	Drop out rate                                    [  (  DTP1   -    DTP3   )   /    DTP1   ]   x  100
	7.72B
	7
	7
	6.5
	6.5
	6
	6
	5.5

	Drop out rate

((BCG- DPT3)/ BCG) x 100
	9.35C
	8.5
	8.5
	8
	8
	7.5
	7.5
	7


A: This is estimated present vaccine wastage rate for DPT & Hepatitis B vaccine.

B: This Drop out rate is based on observations of Multi Indicator Cluster Survey 2001 by UNICEF, for evaluated vaccination coverage of DPT1 & DPT3.

C: This Drop out rate is based on observations of Multi Indicator Cluster Survey 2001 by UNICEF, for evaluated vaccination coverage of BCG & DPT3.

· Countries requesting YF vaccine have to present the same table for measles vaccine wastage rates.
                                           Not Applicable.

8. Planning and constraints for the Polio Eradication Initiative:

The progress achieved by India in this area is summarized in the table stated below:

	Year
	Virologically confirmed polio cases
	Number of districts affected

	1998
	1934
	314

	1999
	1126
	192

	2000
	265
	89

	2001
	268
	63

	2002
	1600
	159

	2003
	225
	87

	2004
	58 (as on 17th September 2004)
	26


The above data have been reproduced from the reports of National Polio Surveillance Project of India.
The latest status of planning & constraints of Polio eradication in India is summarized below. 
Following a large poliovirus outbreak in 2002, India has made substantial progress toward polio eradication in 2003 and there are only 225 cases in 2003 as compared to 1600 in 2002.  As of 17h September 2004, number of polio cases reported stands at 58.

GoI is committed to take all necessary steps to interrupt the transmission of polio virus by the year end of 2004 and go for certification by 2007.

Of the above 58 cases in 2004, 10 cases are from state of  Bihar (spread all over the state) and 39 cases are from the state of Uttar Pradesh (concentrated Western U.P).  Understandably, GoI’s polio eradication efforts are giving special attention to these two states to interrupt the transmission of virus with the help of various agencies involved in the polio eradication such as  National Polio Surveillance Program (NPSP), India Expert Advisory Group for Polio Eradication (IEAG) and other partners/ICC.  Remaining 9 cases are spread across six states.
9. Injection safety

9.1 Summary of the injection safety strategy for immunization:                                                             

In most of the cities of the country the medical waste from hospitals, and health centres is being collected and disposed by using the incinerators as centralised facilities. In the rural areas of the country the disposal of the AD syringes is being planned by burying in a safe pit created close to each health centre for this purpose. The consultation with members of ICC, experts, NGOs, and Central Pollution Control Board is under way to find out most appropriate and feasible method for disposal of AD syringes in the rural setting. The separation / mutilation of sharp (needle) from the body of AD syringe, before disposal is also being considered. This helps in reducing significantly the volume of waste being disposed in the safe pit & opens up the option of selling off the remaining non sharp body of AD syringe to scrap dealers for recycling, to manufacture useful household items after melting. Recently the Central Pollution Control Board of the country has expressed its reservations on burning/ incineration of the AD syringes. Hence the non burn alternatives are being considered also for the urban areas of the country.

The preliminary findings of the Study on assessment of Injection Safety in different areas of the country have been received. This study has been done by independent agency on request of Government of India. Based on the observations of the study the National Technical Advisory Group, Indian Academy of Paediatrics  & other relevant experts are assisting the Govt. of India in developing a plan to ensure Safe Injections (including plans for transition to auto-destruct syringes) and the best alternatives available for Safe Management of Sharps Waste. 

9.2 Injection Waste Disposal: 

In India, the Central Pollution Control Board (CPCB), an autonomous regulatory body under the Ministry of Environment & Forests, is the law making authority with regard to disposal of bio-medical waste.  Disposal of injection waste falls under the broad “Bio-Medical Waste (Management and Handling) Rules, 1998” amended from time to time.    There are State Pollution Control Boards (SPCB) in each state which are the implementing agencies for CPCB guidelines.

As such, the disposal of injection waste generated by the Universal Immunization Program has to conform to the existing CPCB regulations which clearly prohibit any incineration and strictly stipulate non-burn options for the disposal of AD syringes. 

As such, the Government of India, in consultation with CPCB and deliberations with partners and other stakeholders, have evolved the following disposal guidelines for injection waste generated in the UIP. The guidelines are still in draft stage pending CPCB approval.   A copy of proposed guidelines is attached.

Draft Disposal Guidelines:   

The needle of each syringe shall be removed by the health worker at the point of use using a manual syringe cutter device. The mutilated syringes shall be stored separately in a red coloured container / bag.  Both needle and syringe containers shall later be treated using an autoclave / chemical disinfectant.  The needles and other sharps shall then be disposed off in a secure needle pit and syringes shall be sent for recycling or land fill.  Where there is access to centralized bio-medical waste treatment facility (CBWTF) (available in many major metropolitan cities), the segregated injection waste shall be handed over to them for further processing and disposal as prescribed under the CPCB guidelines.

Attachments.
	· Draft guidelines for disposal of bio-medical waste generated during Universal Immunization Program  (Central Pollution Control Board, Ministry of Environment & Forests, Govt. of India, 2004)

	Document number 7


9.3 Injection safety Equipment:
	Table 6.1: Estimated supplies for safety of vaccination with …… BCG, in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for BCG vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	27.336
	27.863
	28.401
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	1
	1
	1
	

	C
	Number of ……  doses
	A x B
	27.336
	27.863
	28.401
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	30.34296
	30.92793
	31.52511
	

	E
	AD syringes buffer stock  
 
	D x 0.25
	0
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	30.34296
	30.92793
	31.52511
	

	G
	Number of doses per vial
	#
	20
	20
	20
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	2
	2
	2
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	3.37
	3.43
	3.50
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions. 


	Table 6.2: Estimated supplies for safety of vaccination with …… DPT, in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for DPT vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	27.336
	27.863
	28.401
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	4(A)
	4
	4
	

	C
	Number of ……  doses
	A x B
	109.344
	111.452
	113.604
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	121.37184
	123.71172
	126.10044
	

	E
	AD syringes buffer stock  7 
	D x 0.25
	0
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	121.37184
	123.71172
	126.10044
	

	G
	Number of doses per vial
	#
	10
	10
	10
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	NA
	NA
	NA
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	NA
	NA
	NA
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions.


(A) This calculation of doses of DPT vaccine includes 3 doses of DPT vaccine for infants and one booster dose of DPT (18-24 months). 

	Table 6.3: Estimated supplies for safety of vaccination with Hepatitis B , in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for Hepatitis B vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	2.59 
	2.64
	2.69
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	3
	3
	3
	

	C
	Number of ……  doses
	A x B
	7.77
	7.91
	8.07
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	8.62
	8.79
	8.96
	

	E
	AD syringes buffer stock  
 
	D x 0.25
	0.00
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	8.62
	8.79
	8.96
	

	G
	Number of doses per vial
	#
	10
	10
	10
	


	Table 6.4: Estimated supplies for safety of vaccination with …… Measles, in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for Measles …… vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	27.336
	27.863
	28.401
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	1
	1
	1
	

	C
	Number of ……  doses
	A x B
	27.336
	27.863
	28.401
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	30.34296
	30.92793
	31.52511
	

	E
	AD syringes buffer stock  
 
	D x 0.25
	0.00
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	30.34296
	30.92793
	31.52511
	

	G
	Number of doses per vial
	#
	5
	5
	5
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	1.6
	1.6
	1.6
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	10.77 
	10.98
	11.19
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions. 


	Table 6.5: Estimated supplies for safety of vaccination with …… DT, in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for DT…… vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	27.336
	27.863
	28.401
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	1
	1
	1
	

	C
	Number of ……  doses
	A x B
	27.336
	27.863
	28.401
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	30.34296
	30.92793
	31.52511
	32.13339

	E
	AD syringes buffer stock  
 
	D x 0.25
	0.00
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	30.34296
	30.92793
	31.52511
	

	G
	Number of doses per vial
	#
	10
	10
	10
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	NA
	NA
	NA
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	NA
	NA
	NA
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions.


	Table 6.6: Estimated supplies for safety of vaccination with ….TT (10 and 16 year) , in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for TT vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	50.543

	51.519
	52.513
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	1
	1
	1
	

	C
	Number of ……  doses
	A x B
	50.543
	51.519
	52.513
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	56.10
	57.18
	58.29
	

	E
	AD syringes buffer stock  
 
	D x 0.25
	0
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	56.10
	57.18
	58.29
	

	G
	Number of doses per vial
	#
	10
	10
	10
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	NA
	NA
	NA
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	NA
	NA
	NA
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions.


	Table 6.7: Estimated supplies for safety of vaccination with ….TT  (pregnant Women) , in million

	
	
	Formula
	2005
	2006
	2007
	

	A
	Target of children for TT vaccination (for TT : target of pregnant women)

	Match with targets in table 4
	32.19
	32.815
	33.449
	

	B
	Number of doses per child (or per woman in case of TT)
	#
	1(B)
	1
	1
	

	C
	Number of ……  doses
	A x B
	32.19
	32.815
	33.449
	

	D
	AD syringes (+10% wastage)
	C x 1.11
	35.73
	36.42
	37.12
	

	E
	AD syringes buffer stock  
 
	D x 0.25
	0.00
	0.00
	0.00
	

	F
	Total AD syringes
	D + E
	35.73
	36.42
	37.12
	

	G
	Number of doses per vial
	#
	10
	10
	10
	

	H
	Vaccine wastage factor 

	Either 2 or 1.6
	25%
	25%
	25%
	

	I
	Number of re-constitution 
 syringes (+10%  wastage)
	C x H x 1.11 / G
	NA
	NA
	NA
	

	J
	Number of safety boxes (+10% of extra need)
	( F +  I ) x 1.11 / 100
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions.


(B) This calculation of doses of Tetanus Toxoid to pregnant women states 1dose in place of 2 doses. This is based on the assumption that number of women coming to receive Tetanus Toxoid in their second or subsequent pregnancy would have already received 2 doses during the first pregnancy. Hence they will need only one booster dose. 

9.4 Areas for injection safety funds 
	Source of fund
	Area of support
	Start of fund utilization

	The support is being requested from GAVI, for AD syringes  for Routine Immunization & for disposal of AD syringes after use in all the districts of the country. This support is expected from the assistance of US $ 40 million ear marked by GAVI for India. The support is requested upto year 2007, and is limited to the funds available over & above the continuation of the existing Hepatitis B project upto year 2007, The Govt. of India is committed to meet from RCH- II & other resources available, any shortfall of funds beyond the above allocation & funds for continuation of injection safety activities initiated & existing Hepatitis B vaccination project after the year 2007/ after utilization of funds received from GAVI.     
	AD syringes  for Hepatitis B vaccination in 33 selected districts & 15 cities of the Country are being received under Hepatitis B Project of GOI supported by GAVI. This application is for partial support for introduction of AD syringes in UIP and maintenance of  Hepatitis- B immunization in existing project areas till year 2007.
	From year 2005


 (Use as many rows as necessary

10.  New and under- used vaccines

· Summary of those aspects of the multi-year immunization plan that refer to the introduction of new and under-used vaccines.

Plan of action for vaccinations with new or under-used vaccines.

The following points are part of the multi year immunization plan of the country which refers to introduction of Hepatitis B vaccine in brief.

A. Continuation of Hepatitis B vaccination in existing project cities &  districts of the country:-

It is proposed that the assistance received from the Global Vaccine Fund will be utilised up to year 2007 for activities related with the continuation of Hepatitis B vaccine in the existing project cities & districts. The activities that need to be sustained in the existing project area namely the provision of the Hep. B vaccine on continuous basis is planned to be supported by Govt. of India, after the year 2007/ allocated GAVI support has been utilized.  Please see enclosure 1.
B. Strengthening the management and monitoring capacity of the central cell for UIP (including Hepatitis B Project and introduction of AD syringes in UIP) in the Child Health Division of the Ministry of Family Welfare:-

The experience of introducing Hepatitis B vaccination in 15 cities and 33 districts of the country in year 2002 – 2003 has made us realise the need for strengthening the existing capacity of UIP cell in the ministry to take up the following functions more effectively:

1. Field monitoring to identify the constraints in delivery of immunization services  and to improve upon the same.

2. Compilation and analysis of performance reports on immunization received from the districts and providing feedback along with discussion with the programme managers for improvements.

3. Maintaining a strong system for, tracking the receipt, supply and balance stock of vaccine, AD syringes, training materials and other project requirements for maintaining the efficient supply chain for the districts.

4. Keeping a close liaison with the Medical Store Depots storing the vaccines and supplies and with the programme managers in the districts, guiding them periodically and answering their day to day queries.

5. Maintaining close coordination with ICC members, GAVI, concerned divisions within the Ministry of Health and Family Welfare, other related departments such as Pollution Control Board, experts and professional bodies of doctors and paediatricians.

6. Strengthening of Financial Management systems to ensure timely disbursement of grant, availability of funds and timely reporting by the units.
In view of the above, a total amount of US $50,000/- is planned to be kept aside for monitoring visits of the project area by the nodal officer of Govt. of India, additional technical assistance and other relevant program management expenses such as short term consultancy, review meetings etc.   It is also proposed to route this money through one of the developmental partners in the country for operational flexibility.
C. The main indicators (in addition to DTP3 coverage) envisaged to monitor implementation of this proposal are:

· Hepatitis B Coverage.

· A D Syringe Use.

11. Assessment of burden of relevant diseases  :

The two documents listed below provide a comprehensive summary of various studies done on Burden of Hepatitis B infection & disease in India & Cost effectiveness of vaccination against it. In the second document published by Regional office of WHO for South East Asia the information from various studies is summarized on page 51 to 56.

	Disease
	Title of the assessment
	Date
	Enclosure

	Hepatitis B
	Hepatitis B in India: Burden of Disease Analysis 
	April 2001
	8

	Hepatitis B 
	Prevention of Hepatitis B in India, An Overview, W.H.O.
	August 2002
	8.1

	Hepatitis-B
	Rapid Assessment of Hep.B Vaccine introduction in India
	August, 2004
	8.2


· Lessons learnt about storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop out rate, wastage rate etc. as per current experience with new and under-used vaccines:

The maintenance of cold chain & storage capacity so far has been found mostly satisfactory under the phase I of the project in 15 cities & 33 selected districts of the country. The approach of training in basic areas of improving immunization program along with specific details about Hepatitis B vaccination & training the trainers has been appreciated by the states & trainees as well. The management of logistics & monitoring of immunization coverage, wastage & drop out rates have been found to be weak areas through observations in the field & the progress reports being received from the cities of Phase I. Similar observations have been revealed from the Rapid Assessment of Hepatitis B project, performed in first week of August 2004. The report of the same is enclosed as enclosure 8.2.  

· Summary of the action points that address possible implications for storage capacity, staff training, cold chain, measures to avoid freezing of vaccines, logistics, drop out rate, wastage rate etc… in the Plan for Introduction of New and Under-used Vaccines :
More attention is planned to be devoted through technical assistance to improve the capacity of districts & states in management of logistics & monitoring of immunization coverage, wastage & drop out rates.  

· First preference: required number of doses and presentations of requested new and under-used vaccines. 

Table 7.1: Estimated number of doses of Hepatitis B vaccine 
	
	
	Formula
	2003
	2004
	2005
	2006
	2007

	A
	Number of children to receive new vaccine 

	#
	0.55
	1.62
	2.59 *
	2.64
	2.69

	B
	Percentage of vaccines requested from The Vaccine Fund 
	%
	100
	100
	100
	100
	100

	C
	Number of doses per child 
	#
	3
	3
	3
	3
	3

	D
	Number of doses 
	A x B/100 x C
	1.65
	4.86
	7.77
	7.91
	8.07

	E
	Estimated wastage factor 
 
	see list in table (
	25
	25
	25
	25
	25

	F
	Number of doses ( incl. wastage)
	 A x C x E x B/100
	2.19
	6.46
	10.33
	10.52
	10.73

	G
	Vaccines buffer stock 

	F x 0.25
	0.55
	1.61
	0.00
	0.00
	0.00

	H
	Total vaccine doses requested
	F + G
	2.74
	8.07
	10.33
	10.52
	10.73

	I
	Number of doses per vial
	#
	10.00
	10.00
	10.00
	10.00
	10.00

	J
	Number of AD syringes (+ 10% wastage) 

	(D + G) x 1.11
	Given Seperately
	Given Seperately 
	Given Seperately
	Given Seperately
	Given Seperately


* Notes for the Table : In consultation with ICC the Govt. of India has planned to cover all the non slum infants of the city also from year 2005. This will help to ensure equity among all the infants & to improve the coverage of infants by expanding the provision of Hepatitis B vaccination from health care facilities in the non slum areas also. The target of 2.59 million infants in year 2005 has been reached by adding 80% coverage of non slum infants in 15 project cities that is target of 0.94 million to the existing target of 1.61 million infants in 33 districts & slum infants in 15 project cities. The factor of population increase at 1.016 has also been applied to the target.. The targets for year 2006 & 2007 have been derived by applying the factor of population increase to the no. of target infants for year 2005. The population increase factor has been taken as 1.016 upto year 2006 & 1.015 there after in line with the population tables published by the office of Registrar General of India. The situation of supply overshooting the demand will be prevented by reviewing the immunization coverage each year & modifying the procurement request for next year accordingly.
· Second preference: Required number of doses and presentations of requested new and under-used vaccines, if first preference is not available. (Please use provided formulae as per table 7.1) 

	· Attached is the plan of action for vaccinations with new or under-used vaccines (if already contained within the national, multi-year plan, indicate pages)
· Rapid Assessment of Hepatitis B Vaccine introduction in India, August 2004
	Document number 1.
Document number 8.2


12. Strategic directions to mobilise additional resources     for immunization

· Summary of strategies that the Government intends to pursue to increase the resources for immunization of children, and that will be converted in a comprehensive Financial Sustainability Plan. Highlights of the agreements made with donor agencies (i.a.: Vaccine Independence Initiative) and the use of funds freed by debt relief:

The major activities currently being undertaken by the Govt. of India for improving immunization coverage are: Strengthening RCH outreach services, better monitoring of immunization services, Better management of vaccines & other related logistics and improving IEC efforts for immunization. The details about the same are stated in the attached enclosures 19, 20 & 21. 

The resource outlays for immunization of children & related activities in the period of year 2005 to 2007 under the Tenth Five Year Plan of the country are stated in the attached enclosure no. 22.

The resource outlays for immunization of children & related activities in the period of RCH II project of Govt. of India  (year 2004 to 2009) being planned are stated in the attached enclosure no. 14. The expenditure in past years on these components has also been presented in this document. A study of the same indicates that Govt. of India has been allocating increasing funds from its own resources & through coordinated donor assistance as well.

Attachments:

	· Copy of the summarised budget outlays for deptt. of Family Welfare, in 10th Five Year Plan (Year 2002-07).  

· Tables of expenditure for 2001 and resource needs detailing the sources of funds for 2001 and subsequent years  are  attached  in Annex 1.  
· Multi-Year Strategic Plan is already annexed as Enclosure 3.


	Document No. 9
Annex.1 is stated on page 41

 of this application


· Remarks on recurrent cost reduction strategies which contribute to financial sustainability, such as vaccine wastage reduction:

As stated above under summary of major action points & time frame for reduction of vaccine wastage, under item 6 of this proposal increased attention is going to be provided in coming years through trainings, on the job supervision & guidelines to the states on: 

· Implementation of computerized Vaccine Logistics Systems 

· Streamline logistics 

· Building systems for assessment of wastage at district level

· Strict maintenance of cold chain

· Implementing the open vial policy

13. Summary of requests to GAVI and the Vaccine Fund

With reference to all points presented above, the Government of India considering that its DTP3 coverage for 2001 was 71.7%  corresponding to 16.63 million children receiving 3 doses of DTP, requests the Alliance and its partners to contribute financial and technical assistance required to increase immunization of children.

Specifically, the Government hereby applies for the following types of support from GAVI and the Vaccine Fund. (Circle “YES” or “NO” according to the requests submitted with this proposal):
· Support for Immunization Services                       

         NO

· Support for New and Under-used vaccines                                  YES           

· Support for Injection Safety                                                           Yes

13.1 SUPPORT FOR IMMUNIZATION SERVICES 
Not Applicable as support under this budget head for Immunization Services is not being received by India.

13.2 SUPPORT FOR NEW AND UNDER-USED VACCINES 

GAVI and the Vaccine Fund are requested to fund the introduction of New and Under-used Vaccines by providing the following vaccines: 

	Table 8: New and under-used vaccines requested from GAVI and the Vaccine Fund

	Vaccine presentation


	Number of doses per vial
	Starting month and year 
	Number of doses requested for first calendar  year
	Number of doses requested for second calendar  year *

	Hepatitis B 
	10 dose
	2005
	10.33 million
	10.52 million (Yr 2006)

	* Vaccines will also be requested for following years as described in tables 7.1, 7.2…


Vaccines will be procured : 


                                   By UNICEF       √                                        By GOVERNMENT

                                Upto Dec. 2007                     

13.3 SUPPORT FOR INJECTION SAFETY 

GAVI and the Vaccine Fund are requested to support the injection safety plan by providing: 

(Tick one choice only):

The amount of supplies listed in table 9





*√        The equivalent amount of funds
	Table 9A: Summary of total supplies for safety of vaccinations with BCG, DTP, TT, MEASLES and Hepatitis B, requested from GAVI and the Vaccine Fund for three years 

	
	ITEM
	2005
	2006
	2007
	

	A
	Total AD syringes
	for BCG
	30.34
	30.92
	31.52
	

	
	
	for other vaccines
	283
	288
	294
	

	 B
	Total  of reconstitution  syringes 
	14.14
	14.41
	14.69
	

	C
	Total Syringes (AD + Reconstitution)
	327.14
	333.41
	339.69
	

	D
	Total expected cost in Indian Rs in Million

	804.56
	780.83
	756.53
	

	E
	Total expected cost in Million US $
	17.86
	17.33
	16.80
	

	F
	Cost Component requested from GAVI
	9.00
	8.00
	8.00
	

	 G
	Total  of safety boxes
	Will be disposed as per country law by removing the needle from AD syringe, disinfect and recycled or land filled. Logistics requirement will be worked on these assumptions.


	Table 9B: Summary of total assistance requested from GAVI and the Vaccine Fund under different budget heads for three years 

	
	ITEM
	2005
	2006
	2007
	 

	1
	Total AD syringes
	for BCG
	30.34
	30.92
	31.52
	

	
	
	for other vaccines
	283
	288
	294
	

	2
	Total  of reconstitution  syringes 
	14.14
	14.41
	14.69
	

	3
	Total Syringes (AD+Reconstitution)
	327.14
	333.41
	339.69
	

	4
	Expected cost in Indian Rs in Million
	804.56
	780.83
	756.53
	

	5
	Hub Cutters cost
 in Rs. Million
	70.40
	70.40
	70.40
	

	6
	Cost of needle pits
Rs.  Million
	151.31
	-
	- 
	

	7
	Cost of Hypochlorite for disinfecting needles

	17.60
	17.60
	17.60
	

	8
	Total Cost in Indian Rs. in Million
	1043.87
	868.83
	844.53
	

	9
	Total expected cost in Million US $
	23.20
	19.30
	18.76
	

	10
	Cost Component requested from GAVI US$ Million

	9.00
	8.00
	8.00
	

	11
	Share from GOI
	10.83
	11.30
	10.76
	

	12
	Cost Component requested from GAVI for Hepatitis B vaccine in million US$
	3.53
	3.59
	3.66
	

	13
	Cost Component requested from GAVI for strengthening Project Monitoring in million US$
	0.0163
	0.0163
	0.0163
	

	14
	Total Budget requested from GAVI for Inj. Safety & Hepatitis B Project
	12.53
	11.59
	11.66
	


· (In case you request funds equivalent to the above supplies at the prices obtained by UNICEF) Please submit the attached “Banking Form”(Annex 3) with the proposal, in case you have not yet already done so for other types of support from GAVI/The Vaccine Fund.
14.  Additional comments and recommendations from the ICC: 

This document has been prepared after consultations with the members of ICC. Comments received from the members have been incorporated after which the document has been endorsed by the members. 

ANNEX 1

Statement of financing and of unmet needs for immunization (USD ,000) 

Table 1

	Summary of Financing of Immunization: 2000-01 to 2002-03

Rs. Million 

(Figures in brackets are USD Million)

	Major Component
	2000-01
	2001-02
	2002-03
	Total

	GOI Recurring Expenditure on EPI
	2484.0

(52.9)
	2856.6

(60.8)
	3285.1

(69.9)
	8625.7

(183.5)

	Immunization as part of RCH program
	5109.0

(108.7)
	5430.0

(115.5)
	5835.0

(124.2)
	16374.0

(348.4)

	Polio Eradication
	6140.6

(130.7)
	5584.5

(118.8)
	5420.5

(115.3)
	17145.6

(364.8)

	World Bank Project Funds
	752.4

(16.0)
	806.0

(17.1)
	1091.5

(23.2)
	2649.9

(56.4)

	TOTAL IN RS. MILLION
	14485.9
	14677.1
	15632.1
	44795

	TOTAL IN USD MILLION
	(308.2)
	(312.3)
	(332.6)
	(953.1)


Table 2

	Estimated GOI Recurring Expenditure on EPI: 2000-01 to 2002-03

Rs. Million 

	Major Component
	2000-01
	2001-02
	2002-03
	Total

	Vaccines
	1173.6
	1349.6
	1552.1
	4075.3

	Salaries
	760.8
	874.9
	1006.2
	2641.9

	Maintenance incl. cold chain
	369.6
	425.0
	488.8
	1283.4

	Supplies & Construction
	78.0
	89.7
	103.2
	270.9

	Transportation
	72.0
	82.8
	95.2
	250.0

	IEC
	30.0
	34.5
	39.7
	104.2

	TOTAL
	2484.0
	2856.6
	3285.1
	8625.7

	USD Million
	(52.9)
	(60.8)
	(69.9)
	(183.5)


ANNEX  2

Summary of documentation
 

	Background information on Health System Development status

	a) Attached are the relevant section(s) of strategies for health system development
	Document number 3, 3.1, 3.2 

	Profile of the Inter Agency Co-ordinating Committee (ICC)

	b) ICC’s work plan for the next 12 months
	Document number 4.

	c) Terms of reference of the ICC 
	Document number 4.1

	d) Minutes of the three most recent ICC meetings or any meetings concerning the introduction of new or under-used vaccines or safety of injections
	Document number 4.2

	Immunization Services Assessment

	e) Most recent, national assessment report(s) on the status of immunization services
	Document number  5, 5.1, 5.2, 5.3 &  5.4

	f) Summary of the recommendations of the assessment report(s) with remarks on the status of implementation of each recommendation.
	 

	Multi-Year Immunization Plan

	g) Complete copy (with executive summary) of the Multi-Year Immunization Plan or of the relevant pages of the health sector plan.
	Document number  3


	h) Action plan for the introduction of new or under-used vaccines into immunization services (if already contained within the national, multi-year plan, please indicate page and paragraphs)

i) A copy of the Plan to achieve Safe Injections (including plans for transition to auto-destruct syringes) and Safe Management of Sharps Waste or of the relevant pages of the health plan.
	Document number 1 

Document number 7

	Unmet needs requiring additional resources

	j) Tables of expenditure for  2001 and resource needs (Annex 1)
	Annexure 1 on page number 41 of this application


ANNEX  3

	GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION


	
	Banking  Form

	

	SECTION 1 (To be completed by payee)

	
	

	In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization and the Vaccine Fund dated . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . ,  

the Government of . .India . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . , 

hereby requests that a payment be made, via  electronic bank transfer, as detailed below:

For the activities stated above under the continuation of Hepatitis B Project & improving injection safety in the country, the payment to Govt. Of India is requested through the channels of 

	Name of Institution:

(Account Holder)
	

	Address:
	

	
	Nirman Bhavan, Maulana  Azad Road, New Delhi. 

	
	PIN- 110001

	City – Country:
	India

	Telephone No.:
	91 11 
	Fax No.:
	91 11 

	Amount in USD:  
	(To be filled in by GAVI Secretariat)
	Currency of the bank account:
	

	For credit to:       Bank account’s title
	

	Bank account No.:
	

	At:                    Bank’s name
	

	Is the bank account exclusively to be used by this programme?
	YES  (   )    NO   (   )

	By whom is the account audited?
	

	Signature of Government’s authorizing official:



	
Name:
	
	Seal:



	Title:
	
	

	Signature:
	
	

	Date:
	
	

	
	
	


	SECTION 2 (To be completed by the Bank) 

	

	FINANCIAL INSTITUTION
	CORRESPONDENT BANK 

(In the United States)

	Bank Name:
	
	

	Branch Name:
	
	

	Address:


	
	

	
	
	

	City – Country:
	
	

	
	
	

	Swift code:
	
	

	Sort code:
	
	

	ABA No.:
	
	

	Telephone No.:
	
	

	Fax No.:
	
	

	
	
	

	I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by  (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution.

	The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories:
	Name of bank’s authorizing official:



	1  Name:

Title:
	
	Signature:                    
	

	
	
	Date:
	

	2  Name:

Title:
	
	Seal:

	
	
	

	
3  Name:

Title:
	
	

	
	
	

	4  Name:

Title:
	
	

	
	
	


COVERING LETTER

(To be completed by UNICEF representative on letter-headed paper)
TO:    GAVI – Secretariat

                                                           



Att. Dr Tore Godal

                                                           



Executive Secretary

                                                           



C/o UNICEF

                                                           



Palais des Nations

                                                           



CH 1211 Geneva 10

                                                           



Switzerland
	On the ……………………………… I received the original of the BANKING DETAILS form, which is attached.

I certify that the form does bear the signatures of the following officials:


	
	Name
	
	
	Title

	Government’s authorizing official
	
	
	
	

	Bank’s authorizing official 
	
	
	
	

	

	                                    

	Signature of UNICEF Representative:



	Name
	

	Signature
	

	Date
	

	
	





� Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided


� The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.


� The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.


� A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.


� Formula to calculate DTP vaccine wastage rate (in percentage): [( A – B ) / A ] x 100. Where by: A = The number of DTP doses distributed for use according to the supply records with correction for stock balance at start and end of the supply period; B = the number of DTP vaccinations. 


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� No buffer stock is being calculated here for AD syringes.  The assumption is that with expected time lags in rolling out the AD introduction and 100% target procurement, there will be sufficient buffer stocks available.








� Only for lyophilized vaccines. Write zero for other vaccines


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.


� Only for lyophilized vaccines. Write zero for other vaccines


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


�No buffer stock is being calculated here for AD syringes.  The assumption is that with expected time lags in rolling out the AD introduction and 100% target procurement, there will be sufficient buffer stocks available.


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� No buffer stock is being calculated here for AD syringes.  The assumption is that with expected time lags in rolling out the AD introduction and 100% target procurement, there will be sufficient buffer stocks available.


� Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.


� Standard wastage factor for Measles reconstitution syringes used is 1.11.  One syringe is estimated for each vial of 5 doses.


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.


� Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.


� Only for lyophilized vaccines. Write zero for other vaccines


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� This includes cohort of 26.37 million of 10 yrs. Age and 24.16 million of 16 yrs.age.


� The buffer stock for vaccines and AD syringes is set at 25%. This is calculated with the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.


� Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.


� Only for lyophilized vaccines. Write zero for other vaccines


� GAVI/The Vaccine Fund will fund the procurement of AD syringes to deliver 2 doses of TT to pregnant women. If the immunization policy of the country includes all Women in Child Bearing Age (WCBA), GAVI/The Vaccine Fund will contribute to a maximum of 2 doses for Pregnant Women (estimated as total births). 


� No buffer stock is being calculated here for AD syringes.  The assumption is that with expected time lags in rolling out the AD introduction and 100% target procurement, there will be sufficient buffer stocks available


� Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, and 1.6 for measles and YF.


� Only for lyophilized vaccines. Write zero for other vaccines


� Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided


� The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials.


� The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25.


� A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.


� Deflation of 5% from year 2 onwards is applied to AD syringe cost (Rs.2.50 in year 1) in view of volumes and local capacity.  Cost of Reconstitution syringe estimated at Rs.1.50/-


� One hub cutter for each of 176,000 health workers in the country @ Rs.400/- p.a.


� Cost of needle pits @Rs.5000/- per pit for 30,263 Primary Health Centres


� Hypochlorite solution for disinfecting, @Rs.100/- per health worker per annum.


� GAVI assistance is requested only for procurement of AD syringes


� Please submit hard copy documents with an identical electronic copy whenever possible





10
37


