Annexe A. the IPV introduction plan

Countries are required to complete and submit a vaccine introduction plan for the IPV.

The WHO has developed guidance to support countries in developing plans for the introduction of new vaccines. The IPV introduction should not replace other new vaccine introductions planned in the same year. Countries are encouraged to find synergy for the IPV introduction with existing plans for other new vaccine introductions scheduled in 2014 or 2015. They are strongly advised to include the other requirements to be considered for the IPV in their new vaccine introduction plan. Potential benefits and challenges of the IPV introduction together with another new vaccine, already scheduled to be introduced, should be carefully considered and planned for.

Executive summary of the introduction plan

- Brief justification for the introduction of the IPV and key complementary considerations that have been taken into account, including comprehensive approaches for disease control.

- Outline of the benefits to the population of introducing the IPV, the cost implication to the program and how the country plans to sustain those costs.

- Overview of how the vaccine will be introduced (national or phased introduction) and key milestones and activities, such as to the schedule for the vaccine introduction and the start of preparations.

- Overview of the capacity of the immunization program to introduce the IPV, including all aspects of supply chain and logistics, health workers’ capacity, etc.

- Summary of preparatory activities completed or to be undertaken.

- Brief description of main risks/ challenges associated with the introduction of the IPV and outline of the mitigating strategies put into place to reduce these risks (or address these challenges).

This document covers the following areas:

1. Justification for introduction of the IPV and national decision-making process

2. Overview of the IPV

3. Introduction and implementation considerations

4. Situational analysis of the immunization program

5. Monitoring and evaluation

6. Advocacy, communication and social mobilization

1. Justification for introduction of the IPV and national decision-making process

- Provide evidence that all key decision-makers in the relevant agencies (e.g., Ministry of Health, Ministry of Finance, etc.) have been participating in discussions on the introduction, have been involved in making the final decision about introducing the IPV and have endorsed its introduction.

- Describe the involvement of other relevant stakeholders, e.g. Civil Society Organizations, community representatives, national regulatory authorities, academic and training institutions and, as applicable, the private sector, in the decision-making process.

- Describe the technical and operational feasibility of introducing the IPV, based on country experience with other new vaccine introductions.

The World Health Assembly adopted a new strategic plan for eradicating poliomyelitis with the final phase of 2013 - 2018 after the approval of the synchronous global cessation of the OPV, in May 2008, despite its efficiency on intestinal and pharyngeal mucosa and the risk of reintroducing medium and long term polio virus from vaccine manufacturing locations.

-	The administrative vaccine coverage against polio appears to be high in Benin (≥95%) but there is a high frequency of acute flaccid paralysis (AFP) as shown in the graph below

Graph 1:  Evolution of cases of WPV and AFP in Benin from 1997 to 2013

Legend: PVS = WPV

PFA = AFP

With respect to the statistics on AFP and vaccine associated paralytic poliomyelitis (VAPP) due to three types of viruses (1, 2 and 3), Benin can be considered as a risk country likely to contact a re-import or recurrence of a vaccine strain to an attenuated live virus;

Table I: Evolution of confirmed WPV and VAPP in Benin from 2004 to 2013 based on the number of OPV doses administered per year

| Years | Confirmed poliomyelitis |  | Other cases | Number of OPV doses |
| --- | --- | --- | --- | --- |
|  | Total cases of confirmed poliomyelitis |  | Vaccine associated poliomyelitis cases |  |
|  | Indigenous | Imported |  |  |
| 2013 | 0 | 0 | 10 | 1,628,167 |
| 2012 | 0 | 0 | 11 | 1,592,933 |
| 2011 | 0 | 0 | 1 | 1,497,305 |
| 2010 | 0 | 0 | 7 | 1,472,006 |
| 2009 | 0 | 20 | 30 | 1,414,486 |
| 2008 | 0 | 6 | 10 | 1,368,943 |
| 2007 | 0 | 0 | 2 | 1,352,840 |
| 2006 | 0 | 0 | 7 | 1,259,826 |
| 2005 | 0 | 0 | 1 | 1,211,646 |
| 2004 | 0 | 6 | 15 | 1,152,089 |
| Total | 0 | 32 | 94 | - 950.241 |

-	SAGE recommends that before withdrawing the OPV2, during the transition from trivalent OPV to bivalent OPV, all the countries should add at least one dose of the IPV in their systematic immunization programs;

-	the IPV has a major role in maintaining immunity against the type 2 polio virus during the global withdrawal of the vaccine against type 2 oral poliomyelitis.

The political wish of the health authorities in Benin is to improve the health of the population by reducing mortality and morbidity by aligning themselves with the objectives of the vaccine decade. This interest is shared by the Technical and Financial Partners (TFP) and the civil society through their commitment during the ICC meetings.

The National Advisory Committee for Immunization and Vaccines in Benin (NACI - Benin) studied the strategic policy for the IPV introduction into the routine EPI, and drafted a recommendation which is forwarded to the Minister of Health for a decision. Hence, the Inter-agency Coordination Committee (ICC), being the decision-making body, approved the introduction of the IPV in routine EPI, in the meeting held on April 22, 2014. This committee is made up of the cabinet members of the Ministry of Health, National Immunization Agency and Primary Health Care (NIA - PHC), representatives from other technical directorates of the Ministry of Health, representatives of the civil society organizations, representatives from the Ministry of Maternal and Primary Education, representatives from the Ministry of Economic Affairs and Finance and the Technical and Financial partners.

The IPV which is pre-qualified by the WHO, Directorate of Pharmacies, Drugs and Diagnostic Investigations (DPDDI) will facilitate its registration and use.

The introduction of the IPV is in response to the appearance and increase in the number of wild polio virus cases with the potential benefit from the availability of GAVI funds for procuring the IPV vaccine.

It is also enhanced by the capability of the country to ensure efficient vaccine storage and distribution, facility to procure it for its country through easy procedures and mechanisms under the UNICEF circuit, possibility to integrate the vaccine in the current immunization schedule and finally by the abilities of the program to ensure a timely and effective introduction with increase in immunization coverage using the experience gained with the introduction of Pentavalent, Yellow Fever and PCV13.

2. Overview of the IPV

2.1 Vaccine preference

- Please specify vaccine preferences in Table B1 below

For obtaining GAVI support for the introduction of a single-dose IPV, the procurement of the wild polio virus vaccine, as well as injection material and safety boxes will go through UNICEF supply chains in collaboration with the GAVI Secretariat, according to the established protocol. The system is the same for the procurement of other non GAVI-funded vaccines which are procured through the UNICEF supply chain. Thus, Benin has selected the following vaccine presentations:

Table B1. The IPV vaccine preferences and estimated date of introduction

| The preferred IPV vaccine | Month and year of first vaccination | Preferred second presentation | Preferred third presentation |
| --- | --- | --- | --- |
| 10 dose vials | June 2015 | 5 dose vials | 5 dose vials |

- For more information on vaccine presentations, please consult the UNICEF Product Menu:

- http://www.unicef.org/supply/index_66260.html. A list of final product presentations will be available after the UNICEF tender is

concluded (by March 2014) and will depend on the WHO pre-qualification processes.

- More information on current WHO pre-qualified IPV vaccines can be found at:

http://www.who.int/immunization_standards/vaccine_quality/PQ_vaccine_list_en/en/index.html.

2.2 Country licensure status

- Provide information on the status of the NRA in the country, i.e. whether functional and/ or WHO-certified.

- State whether national vaccine licensure will be needed for the IPV, in addition to WHO pre-qualification, and if so, describe the procedure and its duration. State whether the country accepts the Expedited Procedure for the national registration of WHO pre-qualified vaccines.

- Provide the actual licensure status of the preferred presentation and of any alternative presentations.

- Describe local customs regulations, requirements for pre-delivery inspection, special documentation requirements that may potentially cause delays in receiving the vaccine. If such delays are anticipated, explain what steps are planned to handle these.

In Benin, the Directorate of Pharmacies, Drugs and Diagnostic Investigations (DPDDI) is the National Regulatory Authority and authorizes the marketing of WHO pre-qualified vaccines.  With the help of its expertise, it facilitates the IPV registration.

The manufacturer should submit a folder to the DPDDI for the registration and marketing of the vaccine. The customs department facilitates the entry of vaccines and vaccine supplies through a tax exemption.

The Government and traditional TFPs are available to support the supply system so that the vaccines always arrive in good condition. The Ministry of Health established an operational mechanism for information and retro-information on the arrival of vaccines by air.

2.3 Target population and vaccine supply

- Provide estimates of the target population for a single dose of the IPV to be given with the OPV3 at the DTP 3/Penta 3 health contact (or DTP 2, depending upon alignment with the current DTP dosing schedule, as illustrated in section 2.3 of the IPV Guidelines) by year through 2018, starting with the first year of the IPV introduction. Please adjust the targets for the first year of the IPV introduction for the month when vaccinations begin.

- GAVI procures and delivers vaccines through UNICEF or the PAHO Revolving Fund. If an alternative mechanism is requested, or the vaccine will be purchased by the country itself, please document the following:

- Other vaccines or immunization commodities procured by the country and descriptions of the mechanism used; and

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with GAVI requirements for the procurement of vaccines and supply of assured quality.

The requirements listed below are calculated using the logistics forecast tool with the following parameters:

- For vaccines

Target: 4% of the total population

Growth rate: 3.2% of the previous year’s population

Each target will receive 1 dose of the IPV vaccine in a 10-dose presentation

Coverage target: 50% in the first year (2015) and 98% in 2016

Wastage rate admissible by GAVI:  50%

- For Consumables

Wastage rate: 10%

Benin uses the target population method to estimate vaccine requirements

Formula = Pcible x Tcv x Ndose x Fperte

Pcible = Target population

Tcv = vaccine coverage

Ndose = Number of doses

Fperte = wastage factor

Quantity of vaccines and supplies ordered

Table: Estimates of the IPV vaccine and supplies requirement in Benin for 2015-2018

For the first year of the IPV introduction (2015), a safety stock has to be planned.

Considering the vaccine requirements for this year, the safety stock should be at 25% of requirements, or 395,997 doses x 25% = 98,821 doses. Hence, the total IPV requirements in 2015 will be 494,106.

(395,997 + 98,821).

| Vaccines and supplies | 2015 | 2016 | 2017 | 2018 |
| --- | --- | --- | --- | --- |
| Target population | 395997 | 408.669 | 421.746 | 435.242 |
| IPV (doses) | 494.106 | 533.034 | 550.091 | 573.487 |
| AD syringes 0.5 ml | 543.517 | 586.337 | 605.100 | 630.835 |
| Safety boxes | 5435 | 5863 | 6051 | 6308 |

3. Introduction and implementation considerations

3.1 Policy development

- Describe any need to alter the National Immunization Policy to include the IPV in the national immunization schedule, including any changes in schedule and the likely impact on existing vaccination contacts this may have. Be sure to clearly describe the timing of the IPV to align with the current DTP dosing schedule (see section 2.3 of the IPV Guidelines).

- Provide information on immunization practice decisions, e.g. injection site, order of injections and which limb for two or more injections.

- Describe any integrated delivery of other health interventions that are planned.

On the political front, indicate the commitment and willingness of the health authorities in Benin to improve general public health by reducing the mortality and morbidity, especially in children who are most vulnerable by aligning with

the vaccine decade objectives. This willingness mentioned in the comprehensive multi-year plan (cMYP 2014 -2018) is shared with the partners of Benin and civil society through various organizations, namely, CNCV-Benin and ICC-EPI. The introduction of the injectable anti-poliomyelitis vaccine (the IPV) is motivated by:

- The appearance and increase in 58 wild polio virus cases during the last five years in Benin while the last outbreak of wild polio virus was recorded in 2009.

- The availability of the proven safe and efficient IPV (vaccine well tolerated in children)

- The opportunity for Benin to benefit from GAVI financial support for introducing the first dose of the vaccine into the routine EPI.

On the programmatic front, the introduction is motivated by the ability of the country to ensure an efficient storage and distribution of the vaccine, presentation of the vaccine in liquid form, easy to handle vials, facility to procure through procedures and mechanisms using UNICEF circuit, possibility to integrate the vaccine into the current immunization schedule and finally the ability of the program to ensure a prompt improvement of vaccine coverage using the experience gained through the introduction of other new vaccines (Pentavalent, PCV13).  Like most of the other vaccines used by the program, this vaccine should also be stored between + 2 °C and + 8 °C and will be administered to children aged 0-11 months starting at 14 weeks from birth.

Target immunization strategies

Benin chose to immunize children less than one year, every year, according to the mixed strategy (fixed and advanced)

- The Fixed Strategy relates to targets living within a radius of 5 km from the health facility, in each health area. This strategy covers 40% of the target  population or 158,510 targets for 2015 and will be held in health facilities and public places selected within the communities.

- The Advanced Strategy relates to the targets living beyond 5 km from the health facility in each health area. It covers 60% of the target population; or 237,766 targets for 2015. It will be implemented in public locations selected within the communities. Hence, the targets located within a radius of 5 km from the health center will be vaccinated by the fixed strategy immunization teams and those located more than 5 km away from the health center will be vaccinated by the advanced strategy immunization teams with the involvement of community volunteers, district/village heads, Red Cross volunteers and the heads of Social Promotion Centers and NGOs. Social mobilization through radio, town criers and other media will help in easily achieving these targets in the communities.

To document immunization, each vaccinated target will be recorded in the previously reviewed immunization register. The IPV administration date will be entered on the child card and health card. For the advanced strategy, the immunization team goes to each locality, once a month, on a date and time arranged with the communities.

Catch-up sessions will be organized for the missed targets.

Benin plans to administer a dose of the IPV at the age of 14 weeks simultaneously with the Pentavalent vaccines (DTP3-HepB-Hib) and OPV3 as shown in the table below.

Table: Immunization schedule for infants in Benin

| VACCINES |  | Administration age |
| --- | --- | --- |
| BCG | OPV0 | At birth |
| OPV1 | Penta 1 (DTP-HepB-Hib1), PCV 13_1 | At 6 weeks |
| OPV2 | Penta2 (DTP-HepB-Hib2), PCV 13_2 | At 10 weeks |
| OPV3 | Penta 3 (DTP-HepB-Hib3), PCV13_3 IPV | At 14 weeks |
| Measles vaccine | Yellow Fever vaccine | At 9 months |

All children lagging behind the ideal immunization schedule should receive a dose of the IPV in primary-immunization after the age of 14 weeks and before their first birthday.

Method and area of vaccine administration

The table below gives the doses, areas and administration methods for the antigens, in the current immunization schedule in Benin.

Table: doses, areas and vaccine administration methods for infants in Benin

| ANTIGENS | DOSES | AREAS | ADMINISTRATION METHODS |
| --- | --- | --- | --- |
| B.C.G. | 0.05 ml | 1/3 outside the upper left forearm | Intradermal |
| OPV | 2 drops | Mouth | Oral |
| Pentavalent (DTP-HepB- Hib) | 0.5 ml | Left arm deltoid muscle | Deep IM |
| IPV | 0.5 ml | Anterior of the right thigh | Deep IM |
| PCV13 | 0.5 ml | Anterior of the left thigh | Deep IM |
| Measles vaccine | 0.5 ml | Right arm | Subcutaneous |
| Yellow Fever vaccine | 0.5 ml | Right thigh | Subcutaneous |

## Vaccine administration

The vaccine against the IPV will be administered to all target children aged 0-11 months who go to the immunization posts for the third dose of their series (DTP-HepB-Hib3) and OPV3 or before their first birthday; from the day on

which the vaccine is officially launched throughout the country, as this vaccine is not combined with other vaccines. The IPV vaccine will be administered through a deep intramuscular injection in the antero-lateral part of the right thigh. The standard dose for the IPV vaccine is 0.5 ml.

## Vaccine requirements 2015-2018

## (Ref. 2.3 Target population and vaccine availability)

## Vaccine supply and distribution

The annual vaccine requirements are estimated by the government with the technical support from UNICEF which plans the orders according to its regular supply mechanisms. Once the vaccines are received, they are stored in the central cold room and distributed every quarter to the departments. This mechanism has some advantages which ensure that the vaccines are of good quality and affordable to purchase through the UNICEF order system and with short delivery schedules. UNICEF and the WHO significantly contribute to the vaccine distribution and storage mechanism.

They plan to ensure the supply of vaccines from health areas to health centers. The lower levels calculate their requirements based on national guidelines and route their requests to the next level that supplies them. The peripheral level is supplied on a monthly basis and intermediate level is supplied every quarter. The central level is supplied twice a year.

Figure 2: Vaccine supply circuit

Legend:

Fabricant = Manufacturer

2 fois l’an = twice a year

Depot central = Central depot

4 fois l’an = 4 times a year

Tous les mois = Every month

District sanitaire = Health District

Centre de Sante = Health Centre

For GAVI support, the supply of the IPV vaccine, injection supplies and safety boxes will be handled through the UNICEF supply chain, in collaboration with the GAVI secretariat. The system is the same for the procurement of other non GAVI-funded vaccines which are procured through the UNICEF supply chain.

3.2 National coordination mechanism to ensure successful introduction

- Summarize the IPV introduction time line, as presented in Annexe C.

- Describe the national management process to oversee the IPV introduction, including any steering committee and/ or subcommittee tasked with various activities for the introduction.

Main steps in the IPV introduction

To ensure an efficient and quick introduction of the IPV, the strategies which were used earlier as a part of Pentavalent and PCV13 introduction will be used for the IPV introduction processes including the following main steps:

- Planning introduction and preparation activities

- Organization and coordination processes (Meetings of the EPI-ICC sub-commissions, and ICC-EPI meetings)

- Training of EPI participants and decision-makers’ meetings at various levels of the health pyramid

- Social mobilization, IEC and advocacy

  - Prepare the communication plan

  - Implementation of communication activities and advocacy

  - Briefing of journalists and presenters of partner radio stations and contract with mass media

- Adaptation and reproduction of tools

- Waste management

- AEFI monitoring and follow-up

- Post-introduction evaluation

- Strengthening cold chain capacity

- Strengthening the capacities of laboratory network

- Updating monitoring guidelines on AEFI

- Preparation and distribution of posters on Cold chain maintenance and temperature monitoring

- Preparation of tools on AEFI monitoring

- Equipment maintenance

- Organization of logistics (set-up of vaccines and supplies)

- Launch of vaccine introduction

- Supervision and monitoring

National coordination will be ensured by the Inter-agency Coordination Committee (ICC). This committee is chaired by the Minister of Health.

The role of the ICC-EPI is, among others, to provide support in defining the EPI policy guidelines, preparation of strategic plans and annual EPI plans, mobilize resources required for implementing action plans of the program, periodically review progress in the implementation of programs and ensure optimal use of mobilized resources.

These attributes have now become strength to EPI Benin and will support the country in the IPV introduction.

The ICC authorizes the NIA-PHC to submit the new vaccine introduction application and approves this IPV introduction plan and ensures that it is successful. The ICC is guided by NACI-Benin.

It is structured into 3 sub-committees (technical, logistics and communication).

These sub-committees are made up of representatives from various directorates of the ministry of health, (National Immunization Agency and Primary Health Care, National Directorate of Public Health, Directorate of Pharmacies, Drugs and Diagnostic Investigations, Directorate of Financial and Material Resources, Directorate of Infrastructures, Equipment and Maintenance), related ministries (Finance, Internal Affairs, Communication, Defense, Energy, Education, Family and Decentralization) and other development partners of the health sector and Civil Society Organizations.

At the intermediate level, the coordination will be provided by the Departmental Director of Health with the support from the Departmental Service Head of Public Health and Head of the Immunization and Cost recovery Division.

At the peripheral level, the coordination will be provided by the zonal Medical Coordinator assisted by chief physicians and community EPI managers.

These focal points will be responsible for supervising the on-site services.

3.3 Affordability and financial sustainability

- Summarize the budget and financing of the IPV introduction, as presented in Annexe D.

- Provide the method used to estimate these costs.

- Include the identification of the non-vaccine operational costs for introduction and whether funds are secured.

- Discuss the overall trend of country immunization financing, of both government funding and donor funding (if applicable), and plans to absorb the additional costs of the IPV.

- If co-financing, please indicate how the co-financing amounts will be paid (and who is responsible for this).

The overall budget for the introduction of the IPV in Benin amounted to US$ 216,183 or 102,903,108 CFA francs (one hundred and two million, nine hundred and three thousand, one hundred and eight CFA francs)

1 USD = 476 CFA Francs

The main operational cost categories for the IPV introduction are summarized in the table below.

Four main technical partners will finance this launch. They are GAVI, the WHO, UNICEF and BENIN

Summary table of operational costs for the IPV introduction

|  |  |  | Government funding | Partner financial support* |  | GAVI financial support |
| --- | --- | --- | --- | --- | --- | --- |
|  | Budget lines | TOTAL COST | Amount | Name | Amount | Amount required |
|  |  | US$ | US$ |  | US$ | US$ |
| 1 | Program management and coordination | 710 |  |  |  | 710 |
| 2 | Planning and preparations | 9.454 | 4740 |  |  | 4714 |
| 3 | Training and meetings | 67.752 |  |  |  | 67.752 |
| 4 | Social mobilization, IEC and Advocacy | 23.845 |  | UNICEF | 23.845 |  |
| 5 | Reproduction of materials | 17.700 | 17.700 |  |  |  |
| 6 | Daily allowances paid to employees and volunteers |  |  |  |  | 0 |
| 7 | Equipment and maintenance of the Cold chain |  |  |  |  | 0 |
| 8 | Vehicles and transport | 882 |  |  |  | 882 |
| 9 | Materials for immunization sessions |  |  |  |  | 0 |
| 10 | Waste management | 0 |  |  |  | 0 |
| 11 | Monitoring and follow-up | 38.067 |  | WHO | 32.083 | 5984 |
| 12 | Post-introduction Evaluation | 37.815 |  | WHO | 37.815 |  |
| 13 | Technical assistance |  |  |  |  | 0 |
| 14 | Others: Strengthening the capacity of laboratory networks | 19.958 |  |  |  | 19.958 |
|  | Total | 216.183 | 22440 |  | 93743 | 100000 |

From this table, the contribution of the main partners is as follows:

- GAVI:   US$ 100,000 or 46.26%

- WHO:   US$ 69,898 or 32.34%

- UNICEF: US$ 23845 or 11.03%

- BENIN: US$ 22,440 or 10.37%

The IPV is not a new vaccine, it will not be co-financed, and hence, after the support for introduction, Benin must work towards procuring this vaccine in routine immunization

Cost calculation methodology

The social mobilization, training, monitoring and program management activities were budgeted based on the resources required for their implementation and then included in the Excel file. The standards applied are those generally used for immunization activities in Benin.

The methodology used for calculating these various vaccine and input costs were entered in the “Data input” and “Financing” sheets of the Excel costing file.

The vaccine and input requirements are reviewed as soon as the Excel file is filled, to consider the budgetary constraints and to be more efficient. The costs given below are those from the requirements and resources estimated per year.

- Resource requirements from 2014 - 2018

The table below gives the financial resource requirements for 2014-2018. The overall financial resource requirement is estimated at USD 104,001,913 for the period. These costs are distributed annually as follows:

Table 20: Summary of resource requirements for EPI 2014-2018

The table below gives us an overview on the IPV cost projections for 2014 - 2018 in EPI Benin

|  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total cost of vaccines and injection material with the IPV |  | $7,530,260 | $8,159,699 | $35,701,576 | $33,052,416 | $13,126,074 | $13,962,149 | $104,001,913 |
|  | Vaccines | $7,269,606 | $7,877,258 | $35,313,571 | $32,646,287 | $12,755,365 | $13,528,365 | $102,120,847 |
|  | Injection supplies | $260,654 | $282,440 | $388,005 | $406,128 | $370,709 | $433,783 | $1,881,066 |

# Financial sustainability of EPI

The IPV introduction in routine EPI, a commendable initiative that can guide in the future, its integration in the immunization program leads to additional costs to the program. The cost projection will be completely clarified during the cMYP review which will be conducted in 2016 during the introduction of the MenAfriVac vaccine. But in the meanwhile, strategies for resource mobilization should be developed for the financial sustainability and viability in the national plan to ensure effective vaccine independence.

One of the strategies is advocacy for resource mobilization with the Government for increasing its participation in procuring vaccines. This advocacy is based on the current display of the Government’s commitment to increase the health budget by at least 10%. The increasing willingness of the partners (USAID, UNICEF, WHO, Bilateral etc...) to continue to support the program is a guarantee that the contributions will be maintained and increased. Added to this is the stated desire of the Ministry to implement the common basket (SWAP), which will help share more with the programs such as HIV/AIDS, malaria.

3.4 Overview of cold chain capacity at district, regional and central levels

- Describe the adequacy of storage capacity for the IPV at each level of the cold chain, based on the vaccine supply and distribution system planned for the introduction.

- Where capacity is deficient, provide an estimate of needs and budget for increased transport and cold chain at central level (cold rooms, refrigerators, cold boxes and icepacks, vaccine carriers) to accommodate the IPV.

- Provide evidence of availability of sufficient funding at local levels for the ongoing power supply and maintenance of any new cold chain equipment.

With the contributions from Partners like GAVI, UNICEF, WHO etc., to the development, Benin currently set-up 4 positive cold rooms with a gross total capacity of 45,000m3 and 1 negative cold room of a gross total capacity of 15,000 m3. They are each equipped with two refrigeration units. EPI also provides 3 refrigerators (3 TCW 1152), with a net total capacity of 752 liters. Two emergency generators ensure the continuity of the operation of the cold rooms in the event of a power cut.

On the other hand, the EVM carried out in 2012 showed that there is an insufficient storage capacity at the central level. As part of the Health system strengthening and implementation of the cold chain capacity improvement plan at the central level, four positive cold rooms of 40 m3 each and one negative cold room of 20m3 are being installed with GAVI support.

The following table shows the annual net volume requirements and delivery schedule

|  |  | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Net available storage capacity of the cold chain, including expected (liters) |  | 12.162 l | 12.162 l | 43.243 l | 43.243 l | 43.243 l | 43.243 l |
| BCG | lyophilized | 1.138 l | 1.175 l | 1.010 l | 1.043 l | 1.087 l | 1.036 l |
| OPV | liquid | 2.059 l | 2.125 l | 2.193 l | 2.263 l | 2.359 l | 2.379 l |
| PCV-13 | liquid | 21.697 l | 22.388 l | 23.110 l | 23.848 l | 24.853 l | 25.654 l |
| DTP-HepB-Hib | liquid | 4.020 l | 4.146 l | 4.532 l | 4.675 l | 4.876 l | 4.915 l |
| Measles | lyophilized | 1.927 l | 1.990 l | 1.507 l | 1.554 l | 1.640 l | 1.587 l |
| YF | lyophilized | 2.657 l | 2.743 l | 2.077 l | 2.142 l | 2.261 l | 2.189 l |
| TT | liquid | 3.075 l | 3.171 l | 3.273 l | 3.519 l | 3.873 l | 4.149 l |
| HPV | liquid | 0 l | 0 l | 9.251 l | 9.548 l | 0 l | 0 l |
| Men_A | lyophilized | 0 l | 0 l | 0 l | 0 l | 952 l | 1.375 l |
| IPV | liquid | 0 l | 0 l | 1.183 l | 1.220 l | 1.646 l | 1.697 l |
| Net annual total volume of vaccine storage, including reserve |  | 36.572 l | 37.738 l | 48.137 l | 49.812 l | 43.546 l | 44.981 l |
| all the vaccines (liquids & lyophilized) | at +5°C | 28.792 l | 29.705 l | 41.350 l | 42.810 l | 35.248 l | 36.415 l |
| OPV only & if possible lyophilized vaccines | at -20°C | 7.780 l | 8.033 l | 6.787 l | 7.001 l | 8.298 l | 8.566 l |
| Minimum no. of deliveries that the current capacity can support, including reserve stock |  |  |  |  |  |  |  |
| positive Cold chain (+2°C to +8°C) | at +5°C | 1.9 | 2 | 2.8 | 2.9 | 2.3 | 2.4 |
| negative Cold chain (-25 °C to -15°C) | at -20°C | 1.3 | 1.3 | 1.1 | 1.1 | 1.3 | 1.4 |

With respect to the Cold Chain at the central level, it is clear from the above table that from 2014 to 2018, with a delivery schedule of the central level at least twice a year for the IPV vaccine, the national level does not need additional Cold Chain capacities.

#### At the department level

From 2013, in Benin, with a rhythm of 3 deliveries per year, all the departments have sufficient cold chain capacities. This will facilitate the introduction of the IPV

#### At the peripheral level

In the health facilities where routine activities are conducted, the equipment available complies with WHO/ UNICEF standards.

In terms of available storage volume, all HCs have sufficient capacity to store routine vaccines for a supply period of one month. They are normally equipped with a refrigerator and freezer. Regarding the storage of vaccines, at least 82% of HCs have a proper storage of vaccines in the cold chain. However, in some of the health facilities, it was observed that they are not compliant with the current regulations but this does not prevent quality storage of the IPV vaccine.

3.5 Waste management and injection safety

- Describe existing injection safety and waste management activities and detail whether any changes are needed to accommodate the IPV in line with national policies and how and when this will be ensured.

- If a country self-procures vaccine delivery devices, provide information on whether these devices are WHO pre-qualified, and if not, the process in use at national level for the licensure of their use in the country.

#### Injection safety

Injection safety is one of the key factors in quality immunization services. The declaration of the national EPI policy in Benin reiterates the urgent need to ensure injection safety by using sterile injection material and the safe disposal of waste. Four requirements are required to ensure injection safety:

- Use of sterile injection material

- Observation of safe injection practices

- Safe destruction of waste.

- Management and use of injection material

Injection material for immunization activities mainly consists of Auto-disable syringes (AD syringes) for administering injectable antigens, safety boxes to collect used syringes and cotton swabs. Proper use of injection material involves its availability at all immunization points, adequate vaccine supplies, good immunization practices and the proper elimination of used needles.

#### Availability of injection material

Today, all health facilities in Benin, have auto-disable syringes (AD syringes) and safety boxes. This material provides greater assurance of safety.

To ensure a bundling of more than 95% everywhere, monitoring consumable stocks and vaccines will be strengthened especially in departments and municipalities.

#### Use of injection material

The results of the review on the use of injection material shows that auto-disable syringes (AD syringes) are used by all the health facilities.

#### Injection practices, use and elimination of used injection material

The following data was collected during the review:

- cleanliness of the injection preparation tables in health facilities;

- cleansing the skin before injection using a clean swab;

- reconstitution of lyophilized vaccines with appropriate diluents;

- Use of a single use dilution syringe by vials.

Efforts will be made to increase staff awareness on these best practices during supervision and training.

#### Injection waste disposal practices

Of the 736 Health Centers visited during the inventory conducted in 2013, 420 of them have a functional incinerator. For those who do not have one, a conveyor system for safety boxes is set up for their incineration.

#### Transport for EPI

#### At the central level:

Refrigerated vehicle of the central level has a breakdown. However, the Directorate of Logistics provided the refrigerated vehicle from the Central Purchasing of Essential Drugs of the Ministry of Health. It also uses other refrigerated vehicles from the private sector.

#### At the intermediary and peripheral levels:

All the Health Areas have a vehicle to conduct immunization activities, transport and distribution of vaccines and inputs.

Transportation is maintained by Departmental Directorates and Health Areas. Sometimes, these facilities get the support from the Ministry of Health which still has administrative difficulties. Efforts are still being taken and financial departments of the Ministry have been contacted for lightening these procedures.

3.6 Health worker training and supervision

- Describe the current adequacy of trained human resources to introduce the IPV across all sectors of the immunization program, e.g. for vaccine storage and management, in-country distribution, training of healthcare workers at peripheral levels, supervision, delivery, etc.

- Describe how any additional needs will be addressed.

- Provide information on the development and provision of training materials for the IPV, e.g., handbook for health workers, FAQs, fact sheets, training video, posters, pre and post-knowledge tests, etc.

- Describe the training plan, method, and any refresher training on immunization practices (e.g. injection safety, AEFI communications, etc.).

- Outline any plans for increased supervision activities before, during and after the introduction of the IPV.

### Benin has staff which is trained and accustomed to EPI management at all levels of the health pyramid. As part of the IPV introduction in the vaccine system, the issue is in organizing training workshops supported by a supportive supervision by covering up the errors after introduction.

### Immunization staff training

## Training health staff (immunization staff) is a crucial step in the IPV introduction. It must be carefully planned and finalized before introduction. WHO training guides and materials will be used for training staff. Appropriate training material will be prepared for briefing staff on IPV specifications for vaccine storage and administration. The trainers will ensure the availability of vaccine samples and other demonstration material during the training to familiarize staff on the use of this vaccine.

## The training will be conducted in phases.   For this purpose, a fact sheet will be prepared for trainers, training supervisors of the national trainers who will train the departmental trainers. They will in turn train the trainers of health areas. Finally, the trainers of the health areas will train the service providers.

## Supportive supervision

The experience of introducing new vaccines in Benin showed that there can be slippages due to inadequate training. A post-training evaluation of service providers should be conducted for three months following the introduction of a vaccine to ensure that the implementation is carried out normally. Consequently, a financing will be mobilized so that the supportive supervision is conducted before, during and immediately after the introduction. There will be a special focus on the low performing municipalities

3.7 Risks and challenges

- Identify risks and challenges to the new vaccine introduction – e.g. financial, mobilization of communities, programmatic, etc., - and outline the plans to address them.

| Domains | Major risks | Challenges | Plans to address them |
| --- | --- | --- | --- |
| Financials | Expensive and inefficient financial intervention | Cost of the IPV introduction | - Advocacy for mobilization of additional EPI resources |
| Programmatic | - Emergence of a spreading vaccine-strain derived polio virus (SVSDPV); when the countries simultaneously stop using OPV; - Reintroduction of polio virus from a vaccine manufacturing site, research center or diagnostic laboratory. - Onset of AEFI - Increased vaccine wastage rate due to vaccine packaging | Eliminate vaccine associated paralytic poliomyelitis (VAPP) and eradicate poliomyelitis | - Technical and financial support from Partners. |
| Linked to community mobilization | - Non-adherence to the IPV introduction - Acceptability of the IPV immunization by the people | Strengthening communication | - Awareness - Communication and education - Advocacy to opinion leaders |

4. Situational analysis of the immunization program

4.1 General context of the country

- Summarize the country context, health system, health priorities and the organizational structure of National Immunization Program.

## 4.1.1. National context

Benin is a West African country which extends between Niger in the North and the Atlantic Ocean in the South. It is bordered by Burkina Faso in the North-West, Togo to the West and Nigeria to the East. Its area is 114,763 km². Its topography is characterized by plains and crystalline plateaus in the southern region of the country that gradually rises towards the north where the altitudes reach to 641 m (Atacora department). Three climatic zones can be distinguished from North to South: dry tropical climate in the North, semi-humid tropical climate in the center and humid tropical climate in the South.

Benin's population was estimated at 9,671,591 inhabitants in 2013 of which 50.87% are women. Children under 5 years are estimated at 1,714,148 or 17.72% of the total population. Approximately 54.2% of the population lives in rural areas.

Benin is divided into 12 Departments (Atacora, Donga, Borgou, Alibori, Zou, Collines, Mono, Couffo, Atlantic, Littoral, Ouémé, and Plateau), 77 Municipalities, 546 Districts and 3,557 Villages or Towns. A new law passed by the National Assembly on February 18, 2013, brings the total number of villages to 5,300

According to 2011 ranking by the Central Intelligence Agency or CIA (CIA Fact book), Benin is ranked 198th of 225 in terms of GDP. In fact, the per capita GDP is US$ 1,500 or 750,000 CFA francs in 2011 and approximately 1/3 of Benin’s population lives below the poverty line. On the macroeconomic level, the economic growth rate increased from 5% in 2008 to 3.5% in 2012. In the health care sector, the nominal budget allocations reduced during the last 5 years. They reduced from 111.354 billion in 2009 to 71.757 billion in 2013. On the other hand, the inflation rate increased from 2.3% in 2010 to 3.1% in 2012. This rate can be at 5% in 2013. The outstanding debt (in % of GDP) tends to fall since 2003, mainly due to the debt relief obtained under the HIPC initiative. These obtained facilities will finance the social sectors primarily (education, health). ⁶. The evolution of tax revenue represents a rising trend and fiscal consolidation has enabled the Government to strengthen its commitment to the EPI by initiating the Vaccine Independence Initiative (VII) in 1996. Note that Benin has financed all its vaccine requirements for traditional vaccines since 2000.

## 4.1.2. National Health System

The Ministry of Health is responsible for the Promotion of Health in Benin. For this, it is responsible for:

- designing, implementing and monitoring the national health policy,

- identifying and suggesting to the Government, if required, strategies and action plans in accordance with the health policy, in consultation with other ministerial departments;

- Developing and implementing training policies and update the health staff, in collaboration with other ministerial departments.

- Implement the Government’s decisions in the areas of health and basic sanitation.

All priority activities of the Ministry of Health contribute in achieving MDGs (4; 5; 6) and are to:

- Improve the quality and access to health services;

- Improve participation of the community and its use of health services;

- Improve the general public's medical coverage, especially for the poor and needy

The national health system is organized based on a three-tier pyramid structure (central, intermediate and peripheral) modeled on the territorial division. The central level consists of the Minister’s office with 3 Departments attached to it, 4 National Agencies including the National Immunization Agency and Primary Health Care (NIA-PHC), 3 Central Directorates, 7 technical directorates and University Hospitals. The intermediary level consists of six (6) departmental directorates of health (DDH), with their intervention zone modeled on administrative departments (old division). They are responsible for the planning, coordination, supervision and monitoring/ evaluation of all health activities in the department.  The peripheral level forms the base of the health pyramid. It is represented by 34 health areas distributed throughout the country. The health area represents the decentralized operational entity of the health system where curative, preventive and promotional activities are conducted. The health area is made up of health facilities of one or more municipalities, is organized as a public service (maternity homes, dispensaries and Health Centers) and private primary care service network, all supported by a public or private referral hospital (area hospital). Each health area covers a population of 100,000 to 200,000 inhabitants. All these facilities are coordinated by the General Secretariat of the Ministry of Health who monitors the activities.

## 4.1.3. Healthcare priorities

For the decade from 2009-2018, Benin developed a national health development plan which emphasized five priority areas, namely:

- Prevention and fight against disease and improving the quality of health care

- Valuation of human resources Strengthening partnership in the sector and promotion of ethics and medical responsibility

- Improving financing mechanisms of the sector

- Strengthening sector management

To fulfill its mission of “improving socio-medical conditions of families based on a system integrating poor and indigent population”, the Ministry of Health of Benin made the fight against disease as one of the priorities of the sector. As part of achieving the Millennium Development Goals by 2015, the Ministry of Health seeks to improve the performances of the Expanded Program on Immunization implemented by NIA - PHC with the support from its major Partners.

The Expanded Program on Immunization (EPI) aims to reduce the morbidity and mortality caused by diseases preventable by vaccination. As part of routine immunization which is conducted under a fixed and advanced strategy, all antigens selected in the program should be administered to children before their first birthday and to pregnant women. Following the introduction of new vaccines between 2002 and 2011, the number of vaccines administered under EPI increased from six (6) to ten (10) covering ten (10) diseases. The immunization services are offered through 855 health facilities (public and private) distributed across 34 health areas of the country. These services are offered to the target population through fixed and advanced strategies. Apart from the public facilities, the immunization activities are also offered to para-governmental, private and religious facilities. All the public-sector health centers, in both fixed and advanced strategy, offer immunization services according to a plan.

## 4.1.4. National Agency for Immunization and Primary Health Care

Established in 1982, after multiple restructurings, the Expanded Program on Immunization of Benin became a National Agency for Immunization and Primary Health Care by Ministerial Decree No. 2011-413 dated May 28, 2011.

It generally aims to implement the national health policy in the Immunization areas and Primary Health Care centers. For this, it is responsible for:

- Follow-up and coordinate the activities of the Expanded Program on Immunization;

- Ensure logistics management for immunization and primary health care;

- Follow-up and evaluate the implementation of the Bamako Initiative;

- Implement the Ouagadougou declaration on reviving primary health care;

- Ensure decentralized operation of health services to the village level, by creating or strengthening the Village Health Units (VHU).

For its operation, the NIA-PHC has an Administrative Council (AC), Directorate General with a Management Committee, three technical Directorates (Immunization Directorate, Primary Health Care Directorate, and Logistics Directorate), an Accounts Manager, administrative Secretariat, an Accountant and a Resources department.  The immunization activities are coordinated at the central level through quarterly meetings of the EPI Inter-Agency Coordination Committee (ICC) bringing together all concerned technical directorates and departments and partners.  The ICC is chaired by the Minister of Health and has three technical sub-commissions; the immunization and monitoring commission, the social mobilization commission and the logistics commission.  Several committees involving a specific immunization domain were installed. They are:

- National Committee for the Eradication of Poliomyelitis in Benin (NCEP)

- National Committee for the Certification of Poliomyelitis in Benin (NCC)

- National Consulting Committee for Immunization and Vaccines (NCCIV-Benin) in Benin

- AEFI Expert Committee (EC)

All members of these committees were nominated by the Minister of Health and are experts from Benin and specialists from various fields.

4.2 Geographical, economic, policy, cultural, gender and social barriers to immunization

- Please complete Table B2 below to report immunization coverage data for the two most recent years. As a part of the priority for gender parity and equity, please report disaggregated coverage data based on sex if available.

Table B2. Trends in national vaccine coverage

| Trends in national vaccine coverage (percentage) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vaccines | Vaccine Used 2012 | Target population in 2012 (number by age and sex, if available) | Coverage reported (JRF) |  |
|  |  |  | Most recent year (2012) | Previous year (2011) |
| BCG | 657.200 | 385.873 | 112 % | 109% |
| OPV3 | 1,170,600 | 360.020 | 100 % | 101% |
| Penta1(DTC-Hep-Hib1) | 1,182,900 | 360.020 | 110 % | 111 % |
| Penta3(DTC-Hep-Hib3) |  | 360.020 | 100 % | 101 % |
| HPV1 | N/A | N/A | [NA] | [NA] |
| HPV3 | N/A | N/A | [NA] | [NA] |
| Measles 1 | 400.200 | 360.020 | 94% | 94 % |
| Measles 2 | N/A | 360.020 | [NA] | [NA] |
| PCV13_1 | 1,159,550 | 360.020 | 109 % | 59 % |
| PCV13_3 |  | 360.020 | 99 % | 36 % |
| Rota 1 | N/A | N/A | [NA] | [NA] |
| Rota 2 or 3 | N/A | N/A | [NA] | [NA] |

- Please describe any specific geographical, economic, policy, cultural, gender and social barriers to immunization. Given the priority of GAVI to ensure gender parity and reduce inequity in immunization services, please describe any gender and/ or equity analyses that have been conducted including actions taken to mitigate barriers.

From a geographic perspective, note the temporary existence of a few geographic obstacles in achieving the targets. They are the difficult access to certain areas especially in the rainy season; which could affect the active search of delayed targets or immunization in the advanced strategy.

From an economic perspective

In Benin, free routine immunization is made effective by the government’s commitment and with support from TFPs who facilitate the achievement of targets, irrespective of the location and without gender discrimination

From a political perspective, we note the political interest and commitment to the Vaccine Independence Initiative in Benin since 1996. However, we must acknowledge that all the available policy documents do not provide a clear vision of activities to be conducted to improve the health status of the population. Moreover, the existence of these policy and strategy documents is hardly known at the decentralized level.

From a sociocultural perspective, we are witnessing the development of an adverse belief on immunization which fortunately did not prevent or

hindered very few parents from immunizing their children. The reluctance is mainly observed during mass campaigns for the fight against poliomyelitis using OPV.

There is no gender bias for immunization in Benin. As per the results of the 2008 Review and Demographic Health Survey 2011-2012, parents haven’t declared having gender preference to immunize one child over another: “Every child should be immunized to be protected from diseases preventable by immunization”.

4.3 Findings from recent program reviews

- Highlight key competencies/ strengths of the immunization program that make it feasible to carry out the IPV introduction – including recent changes to address any previously identified weaknesses.

- Summarize findings from recent program reviews, indicating whether the recommendations are part of a subsequent national Plan of Action, and describe the status of implementation of recommendations and how these will impact on the proposed new vaccine introduction.

- Highlight whether there are resource constraints in implementing recommendations from recent reviews and how these will be overcome.

- Describe any previous experience with introducing a new vaccine and how lessons learned will be used to ensure a smooth introduction of the new vaccine under consideration.

Benin conducted the efficient vaccine management evaluation in 2012 which revealed a lack of capacity of the cold chain at all levels of the health pyramid.

The improvement plan prepared to correct these weaknesses received financial support from GAVI/ HSS. This support helped rehabilitate the Cold Chain at the central level. Support from the government and other Partners helped build a regional Cold Chain in Atacora and provide five refrigerators and a hundred motorcycles for health facilities.

All this will facilitate the logistical introduction of the IPV.

Experience of introducing new vaccines in Benin’s program

Like most countries, Benin also introduces new vaccines in its program and attempts to implement the strategies proposed in the GIVS. Thus, the introduction of new vaccines into the Routine EPI in Benin started in 2004 through the Yellow fever vaccine, through Hepatitis B vaccine in 2005, which contributed to an improvement in immunization coverage and a strengthening of the immunization system. To further increase the minimum vaccine package administered to children aged 0-11 months and maintain immunization coverage at high levels, the vaccine against Haemophilus Influenza b was introduced in 2009 as a Pentavalent and one against Streptococcus Pneumonia in 2011. (See immunization schedule)

For this, Benin prepared a new vaccine introduction plan (2011) which defined the terms and milestones for this introduction. These include:

- Strengthening the EPI logistics system: Evaluation of cold chain equipment, requirement identification, order and receipt of vaccines;

- Strengthening of staff capabilities: Revision of training modules and management tools, training the trainers with support from IST consultants, training health workers;

- Setting up vaccines and injection material in the departments, municipalities and health centers in June 2011.

- Communication: Preparation and production of communication tools, conducting a briefing workshop for media communicators on the introduction of the PCV13 vaccine, distribution of micro-programs on local radio and television channels;

- Official launch of the new vaccine introduction

- And supervision and monitoring the introduction.

Currently, it is preparing for introducing the first dose of the IPV. The main criteria facilitating the IPV introduction are:

- system performances (performing EPI, operational ICC, existence of a multi-year plan, vaccine independence for routine antigens);

- ability to administer several antigens at once;

- GAVI financial support.

- Public support for new vaccines (vaccine against Hepatitis B and yellow fever vaccine, Hib, PCV13).

- A good planning and a good co-ordination of activities

With respect to the above, Benin has experienced staff for the IPV introduction.

4.4 Stock management

- Provide a brief overview of the stock management system in use in the country, i.e. whether computerized, manual or other, highlighting foreseeable issues in stock management with the IPV introduction and how these will be addressed.

- Provide a description of the transport system available for the delivery of vaccines to the periphery, how this will accommodate the IPV, whether the frequency of deliveries need to be increased, and if so, whether there are sufficient funds, e.g. for vehicles, drivers fuel, and per day for the distribution of the new vaccine at all levels.

- The monitoring and control of vaccine and consumable stock is required for quality immunization services. The quality of this monitoring is primarily based on a good input movement recording system (inputs and outputs). Registration, focused not only on basic input output information (quantities, batch, expiry date...), but also on specific information on beneficiaries/ recipients (location...).

- Manual stock management registers and sheets for vaccines are also used and normally updated. Stock management tools are available in departmental depots and are up to date.

- The health centers mainly use stock sheets to monitor vaccines and injection material. Basic information, like the batch number and expiry dates, are not always recorded, especially when only one batch per antigen is received at a time. The immunization data collection tools (doses and vaccinated children) were provided to the health facilities of Benin. Trainings on computerized EPI management tools (DVD, SMT) were provided at the departmental level with a post-training follow-up of all EPI managers. This training was extended to the municipality level for a better use of these tools.  For diluents and injection materials, a physical inventory at all intermediary depots was conducted regularly (twice a year).

- The annual vaccine requirements are estimated by the government with the technical support from UNICEF which plans the orders according to its regular supply mechanisms. Once the vaccines are received in the country, they are stored in the central cold room and distributed every quarter to the departments. This mechanism has some advantages which ensure that the vaccines are of good quality and affordable at purchase due to the UNICEF group order system and short delivery schedules. UNICEF and the WHO significantly contribute to the vaccine distribution and storage mechanism.

- The vaccines are supplied upwardly at all levels of the EPI system. The lower levels calculate their requirements and route their requests to the next level that supplies them. The peripheral level is supplied on a monthly basis and intermediate level is supplied every quarter. The central level is supplied twice a year.

- Figure 2: Vaccine supply circuit

- Legend:

- Fabricant = Manufacturer

- 2 fois l’an = twice a year

- Depot central = Central depot

- 4 fois l’an = 4 times a year

- Tous les mois = Every month

- District sanitaire = Health District

- Centre de Sante = Health Centre

5. Monitoring and evaluation

5.1 Updating of monitoring tools

- Describe measures to update, print and distribute EPI monitoring and supervision tools (recording and reporting formats, including tally sheets, registers, immunization cards, wall charts, computerized database, other) to include the IPV and other new vaccines envisioned in the current cMYP, prior to the launch of the IPV.

- In line with GAVI’s policy advocating for gender equality as a means to improve coverage and access to services, please be sure all immunization tracking forms can collect and report vaccine delivery by sex, if current forms do not already do so.

## Revision of EPI management tools and other documents

Hib

The introduction of the IPV in the program will require revision of certain documents as the EPI tools were updated in 2013 and did not consider the introduction of new vaccines. This revision will focus on the following points:

- Time sheets (fixed strategy, advanced strategy)

- Child register

- Health records

- Child cards

- Coverage curve graph records

- C6 monthly reports

- C7 reports

- Monitoring sheets for vaccine wastage and following-up on the unvaccinated

- Vaccine stock sheet

- A25 vaccines and supplies management sheet

- A26 vaccines and supplies management sheet

- AEFI information collection sheet

- Computerized management tools for vaccines and supplies (DVD MT and SMT)

As per the current schedule for Benin, DTP-HepB-Hib immunization will be administered at 6, 10, 14 weeks of life. As before, all other vaccines will be introduced and administered, according to the recommendations of the Strategic Consulting Group of the IPV Experts, to the child along with DTP-HepB-Hib3. So, the following words must appear on all monitoring documents: DTP-HepB-Hib3/IPV.

For children lagging behind on the schedule and who will be seen after 3 months, it is recommended to administer the IPV with the DTP-HepB-Hib1 at first contact and complete it with DTP-HepB-Hib1/IPV and update the track sheet, register, health card and child card. Then, these documents will be printed, distributed and provided to all the levels. Obviously, this activity must be completed well before the staff training so that the tools are finally shown for discussion and consensus for their use.

Since January, Benin has been preparing the EPI review, the last review was in 2008. The revised cMYP 2014-2018 prepared in 2013 was scheduled to be updated by considering the current review. This updated cMYP will include the IPV.

## Supportive supervision

The experience of introducing new vaccines in Benin showed that there can be slippages due to inadequate training, lack of training before introducing vaccines or inadequate supervision. The frequency of supervisions should be increased for three months following the introduction of new vaccines to ensure that the implementation is carried out normally. Therefore the funding will be mobilized so that intense training can be conducted before the introduction with a specific emphasis on low-performing districts. For this purpose, a fact sheet will be prepared before the training to be used by the trainers and supervisors during the training and implementation of activities.

5.2 Adverse Event Following Immunization (AEFI) monitoring and reporting

- Provide information on the national AEFI policy, e.g. describe the national capacity to implement pharmaco-vigilance, AEFI investigation and response to AEFIs, to address relevant rumors and potential allegations.

- Provide information on a national AEFI Expert Review Committee (if available) and methods of establishing causality assessments of AEFI.

- Describe the process and procedures for monitoring adverse events following the IPV introduction at local, district, region/ provincial and national levels.

AEFI monitoring is an important activity of the immunization department which is still not completely implemented into the routine EPI. However, during these mass campaigns, specific emphasis is placed on communication and management of AEFI cases.

With the preventive immunization campaign against meningitis A which was conducted in November 2012, an AEFI management team and AEFI experts committee (reference) already exists at the central level. It also had a focal point for AEFI management by department. These committees will be revived and focal points will be replaced.

For the IPV introduction, AEFI monitoring will be strengthened with the establishment of guidelines as part of the routine EPI and its notification tools. A team will be formed which will be responsible for the follow-up and investigation of severe AEFI cases (investigation and communication with people) for all possible serious AEFI cases after the IPV introduction. The measures taken during the introduction of pneumococcal and the campaign against meningitis A will again be strengthened with a briefing to pediatricians.

The central level team will be responsible for:

- Ensuring the daily monitoring of reported AEFI cases, especially serious cases. Once an alert for a serious AEFI case is given, a case sheet will be completed by the team and the case history will be updated with additional investigation results and proceedings from the experts committee;

- Providing the interface between the experts committee and clinicians responsible for serious cases for their investigation and appropriate care;

- Ensuring total coordination of AEFI monitoring activities, including supervision of participating teams;

- Provide secretariat for the experts committee and prepare the final report for this committee.

The AEFI experts committee will meet once a month for the first 6 months of the introduction and later once a quarter, to examine the reported cases, propose additional tests, if any, and to take appropriate care. The case by case accountability analysis will be made according to the algorithm developed for this purpose.

- If required, special meetings can be convened by its President.

- Apart from the meetings, expert opinion on an AEFI case, depending upon their discipline, may be requested by a member of the central AEFI team, to ensure proper investigation of the patient and to take appropriate care during his/ her hospitalization.

6. Advocacy, communication and social mobilization

- Describe the plans to sensitize political and opinion leaders at national, regional and district levels on the IPV introduction, benefits to the population and contribution to the polio Endgame Strategy.

- Describe the development of a communication strategy for the IPV introduction at community level with the identification of key messages, communication channels and methods for greatest impact. If relevant, describe how results of knowledge, attitude, practice and behavior (KAPB) and/ or barriers to immunization studies were used to inform the communication strategy for the IPV introduction.

- Describe development of information, education and communication (IEC) materials, focus groups and anthropological assessments and media outlets for key target audiences as appropriate.

- Describe plans for a national launch ceremony, if required and sub-national ceremonies if appropriate including the potential promotion of immunization in general, as well as of relevant comprehensive approaches to disease control.

In the context of introducing the first dose of the IPV in Benin, a communication plan will be prepared and this plan will include the strategies, activities and people from various targets. Hence, awareness sessions and advocacy will be organized for opinion leaders, policy and administrative decision-makers, medical journalists, radio presenters and members of the national AEFI committee.

Departmental orientation workshops for health professionals and briefing of journalists and presenters from Partner radio stations and members of AEFI committee will be organized, on the other hand, a national workshop will be organized for all major media to elaborate various media plans specific to each medium and also prepare key messages to the local administrative political authorities.

Health workers, including clinicians, will be trained on the IPV introduction. They will also be trained on inter-personal communication which will help them to discuss the advantages of the IPV introduction and Final Strategy on the eradication of Polio, by using simple and clear messages and appropriate media.

These health workers will be equipped to educate the communities on the IPV introduction and Final Strategy for Polio. This will be done in collaboration with resource persons through national communication and departmental health management teams.

At the community level, women associations will be supported by communal teams

These women groups can compose and sing educational songs on HPV and Final Polio Strategy.

The traditional communicators (town criers, griots and community volunteers) will also be used as health communication agents in the community.

Contracts will be signed with community radios and commercials for broadcasting radio messages and radio plays on the advantages of the IPV  introduction. The health officers will host programs on these radio stations.

A national launch will be made at the central level before the IPV introduction; this launch will be presided by the Minister of Health with the involvement of government members, diplomatic corps representatives, members from the leader groups and Technical Development Partners.

During the launch, the role played by the IPV will be demonstrated by folk groups.

Crisis communication will be made, for managing rumors, at all levels, by the communication teams which will be implemented at municipality level.

GAVI will calculate vaccine and AD syringe supply based on target population totals given and vaccine preference specified, factoring in appropriate wastage rates for the vaccine preference in this application and buffer stock allowances (25% in the first year). If there are differences between country and WHO-UNICEF coverage estimates, the Secretariat will default to the latter when estimating vaccine requirements.

National Geographic Institute, 1998.

Law no. 97-028 dated 15 January 1999.

Law for the creation, organization, attribution and operation of administrative and local units in the Republic of Benin

http://www.statistiques-mondiales.com/taux_de_croissance.htm