
[image: image1.png]AAAAAAAA




Application Form for Country Proposals   
Providing support for IPV Introduction    
Submitted by 

The government of [BENIN]   

Date of submission: [1st May 2014]   

This form is applicable to applications submitted in:   

February 6, 2014
Or 
 March 30, 2014

New deadlines for 2014 and 2015 will be issued on an updated form.    

Please send your request using the form provided for this purpose.   

Enquiries to: proposals@gavialliance.org  or representatives of a GAVI partner agency. The documents may be shared with GAVI partners, collaborators and the general public. The application and attachments must be submitted in English, French, Spanish, or Russian.    
Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.    

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.   
Application Specification  
A list of required attachments is included at the end of this form.   
Summary    
	The Government of: BENIN   

	Date of Submission:   May 1st, 2014


	IPV introduction date (month/ year): June 2015

	Current DPT schedule: 
1st dose
  6th week
2nd dose
  10th week
3rd dose
  14th week


	Co-financing (yes/no): No
	If co-financing, please specify amount ($) per dose: N/A


	Procurement mean (UNICEF SD, PAHO, self-procurement): UNICEF supply division

	
	

	Vaccine preference (in order of first to third): 
	Reason for choice of presentation 

	Expected wastage rate*:


	1. 10 doses 
	1. Introduction of IPV currently pre-qualified by WHO and available in sufficient quantity.
Affordable  
GAVI support provided for now 
Following these reasons, Benin opts for this package for the introduction the first dose of IPV

	1. 50% 

	2. 5 doses 
	2.  This packaging is currently not available and will be in limited quantity in 2014, main reasons for its selection in second position. 
Note: When this packaging will be in sufficient quantities, Benin will consider using it by replacing the 10-dose packaging to reduce the wastage rate and reduce the missed opportunities of targets with its corollary of increased immunization coverage.

	2. 30%

	3. 2 doses
	3. This is the ideal presentation but it is very expensive and still not certified by the WHO
	3. 10% 

	
	
	* Cannot exceed 50% for 10-dose vials, 30% for 5-dose vials, 10% for 2-dose vials, or 5% for 1-dose vials 

	
	
	
	

	Year 
	Number in target population for IPV
 
	Number in birth cohort
	Number of surviving infants  

	2014
	383.719
	411.274
	383.719

	2015
	395.997
	424.434
	395.997

	2016
	408.669
	438.016
	408.669

	2017
	421.746
	452.032
	421.746

	2018
	435.242
	466.497
	435.242

	       Total
	2,045,373
	       2,192,254   
	2,045,373


IPV introduction plan  
	 
	(generic template, adjust if necessary)
	Month of the IPV introduction plan 


Using the guidance in Annexe A and the new WHO vaccine introduction template, attach your detailed IPV introduction plan as Attachment 1 to this application form.    
Timeline   
Using the Excel template provided in Annexe C, please complete a detailed time line for all activities related to the IPV Introduction Plan. The completed Annexe C should be attached to this application as Attachment 2.    
Schedule
	 
	(generic template, use if required)
	IPV introduction plan (Month) 

	 
	Activities
	Jan-14
	Feb-14
	Mar-14
	Apr-14
	May-14
	Jun-14
	Jul-14
	Aug-14
	Sept-14
	Oct-14
	Nov-14
	Dec-14
	Jan-15
	Feb-15
	Mar-15
	Apr-15
	May-15
	Jun-15
	Jul-15
	Jun-16

	1
	 Planning introduction and preparation activities
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	2
	 Organization and coordination processes 
 (Meetings of the EPI-ICC sub-commissions, 
and EPI-ICC meetings)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	3
	Reproduction of tools
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	4
	Updating of monitoring guidelines on AEFI
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	5
	Preparation of tools on AEFI monitoring
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	6
	Preparation and distribution of posters on
 cold chain maintenance and temperature
 monitoring
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	7
	Strengthening cold chain capacity
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	8
	Strengthening the capacities of the laboratory network
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	9
	Social mobilization, IEC and advocacy
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	10
	Training EPI participants and meetings of the decision-makers
 at various levels of the health pyramid
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	11
	Equipment maintenance
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	12
	Logistical organization (set up 
of vaccines and supplies)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	13
	 Launch the introduction
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	

	14
	Waste management 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	15
	Monitoring and follow-up
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	16
	Supervision and monitoring
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	

	17
	Post introduction evaluation
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	


Budget and financing   
Using the Excel template provided in Annexe D, please complete the budget template in Table E1 detailing expected expenses and funding sources. An example worksheet (Table E2) is provided to assist with estimating detailed costs for items related to vaccine introduction. The completed Annexe D should be attached to this application as Attachment 3.    
Fiduciary management arrangement data   
Please indicate below whether the one-time vaccine introduction grant for IPV should be transferred to the government, to the WHO or to UNICEF. Please attach a bank transfer application form if the funds should be transferred to the government. Please note that WHO and/ or UNICEF will require administrative fees of approximately 7% which would need to be covered by the operational funds.   
	FIDUCIARY MANAGEMENT ARRANGEMENT DATA
Funds allocated for the introduction of IPV can be transferred to the WHO
· For the partners
· Drafting of TDR by ANV and approval by TFPs
· Drafting of queries and dispatch to TFPs
· Filling FACE
· Fund transfers into bank account no.... see proof of bank details in appendix X.
· Execution of activities (implementation - payment)
· Report (financial and technical reports)
· For the national budget
· Preparation of TDR and validation
· Execution of activities
Orders
· Purchase order or contract (dispatch)
· Delivery or receipt
· Payment to the beneficiary by check
                       Co-financing 
· FORECAST
· Fund transfer to UNICEF
· Receipt of materials
    Activities
· Issuance of mission orders
· Implementation and presentation of reports
· Payment to participants



If the vaccine introduction grant for IPV should be transferred to the government, countries which have completed a financial management assessment (FMA) should confirm whether the financial management modalities – including bank details – agreed with GAVI are still applicable. Alternatively, provide details of any modification they intend to submit relating to the existing financial management arrangements. 
Countries without an existing signed Aide Memoire derived from an FMA, but who would like the vaccine introduction grant for IPV transferred to the Government, should provide a description of their proposed funding mechanism to manage the IPV introduction grant, as Attachment 4, covering the following processes:
1. Planning, budget and coordination
2. Budget execution arrangements including internal controls
3. Procurement arrangements 
4. Accounting and financial reporting
5. External audit arrangements 
6. Internal audit oversight 
Signatures
Government    
The Government of [Benin] acknowledges that this new vaccine introduction is intended to contribute to the eradication of polio as reflected the Global Polio Eradication Initiative’s Polio Eradication and Endgame Strategic Planhttp://www.polioeradication.org/resourcelibrary/strategyandwork.aspx#strategyandwork.aspx?s=2&_suid=1382372983385049930892531473775). 
The Government of [Benin] requests support from GAVI for the use of inactivated polio vaccine (IPV).   
The Government of [Benin] commits itself to improving immunization services on a sustainable basis. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support the immunization of the targeted population with one dose of IPV as outlined in this application.    
Annexe D attached shows the amount of support requested from the GAVI Alliance as well as the Government of [Benin] and partner’s financial commitment for the introduction of IPV.    
Please note that this application will not be reviewed by GAVI’s Independent Review Committee (IRC) without the signature of the Minister of Health, Minister of Finance and the ICC membership, or their delegated authority.    
Please provide the appropriate signatures below.    
	Minister of Health
 (or delegated authority)

	Name   
	[Dorothée A. KINDE GAZARD]

	Date
	

	Signature
	


	Minister of Finance
(or delegated authority)

	Name   
	[Jonas GBIAN]

	Date
	

	Signature
	


Enter family name in capital letters.  
This application has been compiled by:   
Enter family name in capital letters.   
	Full Name  
	Title
	Telephone
	Email

	[N’Déye Marie BASSABI-ALLADJI]
	[Director General of NIA-PHC]
	[00229 95426797]
	[nmab12000@yahoo.fr]

	[Evariste TOKPLONOU] 
	[Immunization Director]
	[00229 95783318]
	[tokev1@yahoo.fr]

	[Celestin GANSE]
	[Director of Primary Health Care]
	00229 95157783
	Celestinganse@yahoofr

	[Justin DJIDONOU]
	[Director of Logistics]
	00229 95494909
	Kocou_just@yahoofr

	[Rock Aristide SOSSOU 
	[WHO EPI Focal point]
	[00229 97604095]
	[sossoua@who.org]

	[Jacques HASSAN] 
	EPI UNICEF Focal point
	00229 96187731
	jhassan@unicef.org


National Coordinating Body – Inter Agency-Coordinating Committee (ICC) for Immunization or equivalent    
We the members of the ICC, HSCC, or equivalent committee confirm that a quorum of the committee met on [Tuesday April 22, 2014] to review this proposal. By the terms of reference for our committee, we endorsed this proposal at that meeting, based on the supporting documentation attached.    
The endorsed minutes of this meeting are attached as Attachment 5.    
Enter the family name in capital letters. (Refer to the attendance sheet of the ICC meeting dated April 22, 2014, in the appendix)
	Name / Title 
	Agency / Organization
	Signature

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	

	[Enter text]
	[Enter text]
	


Should the GAVI Secretariat have queries on this submission, please contact: 
Enter family name in capital letters.   
	Name 
	[BASSABI-ALLADJI N’Dèye Marie]
	Title
	[Director General of NIA-PHC]

	Tel. No. 
	[00229 21 33 75 90]
[00229 95 42 67 97] 
	
	

	Fax No.
	[00229 21 33 04 64]
	Address
	[Ministry of Health of Benin
BP 01-882]

	Email
	[nmab12000@yahoo.fr]
	
	


Attachments required   
· Attachment 1. IPV introduction plan prepared using the WHO NVPI template (see Annexe A)   
· Attachment 2. Detailed time line for key activities of the IPV introduction plan (see Annexe C)   
· Attachment 3. Completed budget and financing Tables E1 and E2 (Annexe D)   
· Attachment 4. Fiduciary management arrangement data (only applies for countries without an existing signed Aide Memoire from an FMA but who would like the IPV introduction grant transferred to the Government).
· Attachment 5. Minutes of the ICC meeting endorsing the IPV introduction plan   
· Attachment 6. A copy of the most recent comprehensive multi-year plan (cMYP). The cMYP does not need to include IPV; however, countries should specify a plan for the inclusion of the IPV into their next cMYP, including date for revision. 
· Attachment 7. A progress report on the implementation of the improvement plan from an EVM conducted within the preceding 36 months. If no EVM has been conducted or if the current EVM was conducted more than 3 years ago, GAVI requires countries to provide a description of the vaccine management system in place and commit to conducting an EVM within six months of the application being approved.     
· Attachment 8. GAVI generally procures and delivers vaccines and supplies through UNICEF or the PAHO Revolving Fund. If an alternative mechanism is requested, or the vaccine will be self-procured by the country itself, please document the requirements as listed in Section 2.3 of the Guidelines.
GAVI ALLIANCE GRANT TERMS AND CONDITIONS    
Countries will be expected to sign and agree to the following GAVI Alliance terms and conditions in the application forms. These terms and conditions may also be included in a grant agreement to be signed between GAVI and the country:     
FUNDING USED SOLELY FOR APPROVED PROGRAMS   
The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance for this application will be used and applied for the sole purpose of fulfilling the programme(s) described in this application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for this application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.    
AMENDMENT TO THIS PROPOSAL   
The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in this application. The GAVI Alliance will document any change approved by the GAVI Alliance, and this application will be amended.   
RETURN OF FUNDS   
The Country agrees to reimburse to the GAVI Alliance, all funding amounts that are not used for the programme(s) described in this application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement. The reimbursed funds will be paid to the account or accounts as directed by the GAVI Alliance.    
SUSPENSION/ TERMINATION  
The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for a purpose other than for the programs described in this application, or any GAVI Alliance-approved amendment to this application. The GAVI Alliance retains the right to terminate its support to the Country for the programs described in this application if a misuse of GAVI Alliance funds is confirmed.    
ANTICORRUPTION  
The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country directly or indirectly seek in connection with this application any gift, payment or benefit that could be construed as an illegal or corrupt practice.    
AUDITS AND RECORDS   
The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessments to ensure the accountability of funds disbursed to the Country.   
The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there are any claims of the misuse of funds, the Country must retain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.   
CONFIRMATION OF LEGAL VALIDITY   
The Country and the signatories for the government confirm that this application is accurate and correct and forms a legally binding obligation for the Country, under the Country’s law, to perform the programs described in this application.    
CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARENCY AND ACCOUNTABILITY POLICY   
The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and will comply with its requirements.   
ARBITRATION   
Any dispute between the Country and the GAVI Alliance arising out of or relating to this application that is not settled amicably within a reasonable period of time will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English.    
For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.    
The GAVI Alliance will not be liable to the country for any claim or loss relating to the programs described in this application, including without limitation, any financial loss, reliance claims, harm to property, or personal injury or death. The Country is solely responsible for all aspects of managing and implementing the programs described in this application.    
USE OF COMMERCIAL BANK ACCOUNTS   
The eligible country government is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support, including HSS, ISS, CSO and vaccine introduction grants. The undersigned representative of the government confirms that the government will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.    
Important upcoming changes to the GAVI application and reporting process





In its meeting on June 11-12, 2013, the GAVI Alliance Board approved a new Grant Application, Monitoring and Review process that will change how the Alliance calls for and reviews new applications for support, undertakes monitoring and reviews the renewal of existing support. 


All modifications will apply from 2014 onwards and all existing and new grants will shift to the new system. 


GAVI will regularly update countries with further details on these changes, and issue updated guidelines for future application rounds.











� If there are differences between country and WHO-UNICEF coverage estimates, the Secretariat will refer to the latter when estimating targets.





4

