|  |  | [V1.8]. |  |
| --- | --- | --- | --- |
| GAVI Alliance.. Application Form for Country Proposals.. For Support to:.. Preventive Campaign Support.. Submitted by.. The Government of.. Cambodia.. Date of submission: 15 September 2014.. Deadline for submission: 17 September 2014.. Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP).. Start Year.; 2009.. End Year.; 2016.. Form revised in 2014.. (To be used with Guidelines of April 2014).. Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet.. Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.... |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application....

1. Application Specification Please specify for which type of GAVI support you would like to apply to... Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Preventive Campaign Support; JE, 5 dose(s) per vial, LYOPHILISED; 2016; 2016.. [1] GAVI may not be in a position to accommodate all countries first product preferences, and in such cases, GAVI will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however GAVI will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country....

2. Table of Contents. 1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. Signature Table for the Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group. 4.2.1. The NITAG. 5. Immunisation Programme Data. 5.1 Background information. 5.1.1 Lessons learned. 5.1.2 Health planning and budgeting. 5.1.3 Preparatory activities. 5.1.4 Gender and equity. 5.1.5 Data quality. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Targets for Preventive Campaign(s). 5.3.1 Targets (JE campaign). 6. New and Under-Used Vaccines (NVS Routine). 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.1.1 Epidemiology and disease burden for JE. 7.2 Request for JE, 5 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for JE campaign support. 7.2.2 Grant Support for Operational Costs of the JE Campaign. 7.2.3 Evidence of introduction of JE in routine programme. 7.2.4 JE surveillance indicators. 7.2.5 JE Vaccine introduction Grant. 8. Procurement and Management. 8.1 Procurement and Management of New and Under-Used Vaccines Routine. 8.2 Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for JE, 5 dose(s) per vial, LYOPHILISED campaign. 8.3 Vaccine Management (EVSM/EVM/VMA). 8.4 Waste management. 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. List of documents attached to this proposal. 11. Annexes. Annex 1 - NVS Routine Support. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine JE, 5 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for JE, 5 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form...

3. Executive Summary.. Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable, including the reason for the choice of presentation. ¡; Projected month and year of introduction of the vaccine. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment and progress on EVM improvement plan. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. ¡; Partners. The Ministry of Health (MOH) of the Kingdom of Cambodia is requesting support from GAVI for conducting a preventive campaign of Japanese Encephalitis vaccine. Evidence from national and regional surveillance is indicative of Japanese Encephalitis (JE) being present throughout Cambodia and of it being more common in children under the age of fifteen. JE is also known to be more common in rural areas and, as these areas often also the poorest, it is a disease that disproportionately impacts vulnerable populations. JE can result in mortality and in serious, life-long squeal as well as devastate household budgets. In view of this, Cambodia has made the decision to introduce JE and this has been added to the current cMYP (2008-2015). The strategy consists of initial nationwide campaign (excepting one province that has already conducted a campaign in 2013) targeting children from 9 months through 14 years of age which transition into routine immunization. It is planned to initiate this SIA activity in January 2016 and to conduct the campaigns in a series of 3 waves (about 8 provinces in each wave) and to conclude these by March of the same year. The goal of the JE campaign is to reduce morbidity and mortality associated with JE by rapidly reaching a large cohort of the most susceptible population. One dose of SA-14-14-2, a live-attenuated JE vaccine, produced by Chengdu Institute of Biological Production and procured through UNICEF, will be administered to a target population in 24 provinces (ages 9 months -14 years inclusive) of 4,305,014. (A limited number of children will also be immunized in Battambang due to inadequate supply of vaccine resulting in missed children during the campaign conducted there in 2013). The major activities of the campaign will include procurement and logistics, training on JE integration and micro planning, strengthening of AEFI surveillance and reporting, advocacy and social mobilization. Particular focus will be given to extending access to hard-to-reach populations and strengthening AEFI reporting. This focus should also bring gains to routine immunization. Cambodia has demonstrated capacity to successfully conduct campaigns of this scale and achieve greater than 95% coverage. The risks associated with the vaccine apply mostly to accurate target population estimation at the lower levels and supply chain capacity. During the micro planning exercises, effort will be made to consider several estimates of target population and doses administered in past campaigns to assure adequate supply of vaccine. An additional cold room will be purchased at the central level to assure adequate capacity; at lower levels, vaccine delivery schedules will be adjusted.<?xml:namespace prefix = "o" ns = "urn:schemas-microsoft-com:office:office" /> The Government of Cambodia is requesting financial support of US$ 2,082,721 from GAVI for vaccine and related supplies to be used in the campaigns. (Kindly refer to the PoA document, Section 5 for a full discussion of this calculation and the difference between amount calculated on the GAVI portal at the time of preparation of this application). A request is also being made to GAVI to contribute US$ 2,779,563 towards campaign operational costs. Both requests are to support the JE campaign planned for January 2016. This proposal has been endorsed by the Technical Working Group for Health in Cambodia on August 7, 2014. This same group will provide oversight and monitoring and supervision for the activities in this proposal....

4. Signatures.. 4.1. Signatures of the Government and National Coordinating Bodies.. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation.. The Government of Cambodia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests GAVI support for:.. JE, 5 dose(s) per vial, LYOPHILISED preventive campaigns.. The Government of Cambodia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application... Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 1 and 2 in Section 10. Attachments... Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Dr. MAM BUNHENG; Name; Dr. AUN PORNMONIROTH. Date; Date. Signature; Signature.. This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):.. Full name; Position; Telephone; Email. Prof. Sann Chan Soeung; Advisor to the Ministry of Health; 855 12 933 344; workmoh@gmail.com.. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation.. Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below... Profile of the ICC, HSCC, or equivalent committee.. Name of the committee; Technical Working Group for Health. Year of constitution of the current committee; 2004. Organisational structure (e.g., sub-committee, stand-alone); Stand-alone. Frequency of meetings; Monthly.. The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4... Major functions and responsibilities of the ICC/HSCC:.. The principal function of the Technical Working Group for Health (TWG-H) is to ensure effective coordination of the response of the Royal Government of Cambodia, led by the Ministry of Health, in responding to the health challenges of the country. The TWG -H provides a mechanism for the MoH and its development partners jointly to: identify priorities; harmonize activities; discuss and address technical issues; improve utilization and mobilization of resources; and facilitate monitoring of progress. <?xml:namespace prefix = o /> TWG-H actions will support Cambodia to attain the Millennium Development Goals through implementation of the RGC’s Rectangular Strategy, the current national development plans and the National Strategic Development Plan (NSDP) 2006–2010. While the TWG-H helps to identify realistic policy goals it is the RGC/MOH that will take policy decisions. The TWG-H will facilitate the implementation, monitoring and evaluation and, where necessary, modification of the Health Strategic Plan linking with other sectors and their TWGs as needed. The TWG-H will help all stakeholders to fully participate in dialogue on issues within its scope. The major functions of the TWG-H are to: • Provide a forum for sharing information between key stakeholders • Advise the MoH on strategic and policy issues • Provide a monitoring overview of sector performance • Facilitate intra-sector and inter-sector harmonization and alignment The objectives of the TWG-H are: 1. To review progress, discuss issues and give over sight to the design, implementation and management of the Health Strategic Plan; 2. To promote the improvement of Sector-Wide Management (SWiM)and progress toward a Sector-Wide Approach (SWAp) in the health sector; 3. To promote efficient use of limited resources in the health sector through prioritization, coordination and joint activities and through use of the Medium-Term Expenditure Framework; 4. To review progress and advise on the development and implementation of sub sector plans; 5. To discuss and advise on plans for the Joint Annual Performance Review and the mid-term review and final evaluation of the Health Strategic Plan and to ensure that review findings are taken into account in the preparation of the Annual Operational Plans and Three -year Rolling Plan; 6. To discuss health sector linkages to larger government initiatives for poverty reduction and to ensure adequate health sector input to the Cambodia Development Cooperation Forum (CDCF) process; 7. To discuss implications of, and provide input to, larger government-wide reforms such as those in public administration, public financial management, decentralization and governance in co -ordination with the Government Donor Co-ordination Committee (GDCC); 8. To ensure regular sharing of information from health sector partners on progress in implementation of projects and to review plans for new projects to ensure their relevance and to avoid duplication; 9. To enhance monitoring and evaluation of progress through use of agreed indicators, including CMDG indicators and Joint Monitoring Indicators (JMIs), and regular reporting on targets and benchmarks; 10. To review results and give advice on important pilot initiatives in service delivery, financing, management and quality improvement and ensure that lessons learned are used in policy development; 11. To strengthen linkages and mechanisms for coordination with the Sub-TWG-H, and Pro-TWG-H to facilitate the achievement of the harmonization and alignment objectives at the implementation level. In addition to its routine business of reviewing progress reports and analytical studies, and providing inputs to sectoral planning, the TWG-H has higher level functions that include: •identifying NSDP strategies, priorities and indicators; •identifying data sources for NSDP monitoring; •agreeing on any additional analytical work to enhance NSDP monitoring; •establishing and monitoring JMIs for the health sector that are linked to NSDP targets; •reporting to GDCC on JMIs, H-A-R Action Plan and the TWG-H Action Plan activities; •following up on relevant discussions which take place at GDCC and CDCF, and identify issues for discussion at those higher-level forum. The Department of International Cooperation/Ministry of Health, as the focal point for ODA coordination and resource to the TWG-H Secretariat, has a key role in ensuring that these higher level functions are fully addressed. GDCC is tasked with coordinating the work of the TWGs and, jointly with Development Partners, monitoring progress on key issues. DIC is responsible for generating progress reports for dissemination and forwarding to GDCC through CRDB/CDC (the GDCC Secretariat), along with issues to be resolved by GDCC. DIC should therefore establish points of contact and liaise closely with CRDB/CDC to ensure the effective development of these reports.. Please describe how partners have provided support in preparation of the proposal:.. WHO and UNICEF have provided documents and insight into the preparation of the proposal. WHO has provided input on target group calculations. It has also been actively involved in reviewing and providing comments to the proposal. PATH has been a partner for JE vaccine for the past four years and provided major support for preparation of the proposal, worrking with EPI staff on the development of the Plan of Action, and budgeting of the proposal... 4.1.3. Signature Table for the Coordinating Committee for Immunisation.. We the members of the ICC, HSCC, or equivalent committee [1] met on the 07/08/2014 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 6 (please use the list for signatures in the section below)... Please refer to Annex C of the ‘GAVI HSS and NVS General Guidelines’ for more information on ICCs... Function; Title / Organisation; Name; Please sign below to indicate the attendance at the meeting where the proposal was endorsed; Please sign below to indicate the endorsement of the minutes where the proposal was discussed. Chair; Secretary of State, Ministry of Health; H.E. Professor Eng Huot. Secretary; Secretariat; Dr. Uch Sophal. Members; WHO representative; Dr Dongil Ahn.. By submitting the proposal we confirm that the quorum has been met. Yes.. The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 7... 4.2. National Immunization Technical Advisory Group.. Has a NITAG been established in the country ? No.. In the absence of a NITAG, countries should clarify the role and functioning of the advisory group and describe plans to establish a NITAG. This document is attached as (Document Number: 9)...

5. Immunisation Programme Data. 5.1 Background information.. Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document... ▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 10. Please attach the cMYP costing tool as DOCUMENT NUMBER 11.. ▪; Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate... Please use the most recent data available and specify the source and date... Figure; Year; Source. Total population; 14,962,591; 2013; General Population Census of Cambodia Report 12 Page 215. Birth cohort; 336,879; From the country's detail budget. Infant mortality rate (per 1000); 45; 2009; CDHS 2010. Surviving infants[1]; 354,407; 2013; cMYP 2008 - 2015 (updated 2013). GNI per capita (US$); 610; %; 2009; World Bank 2010. Total Health Expenditure (THE) as a percentage of GDP; 5; %; 2012; National health accounts:country information. Geneva, World Health Organization. Accessed Aug. 2014. General government expenditure on health (GGHE) as % of General government expenditure; 13; %; 2012; National health accounts: country information. Geneva, World Health Organization. Accessed Aug. 2014.. [3] Surviving infants = Infants surviving the first 12 months of life.. 5.1.1 Lessons learned.. Routine New Vaccines Support.. Preventive campaign support.. If campaigns with JE vaccines have already been conducted in your country, please give details of the lessons learned, specifically for: storage capacity, protection from additional freezing, staff training, cold chain, logistics, coverage, wastage rate, etc, and suggest action points to address them in future campaigns. If they are included in the Introduction Plan or Plan of Action, please cite the section only... Lessons Learned; Action Points. Please refer to section 1.5 in the Plan of Action... 5.1.2 Health planning and budgeting.. Please provide information on the planning and budgeting cycle in your country. The first national Health Sector Strategic Plan, approved in 2002, was reviewed in 2007 and resulted in the Health Strategic Plan 2008-2015 (HSP2). It presents the vision as "To enhance sustainable development of the health sector for better health and well-being of all Cambodia, especially of the poor, women and children, thereby contributing to poverty alleviation and socio-economic development. "The mission of the Ministry of Health" is to provide stewardship for the entire health sector and to ensure a supportive environment for increased demand and equitable access to quality health services in order that all the peoples of Cambodia are able to achieve the highest level of health and well-being", based on values of equity and the right to health.<?xml:namespace prefix = o /> The building blocks of HSP2 are three main health program areas to: •reduce maternal, newborn and child morbidity and mortality, with increased reproductive health; • reduce morbidity and mortality due to HIV/AIDS, malaria, TB and other communicable diseases; and • reduce the burden of non-communicable diseases and other health problems, which implement a set of the following five cross-cutting health strategies: • health service delivery; • healthcare financing; • human resource for health; • health information system; and • health system governance. The HSP2 implementation plan identifies an initial three-year consolidation phase to decide key policies in relation to health financing and health system governance requirements under decentralization and de-concentration, followed by a scaling-up phase. A monitoring and evaluation process has been established, including indicators to measure performance, refine existing health policies and determine the effectiveness of interventions. Annual targets are monitored at the National Health Congress and Joint Annual Performance Review and directives for the next Annual Operational Plan issued. Three year Rolling Plans provide medium term guidance. In order to strengthen its stewardship over the health sector, the Ministry of Health has been developing tools to apply sectorial resources where they are most needed, through direct allocation as well as through advocacy, influence and regulation. The Ministry recently developed a comprehensive system of sectorial operational planning to support implementation of the Health Strategic Plan. Strategic planning, aligned with the National Strategic Development Plan, is operationalized through Annual Operational Plans, forming the basis for three year Rolling Plans that link mid-term operational and investment planning. This is consolidated planning, encompassing the entire public health sector. It is bottom-up ,with each facility or administrative unit preparing annual plans based on sector wide priorities, but accounting for its own specific goals, capacities and challenges. The year 2012 marked the eight year of the Annual Operational Plans, which will become an increasingly useful tool for resource allocation as the links between planning and budgeting processes are strengthened in coming years. The Ministry of Health has introduced the Joint Annual Plan Appraisal for review of resource allocation with health partners to facilitate this. Implementation of strategic and operational plans is monitored through the Ministry of Health’s health information systems, which inform the Joint Annual Performance Review and the National Health Congress. This consultative event reviews performance toward strategic goals and identifies priorities for action during the coming year. At the 2009 and 2010 Joint Annual Performance Review, key bottlenecks to improvement of sector performance were identified, and a set of priority interventions was recommended for which resource allocations within individual operational plans should increase. Health facility development is guided by the Health Coverage Plan, which will become an important strategic management tool for the health sector once linkages with human resource planning and national capital investment planning are strengthened. Please indicate the name and date of the relevant planning document for health. Key guiding documents for the Health system in Cambodia are:<?xml:namespace prefix = o /> · National Strategic Development Plan 2008 – 2015 · Health Strategic Plan 2008 – 2015 - Multi Year Plan for Immunization 2008 – 2015 (updated May 2013). Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.). The cMYP for immunizations is specifically aligned with the Health Strategic Plan 2008 -2015 both in terms of strategic goals and time frame. It is the cMYP for immunization that operationalizes the key strategic goals of the Ministry of Health and the Government of Cambodia within National Strategic Development Plan. The cMYP was updated in April 2010 to incorporate the inclusion of a 2nddose of measles vaccine as part of the routine EPI schedule (introduced June 2012), with an addendum developed in May 2012 to incorporate the inclusions of measles/rubella vaccine into the routine EPI schedule and undertaking of a wide age range measles/rubella vaccine supplementary immunization activity, 2013 for PCV introduction and 2014 for IPV and JE introduction.<?xml:namespace prefix = o /> These updates to the cMYP are fully in line with the goals of the Health Strategic Plan 2008 - 2015. Financial costing for the cMYP and the updates are used by the NIP for inclusions in wider health planning processes. It is expected that the cMYP will be updated in line with the development of the next Health Strategic Plan when the current one ends in 2015, and the NIP is expecting to start this process of mapping out strategic immunization goals for the period post 2015 in the 1st quarter 2015.. Please indicate the national planning budgeting cycle for health. Budgets are submitted by national programs and provincial Health Departments to the Dept. of Finance Ministry of Health in June. The Ministry of Health advises institutions of the budget envelope in December of the same year. Health Plans are then reviewed in the context of the budget to be provided. Operational costs for Provincial Health Departments and programs are released on a quarterly basis by the Dept. of Finance<?xml:namespace prefix = o />. Please indicate the national planning cycle for immunisation. January: Annual Program Review involving representatives for all 24 provincial and 81 operational district departments and partner and donor agencies<?xml:namespace prefix = o /> March– April: Set Objectives and Targets for 3 years and detailed activities with annual budget for the following year, based on the c-MYP. June: Submit Annual Operational Plan (AOP) to Dept. of Planning and Dept. of Finance December: Review and Revise AOP based on current situation and budget available.. 5.1.3 Preparatory activities.. Please provide an outline of all preparatory activities for vaccine(s) introduction or campaigns. If they are included in detail the Introduction Plan and/or Plan of Action, please cite the sections only.. All preparatory activities are listed in section 4.0 (from 4.1-4.9) of Plan of Action and the same section 4.0 of Introduction Plan and listed in the PURPLE in the Campaign Operational Costs and the Vaccine Introduction Grant spreadsheets provided as attachments. These include pre-assessments, training, guide preparations, and IEC material preparation.<?xml:namespace prefix = o />.. 5.1.4 Gender and equity.. Please describe any barriers in access to immunisation services that are related to geographic, socio-economic and/or gender equity and actions taken to mitigate these barriers. Highlight where these issues are addressed in the vaccine introduction plan(s).. The 2010 EPI review focused on immunization service delivery and aimed to review fixed and outreach strategies and their ability to reach the unimmunized. Coverage data at health centre level was collected and under-served villages were visited. At village level immunization cards were checked form house to house and mothers were asked questions about obstacles they encountered. The review found the following four categories of social situation that act as barriers to full immunization.<?xml:namespace prefix = o /> Mobile populations: people who regularly move from one place to another, usually in search of work. Rural Hard to Reach: people who live in rural areas that have obstacle to easy access. This can include not only physical distance but also poor quality roads seasonal flooding and newly settled areas. Ethnic groups: This category includes minority people who may have a different language and cultural identity. Urban poor: typically urban slum dwellers and squatters who are often the poorest of the poor. As a result of the 2010 review, the NIP increased its efforts to reach these high risk or under-served populations for the measles SIAs in 2011 and for routine immunization from 2012 onwards. New micro planning guidelines have been distributed with a major focus on reaching high risk underserved communities. The measles second dose opportunity at 18 to 23 months is being used as an opportunity to monitor high risk communities and catch upon missing immunization doses for all vaccines.. Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s).. The JE SIA will utilize 2 co-ordinated approaches:<?xml:namespace prefix = o /> Health Centers and Outreach, with a focus on children under 5 years of age using both fixed site and outreach posts. Special efforts (planned in the microplanning phase) will be made to access high risk communities (mobile, rural hard-to-reach, ethnic, and urban poor). Any gaps in coverage identified during the campaign will be addressed through mop-up activities. All efforts to extend access and improve equity will build on prior work of the NIP during the Measles Rubella SIA to identify and reach high-risk populations. School based delivery (collaboration with the Ministry of Education) will focus on children from 6 years old through 14 years and 11 months. Cambodia has high rates of school attendance, and past measles and measles-rubella SIAs have successfully utilized this delivery option to improve coverage and reduce costs.. Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems.. Sex disaggregated data are not collected in the routine immunization reporting system in Cambodia. The 2010 DHS survey shown that a minimal gap in gender disaggregated coverage rates, female DPT3 coverage rates (85%) and for males (84%) (DHS Survey 2010)<?xml:namespace prefix = o />. Is the country currently in a situation of fragility (eg. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities.. No. If available, please provide additional information and documents on subnational coverage data, e.g. comparing urban/rural districts or districts with highest/lowest coverage, etc.. The results of table 13.3 page 136 of DHS shown some distributions by urban/rural districts.. 5.1.5 Data quality.. Please attach a data quality assessment report, if one has been completed within the previous 36 months (DOCUMENT NUMBER : 14). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER : 15, DOCUMENT NUMBER : 16).. If DQA not available, please briefly describe plans to establish mechanisms for data quality assessment.. DQA conducted in 2012...

5.2. Baseline and Annual Targets (NVS Routine Support). No NVS Routine Support is requested...

5.3. Targets for Preventive Campaign(s).. 5.3.1 Targets (JE campaign). Please specify cohort for Japanese Encephalitis vaccines (JEV):. JE Start 9 months. JE End 14 years. Cohort population = population 9 months - 14 years old. GAVI will only provide support to countries for Japanese encephalitis catch-up campaign by providing JE vaccine for a target population of males and females aged 9 months to 14 years (the exact range in the scope of 9 months to 14 years old will depend on Japanese encephalitis in the country)... Table 5.3.1 Baseline NVS preventive campaign figures for JE.. Number; Targets. 2016. Total target population; 4,100,013. Wastage rate (%) for JE (campaign); 10......

6. New and Under-Used Vaccines (NVS Routine). No NVS Routine Support is requested...

7. NVS Preventive Campains.. 7.1. Assessment of burden of relevant diseases related to campaigns (if available).. Disease; Title of the assessment; Date; Results. Japanese Encephalitis; JE surveillance in Battambang and Banteay Meanchey currenstatus and activities; July 2014; Since surveillance activities commenced on June 1, 2011, a total of 647 meningoencephalitis cases have been identified, including 373 children from Battambang and 274 children from Banteay Meanchey. Among these cases, 386 (60%) had at least one sample collected. Overall, 41 (11%) patients with samples collected tested positive for JE, 26 in Battambang and 15 in Banteay Meanchey. The median age of the JE cases was 4.5 years (range: 8 months–14 years) with the majority of cases 27 (66%) being male. Japanese Encephalitis; Disability from Japanese encephalitis in Cambodia and Viet Nam; 2011; A cohort of Japanese encephalitis (JE) survivors in Cambodia and Viet Nam were assessed at least 4 months after hospital discharge in order to understand the extent of disability after JE. We used a simple assessment tool which focuses on the impact on daily life. In total, 64 disability assessments were conducted: 38 in Cambodia and 26 in Viet Nam. In Cambodia, 4 (11%) children had severe sequelae, suggesting the children would likely be dependent, 15 (39%) had moderate sequelae and 17 (45%) had mild sequelae. In Viet Nam, two (8%) persons had severe sequelae, five (19%) had moderate sequelae and eight (31%) had mild sequelae. In many JE-endemic areas there are no multi-disciplinary teams with sophisticated equipment to assess patients after JE disease. This assessment tool can assist with patient management and generate data to support the need for programmes to prevent disease and improve outcomes for survivors.. Please attach the Plan of Action for each campaign as Document No. in Section 10... 7.1.1 Epidemiology and disease burden for JE. Please select at least one of the following information sources to justify JEV diseases burden results:. Epidemiological information on burden of disease:. þ; 1 - JE data from the JE/AES surveillance system including the definition of the geographical extent of high risk areas for JE. þ; 2 - Reports on outbreak or clustering of cases in the past three years. o; 3 - In case of absence of data from JE/AES surveillance, an argumentation on environmental and biological plausibility....

7.2.Request for JE, 5 dose(s) per vial, LYOPHILISED campaign support. 7.2.1. Summary for JE campaign support. When is the country planning to conduct this campaign? January 2016. When is the country planning to introduce JE into routine immunisation? April 2016. Please give a summary of the cMYP and/or the JE, 5 dose(s) per vial, LYOPHILISED introduction plan sections that refer to the introduction of JE, 5 dose(s) per vial, LYOPHILISED. Outline the key points that informed the decision-making process (data considered etc) and describe the plans for social mobilisation and microplanning, including strategies for insecure or hard-to-reach areas. If they are included in the introduction plan or plan of action, please cite the sections only.. Refer to the following sections in the Plan of Action:<?xml:namespace prefix = o /> Decision-making process: 1.7 Plans and activities for the campaign from 4.1 through 4.9. Please summarise the cold chain capacity (at central and other levels) and readiness to accommodate new vaccines, taking into consideration training, cold chain and other logistic requirements. If cold chain expansion is required, state how it will be financed, and when it will be in place. Please describe how the surge capacity for campaigns will be managed. Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled. The Independent Review Committee requires a certain level of assurance that the cold chain is ready or will be ready for the campaign, and evidence/plans need to be provided (if they are included in detail in the plan of action, please cite the section here).. Refer to section 4.3 as well as to an additional document attached to this proposal: CAMBODIA DOSES COSTS_price update_August 17 which specifies the volumes required at the central JE campaign.<?xml:namespace prefix = o />. Please describe how the campaign activities will contribute to strengthening routine immunisation services. Please refer to specific activities to be undertaken during planning and implementation, to evaluate the implementation of the routine strengthening activities completed during the campaign, and to assess, via an independent survey, the quality and coverage achieved through the campaign.. The proposed JE campaign is expected to strengthen routine immunization through the following:<?xml:namespace prefix = o /> · The capacity of health workers will be strengthened through training on micro-planning, vaccine safety, waste management, disease surveillance, cold chain, etc. This should benefit not only for JE campaign but also the for routine immunization program. · Further strengthening of strategies to improve equitable access to vaccines building upon efforts already initiated in identifying and reaching hard-to-reach populations. · Monitoring focused on improving routine coverage and equity: An additional rapid coverage assessment activity focused on hard-to-reach populations will focus on immunization coverage of routine infant vaccines in these populations. - Coverage survey: Gain experience with statistical methods to estimate coverage that can be adapted and utilized for routine household coverage surveys. Please submit relevant documentation to support the estimates of the size of the campaign target population (as DOCUMENT NUMBER : 20)... 7.2.2. Grant Support for Operational Costs of the JE Campaign.. Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of JE support; Total target population (from Table 5.3); GAVI contribution per target person in US$; Total in US$. 2016; 4,100,013; 0.65; 2,665,008.. [1] The Grant will be based on a maximum award of $0.65 per target person.. Please describe how the grant will be used to facilitate the preparation and timely and effective delivery of the campaigns to the target population (refer to the cMYP and the Vaccine Introduction Plan).. The grant will finance planning and preparation, including enhanced training in micro planning. it also contains support for training for JE campaigns and integration of JE vaccine into routine EPI. As part of this refresher training in injection technique, injection safety, and AEFI reporting will be included. The development of appropriate communications materials is included. The plan also includes the production and distribution of all necessary materials, and associated human resource costs for the campaign a subsequent monitoring. Finally, a post-campaign coverage survey is included. Refer to the Campaign Operational Support Grant for details.<?xml:namespace prefix = o />.....

Cost (and finance) of the JE, 5 dose(s) per vial, LYOPHILISED campaign US$.. Government support; Partners' support*; GAVI support. Cost Category; TOTAL COST US$; Amount US$; Name(s); Amount US$; Amount requested US$. 2016. 1; Program management and coordination; 20,400; 0; 0; 20400. 2; Planning and preparations; 174,500; 0; 0; 174500. 3; Social mobilization, IEC and advocacy; 50,750; 0; 0; 50750. 4; Other training and meetings; 476,700; 0; 0; 476700. 5; Document production; 285,000; 0; 0; 285000. 6; Human resources and incentives; 1,141,463; 0; 0; 1141463. 7; Cold chain equipment; 18,000; 0; 0; 18000. 8; Transport for implementation and supervision; 104,000; 0; 0; 104000. 9; Immunisation session supplies; 198,000; 0; 0; 198000. 10; Waste management; 15,750; 0; 0; 15750. 11; Surveillance and monitoring; 20,000; 0; 10000; 10000. 12; Evaluation; 35,000; 0; 0; 35000. 13; Technical assistance; 35,000; 0; 10000; 25000. 14; Data management; 0; 0; 0; 0. Other (please specify). Mop-up campaign, dealling with AEFI cases; 110,000; 110000. Total; 2,684,563; 0; 20000; 2664563.. * If more than one partner is providing financial support to a specific cost category, please list all partners for that category and the amount of support provided...... Where GAVI support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs... Administrative bodies at provincial and district level will also support media related activities and the supervision and monitoring of the campaign. It is expected that other organizations such as WHO, UNICEF, PATH and other NGOs will also contribute to independent monitoring of the campaign, as they have done for past campaigns. At this moment, WHO committed to contribute US$20,000 to support the campaign (included in budget above)... Please complete also the ‘Detailed budget for VIG / Operational costs’ template provided by GAVI and attach as a mandatory document in the Attachment section.. Detailed budget attached as Document No. 25......

7.2.3 Evidence of introduction of JE in routine programme... Will the country initially benefit from donated vaccines in for the introduction of JE vaccines in the routine immunization? Yes.. Please provide evidence that the country can finance the introduction of Japanese Encephalitis Vaccine (JEV) into the routine programme through one of the following:(Please attach available documents AS DOCUMENT NUMBER 19 in Section 10. Attachments). o; 1 - A commercial contract for purchase of JE vaccine with or without shipping documents, invoice, etc.. þ; 2 - Integration of JEV into the cMYP with a corresponding increase in the budget line for vaccines in the health sector budget adequate to cover purchase of JEV (please highlight the budget line in the cMYP costing or other document showing the corresponding increase to cover the purchase of JEV). þ; 3 - A letter from the Minister of Finance or Budget ensuring additional funding for JEV purchase. In this case, the country must show additional evidence that the country will include JE vaccination in the routine after the campaign.. o; 4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of JE for use in the routine programme. þ; 5 - Other. This proposal has been submitted to the direction of both the Ministry of Health and the Ministry of Finance. The signature of the Minister of Finance accompanying this application constitutes the commitment of the Government of Cambodia to finance the costs required to introduce and sustain JE vaccine in the routine programme. The 2016 JE SIA and subsequent integration of JE vaccine into the routine programme has been added to cMYP through an addendum and included in the cMYP costing. <?xml:namespace prefix = o />.. 7.2.4 JE surveillance indicators.. Please provide information on the following indicators of the quality of JE surveillance for at least two years prior to application (if available):.. Surveillance indicator; 2012; 2013. Reporting rate at national level 1). 100,000; 100,000. Laboratory confirmation rate (%) 2); 11.4; 11.2.. Note:. ; 1) Reporting rate at national level: (number of reported AES cases per 100,000 population). ; 2) Laboratory confirmation rate: (% of tested AES cases that were JE igM-positive).. 7.2.5 JE Vaccine introduction Grant... Has a JE vaccine already been introduced nationally on a routine basis? No. Calculation of Vaccine Introduction Grant for the JE, 5 dose(s) per vial, LYOPHILISED.. Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed... Year of New Vaccine Introduction; Birth cohort (from Table 5.1); GAVI contribution per target person in US$; Total in US$. 2016; 336,879; 0.80; 269,503.. [1] The Grant will be based on a maximum award of $0.80 per person in the birth cohort with a minimum starting grant award of $100,000.. Please describe how the GAVI Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan).. Please summarise in the table below the full costs of preparing for and conducting the campaign, and specify which items are expected to be covered with the GAVI grant. Please note that the country will be required to submit a detailed budget for the Campaign Operational Support Grant prior to release of funds.............

Cost (and finance) to introduce the JE, 5 dose(s) per vial, LYOPHILISED US$.. Government support; Partners' support*; GAVI support. Cost Category; TOTAL COST US$; Amount US$; Name(s); Amount US$; Amount requested US$. 1; Program management and coordination; 0; 0; 0; 0. 2; Planning and preparations; 6,500; 0; 0; 6500. 3; Social mobilization, IEC and advocacy; 143,430; 0; 0; 143430. 4; Other training and meetings; 0; 0; 0; 0. 5; Document production; 110,000; 100,000; 0; 10000. 6; Human resources and incentives; 109,500; 0; 0; 109500. 7; Cold chain equipment; 0; 0; 0; 0. 8; Transport for implementation and supervision; 0; 0; 0; 0. 9; Immunisation session supplies; 0; 0; 0; 0. 10; Waste management; 0; 0; 0; 0. 11; Surveillance and monitoring; 40,000; 0; 40000; 0. 12; Evaluation; 0; 0; 0; 0. 13; Technical assistance; 0; 0; 0; 0. 14; Data management; 0; 0; 0; 0. Other (please specify). Total; 409,430; 100,000; 40000; 269430.. * If more than one partner is providing financial support to a specific cost category, please list all partners for that category and the amount of support provided................

8. Procurement and Management.. 8.1 Procurement and Management of New and Under-Used Vaccines Routine.. No NVS Routine Support is requested.. 8.2 Procurement and Management for NVS Preventive Campaign(s).. 8.2.1 Procurement and Management for JE, 5 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. Cambodia requests procurement of GAVI supported JE vaccine and injection safety supplies through UNICEF supply system, as is the current modality for procurement of other GAVI supported vaccines (pentavalent, measles 2nd dose, PCV) EPI vaccines for the MOH.. b) Please describe the financial management procedures that will be applied for the management of the preventive campaign cash support, including any procurement to be incurred.. All funds received by GAVI will be used in accordance of the recently agreed Aide Memoir between GAVI and the MOH Cambodia, which was developed following the financial management assessment in 2012<?xml:namespace prefix = "o" ns = "urn:schemas-microsoft-com:office:office" />. c) Please indicate if the campaign is going to be phased, and if so, how this will be done.. The JE SIA will utilize 2 co-ordinated approaches:<?xml:namespace prefix = "o" ns = "urn:schemas-microsoft-com:office:office" /> Health Centers and Outreach, with a focus on children under 5 years of age using both fixed site and outreach posts. Special efforts (planned in the microplanning phase) will be made to access high risk communities (mobile, rural hard-to-reach, ethnic, and urban poor). Any gaps in coverage identified during the campaign will be addressed through mop-up activities. All efforts to extend access and improve equity will build on prior work of the NIP during the Measles Rubella SIA to identify and reach high-risk populations. School based delivery (collaboration with the Ministry of Education) will focus on children from 6 years old through 14 years and 11 months. Cambodia has high rates of school attendance, and past measles and measles-rubella SIAs have successfully utilized this delivery option to improve coverage and reduce costs. The campaign will roll out in three phases within the first quarter of 2016 with each phase covering about 8 districts over a period of two to three weeks.. d) Please outline how coverage of the campaign will be monitored, reported and evaluated (refer to the cMYP and/or the JE, 5 dose(s) per vial, LYOPHILISED campaign introduction plan). M&E plan: The expected coverage of this JE campaign is 100% . NIP together with partners will utilize the following approaches to assess the JE campaign:<?xml:namespace prefix = "o" ns = "urn:schemas-microsoft-com:office:office" /> Rapid Coverage Assessments (RCA): RCA was used as the most reliable forms of monitoring progress, during MR Campaigns and JE Campaign in the country. During the MR SIA two types of RCA were carried out and this JE campaign will do similarly: - JE vaccine RCA will be conducted at every site to confirm the quality of implementation, using random samples of 20 children in the target age ranges. This will be conducted by local level supervisors or other non-vaccination team members, and will provide a pass/fail assessment of the area. Areas that fail the RCA require further mop up activities and additional RCA to confirm that no children have been missed. - Identified high risk communities, in addition to the RCA for JE vaccine, a RCA for routine EPI coverage for children from 9 to 23 months that will assess their routine immunization “up to date” status, based on the system implemented during the 2011 measles SIA. This will be collated by the NIP at the provincial and national levels and allow a post SIA detailed assessment to be made where areas of weak routine immunization remain for focus and correction through the routine EPI. Data from this campaign will be compared to data from a similar activity conducted during the MR campaign Administrative Coverage Data: In addition to the use of RCA for monitoring the quality of coverage, traditional reporting systems based on administrative data will be used, and monitored in “real time” with daily reporting, collation and assessment of coverage data by the WHO/NIP. All districts will report summary results at the end of each day to their NIP supervision focal point that will then transmit this data to a centralized data focal point, either via email or SMS. Data will be reviewed each evening and a detailed report issued to all NIP and partner focal points the following morning to allow rapid sharing of information and issues, and immediately identify areas of concern for swift correction. These systems were developed during the 2011 measles SIA, used in the subsequent MR SIA, and the NIP is experienced in their use. Post-campaign coverage survey. This will be a statistically representative survey conducted in May or June, 2016. During JE campaign in Battambang in 2013, a coverage survey was carried out and NIP has experience in managing and conducting such survey with support from consultants....

8.3 Vaccine Management (EVSM/EVM/VMA).. It is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for introduction of new vaccine. This EVM should have been conducted within the preceding 36 months.. When was the EVM conducted? March 2012. Please attach the most recent EVM report (DOCUMENT NUMBER : 22,23,24), the corresponding EVM improvement plan (DOCUMENT NUMBER : 23) and progress on the EVM improvement plan (DOCUMENT NUMBER : 24). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation.. When is the next Effective Vaccine Management (EVM) Assessment planned? April 2015.. 8.4 Waste management.. Countries must have a waste management and monitoring plan as appropriate for their immunisation activities (especially for campaigns). This should include details on the safe handling, storage, transportation and disposal of immunisation waste, as part of a healthcare waste management strategy. Please describe in detail, the country’s waste management plan for immunisation activities (including campaigns).. A waste management plan exists that involves health workers filling safety boxes with used needles and syringes (uncapped) until 100 syringe capacity, closing the box, and storing it in a safe location. During supervisor visits these boxes are taken back by the supervisor and in this manner move up in administrative levels until the provincial level where these are incinerated. For campaigns, the process is similar, except the supervisors present during the campaign take the boxes back with them directly afterwards.<?xml:namespace prefix = "o" ns = "urn:schemas-microsoft-com:office:office" /> Training in injection safety: Health worker training prior to the JE campaign will encompass both injection safety and appropriate procedures for waste disposal. Health worker training prior to the JE campaign will encompass both injection safety and appropriate procedures for waste disposal. Training of health workers on injection safety and waste disposal will be integrated with training on JE campaign implementation. Vaccination teams will have sufficient safety boxes for the number of AD syringes (1 safety box for every 100 AD syringes). Used AD syringes and syringe caps should be placed in safety boxes immediately after the vaccine has been given, and when a safety box is approximately ¾ full it will be closed off and a new one used. Empty JE vials will be placed in the waste. Used safety boxes will be sent to the HC at the end of each day, and stored in a secure and waterproof area. At the end of the campaign, all used safety boxes will be sent to the OD or PHD incinerator and disposed through incineration. OD and PHD supervisors will be responsible to ensure this occurs....

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. Comments and Recommendations from the National Coordinating Body (ICC/HSCC).. The TWG-H conveyed a meeting on August 7, 2014. All agreed the important of both JE and IPV introduction nation-wide in Cambodia in 2016 and 2015 respectively....

10. List of documents attached to this proposal. 10.1. List of documents attached to this proposal.. Document Number; Document; Section; Mandatory; File. 1; MoH Signature (or delegated authority) of Proposal; 4.1.1; Signature of Minister of Health.pdf File desc: Date/time : 15/09/2014 07:09:22 Size: 148 KB. 2; MoF Signature (or delegated authority) of Proposal; 4.1.1; Cover letter for Signature of Minister of Finance.pdf File desc: Date/time : 15/09/2014 07:09:45 Size: 41 KB. 3; MoE signature (or delegated authority) of HPV Proposal; 4.1.1; No file loaded. 4; Terms of Reference for the ICC; 4.1.2; TOR of TWGH (ICC) - Annex III of MOH Op Guidelines.pdf File desc: Date/time : 09/09/2014 10:06:54 Size: 650 KB. 5; Minutes of ICC/HSCC meeting endorsing Proposal; 4.1.3; TWGH (ICC) minutes August 7, 2014 ( endorsement).PDF File desc: Date/time : 09/09/2014 10:05:20 Size: 2 MB. 6; Signatures of ICC or HSCC or equivalent in Proposal; 4.1.3; Signature of participants of TWGH (ICC) meeting August, 2014.PDF File desc: Date/time : 09/09/2014 10:05:53 Size: 1 MB. Signature,Chair of TWGH (ICC).pdf File desc: Date/time : 15/09/2014 07:10:35 Size: 709 KB. 7; Minutes of last three ICC/HSCC meetings; 4.1.3; TWGH (ICC) minutes July 2014.PDF File desc: Date/time : 09/09/2014 10:07:29 Size: 1 MB. TWGH (ICC) minutes June 2014.PDF File desc: Date/time : 09/09/2014 10:08:06 Size: 1 MB. TWGH (ICC) minutes May 2014.PDF File desc: Date/time : 09/09/2014 10:08:46 Size: 2 MB. 8; Minutes of NITAG meeting with specific recommendations on the NVS introduction or campaign; 4.2; No file loaded. 9; Role and functioning of the advisory group, description of plans to establish a NITAG; 4.2.1; Plan for establishing NITAG.pdf File desc: Date/time : 13/09/2014 09:42:59 Size: 103 KB. 10; comprehensive Multi Year Plan - cMYP; 5.1; ADDENDUM TO cMYP 2008 to 2015 JEV.docx File desc: Date/time : 04/09/2014 02:20:38 Size: 75 KB. Cambodia-Comprehensive multi-year plan for 2008-2015 - Year 2008.pdf File desc: Date/time : 15/08/2014 02:52:33 Size: 699 KB. 11; cMYP Costing tool for financial analysis; 5.1; cMYP Costings Cambodia JE 2016 added.xlsx File desc: Date/time : 18/08/2014 08:16:44 Size: 1 MB. 12; Vaccine introduction plan; 5.1; No file loaded. 13; Introduction Plan for the introduction of RCV / JE into the national programme; 7.x.4; CAMBODIA JE NVIP_revised_August 18.doc File desc: Date/time : 04/09/2014 02:16:02 Size: 312 KB. 14; Data quality assessment (DQA) report; 5.1.5; KH_DataQualityReportCard_2012_fin.pdf File desc: Date/time : 15/08/2014 02:53:19 Size: 2 MB. 15; DQA improvement plan; 5.1.5; Cambodia DQA improvement plan.pdf File desc: Date/time : 18/08/2014 05:10:35 Size: 67 KB. 16; Progress report on implementation of DQA improvement plan; 5.1.5; Cambodia Progress report on implementation of DQA improvement plan_2013.pdf File desc: Date/time : 18/08/2014 05:11:59 Size: 474 KB. 17; HPV roadmap or strategy; 6.1.1; No file loaded. 18; HPV summary of the evaluation methodology; 5.1.6; No file loaded. 19; Evidence of introduction of RCV / JE / YF in routine programme; 7.x.3; Evidence of GOV commitment for JE introduction in routine.pdf File desc: Date/time : 13/09/2014 09:43:55 Size: 66 KB. 20; Campaign target population documentation; 7.x.1; Cambodia Target Population 2016 JE SIA_August 17.xls File desc: Date/time : 18/08/2014 05:13:38 Size: 75 KB. 21; Roadmap or strategy for strengthening a comprehensinve approach to pneumonia and/or diarrhoea prevention and treatment; 6.x.6; No file loaded. 22; EVM report; 8.3; EVM_report-Cambodia - Final 13 Mar 2012.pdf File desc: Date/time : 15/08/2014 02:54:15 Size: 1 MB. 23; Improvement plan based on EVM; 8.3; EVM-imp-plan-Cambodia-2012 - Final.xlsx File desc: Date/time : 11/09/2014 10:37:21 Size: 95 KB. 24; EVM improvement plan progress report; 8.3; Progress Report on the EVM Improvement Plan Bt Mr Kry.pdf File desc: Date/time : 11/09/2014 10:39:02 Size: 69 KB. 25; Detailed budget template for VIG / Operational Costs; 6.x,7.x.2; Cambodia Op Cost Detail for JE campaign_August 15.xlsx File desc: Date/time : 15/08/2014 02:59:17 Size: 25 KB. Cambodia VIG JE routine_August 15.xlsx File desc: Date/time : 04/09/2014 02:22:52 Size: 22 KB. 26; Risk assessment for Meningitis / Yellow Fever; 7.1; No file loaded. 27; Plan of Action for campaigns; 7.1, 7.x.4; CAMBODIA JE Plan of Action_revised_August 18.doc File desc: Date/time : 04/09/2014 02:17:39 Size: 422 KB. Other; CAMBODIA DOSES COSTS_price update_August 18v2.xlsx File desc: Date/time : 18/08/2014 08:20:16 Size: 90 KB. CDHS 2010 complete report 20110831.pdf File desc: Date/time : 15/08/2014 03:00:03 Size: 4 MB. J Trop Peds 2011_Disability from JE in Cambodia and Viet Nam.pdf File desc: Date/time : 15/08/2014 03:00:57 Size: 116 KB. JE Surveillance in BB-BM 2014 Quarterly Report 2_June2014 - clean.pdf File desc: Date/time : 15/08/2014 03:00:24 Size: 457 KB. Supply_Chain_Tool_ _Cambodia_Shafi.xlsx File desc: Date/time : 10/09/2014 07:31:44 Size: 2 MB...

11. Annexes... Annex 1 - NVS Routine Support. No NVS Routine Support is requested.. Annex 2 - NVS Routine – Preferred Second Presentation.. No NVS Routine – Preferred Second Presentation requested this year.. Annex 3 - NVS Preventive campaign(s).. Annex 3.1 - NVS Preventive campaign(s) (JE, 5 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN JE, 5 dose(s) per vial, LYOPHILISED.. Data from; 2016. Total target population; Table 5.3.1; #; 4,100,013. Number of doses per persons; Parameter; #; 1. Wastage Rate; Table 5.3.1; #; 10. Estimated vaccine wastage factor; #; 1.11. Number of doses per vial; Parameter; #; 5. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; Yes. Safety boxes required; Parameter; #; Yes. AD syringe price per unit; Table Annexes 4A; $; 0.0448. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.035. Safety box price per unit; Table Annexes 4A; $; 0.544. Freight cost as % of vaccines value; Table Annexes 4B; %; 37.00 %. Freight cost as % of devices value; Parameter; %; 10.00 %......

Table Annex 3.1 D: Estimated number of JE, 5 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1).. Formula; GAVI. 2016. B; Total target population; Table 5.3.1; 4,100,013. C; Number of doses per persons; Vaccine parameter (schedule); 1. D; Number of doses needed; B x C; 4,100,013. E; Estimated vaccine wastage factor; 100 / (100 - Vaccine wastage rate); 1.11. F; Number of doses needed including wastage; D x E; 4,551,015. G; Vaccines buffer stock; 0; 0. I; Total vaccine doses needed; Round up((F + G) / Vaccine package size) * Vaccine package size; 4,551,050. J; Number of doses per vial; Vaccine parameter; 5. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 4,551,015. L; Reconstitution syringes (+ 10% wastage) needed; (I / J) x 1.11; 1,010,334. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) / 100 x 1.11; 61,731. N; Cost of vaccines needed; I x vaccine price per dose (g); 1,228,784. O; Cost of AD syringes needed; K x AD syringe price per unit (ca); 203,886. P; Cost of reconstitution syringes needed; L x reconstitution price per unit (cr); 35,362. Q; Cost of safety boxes needed; M x safety box price per unit (cs); 33,582. R; Freight cost for vaccines needed; N x freight cost as of % of vaccines value (fv); 454,651. S; Freight cost for devices needed; (O+P+Q) x freight cost as % of devices value (fd); 27,283. T; Total fund needed; (N+O+P+Q+R+S); 1,983,548... Note: There is no cofinancing for NVS preventive campaigns.....

Annex 4. Table Annex 4A: Commodities Cost.. Estimated prices of supply are not disclosed... Table Annex 4B: Freight cost as percentage of value.. Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB-Hib; HEPBHIB; 25.50 %; 6.40 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. JE; JE; 37.00 %. Measles second dose; MEASLES; 14.00 %. Meningococcal type A; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %.. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine... Vaccine...

Table Annex 4D: Wastage rates and factors.. The following table shows the wastage rates for routine and campaign vaccines, set for 2016... Vaccine; dose(s) per vial; Maximum Vaccine wastage rate*; Benchmark Wastage Rate**. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 5 %. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 25 %; 15 %. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 10 %. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 10 %. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5 %. JE, 5 dose(s) per vial, LYOPHILISED; 5; 10 %. Measles second dose, 10 dose(s) per vial, LYOPHILISED; 10; 40 %. Meningococcal type A, 10 dose(s) per vial, LYOPHILISED; 10; 10 %. MR, 10 dose(s) per vial, LYOPHILISED; 10; 15 %. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 10 %. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 5 %. Rotavirus, 2-dose schedule; 1; 5 %. Rotavirus, 3-dose schedule; 1; 5 %. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 40 %. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 10 %.. Comments:.. * Source - WHO indicative wastage rates.. ** Source - Country APRs and studies, approved by WHO, UNICEF, and the GAVI Secretariat.. Note: HPV demonstration project wastage rates are the same as the vaccine.. Table Annex 4E: Vaccine maximum packed volumes.. Kindly note that this table is for reference purposes only and includes GAVI- and non GAVI-supported vaccines... Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 1; 5; 2.5; 2.9. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5...

12. Banking Form.. In accordance with the decision on financial support made by the GAVI Alliance, the Government of Cambodia hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:.. Is the bank account exclusively to be used by this program?.. By who is the account audited?.. Signature of Government's authorizing official.. Seal. Name:. Title:. Signature:. Date:.. FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:.; CORRESPONDENT BANK. (In the United States).. I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:.. Name of bank's authorizing official. Signature:. Date:. Seal:...