
	[image: image1.png]



	
	
	

	
	
	[V1.4.1]

	

	
	
	
	

	Application Form for Gavi NVS support
Submitted by
The Government of
Myanmar
Date of submission: 30 April 2016
Deadline for submission:
i.
1 May 2016
ii.
1st May 2015
9 September 2015
iii.
Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)
Start Year
2017
End Year
2021
Form revised in 2015
(To be used with Guidelines of November 2015)
Note: Please ensure that the application has been received by Gavi on or before the day of the deadline.

	
	
	


	Gavi
GRANT TERMS AND CONDITIONS

	FUNDING USED SOLELY FOR APPROVED PROGRAMMES

	The applicant country ("Country") confirms that all funding provided by the Gavi will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the Gavi. All funding decisions for the application are made at the discretion of the Gavi Board and are subject to IRC processes and the availability of funds. 

	AMENDMENT TO THE APPLICATION

	The Country will notify the Gavi in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The Gavi will document any change approved by the Gavi, and the Country's application will be amended.

	RETURN OF FUNDS

	The Country agrees to reimburse to the Gavi all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the Gavi, within sixty (60) days after the Country receives the Gavi's request for a reimbursement and be paid to the account or accounts as directed by the Gavi.

	SUSPENSION/ TERMINATION

	The Gavi may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any Gavi-approved amendment to the application.The Gavi retains the right to terminate its support to the Country for the programmes described in its application if a misuse of Gavi funds is confirmed.

	ANTICORRUPTION

	The Country confirms that funds provided by the Gavi shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.

	AUDITS AND RECORDS

	The Country will conduct annual financial audits, and share these with the Gavi, as requested. The Gavi reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.

	The Country will maintain accurate accounting records documenting how Gavi funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of Gavi funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the Gavi in connection with any audit.

	CONFIRMATION OF LEGAL VALIDITY

	The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.

	CONFIRMATION OF COMPLIANCE WITH THE Gavi TRANSPARENCY AND ACCOUNTABILITY POLICY

	The Country confirms that it is familiar with the Gavi Transparency and Accountability Policy (TAP) and complies with the requirements therein.

	USE OF COMMERCIAL BANK ACCOUNTS

	The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage Gavi cash-based support. The Country confirms that it will take all responsibility for replenishing Gavi cash support lost due to bank insolvency, fraud or any other unforeseen event.

	ARBITRATION

	Any dispute between the Country and the Gavi arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the Gavi or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland

	. The languages of the arbitration will be English or French.

	For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the Gavi. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The Gavi and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.

	The Gavi will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.


	

	

	


	1. Type of Support requested

	Please specify for which type of Gavi support you would like to apply to.


	
	
	Type of Support
Vaccine
Start Year
End Year
Preferred second presentation[1]
Preventive Campaign Support
JE, 5 dose(s) per vial, LYOPHILISED
2017
2017
If the selected vaccine is not your 1st preference, please state your preferred vaccine and presentation
If the selected vaccine is not your 1st preference, please state your preferred vaccine and presentation

	
	[1] Gavi may not be in a position to accommodate all countries first product preferences, and in such cases, Gavi will contact the country and partners to explore alternative options. A country will not be obliged to accept its second or third preference, however Gavi will engage with the country to fully explore a variety of factors (such as implications on introduction timing, cold chain capacity, disease burden, etc.) which may have an implication for the most suitable selection of vaccine. If a country does not indicate a second or third preference, it will be assumed that the country prefers to postpone introduction until the first preference is available. It should be noted that this may delay the introduction in the country.


	

	


	2. Table of Contents


		
		
	1. Type of Support requested
2. Table of Contents
3. Executive Summary
4. Signatures
4.1. Signatures of the Government and National Coordinating Bodies
4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation
4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation
4.1.3. Signature Table for the Coordinating Committee for Immunisation
4.2. National Immunization Technical Advisory Group (NITAG)
4.2.1. The NITAG
5. Immunisation Programme Data
5.1 Background information
5.1.1 Lessons learned
5.1.2 Health planning and budgeting
5.1.3 Gender and equity
5.1.4 Data quality
5.2. Baseline and Annual Targets (NVS Routine Support)
5.3. Targets for Preventive Campaign(s)
5.3.1 Targets (JE campaign)
5.4. Targets for One time mini-catchup campaign(s)
6. New and Under-Used Vaccines (NVS Routine)
7. NVS Preventive Campaigns
7.1. Assessment of burden of relevant diseases related to campaigns (if available)
7.1.1 Epidemiology and disease burden for JE
7.2 Request for JE, 5 dose(s) per vial, LYOPHILISED campaign support
7.2.1 Summary for JE campaign support
7.2.2 Grant Support for Operational Costs of the JE Campaign
7.2.3 Evidence of introduction of JE in routine programme
7.2.4 JE surveillance indicators
7.2.5 JE Vaccine introduction Grant
8. Procurement and Management
8.1 Procurement and Management of New and Under-Used Vaccines Routine
8.2 Procurement and Management for NVS Preventive Campaign(s)
8.2.1 Procurement and Management for JE, 5 dose(s) per vial, LYOPHILISED campaign
8.3 Product Licensure
8.4 Vaccine Management (EVSM/EVM/VMA)
8.5 Waste management
9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC)
10. List of documents attached to this proposal
11. Annexes
Annex 1 - NVS Routine Support
Annex 2 - NVS Routine – Preferred Second Presentation
Annex 3 - NVS Preventive campaign(s)
Table Annex 3.1 C Summary table for vaccine JE, 5 dose(s) per vial, LYOPHILISED
Table Annex 3.1 D Estimated numbers for JE, 5 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget
Annex 4
Table Annex 4A: Commodities Cost
Table Annex 4B: Freight cost as percentage of value
Table Annex 4C: Preparing transition phase - Minimum country co-payment per dose of co-financed vaccine
Table Annex 4D: Wastage rates and factors
Table Annex 4E: Vaccine maximum packed volumes
12. Banking Form
	

	

	


	3. Executive Summary


	
	
	Please provide a summary of your country's proposal, including the following the information:
l
For each specific request, NVS routine support or NVS campaign : 
¡
The duration of support
¡
The total amount of funds requested
¡
Details of the vaccine(s), if applicable, including the reason for the choice of presentation
¡
Projected month and year of introduction of the vaccine (including for campaigns and routine)
l
Relevant baseline data, including:
¡
DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form)
¡
Target population from Risk Assessments from Yellow Fever and Meningitis A
¡
Birth cohort, targets and immunisation coverage by vaccines
l
Country preparedness
¡
Summary of planned activities to prepare for vaccine launch, including EVM assessments, progress on EVM improvement plans, communication plans, etc.
¡
Summary of EVM assessment and progress on EVM improvement plan
l
The nature of stakeholders' participation in developing this proposal
¡
Inter-Agency Coordinating Committee
¡
Partners, including CSO involvement
JE is endemic disease in Myanmar. There has been significant number of labotory confirmed JE cases reported each year despite limited surveillance. The Central Epidemiological Unit first conducted serological surveys for JE in 1988 and they found JE antibody in 1325 people. A study conducted from 1988-1989 showed that 19.5% of viral encephalitis admitted in Yangon Children Hospital was due to JE virus. Similarly another study in 2010 showed that 12.5% viral encephalitis cases admitted to Yangon Children Hospital were due to JE. In 2014, there were 319 CNS infection children admitted to the hospital of which 26 died. The outcomes of viral encephalitis cases included 28% complete recovery, 17% with movement disorder and 22% with motor deficit.Serological survey in 1973, among domestic pig herds nationwide showed about 90% of the pigs had presence of the JE HI antibody, whereas cattle and buffaloes showed a very low prevalence. JE outbreak was reported as early as in November 1977 at Animal Breeding Centre at Bahtoo Township, Southern Shan State. There is a long history of JE/AES cases reported from Rakhine State since 1979 with  an alarming increase in cases in recent years (2014: 52 cases from 10 townships, 2015: up to July, 48 cases from 8 townships, 7 deaths and 16 confirmed JE case by lab). The main age group was from 1-14 years old, and most cases were reported from May to August. JE cases are detected in all states/regions of Myanmar. All age groups were affected but the highest group was children 5-9 years of age, followed by children 1-4 years of age. It’s also very alarming that in early 2015 (from Jan to June, 2015), data collected from 3 states and 4 regions shown that there were 36 JE positive cases from 211 serum samples and in Rakhine state alone, there were 45 AES cases with 5 deaths.. 30 serum samples were tested with 6 samples being JE positive.
Due to high mortality, morbidity and disability due to JE and significant disease burden, the Government of Myanmar decided to conduct JE campaign followed by introduction in to routine immunization.In this regard, the Government of Myanmar is requesting one time financial support of US $ 7,202,324 from Gavi for 15,583,300 doses of JE vaccine and related supplies to be used in the campaigns. A request is also being made to Gavi to contribute US$ 9,125,350 towards campaign operational costs.  Both requests are to support the JE campaign planned for October - December 2017.
The Union Government of Myanmar is requesting one time support for vaccine introduction grant of US$ 796,661 to support  introduction of JE vaccine in routine immunization from 1st January 2018.
Live attenuated SA 14-14-2 vaccine (CD-JEV) is the vaccine of choice to be used for the campaign and routine immunization. This is vaccine is  WHO-prequalified vaccine that uses one dose for all the age groups and has documentation of field vaccine effectiveness.
The target population for JE campaign is estimated of 14.039 million children aged 9 months through 14 years of age in 2017. For routine immunization it is estimated that the surviving infant population of 951,000 in 2018. The 2015 birth cohort in Myanmar was 956,401 and routine immunization programme was targeting 928,612 surviving infant for BCG, Penta, OPV, IPV, and Measles and 1,012,556 pregnant women for TT vaccinations in 2015. Myanmar JRF reported coverages by antigen as:  BCG -93%, DPT 3 (Penta 3) - 89%, OPV 3 - 89%, MCV1 – 84%, MCV 2 – 78% and TT2 – 83%.
To ensure that the country is adequately prepared, the planning process will be initiated by forming campaign planning and task forces including communication, technical task force, logistics and advocacy and inter-agency coordination. The EVM assessment was conducted and its improvement plan final were finalized in 2015, and currently being implemented. There was a 9% increase in the overall EVM performance compared to 2011 EVM. Currently the cold chain systems are being upgraded with technical and funding support from UNICEF which will benefit the JE campaign and introduction in to routine. The communication plan for the campaign and introduction will be prepared with a focus on increasing demand and uptake of JE vaccine.
WHO and UNICEF will provide technical support in planning, implementation, advocacy and social mobilization, logistics and transportation and monitoring an evaluation of the campaign. Other INGOs, Community Based Organizations, professional organizations and Women’s organization will provide support for advocacy and social mobilization, human resources and random coverage surveys. PATH will provide technical support for planning, preparation of the campaign and participate in monitoring the implementation of the campaign including participation in the post campaign coverage survey. PATH will also donate enough vaccine for the first year (2018) for routine JE vaccination as stated in the accompanying commitment letter. The vaccines for the subsequent years starting from 2019, will be secured through the Ministry of Health by ensuring the JE vaccine procurement is included in the Government Budget and the draft estimations.
The proposal was developed by CEPI with the technical support from WHO, UNICEf and PATH. The senior official in the Ministry of Health and ICC members had an opportunity to review the proposal. The ICC meeting on 29th April 2016 endorsed this proposal.


	

	


			
	4. Signatures
		
	4.1. Signatures of the Government and National Coordinating Bodies
		
	4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation
		
	The Government of Myanmar would like to expand the existing partnership with the Gavi for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests Gavi support for:
		
			
		JE, 5 dose(s) per vial, LYOPHILISED preventive campaigns
	
			
	The Government of Myanmar commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the Gavi and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.
		
			
	Please note that this application will not be reviewed or recommended for approval by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority. These signatures are attached as DOCUMENT NUMBER : 2 and 1 in Section 10. Attachments.
		
			
	Minister of Health (or delegated authority)
Minister of Finance (or delegated authority)
Name
Prof. Dr. Thet Khaing Win
Name
U Maung Maung Win
Date
Date
Signature
Signature
		
			
	This report has been compiled by (these persons may be contacted in case the Gavi Secretariat has queries on this document): 
		
			
	Full name
Position
Telephone
Email
Dr. Daniel Ngemera
Immunization Specialist
+959254116560
dngemera@unicef.org
Dr. Htar Htar LIN
Deputy Director/Program Manager - CEPI
+959428188188
 dr.htarhtarlin@gmail.com
Dr. Rajendra Bohara
Technical Officer - EPI
+95943064757
boharar@who.int
Dr.Bill Letson 
Scientific Advisor for Japanese Encephalitis 
+12063886871
bletson@path.org
		
			
	4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation
		
			
	Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, Health Sector Coordinating Committee (HSCC), or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the Gavi NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.
		
			
	Profile of the ICC, HSCC, or equivalent committee
		
			
	Name of the committee
ICC
Year of constitution of the current committee
2007
Organisational structure (e.g., sub-committee, stand-alone)
stand-alone
Frequency of meetings
3 times
		
			
	The Terms of Reference or Standard Operating Principles for the ICC, including details on the ICC membership, quorum, dispute resolution process and meeting schedules is attached as DOCUMENT NUMBER : 4.
		
			
	Major functions and responsibilities of the ICC/HSCC:
		
			
	In Myanmar Inter-agency Coordinating Committees (ICC) is chaired by Director General Health, DoPH, and Ministry of Health Myanmar. The ICC has been  formed to improve coordination among partners in support of immunization programs and control of vaccine-preventable diseases, The membership of the ICC was revised in 2012 with inclusion of more INGO, NGO and other relevant partners such as PATH, Women and children  associations.
Every year ICC meets 3-4 times to review the progress and performance, identify gaps and address needs to ensure EPI is well supported.
The following Major Functions are undertaken by the ICC
1. Leadership and active participation from the MOH to guide the EPI program
2. Collective monitoring and evaluation of Immunization activities.
3. Input and assistance from other MOH departments, like MCH, nutrition, Health System Strengthening, Planning, Finance Primary Health care unit etc. UN agencies like WHO and UNICEF for appropriate decision-making for support and program continuity. This includes joint Collaboration, joint prioritization, the establishment of common goals and objectives, and harmonized work plans with MOH under the guidance of National Health policy
4. Advocacy for Resource mobilization internally as well as by donors
5. Review and approve the GAVI supported activities related to EPI
6. Review needs for Supplementary Immunization activity or other additional immunization activity. Such as NID, SIA, measles catch up , rubella catch up etc.
7. Coordinated Implementation and Monitoring
8. Review and endorse CEU plans for disease burden study, cold chain assessment, or new vaccine introduction, evaluations etc
9. Any other issues where Immunization program needs attention
		
			
	Please describe how partners have provided support in preparation of the proposal:
		
			
	The partnership consisted of the Myanmar Ministry of Health (MOH), World Health Organization (WHO) at several levels and UNICEF in Myanmar along with PATH, an NGO that has been intimately involved in JE vaccine introduction for over 13 years in areas of JE endemicity. In addition, members of the Myanmar National Commitee for Immunization Practice (NCIP) which is equivallent of the NITAG for Myanmar and Inter-agency Committee (ICC) were actively involved in the process.
This partnership began in 2014 with meetings between Myanmar MOH officials including the Director General at the time, WHO, UNICEF and PATH.  This meeting took place to discuss the prospects for JE vaccine introduction in the context of recent outbreaks and also addressed concerns relating to routine introduction.  This productive exchange led to a second meeting with the same partnership group at a NCIP meeting in July 2015 to address what was then nown of JE disease patterns throughout the country and resulted in a tentative decision to pursue JE vaccine introduction in the near future.
In order for the MOH to plan to prepare for the submission of an application to Gavi for JE introduction, a meeting of the same partners was held in March of 2016, to discuss working together on the Gavi proposal to be submitted on 1st May 2016.  The proposal development involved a collaborative effort between MOH, UNICEF, WHO and PATH. Consultative discussions with MOH, UNICEF and WHO reached an agreement that PATH should participate actively and provide the needed support in proposal development. In addition, PATH made commitment to provide sufficient quantities of JE vaccines to cover the needs for one year for introduction in routine immunization after the JE campaign based on the demand forecast projections agreed to by the multi-lateral partners and specified in the PATH letter of commitment (attached). As a result of this collaborative effort, in late April 2016, the partners met to put the finishing touches on the proposal in time for the May 1st submission, of which this note is a part. The partnership worked together on matters of cost estimates, cold chain, and logistics. Once Gavi approval is secured the partnership will work on matters of implementation.
This has been a truly collaborative and effective partnership, making it possible to craft what we believe is a cogent proposal in time for submission.  The plan is to have all partners continue collaborating on technical aspects of the planning for and eventual introduction of JE vaccine through the integration of the vaccine into the routine EPI schedule for Myanmar. The Ministry of Health and collaborating partners is looking forward to hearing of Gavi’s decision and then working to make this important vaccine introduction a success for Myanmar and for reducing both morbidity and mortality of JE.
		
			
	4.1.3. Signature Table for the Coordinating Committee for Immunisation
		
			
	We the members of the ICC, HSCC, or equivalent committee [1] met on the 29/04/2016 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached. The minutes of the meeting endorsing this proposal are attached as Document number 5. The signatures endorsing the proposal are attached as Document number 7 (please use the list for signatures in the section below).
		
			
	Please refer to Annex C of the ‘Gavi HSS and NVS General Guidelines’ for more information on ICCs.
		
			
	Function
Title / Organisation
Name
Please sign below to indicate the attendance at the meeting where the proposal was endorsed
Please sign below to indicate the endorsement of the minutes where the proposal was discussed
Chair
Director General/Department of Public Health
Prof. Dr. Soe Lwin Nyein
Secretary
EPI Program Manager
Dr. Htar Htar Lin
Members
Deputy Director General/Disaster and Epidemiology
Dr. Than Tun Aung
Depiuty Director General/DoPH
Dr. Than Win
Depiuty Director General/DoPH
Dr. Yin Thandar Lwin
Depiuty Director General/DoPH
Daw Aye Aye Sein
Director (Planning), DoPH
Dr. Wai Mar Mar Htun
Director (Disaster/EPI), DoPH
Dr. Htun Tin
Director (Disease Control), DoPH
Dr. Thandar Lwin
Director (Admin), DoPH
Dr. San Myint
Director (Health Promotion), DoPH
Dr. Thu Zar Chit Tin
Director (HMIS), DoPH
Dr. Thet Thet Mu
Director (Maternal and Reproductive Health), DoPH
Dr. Hla Mya Thwe Eidar
Director (Child Health), DoPH
Dr. Myint Myint Than
Director (Finance), DoPH
Daw Khing Khing Kyi
Director (Procurement and Supply)' DoPH
Dr. Kyaw Kan Kaung
Director (school Health), DoPH
Dr. Sandar
Director (HED), DoP
Dr. Maung Maung Than Hteike
Deputy Director (VBDC)
Dr. Zaw Lin
President, Myanmar Maternal and Child Welfare Association
Dr. Nu Nu Thar
President Myanmar Red Cross Society
Pro. Dr. Thar Hla Shwe
WHO Representative to Myanmar
Dr. Jorge Mario Luna
UNICEF Country Representative
Mr. Bertrand Bainvel
		
			
	By submitting the proposal we confirm that the quorum has been met. Yes
		
			
	The minutes from the three most recent ICC meetings are attached as DOCUMENT NUMBER : 6.
		
			
	4.2. National Immunization Technical Advisory Group (NITAG)
		
			
	Has a NITAG been established in the country ? Yes
		
			
	We the members of the NITAG met on the 29/04/2016 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation describing the decision-making process through which the recommendations were reached, attached as Document number 26.
4.2.1. The NITAG
Profile of the NITAG
Name of the NITAG
National Committe for Immunization Practice (NCIP)
Year of constitution of the current NITAG
2009
Organisational structure (e.g., sub-committee, stand-alone)
stand-alone
Frequency of meetings
2
Function
Title / Organisation
Name
Chair
Head of Paediatric Department (Retired)
Prof: Dr Saw Win
Secretary
Program Manager EPI
Dr. Htar Htar Lin
Members
Head of Paediatric Department (Retired)
Prof. Dr Thein Aung
Head of Paediatric Department (Retired)
Prof: Dr Thein Thein Myint
Epidemiologist
Dr Ye Myint 
Clinical pathologist
Dr Nay Win 
Deputy Director General/ National Health Lab/Virologist
Dr Latt Latt Kyaw 
Major functions and responsibilities of the NITAG
The NCIP will independently serve (advise) Ministry of Health by making technical advices (recommendations) on the followings:
1. to advise MOH to be able to make regulations on National immunization policy and strategies for public and private setting
2. to advise MOH to be able to make evidence-based decision for the prioritized disease in the country
3. to advise MOH to be able to decide the introduction of new or underutilized vaccines
4. to optimize the impact of immunization services in the country
5. to identify the need of information on pharmacovigilence including Adverse Events Following Immunization (AEFI) and further evidence on the selection of new vaccine to be introduced
6. to play a role in risk communication to the community, professionals and media
7. to advise MOH on response to ad hoc and emergency situations including supplementary immunization, control of outbreaks, and imminent epidemics/ pandemics.
		
			
	In the absence of a NITAG, countries should clarify the role and functioning of the advisory group and describe plans to establish a NITAG. This document is attached as (Document Number: 8)
		

	

	


	5. Immunisation Programme Data


	
	
	5.1 Background information

	
	Please complete the table below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

	
	▪ 
Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 9. Please attach the cMYP costing tool as DOCUMENT NUMBER 10.
▪ 
Please attach relevant Vaccine Introduction Plan(s) as DOCUMENT NUMBER : 12
▪ 
Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases
▪ 
Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.
▪ 
Please refer to the attached risk assessments in the case of yellow fever and meningitis A mass preventive campaigns.

	
	Please use the most recent data available and specify the source and date.

	
	Figure
Year
Source
Total population
53,539,047
2015
cMYP
Birth cohort
995,826
2015
cMYP
Infant mortality rate (per 1000)
45
2015
cMYP
Surviving infants[1]
951,014
2015
cMYP
GNI per capita (US$)
1,270
2014
World Bank
Total Health Expenditure (THE) as a percentage of GDP
2
2013
World Bank
General government expenditure on health (GGHE) as % of General government expenditure
3
2013
World Bank

	
	[3] Surviving infants = Infants surviving the first 12 months of life

	
	5.1.1 Lessons learned

	
	Routine New Vaccines Support

	
	Preventive campaign support
If campaigns with JE vaccines have already been conducted in your country, please give details of the lessons learned, specifically for: storage capacity, protection from additional freezing, staff training, cold chain, logistics, coverage, wastage rate, etc., and suggest action points to address them in future campaigns. If they are included in the Introduction Plan or Plan of Action, please cite the section only. If this information is already included in NVIP/POA, please reference the document and in which section/page this information can be found.
Lessons Learned
Action Points
Myanmar has not implemented JE campaign

	
	5.1.2 Health planning and budgeting

	
	Please provide information on the planning and budgeting cycle in your country
National comprehensive development plan (Health Sector) was formulated (2010-2011 to 2030-2031) and medium term five year National Plans are formulated.  The last planning cycle covered the period of 2011-2016. New medium term plan will start in 2017 and extend to the year 2021.Planning and budgeting cycle covered the same period. Formulation of NCDP is linked with related sectors and also link with the Regional or State Comprehensive Development Plan
Please indicate the name and date of the relevant planning document for health
National Health Plan (2011-2016), the new national plan for 2017 to 2021 is being finalized
Is the cMYP (or updated Multi-Year Plan) aligned with the proposal document (timing, content, etc.)
Yes
Please indicate the national planning budgeting cycle for health
National Health Plan 2011-2016 is formulated in relation to the fifth five years National Development Plan. It is also developed within the objective frame of the short term first five year period of national comprehensive development plan. That plan covered the fiscal year 2011-12 to 2015-2016. New National Health Plan is under preparation and the plan and budget will cover the period 2017 to 2021.
Please indicate the national planning cycle for immunisation
National planning for immunization was made as one of the elements of the disease control programme in the context or framework of National Health Plan.  Budget by each year in the plan period is estimated during the plan period. Annual work plans are developed based on Government financial year which starts from 1st April.

	
	5.1.3 Gender and equity

	
	Please describe any barriers to access, utilisation and delivery of immunisation services at district level (or equivalent) that are related to geographic, socio-economic and/or gender equity. Please describe actions taken to mitigate these barriers and highlight where these issues are addressed in the vaccine introduction plan(s).
No significant difference can be found in immunization coverage between urban and rural areas, or between male and female children. There is no clear association between immunization coverage and wealth level of the households. While the percentage of 12-23 months-old children with all recommended immunizations does not vary notably between children of mothers with primary (97.2 per cent) and secondary or higher education (98.7 per cent), there is a small gap down to children of mothers with no education, of whom 90.6 per cent have all recommended immunizations (Myanmar Multiple Indicator Cluster Survey 2009 – 2010). However, the geography, ethnicity and long years of internal conflict have made the provision of universal health care a challenge. Although the DPT3 vaccination coverage has increased by 15% in 2014 compared to 2013 and there is discrepancies and difference in coverage across Townships (JRF), and one of the challenges with immunization coverage data is related to unreliable denominator. The head counting that midwives conduct every year may not include hard to reach population, population in conflict zone and migratory population (EPI Evaluation 2014).  However concerted efforts has been made to reach these uncounted children. This  is consistent with Government committment to achieve universal health coverage as part of its vision 2030, defined as ‘the provision of optimal quality of health care for everyone in the country that is accessible, efficient, equitably distributed, adequately funded, fairly financed and appropriately used by an informed and empowered public’ (MOH 2014, ‘Strategic Directions for Universal Health Coverage).
The EPI evaluation undertaken in 2012 by CEPI, found that 40% of low performing RHC were geographically and/or socially hard to reach.  Security challenges and absence of health workers were also the cause for no immunisation activities in 25% of the instances.  Lack of vaccine (global supply availability) contributed to 15% and higher/faulty target setting contributed to 16% of the causes for low coverage (Progress Report on the implementation of Intensification of routine immunization in Myanmar 2013).
Discuss how equity issues (geographic, socio-economic and/or gender) are being taken into account in the design of social mobilisation and other strategies to increase immunisation coverage. Highlight where these issues are addressed in the vaccine introduction plan(s).
a) For mobile peri-urban population (Area of migrants, Work sites and Farming places)
· Expanding outreach services by mobile teams
· Strengthen microplanning and  provision of additional operational cost (REC)
· Creation of demand generation
b) For urban areas where immunization service is available only within  limited period in a month
· Expansion of EPI  services with fixed post at Government hospitals, MCH and UHC
· Increasing the number of immunization sessions.
c) For Hard to reach areas (Geographically and Socially hard to reach)
· Support microplanning and operational cost
· Intensification of service delivery through CRASH program
· Empowering the local community/ 3rd party immunization
d) For Security Concerns in ethnic groups areas
· Map Partners active in the region,
· Implement immunization through the trained INGOs/Ethnic Group Health Volunteers (Kachin/WA)
· Advocacy in Special Regions
e) For Inadequate knowledge and demand for immunization services
· Communication plan of action (2015-16) starting with nationwide campaign.
· Training, orientation and coaching of BHS on IPC skills and provision of communication materials.
· Creation of IEC corner at Immunization clinics
Issues  addressed in Vaccine Introduction:
(a)        For Hard to reach areas (Geographically and Socially hard to reach)
•           Special  microplanning and operational cost
•           Empowering the local community/ 3rd party immunization
(b)        For Security Concerns in ethnic groups areas
•           Implement immunization through the trained INGOs/Ethnic Group Health Volunteers (Kachin/WA)
•           Advocacy in Special Regions
(c)        For Inadequate knowledge and demand for immunization services
•           Special social mobilization and advocacy activities at all level
Equity issue: Specific social mobilization plan will developed and implement e.g., Mass Media/Printed Media in Local Languages
Please indicate if sex disaggregated data is collected and used in immunisation routine reporting systems.
The current data collection tools for routine  immunization as well as HMIS do not disaggregate data by sex. It is only available through surveys.
Is the country currently in a situation of fragility (e.g. insecurity, conflict, post-conflict, refugees/and or displaced persons and recent, current or potential environmental disaster, such as flooding, earthquake or drought or others)? If Yes, please describe how these issues may impact your immunisation programme, planning for introduction of routine vaccines or campaigns and financing of these activities.
Yes. Conflict and insecurity are ongoing barriers and one of few reasons for un/undercoverage in some townships. Vaccine introduction will address specialized activities described above.
If available, please provide additional information and documents on subnational coverage data, e.g. comparing urban/rural districts or districts with highest/lowest coverage, etc.
The 2015 Joint Report form (JRF) indicates penta/DPT3 coverage as follows:
· 16 Townships: < 50%
· 24 Townships: 50% - 70%
· 63 Townships: 80% -89%
· 105 Townships: 90-94%
· 114 Townships: > 95%

	
	5.1.4 Data quality

	
	Please attach a data quality assessment (DQA), report if one has been completed within the previous 48 months (DOCUMENT NUMBER: 27). If available, an improvement plan and progress report on the implementation of the improvement plan should also be submitted (DOCUMENT NUMBER: 11, DOCUMENT NUMBER: 28).
If DQA not available, please briefly describe plans to establish mechanisms for data quality assessment.
The last DQA was conducted in 2010 covering 10 Townships and 2011 additional 10 Townships were covered. The Ministry of Health with technical support from WHO is planing to conduct DQA in July 2016.
Please indicate what routine mechanisms to independently assess the quality of administrative data are in place, and if so what these mechanisms are and how they enable the country to track changes in data quality over time.
There are two annual evaluation meetings held at townships, States/Regions and national levels, the first annual review meeting is the community healthcare evaluation meeting (which discuss the overall performance related to general health care attendance, neonatal, maternal, reproductive, child health, environmental and sanitation, other disease control activities and hospital performance and demographic data).  The second evaluation meeting is the annual EPI evaluation held at all levels starting with townships compiling health facility based EPI coverage reports into the township annual EPI evaluation report. Townships reports are submitted to State/Region level for consolidation into the States/Regions specific EPI annual evaluation reports which are presented in the annual EPI evaluation meeting.  These meetings bring together all states/regions Health Directors and SCDU Team leaders and/ or EPI Focal Persons.  During the annual evaluations, the states/regions categorizes the performance of their respective townships based on Reaching Every Community (REC) classification using the pentavalent/DPT coverage and drop-out rates.  The annual evaluation data is mainly used to inform planning for the following year EPI based on the findings identified through a strength, weakness, opportunity, threat (SWOT) analysis, updated cold chain and logistic inventory, and VPDs surveillance data. The EPI review meetings especially at central level are supported jointly by WHO and UNICEF, and the main areas of support include review of the performance for each state and region and provide guidance on how to improve the coverage particularly on prioritization of areas and interventions needed. At Region/State and Townships, WHO and UNICEF are represented by the Regional Surveillance Officers (RSO) and Heath Specialist respectively who work closely with the state/region health department to prioritize Townships according to performance and design intervention to support low performing Townships.
Please detail what household surveys have been conducted in recent years to independently assess immunisation coverage and equity, and describe any survey plans for the coming five year period.
There have been households and health surveys conducted in the past including specialized surveys such as health facility assessments as well as Service Availability Readiness Assessment (SARA) supported by UNICEF and WHO respectively.  One of the main challenges is the lack of periodic surveys to assist with monitoring the performance of the programme.  For instance, through UNICEF support, the last Multiple Indicator Cluster Survey (MICS) was conducted in 2008/2009 and also it is important to note that the last EPI review was conducted in Myanmar in 2008. Likewise, the Integrated Household Living Condition Survey in Myanmar was conducted in 2009-2010.  To overcome these challenges, the Ministry of Health with support from partners and funding support from USAID is currently conducting a Demographic and Health Survey (DHS) with preliminary results expected early 2017.

	

	

	


	5.2. Baseline and Annual Targets (NVS Routine Support)


	
	
	No NVS Routine Support is requested

	

	

	


	5.3. Targets for Preventive Campaign(s)


	
	
	5.3.1 Targets (JE campaign)
Please specify cohort for Japanese Encephalitis vaccines (JEV):
JE Start 9 months
JE End 14 years
Cohort population = population 9 months - 14 years old
Gavi will only provide support to countries for Japanese Encephalitis catch-up campaign by providing doses of JE vaccine for a target population of males and females aged 9 months to 14 years (the exact range in the scope of 9 months to 14 years old will depend on JE in the country).
Table 5.3.1 Baseline NVS preventive campaign figures for JE
Number
Targets
2017
Total target population
14,039,000
Wastage rate (%) for JE (campaign)
10
Maximum wastage rate value for JE (campaign)
10 %


	

	


	5.4. Targets for One time mini-catchup campaign(s)


	
	
	No One time mini-catchup campaign this year

	

	

	


	6. New and Under-Used Vaccines (NVS Routine)


		
		
	No NVS Routine Support is requested
	
		
		

	

	


	7. NVS Preventive Campaigns


	
	
	7.1. Assessment of burden of relevant diseases related to campaigns (if available)

	
	Disease
Title of the assessment
Date
Results
JE
Serological survey
1988
JE antibody in 1325 people
JE
Study on JE in Yangon children hospital (YCH)
1988/89
19.5% of viral encephalitis admitted in YCH were due to JE virus
JE
Study on JE in Yangon children hospital (YCH)
2010
12.5% of viral encephalitis admitted in YCH were due to JE virus
JE
Serological survey among domestic herd
1973
90% of pigs had presence of JE antibody

	
	Please attach the Plan of Action for each campaign as Document No. 29,23 in Section 10.

	
	7.1.1 Epidemiology and disease burden for JE
Please select at least one of the following information sources to justify JEV diseases burden results:
Epidemiological information on burden of disease:
þ
1 - JE data from the JE/AES surveillance system including the definition of the geographical extent of high risk areas for JE
þ
2 - Reports on outbreak or clustering of cases in the past three years
o
3 - In case of absence of data from JE/AES surveillance, data from rapid assessments and/or an argumentation on environmental and biological plausibility.


	

	


	7.2.Request for JE, 5 dose(s) per vial, LYOPHILISED campaign support

	7.2.1. Summary for JE campaign support

	When is the country planning to conduct this campaign? October 2017

	When is the country planning to introduce JE into routine immunisation? January 2018

	Please give a summary of the cMYP and/or the JE, 5 dose(s) per vial, LYOPHILISED introduction plan sections that refer to the introduction of JE, 5 dose(s) per vial, LYOPHILISED. Outline the key points that informed the decision-making process (data considered etc) and describe the plans for social mobilisation and microplanning, including strategies for insecure or hard-to-reach areas. If they are included in the introduction plan or plan of action, please cite the sections only.

	The JE preventive campaign and introduction in to routine immunization is well elaborated in both the cMYP (page 25 to 28) as well the campaign plan of action (pages 11-15) and introduction plan (pages 15-19). The JE campaign and introduction in to routine will contribute to forth objective of the cMYP aiming achieving goals of eradication, elimination and control of the Vaccine Preventable Diseases (VPDs). Reference is made in cMYP section 2.2 in objective, strategies and Key activities.
Section 1.2 of the campaign plan of action describes the Objectives, targets, and justification for the campaign, where there sub-section 1.2.3 provides details on justification for JE campaign and decision making process of JE vaccine introduction.
1. Data available from the AES/JE surveillance system and details recent outbreaks in several states and regions in Myanmar proves that JE disease burden is public health problem in Myanmar.
2. Experiences from other countries introducing JE vaccine has demonstrated significant impact after vaccine introduction, for example, in Nepal the incidence rate of JE after campaigns was deemed to be 72% lower than what it otherwise would have been (Upreti, SR, et. al, American Journal of Tropical Medicine Hygiene, 2013).
3. Other interventions such as vaccination of pigs, environmental management for vector control, and chemical control of vectors are not effective and furthermore, prevention of JE will be especially beneficial to the poorer wealth quintiles that are least able to bear the financial burdens associated with long hospital stays and family care-givers for those with lifelong disabilities.
Section 2.4 (page 17) of JE introduction plan points out that the Stakeholders’ meeting for JE control program was held in July 2015 with to review the current status of Acute Encephalitis Syndrome (AES) surveillance systems in Myanmar and the data available from these systems, to review recent JE outbreaks in Myanmar and the implemented measures to respond those outbreaks, to discuss opportunities for JE control in Myanmar.  The recommendations from stakeholders meeting was to integrate AES surveillance with AFP surveillance, to introduce JE vaccination first as catch up campaign in children 9 months to 14 years of age followed by nationwide routine immunization, develop JE control strategy and to propose government budget and commitment for JE immunization as per NCIP endorsement.
Based on this information, NCIP and ICC recommend the introduction of JE vaccine for infants to all national immunization programs preceded by a wide age range catch up campaign based on the available local disease burden data.

	Please summarise the cold chain capacity (at central and other levels) and readiness to accommodate new vaccines, taking into consideration training, cold chain equipment and other logistical requirements. If cold chain expansion is required, state how it will be financed, and when it will be in place. Please describe how the surge capacity for campaigns will be managed. Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled. The Independent Review Committee requires assurance that the cold chain is ready or will be ready for the campaign, and evidence/plans need to be provided (if they are included in detail in the plan of action, please cite the section here). All proposals that include Gavi-financing for cold chain equipment intended for vaccine storage shall need to procure equipment pre-qualified by WHO under their Performance Quality and Safety (PQS) program. The purchase of non-PQS equipment will only be considered on an exceptional basis, with justification and advance agreement from Gavi. Please note that all Gavi-financed cold chain equipment needs to be WHO pre-qualified. The purchase of non-PQS equipment will only be considered on exceptional basis, with justification and advance agreement from Gavi.

	Both the campaign plan of action (section 2.2, on page 20-22) and introduction plan (section 4.11 on page 22-23) provides details on the cold chain capacity. The current gross storage capacity at national vaccine store is estimated at 175m³, while the current storage requirement is less than 65m³. Therefore at central level there is sufficient capacity to accommodate additional JE vaccine both for the campaign and routine immunization. The estimated storage space in the sub-national stores (22 sub-depots in the 17 state/regions) is estimated at nearly 40m³ with variations among different sub-depots. The total requirement at one point in time for all current vaccines is about 22m³, received in 4 shipments yearly. At lower level, mainly Township and service delivery points, the storage space is sufficient due to the fact that most of these levels receive vaccines in several shipments. Taking in to account of these scenarios, it is anticipated that the expected additional storage space required by the JE campaign will be easily accommodated given the fact that ongoing efforts to increase cold chain storage capacity at all levels.
Furthermore, in an efforts to increase the cold chain storage capacity at all levels, it is important to note that over the past 3 years a lot of investment has been made in strengthening cold chain systems throughout the country with technical support and guidance from UNICEF. These efforts started in 2014, with the comprehensive cold chain equipment inventory, capacity gap analysis and development of the cold chain replacement and expansion plan for Myanmar. This plan had more than 6 scenarios taking in to consideration the current capacity for storage of routine vaccines, the expected campaigns and the new vaccines to be introduced. The investment started during the measles rubella campaign in 2014/2015 including 10 walk-in freezer room, over 200 ice-lined refrigerators and 50 solar refrigerators were procured and installed at various levels. AAs a result, the measles and rubella campaign was implemented successfully, accommodating more than 16 million doses of MR vaccine. In addition, in preparation for the introduction of the pneumococcal conjugate vaccines (PCV) in 2016,  more than 450 ice-lined refrigerators and 400 solar refrigerators have been procured, distributed and are currently being installed throughout the country. This has contributed significantly in increasing the storage space.
As the ministry is planning to implement the campaign in a phased manner through school and community based approaches, vaccine will be shipped corresponding to the targeted number of children in each phase which will ensure that there is adequate space for both the JE campaign vaccine and also for other antigens used for routine immunisations. During the period 2016 to 2018, it is also important to note that more cold chain equipment will be procured through:
1. The 3 MDG supported project through UNICEF where more equipment will be procured in 2017 (at least 4 Walk in cold rooms and 150 ice-lined Refrigerators).
2. The Gavi supported vaccine introduction grant for pneumococcal conjugate vaccine has a provision for procurement of 100 ice-lined refrigerators to support the establishment of immunization services in all major hospitals in Myanmar. These refrigerators have already been ordered and are expected to arrive in the country in June 2016.
3. The Gavi Health System Strengthening (HSS) proposal for the duration 2017 to 2019 which was submitted to Gavi this year includes strengthening and expansion of cold chain systems as one of the key objectives to be achieved through procurement, distribution and installation of various types of cold chain equipment.

	Please describe any plans for expanding measles surveillance to include rubella and plans for the introduction of Congenital Rubella Syndrome (CRS) surveillance.

	The proposed JE campaign is expected to strengthen routine immunization through the following:
· The capacity of health workers will be strengthened through training on micro-planning, AEFI, vaccine safety, waste management, disease surveillance, cold chain, etc. This should benefit not only for JE campaign but also the for routine immunization program.
· Further strengthening of strategies to improve equitable access to vaccines building upon efforts already initiated in identifying and reaching hard-to-reach populations.
· Monitoring focused on improving routine coverage and equity:  An additional rapid coverage assessment activity focused on hard-to-reach populations will focus on immunization coverage of routine infant vaccines in these populations.
Coverage survey:  Gain experience with statistical methods to estimate coverage that can be adapted and utilized for routine household coverage surveys.

	Please submit relevant documentation to support the estimates of the size of the campaign target population (as DOCUMENT NUMBER : 18).


	
	
	7.2.2. Grant Support for Operational Costs of the JE Campaign

	
	Table 7.2.2: calculation of grant to support the operational costs of the campaigns
Year of JE support
Total target population (from Table 5.3) 
Gavi contribution per target person in US$
Total in US$
2017
14,039,000
0.65
9,125,350
[1] The Grant will be based on a maximum award of $0.65 per target person
Please describe how the grant will be used to facilitate the preparation and timely and effective delivery of the campaigns to the target population (refer to the cMYP and the Vaccine Introduction Plan).
The operation cost from Gavi will support
1. programme management and coordination
2. Planning and preparations for the campaign
3. Social mobilisation, IEC and advocacy
4. Human resources and icentives
5. Cold chain system support
6. Transporatation of essential supplies and supervision cost for the campaign.
7. Immunization session supplies
8. Surveillance and monitoring
9. Campaign evaluation
10. Technical assistance
11. Data management
The detailed budget is provided as an attachment (the operational cost budget template).


	

	

	

	


	
	Where Gavi support is not enough to cover the full needs, please describe other sources of funding and the expected amounts to be contributed, if available, to cover your full needs.

	
	The estimated cost for the campaign is US$ 10,634, 594 of which Gavi will provide US$ 9,125,350 and the remaing balances will be contributed by Government US$ 742,353), UNICEF (US$ 375,000) and WHO (U$S 391,891).

	
	Please complete also the ‘Detailed budget for VIG / Operational costs’ template provided by Gavi and attach as a mandatory document in the Attachment section.
Detailed budget attached as Document No. 22.


	
	

	

	

	

	


	7.2.3 Evidence of introduction of JE in routine programme


		
		
	Will the country initially benefit from donated vaccines in for the introduction of JE vaccines in the routine immunization? Yes
	
		
	Please provide a statement with a commitment that the country can finance the introduction of Japanese Encephalitis Vaccine (JEV) into the routine programme through one of the following:(Please attach available documents AS DOCUMENT NUMBER 17 in Section 10. Attachments)
o
1 - A commercial contract for purchase of JE vaccine with or without shipping documents, invoice, etc.
þ
2 - Integration of JEV into the cMYP with a corresponding increase in the budget line for vaccines in the health sector budget adequate to cover purchase of JEV (please highlight the budget line in the cMYP costing or other document showing the corresponding increase to cover the purchase of JEV)
o
3 - A letter from the Minister of Finance or Budget ensuring additional funding for JEV purchase. In this case, the country must show additional evidence that the country will include JE vaccination in the routine after the campaign.
þ
4 - An MOU between government and donor(s) (or other written document that proves donor commitment) for at least one year for purchase of JE for use in the routine programme
o
5 - Other
	
		
	7.2.4 JE surveillance indicators
	
		
	Please provide information on the following indicators of the quality of JE surveillance for at least two years prior to application (if available):
	
		
	Surveillance indicator
2014
2015
Reporting rate at national level 1)
100,000
100,000
Laboratory confirmation rate (%) 2)
21.6
40.7
	
		
	Note:
�
1) Reporting rate at national level: (number of reported AES cases per 100,000 population)
�
2) Laboratory confirmation rate: (% of tested AES cases that were JE igM-positive)
	
		
	7.2.5 JE Vaccine introduction Grant
Has a JE vaccine already been introduced nationally on a routine basis? No
Calculation of Vaccine Introduction Grant for the JE, 5 dose(s) per vial, LYOPHILISED
Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). Gavi’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed.
Year of New Vaccine Introduction
Birth cohort (from Table 5.1)
Gavi contribution per target person in US$
Total in US$
2017
995,826
0.80
796,661
[1] The Grant will be based on a maximum award of $0.80 per person in the birth cohort with a minimum starting grant award of $100,000
Please describe how the Gavi Vaccine Introduction Grant will be used to facilitate the timely and effective implementation of critical activities in advance of and during the introduction of the new vaccine (refer to the cMYP and the Vaccine Introduction Plan).
The Gavi Vaccine Introduction Grant will be mainly used to support the following main categories:
1. Programme management and coordination
2. Planning and preparation for introduction of JE
3. Social mobilisation, IEC and advocacy.
4. Document production (training documents)
5. Support for human recources and incentives
6. Transportation and supervision cost.
7. Surveillance and monitoring
8. Technical support and assistance to acceralate implementation of introduction activities.
	

	

	

	

	

	

	


	8. Procurement and Management


	
	
	8.1 Procurement and Management of New and Under-Used Vaccines Routine

	
	No NVS Routine Support is requested

	
	8.2 Procurement and Management for NVS Preventive Campaign(s)

	
	8.2.1 Procurement and Management for JE, 5 dose(s) per vial, LYOPHILISED campaign
 a) Please show how the support will operate and be managed including procurement of vaccines (Gavi expects that countries will procure vaccine and injection supplies through UNICEF): 
The vaccine for the SIA will be procured through UNICEF Supply Division with a shipment schedule to be coordinated through UNICEF SD to ensure timely arrival as well and appropriate storage capacity.
b) Please describe the financial management procedures that will be applied for the management of the preventive campaign cash support, including any procurement to be incurred.
Ministry of Health has been working closely with UNICEF and WHO in the management of funds for the campaign (lessons learned from the measles and rubella campaign) as well as the vaccine introduction Grant based on the areas of technical support. Specifically for the JE campaign, it is being proposed for the funds to be managed jointly by Ministry of Health, UNICEF and WHO. The detailed operational cost template provides an indication on how the funds will be managed between different partners including the Ministry. The management of funds will follow the existing financial management procedures for each of the reciving agents.
c) Please indicate if the campaign is going to be phased, and if so, how this will be done.
Drawing experience from the measles and rubella campaign, the campaign will be implemented two phase
a) Phase 1- school based campaign involving all children in school above 5 years up to 14 years.
b) Phase 2- community based campaign which will include all children 9 month to 5 years; ii) out of school children - those school aged children who are not in school for various reasons; iii) school children who were missed during the schoo phase.
In adidtion, to the above and considering the logistics challenges of implementing campaign in the hard to reach areas especially the conflic affected, georaphically hard to reach, self-administrarive and non - government controlled area, the campaign will be implemented in one phase only. This will will make it easy to organize logistics and ensure quality campaign in the special designated areas.
d) Please outline how coverage of the campaign will be monitored, reported and evaluated (refer to the cMYP and/or the JE, 5 dose(s) per vial, LYOPHILISED campaign introduction plan)
A JE Campaign Vaccination Card will be designed, printed and distributed during the campaign for children with JE vaccination. This JE Campaign Vaccination Card will be used for tracking children who got JE vaccine during the post-campaign coverage survey.
Recording and reporting forms for tracking and reporting vaccination and supply will be developed/adapted, printed and distributed using existing resources already developed and used in other countries (Cambodia, Nepal, Laos, etc.)
Success of the JE SIA will be measured using two indicators:
1. Overall JE vaccination coverage at RHC, township, region/state and national level [target 100%].  All levels must have JE SIA coverage monitoring chart available with the JE target, and update and monitor this daily during the course of the SIA.
2. Rapid coverage assessments, especially in areas with large populations or uncertain population targets [target is final RCA results for all selected communities pass RCA]
All vaccination teams will use a standard reporting form with the results to be telephoned to the township level every evening before 06:00pm.  All vaccination teams are to report the following information for all immunization sites:
General village:
· Number of JE doses given
· Rapid Coverage Assessment results for selected villages.
High Risk Communities will also have special reporting requirements:
· Number of JE doses given
· Rapid Coverage Assessment results for ALL High Risk Communities
· Check of children routine immunization status [12 to 23 months]
Rapid Coverage Assessments (RCA): RCA was used as the most reliable forms of monitoring progress of SIA campaign.  During the JE SIA two types of RCA will be carried out:
· JE vaccine RCA will be conducted at every site to confirm the quality of implementation, using random samples of 20 children in the target age ranges. This will be conducted by local level supervisors or other non-vaccination team members, and will provide a pass/fail assessment of the area. Areas that fail the RCA require further mop up activities and additional RCA to confirm that no children have been missed.
· Identified high risk communities, in addition to the RCA for JE vaccine, a RCA for routine EPI coverage for children from 9 to 23 months that will assess their routine immunization “up to date” status. This will be collated by the cEPI at the regional/state and national levels and allow a post SIA detailed assessment to be made where areas of weak routine immunization remain for focus and correction through the routine EPI.
Administrative Coverage Data: In addition to the use of RCA for monitoring the quality of coverage, traditional reporting systems based on administrative data will be used, and monitored in “real time” with daily reporting, collation and assessment of coverage data by the WHO/cEPI. All township will report summary results at the end of each day to their cEPI supervision focal point that will then transmit this data to a centralized data focal point, either via email or SMS. Data will be reviewed each evening and a detailed report issued to all cEPI and partner focal points the following morning to allow rapid sharing of information and issues, and immediately identify areas of concern for swift correction.
Post-campaign coverage survey.  This will be a statistically representative survey conducted in February or March, 2018. Modified cluster survey is two-stage sampling method where villages selected randomly first, then individual households in each village selected randomly.

	
	8.3 Product Licensure

	
	For each of the vaccine(s) requested, please state whether manufacturer registration and/or national vaccine licensure will be needed in addition to WHO prequalification and, if so, describe the procedure and its duration. In addition, state whether the country accepts the Expedited Procedure for national registration of WHO-prequalified vaccines.
Note that the necessary time for licensure should be factored into the introduction timeline and reflected in the Vaccine Introduction Plan or Plan of Action.
SA 14-14-2 is already licenced in Myanmar since 2010.
For each of the vaccine(s) requested, please provide the actual licensure status of the preferred presentation and of any alternative presentations, if required.
CDIBP SA 14-14-2 is licensed in Myanmar since 2010 and its’ WHO prequalified since October 2013.
Please describe local customs regulations, requirements for pre-delivery inspection, special documentation requirements that may potentially cause delays in receiving the vaccine. If such delays are anticipated, explain what steps are planned to handle these.
The Ministry of Health will be the consignee for the JE vaccine for the campaign, and prior arrangements will be made to ensure that all documents for processing customs clearance are made available to the country at least 5 months before the delivery of the vaccine. The Ministry of Health will apply for the import permit from the Ministry of commerce and aftrer pre-delivery note is received the application for taxi excemption from the Ministry of Finance will be processed.
Currently UNICEF is providing technical support to the Ministry of Health to address all challenges related to delays in customs clearance and it is anticipated that these effortrs will benefit the JE clearance as well.
Please provide information on NRA in the country, including status (e.g. whether it is WHO-certified).  Please include points of contact with phone numbers and e-mail addresses.  UNICEF will support the process by communicating licensing requirements to the vaccine manufacturers where relevant.
The Food and Regulatory Authority for Myanmar which is the Food and Drug Administration (FDA) is still evolving and WHO has been working closely with the Ministry of Health to strengthen FDA capacity and fast-track the certification process .The main point of contact is the Director General of FDA
Department of Food and Drug Administration
Ministry of Health
Pyigyi Zayyar Road,(in front of Sabel Housing)
Zayyar Thiri Ward, Zabu Thiri Township,
Nay Pyi Taw, Myanmar.
Phone : +95-67-403609067-403609
Fax     : +95 67-403350
http://www.fdamyanmar.gov.mm/index.php/en

	
	8.4 Vaccine Management (EVSM/EVM/VMA)

	
	It is mandatory for countries to conduct an Effective Vaccine Management (EVM) assessment prior to an application for the introduction of a new vaccine. This EVM should have been conducted within the preceding 5 years.
When was the EVM conducted? May 2015
Please attach the most recent EVM assessment report (DOCUMENT NUMBER : 20,19,21), the corresponding EVM improvement plan (DOCUMENT NUMBER : 19) and progress on the EVM improvement plan (DOCUMENT NUMBER : 21). The improvement plan should include a timeline, budget of committed resources for these activities and funding gaps, if any, as well as M&E indicators to monitor progress of implementation.
If any of the above mandatory documents (EVM Assessment Report, EVM Improvement Plan, Progress on the EVM Improvement Plan) are not available, please provide justification and reference to additional documents such as PIE and External EPI Reviews.
When is the next Effective Vaccine Management (EVM) Assessment planned? May 2018
EVMA report and improvement plan are attached.

	
	8.5 Waste management

	
	Countries must have a detailed waste management and monitoring plan as appropriate for their immunisation activities. This should include details on sufficient availability of waste management supplies (including safety boxes), the safe handling, storage, transportation and disposal of immunisation waste, as part of a healthcare waste management strategy. Please describe the country’s waste management plan for immunisation activities (including campaigns).
A waste management plan exists that involves health workers filling safety boxes with used needles and syringes (uncapped) until 100 syringe capacity, closing the box, and storing it in a safe location. During supervisor visits these boxes are taken back to RHC. Main disposal method is done through burning and burying but in urban areas, incinerator is used for burning used needles and syringes.
Training in injection safety: Health worker training prior to the JE campaign will encompass both injection safety and appropriate procedures for waste disposal. Health worker training prior to the JE campaign will encompass both injection safety and appropriate procedures for waste disposal. Training of health workers on injection safety and waste disposal will be integrated with training on JE campaign implementation.
Vaccination teams will have sufficient safety boxes for the number of AD syringes (1 safety box for every 100 AD syringes).Used AD syringes and syringe caps should be placed in safety boxes immediately after the vaccine has been given, and when a safety box is approximately ¾ full it will be closed off and a new one used.Empty JE vials will be placed in the waste.
Used safety boxes will be sent to the HC at the end of each day, and stored in a secure and waterproof area and will be burnt/buried or incinerated at the end of the campaign.


	

	


	9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC)


	
	
	Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

	
	The ICC meeting that took place on 29th April 2016 to endorse the proposal made the following comments
1. The procurement arranegements for the routine vaccine: MOH wanted to know how PATH donated JE will arrive in the country and how vaccines for subsequent years will be procured (i.e vaccine procured through UNICEF procurement services or Government Self- procurement).
2. There is a need to strengthen AES/JE surveillane and strengthen coordination with livestock ministry.
3. The Deputy Director - Department of Public Health (Disaster and Epidemiology) emphasized that the most effective strategy of control JE is through immunization.
4. UNICEF, WHO and PATH representative pledged their full support for a successfull campaign and introduction of JE in to routine immunization.
All ICC members were in agreement with the proposal and endorsed with no objection.


	

	


	10. List of documents attached to this proposal


		
		
	10.1. List of documents attached to this proposal
	
		
	Table 1: Checklist of mandatory attachments
	
		
	Document Number
Document
Section
File
Endorsements
1
MoH Signature (or delegated authority) of Proposal
4.1.1
signature MOH.jpg
File desc: 
Date/time : 29/04/2016 11:53:04
Size: 2 MB
2
MoF Signature (or delegated authority) of Proposal
4.1.1
Signature of Ministry of Finance.pdf
File desc: 
Date/time : 29/04/2016 11:58:30
Size: 16 KB
4
Terms of Reference for the ICC
4.1.2
ICC TOR .doc
File desc: 
Date/time : 29/04/2016 05:24:50
Size: 41 KB
5
Minutes of ICC/HSCC meeting endorsing Proposal
4.1.3
Meeting minutes on 3rd ICC for JE.pdf
File desc: 
Date/time : 30/04/2016 01:58:25
Size: 37 KB
6
Signatures of ICC or HSCC or equivalent in Proposal
4.1.3
ICC signatures Apr 30 2016 1046.pdf
File desc: 
Date/time : 30/04/2016 12:40:45
Size: 2 MB
7
Minutes of last three ICC/HSCC meetings
4.1.3
Attachment 7  Minutes of Last 3 ICC Meetings.zip
File desc: 
Date/time : 29/04/2016 12:16:35
Size: 4 MB
8
Role and functioning of the advisory group, description of plans to establish a NITAG
4.2.1
Roles and functionality of National Committee on Immunization in Practices.docx
File desc: 
Date/time : 29/04/2016 05:32:51
Size: 16 KB
Planning, financing and vaccine management
9
comprehensive Multi Year Plan - cMYP
5.1
Myanmar cMYP 2017-2021 .docx
File desc: 
Date/time : 29/04/2016 09:40:41
Size: 1 MB
10
cMYP Costing tool for financial analysis
5.1
MMR cMYP Costing ver_29April2016.xlsx
File desc: 
Date/time : 29/04/2016 10:52:13
Size: 3 MB
11
M&E and surveillance plan within the country’s existing monitoring plan
5.1.5
Monitoring and evaluation plan for JE campaign.docx
File desc: 
Date/time : 29/04/2016 05:47:47
Size: 18 KB
13
Introduction Plan for the introduction of RCV / JE / Men A / YF into the national programme
7.x.4
JE vaccine introduction plan final.doc
File desc: 
Date/time : 29/04/2016 05:49:55
Size: 1 MB
17
Evidence of commitment to fund purchase of RCV for use in the routine system in place of the first dose of MCV
7.x.3
JEVaccine2017-2018Myanmar.pdf
File desc: 
Date/time : 29/04/2016 05:48:35
Size: 46 KB
18
Campaign target population documentation
7.x.1, 6.x.1
target population justification.docx
File desc: 
Date/time : 29/04/2016 05:49:04
Size: 12 KB
19
EVM report
8.3
Myanmar 2015  EVMA Report.pdf
File desc: 
Date/time : 29/04/2016 10:42:41
Size: 4 MB
20
Improvement plan based on EVM
8.3
Myanmar 2015 Effective Vaccine Management Improvement Plan.pdf
File desc: 
Date/time : 29/04/2016 10:46:51
Size: 469 KB
21
EVM improvement plan progress report
8.3
Attachment 14 EVM progress report.pdf
File desc: 
Date/time : 29/04/2016 10:44:13
Size: 172 KB
22
Detailed budget template for VIG / Operational Costs
6.x,7.x.2, 6.x.2
JE Budget.zip
File desc: 
Date/time : 30/04/2016 01:07:41
Size: 27 KB
27
Data quality assessment (DQA) report
5.1.5
DQA and SQA findings of year 2010- 10 townships.doc
File desc: 
Date/time : 29/04/2016 06:07:03
Size: 3 MB
29
Plan of Action for campaigns
7.1, 7.x.4
Myanmar POA April 28 Final Version.docx
File desc: 
Date/time : 29/04/2016 05:50:56
Size: 282 KB
	
		
	Table 2: Checklist of optional attachments
	
		
	Document Number
Document
Section
File
3
MoE signature (or delegated authority) of HPV Proposal
4.1.1
No file loaded
12
Vaccine introduction plan
5.1
JE vaccine introduction plan final.doc
File desc: 
Date/time : 29/04/2016 06:09:12
Size: 1 MB
15
HPV roadmap or strategy
6.1.1
No file loaded
16
HPV summary of the evaluation methodology
5.1.6
No file loaded
23
Risk assessment and consensus meeting report for MenA. If the DPT was used instead, please include this.
7.1
No file loaded
25
A description of partner participation in preparing the application
4.1.3
JE GAVI _Description of partners collaboration_29th April 2016 Final.docx
File desc: for JE application
Date/time : 29/04/2016 11:24:20
Size: 14 KB
26
Minutes of NITAG meeting with specific recommendations on the NVS introduction or campaign
4.2
NCIP recommendation 2015 on JE introduction.docx
File desc: 
Date/time : 29/04/2016 10:56:50
Size: 38 KB
28
DQA improvement plan
5.1.5
No file loaded
30
Other
Partner JE consultative workshop.zip
File desc: 
Date/time : 30/04/2016 01:03:13
Size: 511 KB
	

	

	


	11. Annexes


	
	
	Annex 1 - NVS Routine Support

	
	No NVS Routine Support is requested

	
	Annex 2 - NVS Routine – Preferred Second Presentation

	
	No NVS Routine – Preferred Second Presentation requested this year

	
	Annex 3 - NVS Preventive campaign(s)

	
	Annex 3.1 - NVS Preventive campaign(s) (JE, 5 dose(s) per vial, LYOPHILISED)
Table Annex 3.1 C: Summary table for CAMPAIGN JE, 5 dose(s) per vial, LYOPHILISED
ID
Data from
2017
Total target population
Table 5.2
#
14,039,000
Number of doses per persons
Parameter
#
1
Wastage Rate
Table 6.4.1
#
10
Estimated vaccine wastage factor
Table 5.2
#
1.11
Number of doses per vial
Parameter
#
5
AD syringes required
Parameter
#
Yes
Reconstitution syringes required
Parameter
#
Yes
Safety boxes required
Parameter
#
Yes
ca
AD syringe price per unit
Table Annexes 4A
$
0.041
cr
Reconstitution syringe price per unit
Table Annexes 4A
$
0.006
cs
Safety box price per unit
Table Annexes 4A
$
0.005
fv
Freight cost as % of vaccines value
Table Annexes 4B
%
0
fd
Freight cost as % of devices value
Parameter
%
0


	

	


	Table Annex 3.1 D: Estimated numbers for JE, 5 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1)


	
	
	Formula
2017
Total
Government
Gavi
B
Total target population
Table 5.3.1
14,039,000
0
14,039,000
C
Number of doses per persons
Vaccine parameter (schedule)
1
D
Number of doses needed
B x C
14,039,000
0
14,039,000
E
Estimated vaccine wastage factor
100 / (100 - Vaccine wastage rate)
1.11
F
Number of doses needed including wastage
D x E
15,583,291
0
15,583,291
G
Vaccines buffer stock
0
0
0
0
I
Total vaccine doses needed
Round up((F + G) / Vaccine package size) * Vaccine package size
15,583,300
0
15,583,300
J
Number of doses per vial
Vaccine parameter
5
K
Number of AD syringes (+ 10% wastage) needed
(D + G) x 1.11
15,583,291
0
15,583,291
L
Reconstitution syringes (+ 10% wastage) needed
(I / J) x 1.11
3,459,493
0
3,459,493
M
Total of safety boxes (+ 10% of extra need) needed
(K + L) / 100 x 1.11
211,375
0
211,375
N
Cost of vaccines needed
I x vaccine price per dose (g)
6,544,986
0
6,544,986
O
Cost of AD syringes needed
K x AD syringe price per unit (ca)
635,047
0
635,047
P
Cost of reconstitution syringes needed
L x reconstitution price per unit (cr)
21,220
0
21,220
Q
Cost of safety boxes needed
M x safety box price per unit (cs)
1,071
0
1,071
R
Freight cost for vaccines needed
N x freight cost as of % of vaccines value (fv)
0
0
0
S
Freight cost for devices needed
(O+P+Q) x freight cost as % of devices value (fd)
0
0
0
T
Total fund needed
(N+O+P+Q+R+S)
7,202,324
0
7,202,324

	
	Note:There is no co-financing for NVS preventive campaigns


	

	

	

	

	

	

	


	

	

	

		
	Annex 4
	
		
	Table Annex 4A: Commodities Cost
	
		
	Estimated prices of supply are not disclosed
	
		
	Table Annex 4B: Freight cost as percentage of value
	
		
	Vaccine Antigen
Vaccine Type
2017
JE, 5 dose(s) per vial, LYOPHILISED
JE
3.00 %
	
		

	

	


	Table Annex 4D: Wastage rates and factors


	
	
	The following table shows the wastage rates for routine and campaign vaccines, set for 2017.

	
	Vaccine
dose(s) per vial
Maximum Vaccine wastage rate*
Benchmark Wastage Rate**
HPV bivalent, 2 dose(s) per vial, LIQUID
2
10 %
0 %
HPV quadrivalent, 1 dose(s) per vial, LIQUID
1
5 %
0 %
JE, 5 dose(s) per vial, LYOPHILISED
5
10 %
10 %
Measles second dose, 10 dose(s) per vial, LYOPHILISED
10
40 %
0 %
Meningococcal A, 10 dose(s) per vial, LYOPHILISED
10
50 %
10 %
MR, 10 dose(s) per vial, LYOPHILISED
10
15 %
0 %
Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID
2
10 %
0 %
Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID
1
5 %
0 %
Rotavirus, 2-dose schedule
1
5 %
0 %
Rotavirus, 3-dose schedule
1
5 %
0 %
Yellow Fever, 10 dose(s) per vial, LYOPHILISED
10
40 %
0 %
Yellow Fever, 5 dose(s) per vial, LYOPHILISED
5
10 %
0 %

	
	Comments:

	* Source - WHO indicative wastage rates

	** Source - Country APRs and studies, approved by WHO, UNICEF, and the Gavi Secretariat

	Note: HPV demonstration project wastage rates are the same as for the national introduction of the vaccine

	
	Table Annex 4E: Vaccine maximum packed volumes

	
	Kindly note that this table is for reference purposes only and includes Gavi- and non Gavi-supported vaccines.

	
	Vaccine product
Designation
Vaccine formulation
Admin route
No. Of doses in the schedule
Presentation (doses/vial, prefilled)
Packed volume vaccine (cm3/dose)
Packed volume diluents (cm3/dose)
BCG
BCG
lyophilized
ID
1
20
1.2
0.7
Diphtheria-Tetanus
DT
liquid
IM
3
10
3
Diphtheria-Tetanus-Pertussis
DTP
liquid
IM
3
20
2.5
Diphtheria-Tetanus-Pertussis
DTP
liquid
IM
3
10
3
DTP liquid + Hib freeze-dried
DTP+Hib
liquid+lyop.
IM
3
1
45
DTP-HepB combined
DTP-HepB
liquid
IM
3
1
9.7
DTP-HepB combined
DTP-HepB
liquid
IM
3
2
6
DTP-HepB combined
DTP-HepB
liquid
IM
3
10
3
DTP-HepB liquid + Hib freeze-dried
DTP-Hib
liquid
IM
3
10
2.5
DTP-HepB liquid + Hib freeze-dried
DTP-HepB+Hib
liquid+lyop.
IM
3
1
22
DTP-HepB-Hib liquid
DTP-HepB+Hib
liquid+lyop.
IM
3
2
11
DTP-HepB-Hib liquid
DTP-HepB-Hib
liquid
IM
3
10
4.4
DTP-HepB-Hib liquid
DTP-HepB-Hib
liquid
IM
3
2
13.1
DTP-HepB-Hib liquid
DTP-HepB-Hib
liquid
IM
3
1
19.2
DTP-Hib combined liquid
DTP+Hib
liquid+lyop.
IM
3
10
12
DTP-Hib combined liquid
DTP-Hib
liquid
IM
3
1
32.3
Hepatitis B
HepB
liquid
IM
3
1
18
Hepatitis B
HepB
liquid
IM
3
2
13
Hepatitis B
HepB
liquid
IM
3
6
4.5
Hepatitis B
HepB
liquid
IM
3
10
4
Hepatitis B UniJect
HepB
liquid
IM
3
Uniject
12
Hib freeze-dried
Hib_lyo
lyophilized
IM
3
1
13
35
Hib freeze-dried
Hib_lyo
lyophilized
IM
3
2
6
Hib freeze-dried
Hib_lyo
lyophilized
IM
3
10
2.5
3
Hib liquid
Hib_liq
liquid
IM
3
1
15
Hib liquid
Hib_liq
liquid
IM
3
10
2.5
Human Papilomavirus vaccine
HPV
liquid
IM
3
1
15
Human Papilomavirus vaccine
HPV
liquid
IM
3
2
5.7
Japanese Encephalitis
JE_lyo
lyophilized
SC
1
5
2.5
2.9
Measles
Measles
lyophilized
SC
1
1
26.1
20
Measles
Measles
lyophilized
SC
1
2
13.1
13.1
Measles
Measles
lyophilized
SC
1
5
5.2
7
Measles
Measles
lyophilized
SC
1
10
3.5
4
Measles-Mumps-Rubella freeze dried
MMR
lyophilized
SC
1
1
26.1
26.1
Measles-Mumps-Rubella freeze dried
MMR
lyophilized
SC
1
2
13.1
13.1
Measles-Mumps-Rubella freeze dried
MMR
lyophilized
SC
1
5
5.2
7
Measles-Mumps-Rubella freeze dried
MMR
lyophilized
SC
1
10
3
4
Measles-Rubella freeze dried
MR
lyophilized
SC
1
1
26.1
26.1
Measles-Rubella freeze dried
MR
lyophilized
SC
1
2
13.1
13.1
Measles-Rubella freeze dried
MR
lyophilized
SC
1
5
5.2
7
Measles-Rubella freeze dried
MR
lyophilized
SC
1
10
2.5
4
Meningitis A conjugate
Men_A
lyophilized
IM
1
10
2.6
4
Meningitis A/C
MV_A/C
lyophilized
SC
1
10
2.5
4
Meningitis A/C
MV_A/C
lyophilized
SC
1
50
1.5
3
Meningitis W135
MV_W135
lyophilized
SC
1
10
2.5
4
Meningococcal A/C/W/
MV_A/C/W
lyophilized
SC
1
50
1.5
3
Meningococcal A/C/W/Y
MV_A/C/W/Y
lyophilized
SC
1
10
2.5
4
Monovalent OPV-1
mOPV1
liquid
Oral
20
1.5
Monovalent OPV-3
mOPV3
liquid
Oral
20
1.5
Pneumo. conjugate vaccine 10-valent
PCV-10
liquid
IM
3
1
11.5
Pneumo. conjugate vaccine 10-valent
PCV-10
liquid
IM
3
2
4.8
Pneumo. conjugate vaccine 13-valent
PCV-13
liquid
IM
3
1
12
Polio
OPV
liquid
Oral
4
10
2
Polio
OPV
liquid
Oral
4
20
1
Polio inactivated
IPV
liquid
IM
3
PFS
107.4
Polio inactivated
IPV
liquid
IM
3
10
2.5
Polio inactivated
IPV
liquid
IM
3
1
15.7
Rota vaccine
Rota_liq
liquid
Oral
2
1
17.1
Rota vaccine
Rota_liq
liquid
Oral
3
1
45.9
Tetanus Toxoid
TT
liquid
IM
2
10
3
Tetanus Toxoid
TT
liquid
IM
2
20
2.5
Tetanus Toxoid UniJect
TT
liquid
IM
2
Uniject
12
Tetanus-Diphtheria
Td
liquid
IM
2
10
3
Yellow fever
YF
lyophilized
SC
1
5
6.5
7
Yellow fever
YF
lyophilized
SC
1
10
2.5
3
Yellow fever
YF
lyophilized
SC
1
20
1.5
2
Yellow fever
YF
lyophilized
SC
1
50
0.7
1


	

	


	12. Banking Form


		
		
	In accordance with the decision on financial support made by the Gavi, the Government of Myanmar hereby requests that a payment be made via electronic bank transfer as detailed below:
Name of Institution (Account Holder):
Address:
City Country:
Telephone no.:
Fax no.:
Currency of the bank account:
For credit to:
Bank account's title:
Bank account no.:
Bank's name:
	
		
	Is the bank account exclusively to be used by this program?  
	
		
	By who is the account audited?  
	
		
	Signature of Government's authorizing official
	
		
	Seal
Name:
Title:
Signature:
Date:
	
		
	FINANCIAL INSTITUTION
Bank Name:
Branch Name:
Address:
City Country:
Swift Code:
Sort Code:
ABA No.:
Telephone No.:
FAX No.:
	CORRESPONDENT BANK
(In the United States)

		
	I certify that the account No  is held by  at this banking institution
The account is to be signed jointly by at least  (number of signatories) of the following authorized signatories:
1
Name:
Title:
2
Name:
Title:
3
Name:
Title:
	
		
	Name of bank's authorizing official
Signature:
Date:
Seal:
	

	

	


	
	Page

	1/1

	



