January 2005 (revised)

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Bosnia and Herzegovina

Date of submission 15.05.2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report √  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# annual progress report  √ Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

Not applicable

#### 1.1.1	Management of ISS Funds    Not applicable

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not applicable. no ISS funds received by BiH

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 __None_________

Remaining funds (carry over) from 2004 _Not applicable

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

X

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

Not applicable

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH: January*            YEAR: 2003*

* Hepatitis B vaccination started in Republika Srpska in January 2003, in Brcko District in January 2004 and in Federation of Bosnia and Herzegovina in May 2004.

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Country Bosnia and Herzegovina level : Total amount of Hep B vaccine received in Bosnia and Herzegovina ( two entities: Federation of BiH, Republika Srpska and District Brcko) in year 2005 was 35, 300 doses in ten-dose vials and 62, 800 doses in mono-dose vials, 96, 700 AD Syringes, and 1,075 Safety boxes. FBiH and Brcko District: Total quantity of 49,300 doses of HepB (out of that 46,000 mono-dose and 3,300 multi-dose HepB, 56,700 AD syringes and 575 safety boxes) was donated by GAVI and received by government of Federation BiH and District Brcko in a year 2005. Out of 49,300 doses received, Distrikt Brcko got 1,000 mono-doses and 1,000 multi-doses of HepB vaccines. According to the request and vaccine procurement plan developed by the Federal Public Health Institute vaccines were received from the GAVI/UNICEF Copenhagen in two separate shipments. The first shipment of 30, 000 mono-dose and 3,300 multi-dose vaccines, was delivered on 13 May 2005, and second shipment of 16,000 mono-dose vaccines was delivered to the PHIs on 5th December. The shipments of vaccines arrived timely and without any problem. On the request of entity Minister of Health, UNICEF BiH continued to handle the custom clearance procedure and internal transportation of vaccines from the airport cold room to the central cold room placed of the Federal PHI. Republika Srpska/ RS : Total quantity of 48,800 doses of HepB (out of that 16.800 mono-dose and 32.000 multi-dose,40.000 AD syringes and 500 safety boxes)was donated by GAVI and received by government of RS in 2005. According to the request and vaccine procurement plan developed by the RS Public Health Institute vaccines and devices were received in one shipment trough UNICEF on 13 may 2005 without any problem. UNICEF BiH was responsible for custom clearance procedure and internal transportation of Hep B vaccines from the airport cold room to the central cold room of RS PHI.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Bosnia and Herzegovina (national level): - UNICEF BiH supported government of two entities and district Brcko to develop Communication plan. - The supported activity under Communication plan was development of the Communication Protocol for the Public Health, which was developed on the country level. - The launching of Communication protocol was organised on the Round table hosted by Federal PHI where representatives from different sectors from whole country such as education, media, and social were present. - Based on the Communication Protocol educational material such as leaflets and posters for health professionals and parents on importance of immunization were produced and distributed trough health centres and maternity wards. Federation of Bosnia and Herzegovina (entity level): - The Order on the Implementation of the Program of mandatory immunization for year 2005 was carefully revised to underpin the new Schedule, the diminished number of contraindications, clarified obligations of reports of AEFI, and a new policy of open bottles. - Monitoring of the Program - monthly/annual, regarding the coverage by EPI vaccines, usage and distribution of vaccines, side effect reactions upon immunization, The Report Forms have been standardised as regulated by the Order on the Implementation of the Program on mandatory immunization for 2005, - Software for Monitoring of Immunization Program - monthly/annually installed in F BiH - Numerous education seminars and consultation meetings with implementers of the Program in connection to all issues related to the Program (in total 40 meetings since the introduction of neonatal and infant hep B Vaccine in May 2004 - Communication between EPI coordinators (cantonal and Federal) was intensified - Intensified work on the improvement of the level of the coverage of vaccination as a strategic indicator for measuring implementation of the Program on immunization; as input for planning of the number of the children to immunise, with monthly reporting on the coverage of immunization, determining the target cohorts for vaccination- - Analysis and feed back of quarterly reporting from cantonal EPI coordinators regarding coverage and use of vaccines- The F-PHI listed, translated a minimal set of indicators for monitoring and evaluation of the program of immunization and delivered to all EPI coordinators. - Training of technical staff on the topic "Planning and distribution of vaccines at the municipal level, control of cold chain, use of AD syringe and security boxes (translation of document WHO) - Translated and distributed questionnaire recommended by WHO to each vaccination place which data will be used for detailed review and analysis of cold chain, staff responsible for the Program of immunization (done in 2006, (Analysis of cold chain, revision of the list of people responsible for immunization done in 2006 – see Proposal for Hib support) - A Three day annual seminar was held in Neum in 2005, with presentations of current issues related to immunization. - Active participation of the team in the work of the II CROATIAN EPIDEMIOLOGY CONGRESS where health professionals from Federation of BiH shared experiences on the introduction of neonatal hepatitis B vaccine into the National Program of Immunization - Participation of the team for "Evaluation of the level of the injections safety" - translation and distribution of Post vaccination injections and safe deposit of vaccines in BiH Republika Srpska (entity level): - Supervisory visits were conducted to 10 hospitals and 30 primary health centres, covering the administration of neonatal dose and following doses Hep B vaccination and other components of the Programme. - Monitoring of the Program - monthly/annual, regarding the coverage by EPI vaccines, usage and distribution of vaccines, side effect reactions upon immunization - Communication between EPI coordinators (regional and entity) was intensified and on regular basis - Participation of the team for "Evaluation of the level of the injections safety" - translation and distribution of Post vaccination injections and safe deposit of vaccines in BiH - Analysis and feed back of reporting from regional EPI coordinators regarding coverage and use of vaccines Brcko District: - The District PHI collaborates with both entities regarding training and monitoring of the Immunisation Programme.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

GAVI/VF financial support was distributed between Federation of Bosnia and Herzegovina, Republic of Srpska and Brcko District based on an ICC decision in 2003, as 52%, 44% and 3% respectively. Entities and national; Distributed amount %; Received amount in local currency (BAM); Utilized amount BAM (% in 2003); Utilized amount BAM (% in 2004); Utilized amount BAM (% in 2005); Remaining amount BAM (% by end of 2005). Federation of Bosnia and Herzegovina; 52%; 86,373.98 (100%); 0 (0%); 32,171.76 (37%); 20,212 (24%); 33, 990.22 (38%). Republic of Srpska; 44%; 72,968.65 (100%); 19,675.60 (27,0%); 16,657.0 (23%); 3,000 4%; 33,636.05 KM 46.%. Brcko District; 3%; 5,000 (100%); 0; 2,500 (50%); 2,500 (50%); 0. Bank charges; 1%; Not relevant; Not relevant; Not relevant; Not relevant. BiH; 100%; 164,342.63; 19,675.60; 51,328.76; 25,712; 67,626.27 (42%). In 2005, financial support were used for following activities; - Federation of Bosnia and Herzegovina (20, 212 BAM, 24% of total allocated amount to FBiH) Seminars on strengthening HepB vaccination ( 19,742 BAM, 98% of 2005 expenditures in FBiH Travel cost for supervision to cantonal and field level (470 BAM, 0.5 % of 2005 expenditure in FBiH) - Republic of Srpska (3,000 BAM, 4 % of total allocated amount to RS) Travel cost for supervision to regional and field level (3,000 BAM, 100 % of 2005 expenditure in RS) - Brcko District (2,500 BAM, 50% of total allocated amount to Brcko) Seminar on strengthening HepB vaccination ( 2,500 BAM, 100 % of 2005 expenditure in Brcko)

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Not applicable. Support was approved on 19 September 2005 for three years from 2006

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### Not applicable

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Not applicable

# 2.  	Financial sustainability

During the ICC meeting held on January 26th of 2005, the first  FSP was presented to ICC members and their initial comments have been received. FSP was seen as a significant novel instrument in the long term planning and financing of the IP. And it is noted by the ICC members that the FSP should be considered as a working document open to appropriate revisions during implementation as new date will be available and the action plan being reviewed. FSP is expected to provide useful management inputs in managing the ongoing overall contextual changes and public reforms, as well as the health sector ones, with critical implications expected for the IP.

In general, the FSP strategies mainly focus on securing public resources (increasing its reliability) and improving both technical and allocative efficiency. And a special strategy element particularly in FBiH address in the FSP was the need for further social mobilization activities to avoid an explosion of negative public attitude toward certain antigens resulting in the failure of planned routine vaccination and introduction of new antigens. Relevant short and medium term activities were identified to implement the financial sustainability strategies in each entity and indicators as well.

Revision of FSP costing and projections is tentatively scheduled for the second half of 2005, following the decisions on vaccine procurement of both entities.

Inception Report	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

The first Annual progress report should be due 2006 – a revised format has been prepared by Unicef and WHO. Guidelines for use are pending.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine, hep B (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| A: Proportion funded by GAVI/VF (%)*** | 100 | 20 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 |
| B: Proportion funded by the Government and other sources (%) | 0 | 80 | 80 | 80 | 80 | 80 | 100 | 100 | 100 | 100 |
| C: Total funding for …………. (new vaccine) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

n table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2.a:	Progress against major financial sustainability strategies and corresponding indicators for Federation of Bosnia and Herzegovina

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| - Resource Mobilization & Reliability: |  |  |  |  |  |  |
| - Ensure that the responsibility of different financial agents (the state budget, the canton budgets, the Federation Solidarity Insurance Fund and the cantonal Health Insurance Funds) for the financing of the NIP are clearly defined in the legislation | - To develop a policy options with the roles of financial agents in the mobilization, management and allocation of funds to the different cost categories of the NIP - To discuss the policy options with policy makers and to arrive at final decision - To draft and endorse the corresponding legal acts | - Policy options for different agents for allocation of funds defined Discussion with policy makers took place Corresponding legal acts developed | Very fragmented and complex administrative structure and lack of enforcement low mechanism | No clear policy | Progress expected in 2006 | n.a. yet – pending revised guidelines of FSP |
| - Ensure that the needs of the NIP in terms of resource requirements and organizational arrangements are well recognized and integrated in short and medium-term planning and institutional reforms of the primary health care system | - To participate in the design of PHC facility standards (enforced by licensing or contracting mechanisms) and integrate the needs of the NIP - To participate in the design of the functional plans and the scope of work of medical professionals of PHC institutions to integrate the needs of the NIP - To develop clear mechanisms of the vaccine distributions and update the legislation to implement them - To include incentives favorable for the immunization services in the health care financing policy options | Discussion and participation in planning and reforms of PHC took place | Lack of understanding of policy makers on sensitivity and needs of NIP | No participation and incentives | Pilot introduction of reformed primary health care system started 2005 in three Cantons: Sarajevo, Tuzla and Zenica. Evaluation in 2007 | n.a. yet – pending revised guidelines of FSP |
| - Efficiency |  |  |  |  |  |  |
| - Ensure that coordination of the vaccine stock management improved (minimized shortages and overages) | - To develop and introduce the stock management procedure (guidelines) - To install (stock) management information system - To train personnel | Review of stock procedure in ten cantons carried out by EPI managers Information system installed in few cantons Professionals trained | Information system adopted in few cantons | No procedures installed at MIS | Procedures installed in 2005, | n.a. yet – pending revised guidelines of FSP |
| - Ensure that vaccines are procured at the lowest cost (close to UNICEF prices) without sacrificing quality | - To revise the legislation to enable state procurements directly from UNICEF - To conduct market assessment to identify suppliers with the lowest prices (meeting quality standards) | n.a.yet | n.a. yet | No clear legislation and market assessment | Legislation enacted see section 1.2.2 | n.a. yet – pending revised guidelines of FSP |
| - Consider to revise the vaccination schedule based on sound cost-benefit analysis | - To conduct cost-benefit analysis of the introduction of costly antigens - To develop proposal on changes in the vaccination schedule - To approve revised schedule | n.a. yet | n.a. yet | No analysis and revised schedule | Progress expected in 2006 | n.a. yet – pending revised guidelines of FSP |
| - Increase public awareness of the benefits of immunization (regarding both traditional and new vaccines), quality of the vaccines used and possibility of side effects to prevent interruption of the immunization) | - To conduct baseline assessment of public attitudes (e.g. KAP survey) - To develop the social mobilization (information campaign) strategy - To implement the strategy - To evaluate changes in public attitude | Communication plan developed Communication Protocol and other educational material developed | n.a. yet | No assessment and social mobilization strategy | High coverage of neonatal HepB vaccination sustained in 2005, Table 3 – suggests adequate mobilisation | n.a. yet – pending revised guidelines of FSP |
| - 2.5 Increase the knowledge and change the attitude of health care providers toward to rationale vaccination (and/or side effects of and contraindications of vaccines) | - To conduct baseline assessment - To develop training master plan - To integrate relevant issues in the human development strategy in health care sector - To evaluate results periodically | Educational materials on HepB for health professionals developed and provided to health profess. | n.a. yet | No assessment and training master plan | Comprehensive training modules used at Hep B introduction shown to be effective – raising specific and general vaccine coverage | n.a. yet – pending revised guidelines of FSP |

Table 2.2.b:	Progress against major financial sustainability strategies and corresponding indicators for Republika Srpska

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| - Resource Mobilization & Reliability: |  |  |  |  |  |  |
| - Ensure that the responsibility of different financial agents (the state budget, Health Insurance Fund) for the financing of the NIP are clearly defined in the legislation | - To develop a policy options with the roles of financial agents in the mobilization, management and allocation of funds to the different cost categories of the NIP - To discuss the policy options with policy makers and to arrive at final decision - To draft and endorse the corresponding legal acts | - Policy options for different agents for allocation of funds defined Discussion with policy makers took place Corresponding legal acts developed. According to the FSP government of RS procured vaccines trough UNICEF SD | Political changes in RS government caused frequent changes within MOH | No clear policy | Progress expected in 2006 | n.a. yet – pending revised guidelines of FSP |
| - Ensure that the needs of the NIP in terms of resource requirements and organizational arrangements are well recognized and integrated in short and medium-term planning and institutional reforms of the primary health care system | - To participate in the design of PHC facility standards (enforced by licensing or contracting mechanisms) and integrate the needs of the NIP - To participate in the design of the functional plans and the scope of work of medical professionals of PHC institutions to integrate the needs of the NIP - To develop clear mechanisms of the vaccine distributions and update the legislation to implement them - To include incentives favorable for the immunization services in the health care financing policy options | Discussion and participation in planning and reforms of PHC took place | Lack of understanding of policy makers on sensitivity and needs of NIP | No incentives | Progress expected in 2006 | n.a. yet – pending revised guidelines of FSP |
| - Efficiency |  |  |  |  |  |  |
| - Ensure that coordination of the vaccine stock management improved (minimized shortages and overages) | - To develop and introduce the stock management procedure (guidelines) - To install (stock) management information system - To train personnel | Review of stock procedure in regions of RS carried out by EPI managers Information system installed in central level Few professionals trained | Information system adopted in few cantons | No set procedure or installed MIS | Clear progress during 2005 | n.a. yet – pending revised guidelines of FSP |
| - Ensure that vaccines are procured at the lowest cost (close to UNICEF prices) without sacrificing quality | - To revise the legislation to enable state procurements directly from UNICEF - To conduct market assessment to identify suppliers with the lowest prices (meeting quality standards) | RS government procured vaccines at the lowest price trough Procurement Service of UNICEF Copenhagen | n.a. yet | No clear legislation and market assessment | Legislation in place 2005, procurement trough procurement service UNICEF Copenhagen | n.a. yet – pending revised guidelines of FSP |
| - Consider to revise the vaccination schedule based on sound cost-benefit analysis | - To conduct cost-benefit analysis of the introduction of costly antigens - To develop proposal on changes in the vaccination schedule - To approve revised schedule | n.a. yet | n.a. yet | No analysis and revised schedule | Progress pending Hib introduction in 2007 | n.a. yet – pending revised guidelines of FSP |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 18). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets. Please see APR for 2004 regarding previous achievements |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 33,973 | 32,614 | 31,310 | 30,527 | 29,764 | 29,020 | 28,294 | 27,587 | 26,897 |
| Infants’ deaths | 322 | 309 | 297 | 289 | 282 | 275 | 268 | 261 | 255 |
| Surviving infants | 34,093 | 32,729 | 31,420 | 30,635 | 29,869 | 29,122 | 28,394 | 27,684 | 26,992 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 32049 94% | 31093 95% | 30478 97% | 29716 97% | 28973 97% | 28248 97% | 27542 97% | 26854 97% | 26182 97% |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 30642 90% | 29456 90% | 28906 92% | 28490 93% | 27778 93% | 27083 93% | 26406 93% | 25746 93% | 25103 93% |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of Hep B (neonatal)* (new vaccine) | 32940 97% | 31636 97% | 30370 97% | 29611 97% | 28871 97% | 28149 97% | 27445 97% | 26759 97% | 26090 97% |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of Hep B ( new vaccine) | 30162 89% | 29456 90% | 28906 92% | 28490 93% | 27778 93% | 27083 93% | 26406 93% | 25746 93% | 25103 93% |
| Wastage rate in 2005 and plan for 2006 beyond *** Hep B Mono-dose vials | 1.04 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| Wastage rate in 2005 and plan for 2006 beyond *** Hep B ten-dose vials | 1.30 | 1.30 | 1.30 | 1.30 | 1.30 | 1.30 | 1.30 | 1.30 | 1.30 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 32353 95% | 31310 96% | 30370 97% | 29611 97% | 28871 97% | 28149 97% | 27445 97% | 26759 97% | 26090 97% |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 31 243 89% | 30330 90% | 29117 90% | 28389 90% | 27679 90% | 26987 90% | 26313 90% | 25655 90% | 25014 90% |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

Coverage targets have been adjusted according to the encouragingly high levels reached in 2005. However, a target of 99% is judged to be unrealistically high, therefore targets of 99% has been reduced to the highest 2005 level.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

There is no change in vial presentation compared to request from the last year.

Table 4a: Estimated number of doses of monodose Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Est coverage | FBiH | RS | Brcko | Formula | TOTAL BiH 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 1st dose of Hepatitis B vaccine (*) | 0,97 | 19578 | 9960 | 831 |  | 30 370 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan |  | 50% | 100% | 50% | % |  |
| C | Number of doses per child |  | 2 | 2 | 2 |  | 2 |
| D | Number of doses |  | 19578 | 19920 | 831 | A x Bx C | 40 329 |
| E | Estimated wastage factor |  | 1,05 | 1,05 | 1,05 | (see list in table 3) | 1,05 |
| F | Number of doses (incl. Wastage) |  | 20557 | 20916 | 873 | A x C x E x B/100 | 42 346 |
| G | Vaccines buffer stock |  | 5139 | 5229 | 218 | F x 0.25 | 10 586 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) |  | 5880 | 3000 | 250 | (**) | 9130 |
| I | Total vaccine doses requested |  | 19816 | 23145 | 841 | F + G - H | 43 802 |
| J | Number of doses per vial |  | 1 | 1 | 1 |  |  |
| K | Number of AD syringes (+10% wastage) (***) |  | 20909 | 24585 | 888 | ( D + G – H ) x 1.11 | 46 382 |
| L | Reconstitution syringes(+10% wastage) |  | n.a. | n.a. | n.a. | I / J x 1.11 |  |
| M | Total safety boxes (+10% of extra need) (***) |  | 232 | 272 | 10 | ( K + L ) / 100 x 1.11 | 514 |

(**) Estimation based on established amount of vaccine buffer stock, vaccine coverage and wastage rates, if not received sufficient amount of buffer stock during 2005, given figure should be added to 2006 request.

(***) Please note that requested amount of AD syringes and safety boxes are twice the amount of Hep B vaccine requested due to Federation of Bosnia and Herzegovina purchasing thiomersal free Hep B vaccine for the first dose, but requesting IS supplies for the total amount.

Table 4b: Estimated number of doses of 10 dose vial Hepatitis B vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | FBiH | RS | Brcko | Formula | Total BiH 2007 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Infants vaccinated/to be vaccinated with 3rd dose of Hepatitis B vaccine (*) | 18636 | 9480 | 791 |  | 28 907 |
| B | Percentage of vaccines requested from The Vaccine Fund taking into consideration the Financial Sustainability Plan | 100% | 100% | 100% | % | 100% |
| C | Number of doses per child | 1 | 1 | 1 |  | 2 |
| D | Number of doses | 18636 | 9480 | 791 | A x Bx C | 28 907 |
| E | Estimated wastage factor | 1,3 | 1,3 | 1,3 | (see list in table 3) | 1,30 |
| F | Number of doses (incl. Wastage) | 24227 | 12324 | 1029 | A x C x E x B/100 | 37 580 |
| G | Vaccines buffer stock | 6057 | 3081 | 257 | F x 0.25 | 9 395 |
| H | Anticipated vaccines in stock at start of year 2006 (including balance of buffer stock) | 2510 | 3000 | 250 | (**) | 5,760 |
| I | Total vaccine doses requested | 27774 | 12405 | 1036 | F + G - H | 41,215 |
| J | Number of doses per vial | 10 | 10 | 10 |  |  |
| K | Number of AD syringes (+10% wastage) (***) | 24623 | 10613 | 886 | ( D + G – H ) x 1.11 | 36 122 |
| L | Reconstitution syringes(+10% wastage) | n.a. | n.a. | n.a. | I / J x 1.11 |  |
| M | Total safety boxes (+10% of extra need) (***) | 273 | 118 | 10 | ( K + L ) / 100 x 1.11 | 401 |

*Please report the same figure as in table 3.

(**) Estimation based on established amount of vaccine buffer stock, vaccine coverage and wastage rates, if not received sufficient amount of buffer stock during 2006, given figure should be added to 2007 request.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2007: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007 -2008

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

Following indicators have been identified, discussed and approved by the ICC (April 19, 2005 meeting) to assess the progress of the Hep B vaccine introduction in Bosnia and Herzegovina.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Hep B 1st dose coverage (national) | >95% by 2008 | Achieved; 97% | No | >95%by 2008 |
| Hep B 1st dose coverage (subnational level) | >90% in all cantons / districts by 2008 | Achieved; >95% | No |  |
| Hep B 3rd dose coverage (national) | >95% by 2008 | Not achieved; >88%; | No | >93% by 2008 |
| Hep B 3rd dose coverage (subnational level) | >90% in all cantons / districts by 2008 | Not achieved; >86% | No |  |
| No stock out of vaccines reported through out the reported year | None by 2008 | Not achieved; There were stock out of MMR | Very slow and complicated tendering procedure |  |
| Availability of AD syringes and safety boxes in all vaccination posts visited during the reported year | 100% by 2008 | Not achieved; 60% | No |  |
| Drop out rate (Hep B 3 – Hep B 1) | Less than 8% by 2008 | Not achieved ; 9% | No |  |
| Vaccine wastage rate for 10 dose vial | 1.33 by 2008 | Achieved; wastage rate was 1.30 | No | 1.30 by 2008 |
| Vaccine wastage rate for monodose | 1.05 by 2008 | Achieved ; wastage rate was 1.04 | No |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | Yes | By the latest May 15, 2006 |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in | No | Not applicable |
| DQA reported on | No | Not applicable |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | No | Not applicable |
| FSP Reported on (progress against country FSP indicators) | Yes |  |
| Table 2 filled-in | Yes |  |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes | Ministry of Civil Affairs, Ministries of Health of both entities |
| ICC endorsed | Yes | ICC meeting .4 May 2005 |

6.  	Comments

ICC/RWG comments:

Conclusions: ICC comments raised during the 4 may 2006 meeting - The members of ICC agreed to submit required amendments/changes to Joint Reporting Immunization Form and Annual Progress GAVI Report for BiH for 2005 by 5 May - The Annual Progress Report to GAVI is approved and accepted by all ICC members and will be signed by both entity Ministers of Health before submission to GAVI Secretariat Regional Working Group remarks and recommendations: Section 1.2.1. Box. Besides amount of HepB vaccines received, problems encountered should be presented if any. Section 1.3.1. Receipt of injection safety support section should be left blank (and filled as ‘not applicable’) as the GAVI ISS will start and/or started in 2006. This APR is for the year 2005. Table 2.1. Please use the same figures presented in previous year’s APR. Table 2.2. Please refer to previous year’s APR and revise progress achieved, problems encountered, current value of progress indicator and proposed changes to financial sustainability strategy if any, against the identified financial sustainability strategies, specific actions taken towards achieving strategies and baseline value of progress indicators for both entities separately. Table 3.1. Please refer to previous year’s APR and replace year 2005 figures with realized ones. And please justify if there is any changes to baseline, targets, wastage rate and vaccine presentation in the following box. Table 4. Please prepare and fill two separate tables for monodose and multidose HepB vaccine indicating amount of request together with injection safety supplies. Do not forget to use the denominator presented in the previous table for the year 2007. And please indicate UNICEF Supply Division’s assurance if there is any change in vial presentations than the last year’s. Table 6. As GAVI injection safety support will start next year, separate tables should be filled for each vaccine BCG, DTP, measles and TT. Figures should match with the approved ISS proposal and the approved amount stated in September 19, 2005 dated letter of GAVI Secretariat. Section 4. Please refer to previous year’s APR and report achievements, constraints and updated targets if any against identified indicators and targets. Section 5. Please fill the provided checklist as completed in previous year’s APR. 10 November 2005 dated letter of the GAVI Secretariat to Bosnia and Herzegovina noted that in order for the future progress reports to be reviewed by the Independent Review Committee: - Reports must be signed by the Minister of Health and endorsed by member of the ICC, - ICC minutes of meetings held during the reporting year must be attached.

7.	Signatures

For the Government of ………………..…………………………………

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Federal Ministry of Health |  |  | Ministry of Health and social welfare Republika Srpska |  |  |
| Public Health Institute FBiH |  |  | Public Health Institute RS |  |  |
| UNICEF BiH | Deborah McWhinney/Officer in charge |  |  |  |  |
| WHO BiH | Haris Hajrulahovic/Head of WHO Country Office |  |  |  |  |

~ End ~