May 2002

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Vaccine Fund

By the Government of

BURKINA FASO

Date of submission: October 2000 Reporting period: 2001 ( previous calendar year ) ( Tick only one ) : Inception report  First annual progress report x  Financial sustainability plan attached  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report 

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/ the Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds : June 2001

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the ICC.

#### 1.1.2	Statement on use of GAVI/ VF immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/the Vaccine Fund contribution.

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |  |  |
| --- | --- | --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines | 0 |  |  | 100% |
| Injection supplies | 217 143 |  |  |  |
| Personnel |  |  |  |  |
| Transportation |  |  |  |  |
| Maintenance and overhead | 0 |  |  |  |
| Training | 0 |  |  |  |
| IEC / social mobilization | 60 000 | 20% | 30% | 50% |
| Monitoring and surveillance | 11 429 | 60% | 40% | 0% |
| Vehicles | 90 000 | 0% | 0% | 100% |
| Cold chain equipment |  |  |  |  |
| Advanced strategy support | 57 143 | 0% | 40% | 60% |

Please indicate the date of the ICC meeting(s) when the allocation of funds was/were discussed : 06 and 16 November 2001.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

X

## YES                              NO

The plan of action has been discussed and endorsed by the ICC in the meeting of ………………………(Date).

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines …………………..

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/VF.

#### 1.2.2	Major activities

Please outline what major activities have been or will be undertaken to prepare for new vaccine introduction.

#### 1.2.3	Statement on use of GAVI/ VF financial support ($100,000) for the introduction of the new vaccine

The following major areas of activities have been funded (specify the amount in US$) with the GAVI/VF support:

## Injection safety

#### 1.3.1	Receipt of injection safety support

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

#### 1.3.3	Statement on use of GAVI/ VF injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/VF injection safety support in the past year:

# 2.  Financial sustainability

Inception Report :		Outline steps towards developing of financial sustainability plan

First Annual Report : 	Submit completed financial sustainability plan

Subsequent Reports :	Summarize progress on financial sustainability

The financial sustainability plan is currently being elaborated. This plan must be submitted by September 2003 according to the adopted schedule.

# 3.	Request for new and under-used vaccines for year …………….. ( indicate forthcoming year )

The application will be submitted in 2003 once the programme has been reviewed.

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

| Table 1 : Baseline and annual targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Baseline and targets |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births |  | 535 016 | 547 857 | 561 005 | 574 470 | 588 257 | 602 375 | 616 832 |
| Infants’ deaths |  | 56 337 | 57 689 | 59 074 | 60 492 | 61 943 | 63 430 | 64 952 |
| Surviving infants |  | 478 679 | 490 167 | 501 932 | 513 978 | 526 313 | 538 945 | 551 880 |
| Infants vaccinated with DTP3 * |  | 323 986 | 318 609 | 376 449 | 398 333 | 421 051 | 458 103 | 482 895 |
| Infants vaccinated with BCG |  | 425 838 | 406 839 | 476 855 | 502 661 | 514 725 | 542 137 | 55 149 |
| Infants vaccinated with MEAS |  | 329 943 | 318 609 | 376 449 | 398 333 | 421 051 | 458 103 | 482 895 |
| Infants vaccinated with AAV |  | 261 947 | 318 609 | 376 449 | 398 333 | 421 051 | 458 103 | 482 895 |
| Infants vaccinated with TT-2 |  | 234 904 | 267 392 | 289 021 | 311 534 | 350 912 | 392 001 | 434 860 |
| Wastage rate of ** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |

- * Indicate actual number of children vaccinated in passed years.

** Indicate actual wastage rate obtained in passed years. / *** The numbers for 2002-2007 were extracted from the strategic forecast plans.

If the request of supply for the coming years differ from previously approved plan:

Please indicate the reasons for those changes and eventually the related modifications of targets of children, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and. Indicate the date of the ICC meeting when the changes have been endorsed.

3.2	Confirmed/revised request of new vaccine (to be shared with UNICEF Supply Division) for the year 2003 (indicate forthcoming year)

Table 2: Estimated number of doses of  DTP – Hib vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from GAVI / the Fund

|  |  | Formula | For year …… | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 501 932 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer Stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from the Fund | % | 100% |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 1 505 796 |  |
| E | Estimated wastage factor | (see list in table 3) | 1,11 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 1 656 375 |  |
| G | Vaccines buffer stock | F x 0.25 | 414 094 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 2 070 469 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 2 131 078 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 229 822 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 26 206 |  |

Table 2: Estimated number of doses of  hepatitis vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from GAVI / the Fund

|  |  | Formula | For year …… | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 501 932 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer Stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from the Fund | % | 100% |  |
| C | Number of doses per child |  | 4 |  |
| D | Number of doses | A x B/100 x C | 2 007 7282 |  |
| E | Estimated wastage factor | (see list in table 3) | 1,11 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 2 228 578 |  |
| G | Vaccines buffer stock | F x 0.25 | 557 144 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 2 785 722 |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 2 847 008 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 309 215 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 35 034 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request of injection safety support

(If quantity of current request differ from the GAVI letter of approval, please present the justification for that difference).

Table 4.1: Estimated supplies for safety of vaccination with BCG (Use one table for each vaccine BCG, DTP, Measles and TT, and number them from 4.1 to 4.4)

|  | ITEM | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | Match with objectives in table 4 | 476 855 | 502 661 | 514 725 | 542 137 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 |
| C | Number of …… doses | A x B | 476 855 | 502 661 | 514 725 | 542 137 |
| D | AD syringes (+10% wastage) | C x 1.11 | 529 309 | 557 954 | 571 344 | 601 773 |
| E | AD syringes buffer stock | D x 0.25 | 132 327 | 0 | 0 | 0 |
| F | Total AD syringes | D + E | 661 636 | 557 954 | 571 344 | 601 773 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 | 2 | 2 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 105 862 | 111 591 | 114 269 | 120355 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8 519 | 7432 | 7610 | 8016 |

Table 4.2: Estimated supplies for safety of vaccination with DTP

|  | ITEM | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for DTP vaccination | Match with objectives in table 4 | 376 449 | - | - | - |
| B | Number of doses per child (for TT woman) | # | 3 | - | - | - |
| C | Number of DTP doses | A x B | 1 129 347 | - | - | - |
| D | AD syringes (+10% wastage) | C x 1.11 | 1 253 575 | - | - | - |
| E | AD syringes buffer stock | D x 0.25 | 313 394 | - | - | - |
| F | Total AD syringes | D + E | 1 566 969 | - | - | - |
| G | Number of doses per vial | # | 10 | - | - | - |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1,6 | - | - | - |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | - | - | - | - |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 17 393 | - | - | - |

Table 4.3: Estimated supplies for safety of vaccination with MEASLES

|  | ITEM | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination | Match with objectives in table 4 | 376 435 | 398 241 | 420 872 | 430 889 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 |
| C | Number of measles doses | A x B | 376 435 | 398 241 | 420 872 | 430 889 |
| D | AD syringes (+10% wastage) | C x 1.11 | 417 843 | 442 048 | 467 168 | 478 287 |
| E | AD syringes buffer stock | D x 0.25 | 104 461 | - | - | - |
| F | Total AD syringes | D + E | 522 304 | 442 048 | 467 168 | 478 287 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1,6 | 1,6 | 1,6 | 1,6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 66 855 | 70 728 | 74 747 | 76 526 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6 540 | 5 692 | 6 015 | 6 158 |

Table 4.4: Estimated supplies for safety of vaccination with yellow fever

|  | ITEM | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for yellow fever vaccination | Match with objectives in table 4 | 376 435 | 398 241 | 420 872 | 430 889 |
| B | Number of doses per child (for TT woman) | # | 1 | 1 | 1 | 1 |
| C | Number of yellow fever doses | A x B | 376 435 | 398 241 | 420 872 | 430 889 |
| D | AD syringes (+10% wastage) | C x 1.11 | 417 843 | 442 048 | 467 168 | 478 287 |
| E | AD syringes buffer stock | D x 0.25 | 104 461 | - | - | - |
| F | Total AD syringes | D + E | 522 304 | 442 048 | 467 168 | 478 287 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1,6 | 1,6 | 1,6 | 1,6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 66 855 | 70 728 | 74 747 | 76 526 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 6 540 | 5 692 | 6 015 | 6 158 |

Table 4.5: Estimated supplies for safety of vaccination with TT

|  | ITEM | Formula | 2003 | 2004 | 2005 | 2006 |
| --- | --- | --- | --- | --- | --- | --- |
| A | Target of children for …… vaccination | Match with objectives in table 4 | 289 021 | 311 534 | 350 912 | 392 001 |
| B | Number of doses per child (for TT woman) | # | 2 | 2 | 2 | 2 |
| C | Number of TT doses | A x B | 578 042 | 623 069 | 701 825 | 784 002 |
| D | AD syringes (+10% wastage) | C x 1.11 | 641 627 | 691 606 | 779 026 | 870 242 |
| E | AD syringes buffer stock | D x 0.25 | 160 407 | - | - | - |
| F | Total AD syringes | D + E | 802 034 | 691 606 | 779 026 | 870 242 |
| G | Number of doses per vial | # | 10 | 10 | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1,6 | 1,6 | 1,6 | 1,6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | - | - | - | - |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 8 903 | 7 677 | 8 647 | 9 660 |

| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES for the forthcoming two years. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM |  | For the year 2003 | For the year 2004 | Justification of changes from originally approved supply: |
| Total AD syringes | for BCG | 661 636 | 557 954 |  |
|  | for other vaccines | 2 847 008 | 1 565 694 |  |
| Total of reconstitution syringes |  | 309 215 | 141 456 |  |
| Total of safety boxes |  | 30 502 | 26 493 |  |

# Signatures

For the Government of BURKINA FASO

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Dr. J.G OUANGO / Secretary-General |  | ROTARY International | Marcel SORGHO / President |  |
| WHO | Dr. M. HACEN / Representative |  | Save the Children | Dr. Yacouba ZINA / Representative |  |
| UNICEF | Mrs. Joan French / Rperesentative |  | International Plan | Dr. Jean Baptiste KOAMA |  |
| FED-ARIVA Project | Dr. Hamidine Mahamane / Coordinator |  | World Bank | Ibrahim MAGAGI |  |

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines