May 2002

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and the

Vaccine Fund

By the Government of

THE UNION OF THE COMOROS

Date of submission: ……17 October 2002………… Reporting period: …2001.. ( previous calendar year ) ( Tick only one ) : Inception report  First annual progress report  Financial sustainability plan attached  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report 

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/ the Vaccine Fund.

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds …November 2001…..

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the ICC.

- The country is in the first phase of using immunization strengthening funds. MLM training is scheduled for November 2002.

- The funds will be managed transparently in accordance with accounting standards with the approval of the ICC. Funds will be disbursed on the basis of requests for the activities to be carried out with approval by at least three signatories.

Tasks of the ICC:

- To provide technical support for the EPI

- To help with the mobilisation of EPI resources

- To coordinate action taken by the various partners in relation to child vaccination

- To monitor and if necessary guide the implementation of EPI activities

- To make the case

#### 1.1.2	Statement on use of GAVI/ VF immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/the Vaccine Fund contribution.

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |  |  |
| --- | --- | --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines |  |  |  |  |
| Injection supplies |  |  |  |  |
| Personnel |  |  |  |  |
| Transportation |  |  |  |  |
| Maintenance and overhead |  |  |  |  |
| Training (MLM training etc.) | 13,000 | X | X | X |
| IEC / social mobilization |  |  |  |  |
| Monitoring and surveillance |  |  |  |  |
| Vehicles |  |  |  |  |
| Cold chain equipment |  |  |  |  |
| Other …………. (specify) |  |  |  |  |

Please indicate the date of the ICC meeting(s) when the allocation of funds was/were discussed : …January 2002….

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

X

## YES                              NO

The plan of action has been discussed and endorsed by the ICC in the meeting of ……NO………(Date).

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines …N/A (not yet) (starting April 2003)..

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/VF. The new vaccines will be introduced in April 2003.

#### 1.2.2	Major activities

Please outline what major activities have been or will be undertaken to prepare for new vaccine introduction.

The following action will be taken to prepare for the introduction of the new vaccines:

- Training of service providers and logistics experts in the management of vaccines and vaccination equipment

- Injection safety

- Supervision

- Awareness-building

- Institution of a mechanism to verify the quality of vaccination data

#### 1.2.3	Statement on use of GAVI/ VF financial support ($100,000) for the introduction of the new vaccine

The following major areas of activities have been funded (specify the amount in US$) with the GAVI/VF support:

## Injection safety

#### 1.3.1	Receipt of injection safety support

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

The country is in the first phase of fund utilisation. For the second phase, it is planned to provide the districts with incinerators. Currently, all vaccination services are using only auto-destruct syringes.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

Since September 2001, only auto-destruct syringes have been used in the context of the EPI, except for BCG vaccine.

A plan to improve injection safety was drawn up in 2002 with the following objectives:

- To reduce morbidity and mortality due to dangerous injection practices

- To prevent the transmission of any infection by employing safe injection practices

- To dispose appropriately of vaccination wastes

The following indicators will be monitored regularly:

- Availability of autodestruct and reconstitution syringes at vaccination services

- Management of used injection equipment

- Sterile injection

#### 1.3.3	Statement on use of GAVI/ VF injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/VF injection safety support in the past year:

- The country benefited from funding (13,000 USD) to strengthen the vaccination services in 2001

# 2.  Financial sustainability

Inception Report :		Outline steps towards developing of financial sustainability plan

First Annual Report : 	Submit completed financial sustainability plan

Subsequent Reports :	Summarize progress on financial sustainability

The financial sustainability plan has not yet been prepared but is one of the priorities for 2003.

# 3.	Request for new and under-used vaccines for year ……2003….. ( indicate forthcoming year )

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

| Table 1 : Baseline and annual targets No change |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Baseline and targets |  |  |  |  |  |  |  |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births | 22,716 | 23,329 | 23,959 | 24,606 | 25,270 | 25,952 | 26,652 | 27,371 |
| Infants’ deaths | 1,340 | 1,376 | 1,414 | 1,452 | 1,491 | 1,531 | 1,572 | 1,614 |
| Surviving infants | 21,376 | 21,953 | 22,545 | 23,154 | 23,779 | 24,421 | 25,080 | 25,757 |
| Infants vaccinated with DTP3 * | 14,322 | 13,830 | 15,782 | 80% 18,523 | 85% 20,212 | 88% 21,490 | 90% 22,572 | 90% 23,181 |
| Infants vaccinated with OPV3 | 14,335 | 14,294 |  |  |  |  |  |  |
| Infants vaccinated with BCG | 17,316 | 17,030 |  |  |  |  |  |  |
| Infants vaccinated with MEAS | 10,917 | 10,977 |  |  |  |  |  |  |
| Infants vaccinated with *…(use one row for any new vaccine) |  |  |  |  |  |  |  |  |
| Wastage rate of ** ………….. ( new vaccine) |  |  |  |  |  |  |  |  |

- * Indicate actual number of children vaccinated in passed years.

- ** Indicate actual wastage rate obtained in passed years.

If the request of supply for the coming years differ from previously approved plan: No change

Please indicate the reasons for those changes and eventually the related modifications of targets of children, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and. Indicate the date of the ICC meeting when the changes have been endorsed.

3.2	Confirmed/revised request of new vaccine (to be shared with UNICEF Supply Division) for the year …… (indicate forthcoming year) No change

Table 2: Estimated number of doses of …… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from GAVI / the Fund

|  |  | Formula | For year 2003 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 18,523 | - Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. - Buffer Stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. - Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from the Fund | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 55,569 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.33 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 73,906 doses |  |
| G | Vaccines buffer stock | F x 0.25 | 18,477 doses |  |
| H | Anticipated vaccines in stock at start of year …. |  | 0 |  |
| I | Total vaccine doses requested | F + G - H | 92,383 doses |  |
| J | Number of doses per vial |  | 10 |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 82,191 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | 9,237 |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 10,115 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request of injection safety support

(If quantity of current request differ from the GAVI letter of approval, please present the justification for that difference).

Table 4.1: Estimated supplies for safety of vaccination with DTP (Use one table for each vaccine BCG, DTP, Measles and TT, and number them from 4.1 to 4.4) No change

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for DTP vaccination | # | 18,523 | 20,212 |
| B | Number of doses per child | # | 3 | 3 |
| C | Number of DTP doses | A x B | 55,569 | 60,636 |
| D | AD syringes (+10% wastage) | C x 1.11 | 61,682 | 67,306 |
| E | AD syringes buffer stock | D x 0.25 | 15,420 | 16,826 |
| F | Total AD syringes | D + E | 77,102 | 84,132 |
| G | Number of doses per vial | # | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 0 | 0 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 856 | 934 |

Table 4.2: Estimated supplies for safety of vaccination with BCG (Use one table for each vaccine BCG, DTP, Measles and TT, and number them from 4.1 to 4.4) No change

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | # | 19,685 | 21,480 |
| B | Number of doses per child | # | 1 | 1 |
| C | Number of BCG doses | A x B | 19,685 | 21,480 |
| D | AD syringes (+10% wastage) | C x 1.11 | 21,850 | 23,843 |
| E | AD syringes buffer stock | D x 0.25 | 5,463 | 5,961 |
| F | Total AD syringes | D + E | 27,313 | 29,804 |
| G | Number of doses per vial | # | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 2,185 | 2,384 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 327 | 357 |

Table 4.3: Estimated supplies for safety of vaccination with MEAS (Use one table for each vaccine BCG, DTP, Measles and TT, and number them from 4.1 to 4.4) No change

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for measles vaccination | # | 16,208 | 17,834 |
| B | Number of doses per child | # | 1 | 1 |
| C | Number of measles doses | A x B | 16,208 | 17,834 |
| D | AD syringes (+10% wastage) | C x 1.11 | 17,991 | 19,796 |
| E | AD syringes buffer stock | D x 0.25 | 4,498 | 4,949 |
| F | Total AD syringes | D + E | 22,489 | 24,745 |
| G | Number of doses per vial | # | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 2,878 | 3,167 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 282 | 310 |

Table 4.4: Estimated supplies for safety of vaccination with TT (Use one table for each vaccine BCG, DTP, Measles and TT, and number them from 4.1 to 4.4)

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of pregnant women for TT vaccination | # | 10,764 (35%) | 15,794 (50%) |
| B | Number of doses per woman | # | 2 | 2 |
| C | Number of TT doses | A x B | 21,528 | 31,588 |
| D | AD syringes (+10% wastage) | C x 1.11 | 23,896 | 35,063 |
| E | AD syringes buffer stock | D x 0.25 | 5,974 | 8,766 |
| F | Total AD syringes | D + E | 29,870 | 43,829 |
| G | Number of doses per vial | # | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 |
| I | Number of re-constitution syringes (+10% wastage) | C x H x 1.11 / G | 0 | 0 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 332 | 486 |

| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and MEASLES for the forthcoming two years. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ITEM |  | For the year 2003 | For the year 2004 | Justification of changes from originally approved supply: |
| Total AD syringes | for BCG | 27,313 | 29,804 |  |
|  | for other vaccines | 129,461 | 152,706 |  |
| Total of reconstitution syringes |  | 5,063 | 5,551 |  |
| Total of safety boxes |  | 1,797 | 2,087 |  |

# Signatures

For the Government of THE UNION OF THE COMOROS

Signature:	……………………………………………...……………...

Title:	Minister for Social Affairs, ALI MOHAMED SOILIHI

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Social Affairs | Dr Said Ahmed Bedja, Director, Endemics and Epidemics |  | UNICEF | Dr ALOYS Kamuragiye, Representative |  |
|  | Mr Said Hassane, Director of the National Pharmacy |  | UNFPA | Mme Batoul Oussein, Assistant to the Representative |  |
| Central Planning Office | Mr Younoussa Ben Imane, Central Planning Office |  | Comoro Red Crescent | Mr Mohamed Mlindasse, Secretary General |  |
| Ministry of Finance and the Budget | Mr Mohamed Abdou Mouigni |  | French Cooperation | Dr Laurence Gleize |  |
| WHO | Dr Kalambay Kalula WR/ Com |  |  |  |  |

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for Measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines