January 2005

Progress Report

Partnering with the Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Federal Democratic Republic of Ethiopia

Date of submission: April 25/ 2005 Reporting period: January to December 2004 ( Information provided in this report MUST refer to 2004 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2004

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use of GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2004

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Management of ISS Funds The 2004 ISS fund was received in August 2004 and half of the fund distributed to all regions based on the target population and expected coverage for the year (annual plan). The remaining half was distributed to zones and districts with poor access (low DPT1 coverage),poor utilization (high DPT1-DPT3 drop out rate) and high number of un-immunized children based on Reaching Every District (RED) approach. The fund was transferred from GAVI on time to regions by ministry of health and approved by ICC. The distribution from regions to the districts also followed the same strategy; target population and target coverage were the two criteria used to distribute the fund. Challenges in ISS fund utilization The fund was sent to federal MOH but there was no letter accompanying it and it was in the bank for many months. For the coming year the transfer of fund should be accompanied by a letter to MOH, copy to WHO and UNICEF country offices.

#### 1.1.2 Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2004     1,928,000 USD

Remaining funds (carry over) from 2003     zero balance at national level.

Table 1: Use of funds during 2004

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) | The fund was 100% transferred to sub- national levels (region, zone and District/woreda) and used only by the public sector. Agreement has been reached with regions to use the fund to strengthen fixed and out reach services, minor maintenance of motor cycles and vehicles, capacity building, monitoring and evaluation like review meetings, supportive supervision. The fund was transferred to the regions at the end of the year and no statement of expenditure at this time. |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: | 0 |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Date of ICC meeting Minutes: June 2004

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Major activities conducted to strengthen immunization: - Planning and policy level - Micro planning was conducted in 80% of the zones and districts using RED approach. - National Reaching Every District review and experience sharing of best practice areas conducted. - Coverage improvement plan was prepared to support districts with poor routine EPI coverage. - Recruitment and deployment of EPI officers by WHO and UNICEF. - Capacity building and service delivery - Pre-service training given to 128 instructors from 29 health training institutions using immunization in practice modules. - In-service training given to 67 peripheral level and 131 midlevel health workers. - RED field guide was developed, printed and distributed to regions - EPI training need assessment was conducted by MOH, WHO and Addis Ababa University. - Better regular monitoring of the program at all levels - Cold chain and logistics management - Multi-year cold chain rehabilitation plan developed and shared with partners. - Three cold rooms procured (two for national level and one for Tigray region) - More than 1,400 refrigerators procured - Spare parts which will be adequate for all kerosene refrigerators for 2 years was procured and distributed - EPI monitoring charts, immunization in practice and MLM modules were printed and distributed to regions . - Accelerated disease control - Catch up measles SIAs was conducted targeting 8,652,791 children 6 months to 14 years and the coverage was more than 90% in all regions. - Two rounds of Polio SIAs targeting 1,090,000 children under five in high risk areas were conducted and the coverage was 96%. - TT SIAs was conducted targeting women of child bearing age (1st dose = 2,255,489, 2nd dose = 2,029,063, 3rd = 1,700,294) - Disease surveillance and monitoring - Case based measles surveillance introduced in most regions. - Measles SIAs coverage survey was conducted by Addis Ababa university in areas covered with measles SIAs - Measles case fatality survey conducted in selected districts. - Social mobilization activities - In collaboration with Core Group– Ethiopia, social Mobilization plan for cross borders areas in Polio Importation response was developed. - Established regional ICCs in Southern Nations and Nationalities People's and Oromia Regional States - Gained commitment and support from zonal administrators and relevant offices for Routine Immunization in RED selected zones . Challenges - High staff attrition rate at all levels - High BCG wastage rate - Insufficient supportive supervision - Limited ownership of the program in some regions

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

X

YES                        NO

## If yes, please report on the degree of its implementation.

The implementation has been on going and some of the actions were the following: - Vaccine and injection materials regular monitoring has been institutionalized in most health facilities. - More than 90% of health facilities use proper tally sheet and others use any paper to tally immunizations. - Regional EPI and surveillance officers conduct supportive supervision regularly. - Monitoring charts were printed and distributed to districts. - Sensitization on information storage for health workers at all levels.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

## It was not discussed in ICC

Please report on studies conducted regarding EPI issues during 2004 (for example, coverage surveys).

EPI training need assessment, December 2004.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2004

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

New vaccines not yet introduced

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

The new vaccine introduction plan will be submitted to GAVI in May 2005.

#### 1.2.3	Use of GAVI/ the Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Not applicable

## Injection Safety

## 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In 2004, Ethiopia received the injection materials support from GAVI on time. - BCG AD syringes 2,555,800 - Other AD syringes 41,476,800 - Mixing syringe 5,358,800 - Safety box 493,914 There was no problem encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

The introduction of AD syringes and safety boxes was done in 2002 and Ethiopia has been using these equipments for three years and the report was covered in previous reports.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Proper utilization of incinerators in health facilities - Burning and burial in protected waste disposal pits in health facilities without incinerators | - All health facilities with incinerators to use it properly. - All health facilities will have protected waste disposal pits | - 80% of health facilities with incinerators use incinerator properly - All health facilities have waste disposal pits, but in most cases not protected. | - High attrition rate of staff - Poorly constructed health facilities. | - All health facilities use their incinerators properly. - 90% of health facilities will have protected waste disposal pits |

#### 1.3.3	Statement on use of GAVI/the Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/the Vaccine Fund injection safety support in the past year:

Not applicable

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial Sustainability plan was submitted to GAVI in January 2005

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (New vaccine)) each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine: New vaccine plan will be submitted for May 2005 round (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 2,835,533 | 2,912,093 | 2,990,719 | 3,071,469 | 3,154,398 | 3,239,567 | 3,327,035 |  |  |
| Infants’ deaths | 274,480 | 281,891 | 289,502 | 297,318 | 305,346 | 313,590 | 322,057 |  |  |
| Surviving infants | 2,561,054 | 2,630,202 | 2,701,218 | 2,774,151 | 2,849,053 | 2,925,977 | 3,004,978 |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 1,931,928 | 2,068,698 |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 1,696,534 | 1,841,142 | 1,998,901 | 2,163,837 | 2,307,733 | 2,457,821 | 2,614,331 |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)*Hep.B1-Hi.b1 (new vaccine) |  |  | 2,233,409 | 2,404,264 | 2,549,981 | 2,700,902 | 2,857,193 |  |  |
| Infants vaccinated 2004 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DPT3-Hep.B3-Hi.b3( new vaccine) |  |  | 1,998,901 | 2,163,837 | 2,307,733 | 2,457,821 | 2,614,331 |  |  |
| Wastage rate in 2004 and plan for 2005 beyond*** ( new vaccine) |  |  | 10% | 10% | 10% | 10% | 10% |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 1,151,037 | 1,459,696 | 1,649,018 | 2,001,458 | 2,213,613 | 2,435,765 | 2,668,299 |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 1,886,968 | 1,893,746 | 2,079,938 | 2,219,320 | 2,364,714 | 2,545,600 | 2,704,481 |  |  |
| Infants vaccinated in 2004 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 1,421,748 | 1,578,121 | 1,755,791 | 1,941,905 | 2,136,789 | 2,340,782 | 2,554,232 |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The multi-year plan has been revised based the previous years coverage.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The new vaccine introduction plan not yet approved.

Table 4: Estimated number of doses of DPT-HepB-HiB vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3

differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of:  50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid

vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer

stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries

with very low or no vaccines in stock must provide an explanation of the use of  the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero  for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater  for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Not applicable

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NA

# 4.	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets 2004 | Achievements 2004 | Constraints | Updated targets 2005 |
| --- | --- | --- | --- | --- |
| - No. of children planned to be vaccinated with DPT3 | 1,703,591 | 1,696,534 | Some regions have poor coverage | 1,841,142 |
| - No. of children planned to be immunized with measles | 1,354,355 | 1,421,748 |  | 1,578,121 |
| - No. of children planned to be immunized with BCG | 1,918,034 | 1,886,968 | Shortage of BCG AD syringes and high BCG vaccine wastage | 1,893,746 |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Table 1 filled-in |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |

6.  	Comments

ICC/RWG comments:

Signatures

For the Government of …Federal Democratic Republic of Ethiopia

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Dr. Tedros Adhanom/ State Minister for Health |  | WHO | Dr. Olusegun Babaniyi/ WHO Representative |  |
| Family Health Department, Ministry of Health | Dr. Tesfanesh Belay/ Department Head |  | UNICEF | Mr Bjorn Ljungqvist/ UNICEF Representative |  |
| Planning and Program Department | Dr. Girma Azene/ Department Head |  | Rotary International | Eng. Shiferaw Bizuneh/ Rotary International |  |
| Pharmaceutical Administration and Supply Service | Mr. Alemayehu Lemma/ Service Head |  | USAID | Mrs. Susan Anthony/USAID Country Representative |  |
| CORE Group | Dr. Filmona Bisrat/Country Director |  | JICA | Mr. Hideki Higashi |  |

~ End ~