May 2005

Progress Report

Partnering with the Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Federal Democratic Republic of Ethiopia

Date of submission May 16 / 2006 Reporting period: January to December 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use of GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

There was no ISS fund received in 2005. The award based on the 2004 achievement was not ready in 2005 and arrived in 2nd quarter of 2006.

#### 1.1.2 Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005     None

Remaining funds (carry over) from 2004     zero balance at national level.

Table 1: Use of funds during 2005 (remaining fund from 2004)

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  | 250,000 |  |  |
| Transportation |  |  | 43,440 |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  | 150,000 |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Other (specify)miscellaneous expenses, ,bank service, Fund still at regions |  |  |  |  |  |
| Total: |  |  | 443,440 |  |  |
| Remaining funds for next year: | None |  | 0 |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan. Major activities conducted to strengthen immunization: - Planning and policy level - The National EPI policy Guide line revised to accommodate the introduction of new technologies and vaccine wastage reduction strategies - Plan of action to reduce vaccine wastage specially BCG and measles vaccines developed and distributed to regions - AEFI surveillance guide line developed and ready for printing. - Capacity building and service delivery - Two Medical school instructors 7 higher EPI experts participated in inter country MLM training - Pre-service training given to 88 instructors from 13 health training institutions using immunization in practice modules. - In-service training given to 222 peripheral level and 33 midlevel health workers. - Cold chain users training given for 24 health workers. - Sibir refrigerator maintenance training given for 18 regional cold chain technicians and higher EPI experts. - Sustainable vaccine , cold chain and data management monitoring conducted at all levels - Four EPI officers and an officer from Pharmacy department trained on AEFI surveillance. - Cold chain and logistics management - About 1,500 sibir and RCW Ek 50 refrigerators procured and distributed to health facilities including health posts. - EPI monitoring charts and immunization in practice modules were printed and distributed to regions - New vaccine introduction guide line was adapted, printed and distributed to regions - Accelerated disease control - Follow up measles SIAs was conducted targeting 1,274,635 children 6 to 59 months and the coverage was more than 93% in all regions. - Five rounds of Polio SIAs targeting 15.5 million children aged 0 to 59 months and the coverage was 98 -100%. - TT SIAs was conducted targeting 4,558,964 women of child bearing age (1st dose = 1,508,203, 2nd dose = 1,486,395, 3rd dose =1,812,310) - Disease surveillance and monitoring - Total of 22 wild polio viruses were identified in 2005. The viruses have similar genetic sequencing with the viruses from neighboring countries, the Sudan. - Out breaks of measles was observed in the pastoralist area, Afar, where adults up to the age of 40 years were also affected. Assessment team was at the affected area to confirm the situation. - Social mobilization activities - In collaboration with Core Group– Ethiopia, social Mobilization plan for cross borders areas in Polio Importation response was developed. - Established regional ICCs in Southern Nations and Nationalities People's and Oromia Regional States - Gained commitment and support from zonal administrators and relevant offices for Routine Immunization. VII. Challenges/Weaknesses - Luck of sustainable financing for Injection safety material - Imported wild polio virus circulation while the routine EPI coverage is still low in some of the regions. - Insufficient supportive supervision - Low DPT3 coverage in some regions despite the distribution of adequate resources and implementation of RED strategy - High BCG and measles vaccines wastage - Inadequate community awareness on immunization - Poor timeliness and completeness of reports at all levels.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

X

YES                        NO                        DQA was conducted in 2002 not in 2005.

## If yes, please report on the degree of its implementation.

The implementation has been on going and some of the actions were the following: - Vaccine and injection materials regular monitoring has been institutionalized in most health facilities. - Leger book to monitor vaccines and other logistics management is prepared and ready for distribution - Tally sheets and other recording and reporting formats accommodating the new vaccines are prepared and sent for printing - Monitoring charts were printed and distributed to districts. - Regional EPI and surveillance officers conduct supportive supervision regularly. - Training on information storage is part of any EPI training at all levels.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

- Evaluation of RED activities was made by team from WHO/ICP/AFRO and HQ, UNICEF/ESARO, CDC, USAID, Immunization Basics and WHO/EPI Ethiopia - Impact assessment of 2002-2004 MLM training was conducted by external evaluators from WHO/AFRO/HQ ,UNICEF/ESARO and nesi

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH………………..           YEAR……………….

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

New vaccines not yet introduced

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- Training of Trainers on the New vaccines at national, and sub national level - Revision of recording and reporting formats - Implementation of cold chain rehabilitation plan (Central cold room capacity doubled, one regional cold room installed, two regional cold rooms installation on process) - Seven cold rooms procured by HIV/AIDS unit of MOH are being installed to be used for HIV kits and when the need arises for vaccines.

#### 1.2.3	Use of GAVI/ the Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The fund was used for training of health workers on the new vaccine introduction at national and sub national levels. 45 health workers at national level and 602 health workers from the governmental and non governmental health institutions at sub national level are trained up to now. The training will continue at the regional and sub regional levels. The fund was received on time but it was inadequate to cover the regional trainings. The fund covered less than one third of the training budget and all other activities like revision and printing of recording and reporting formats, and other training were covered from other sources. 100,000USD is very small for the preparation for introduction of new vaccines in countries like Ethiopia. GAVI should consider additional fund to cover the remaining activities in the preparation like social mobilization.

## Injection Safety

## 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Ethiopia was not eligible for the INS support in 2005.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

INS support phased out after the end of 2004, In that same year the ICC discussed on the source of funding for the next year injection materials procurement. Among the partners DCI and UNICEF covered the requirement for 2005. Despite the absence of sustainable financing source there was no shortage encountered.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Proper utilization of incinerators in health facilities - Burning and burial in protected waste disposal pits in health facilities without incinerators | - All health facilities with incinerators to use it properly. - All health facilities will have protected waste disposal pits | - 80% of health facilities with incinerators use incinerator properly - All health facilities have waste disposal pits, but in most cases not protected. | - High attrition rate of staff - Poorly constructed health facilities. | - All health facilities use their incinerators properly. - 90% of health facilities will have protected waste disposal pits |

#### 1.3.3	Statement on use of GAVI/the Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/the Vaccine Fund injection safety support in the past year:

Not applicable

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial Sustainability plan was submitted to GAVI in January 2005

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (New vaccine)) each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine: New vaccine plan submitted in May 2005 and approved. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 20..** | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. | 20.. |
| A: Proportion funded by GAVI/VF (%)*** |  |  |  |  |  |  |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) |  |  |  |  |  |  |  |  |  |  |
| C: Total funding for …………. (new vaccine) |  |  |  |  |  |  |  |  |  |  |

Ethiopia is waiting for the vaccine to arrive in country and it will be covered fully by GAVI. Ethiopia will be part of the bridge financing and the details will be discussed with GAVI secretariat.

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| FSP submitted and approved by the GAVI Secretariat. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |  |  |  |
|  | 2004 |  | 2005 |  |  | 2006 |  | 2007 |  | 2008 | 2009 | 2010 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |  |  |  |
| Births | 2,835,533 |  | 2,904,831 |  |  | 2,990,719 |  | 3,071,469 |  | 3,154,398 | 3,239,567 | 3,327,035 |
| Infants’ deaths | 274,480 |  | 285,149 |  |  | 289,502 |  | 297,318 |  | 305,346 | 313,590 | 322,057 |
| Surviving infants | 2,561,054 |  | 2,619,682 |  |  | 2,701,218 |  | 2,774,151 |  | 2,849,053 | 2,925,977 | 3,004,978 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 1,931,928 |  | 2,054,283 |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DTP (DTP3)* | 1,696,534 |  | 1,811,430 |  |  | 1,998,901 |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)*Hep.B1-Hi.b1 (new vaccine) |  |  | NA |  |  | 2,233,409 |  | 2,672,178 |  | 2,838,958 | 2,980,402 | 3,160,683 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 3rd dose of DPT3-Hep.B3-Hi.b3( new vaccine) |  |  | NA |  |  | 1,998,901 |  | 2,395,746 |  | 2,555,062 | 2,721,236 | 2,894,520 |
| Wastage rate in 2004 and plan for 2005 beyond*** ( new vaccine) |  |  | NA |  |  | 10% |  | 10% |  | 10% | 10% | 10% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with TT2 | 1,151,037 |  | 1,297,666 |  |  | 1,649,018 |  | 2,001,458 |  | 2,213,613 | 2,435,765 | 2,668,299 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 1,886,968 |  | 1,954,940 |  |  | 2,079,938 |  | 2,457,175 |  | 2,618,150 | 2,818,423 | 2,994,332 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with Measles * | 1,421,748 |  | 1,556,834 |  |  | 1,755,791 |  | 2,150,028 |  | 2,365,799 | 2,591,654 | 2,827,980 |
| * Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined) |  |  |  |  |  |  |  |  |  |  |  |  |
| ** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced |  |  |  |  |  |  |  |  |  |  |  |  |
| *** Indicate actual wastage rate obtained in past years |  |  |  |  |  |  |  |  |  |  |  |  |
| **** Insert any row as necessary |  |  |  |  |  |  |  |  |  |  |  |  |

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The number of children targeted for immunization in all antigens is revised (2007 to 2010) we used total births as a base for estimation of requirement instead of surviving infants. ..

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The amount of requested vaccine is revised (total birth used instead of surviving infants), however the presentation of the new vaccine is as per the approved application. The approved formulation is pentavalent 2 dose vial.

Table 4: Estimated number of doses of DPT-HepB-HiB vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

**As Ethiopia has not yet received penta vaccine it is not possible to anticipate the stock at the beginning of 2007

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3

differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of:  50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid

vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer

stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries

with very low or no vaccines in stock must provide an explanation of the use of  the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero  for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater  for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Not applicable

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

NA

# 4.	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets 2005 | Achievements 2005 | Constraints | Updated targets 2006 |
| --- | --- | --- | --- | --- |
| - No. of children planned to be vaccinated with DPT3 | 1,841,142 | 1,810,927 | - Repeated NIDs and SIAs - Increased Staff attrition rate - Very high number of health workers joined post graduate studies | 1,998,901 |
| - No. of children planned to be immunized with measles | 1,578,121 | 1,556,512 | Same as above | 1,755,791 |
| - No. of children planned to be immunized with BCG | 1,893,745 | 1,954,461 |  | 2,079,938 |

The Ethiopian government is working with partners on Health System Strengthening Support proposal and will submit soon.

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | May 16, 2006 |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Table 1 filled-in | Yes |  |
| DQA reported on | Yes |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | No |  |
| Table 2 filled-in | No | delayed for further discussion |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | No |  |
| ICC minutes attached to the report | No |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

Signatures

For the Government of …Federal Democratic Republic of Ethiopia

Signature:	……………………………………………...……………...

Title:	………………………………………….………………….

Date:	………………………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Health | Dr. Kebede Worku/ State Minister for Health |  | WHO | Dr. Olusegun Babaniyi/ WHO Representative |  |
| Family Health Department, Ministry of Health | Dr. Tesfanesh Belay/ Department Head |  | UNICEF | Mr Bjorn Ljungqvist/ UNICEF Representative |  |
| Planning and Program Department | Dr. Nejmudin Kedir/ Department Head |  | Rotary International | Eng. Shiferaw Bizuneh/ Rotary International |  |
| Pharmaceutical Administration and logistics temporary Department | Mr. Alemayehu Lemma/ Department Head |  | USAID | Mrs. Susan Anthony/USAID Country Representative |  |
| CORE Group | Dr. Filmona Bisrat/Country Director |  | JICA | Representative |  |

~ End ~