Annual Progress Report 2006

Submitted by

The Government of

Ethiopia

to the

# Date of submission: May 10, 2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of  Ethiopia………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title:Dr. Kebede Worku, State Minister for Health | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| Dr.Kebede Worku/State Minister for Health | Ministry of Health |  |  |
| Dr. Ayele Debebe, Family Health Department Head | Ministry of Health |  |  |
| Dr. Nejmudin Kedir/Plan and Program Department Head | Ministry of Health |  |  |
| Dr. Zerihun Tadesse, Disease Prevention and Control Department | Ministry of Health |  |  |
| Miss Hiwot Teshome/Head Pharmacy Administration and Logistics T/ Department | Ministry of Health |  |  |
| Dr. Olusegun Babaniyi/ WHO Representative | WHO/Ethiopia |  |  |
| Mr. Bjorn Ljungqvist/UNICEF Representative | UNICEF/Ethiopia |  |  |
| Dr.Mulugeta Gebre Yohannis | USAID/Ethiopia |  |  |
| Engineer Shiferaw Bizuneh | Rotary International |  |  |
| Dr.Filimona Bisrat | CORE Group |  |  |
| Tomoyo Miyake JICA | JICA Representative |  |  |

Signatures Page for HSS

For the Government of Federal Democratic Republic of Ethiopia

We, the undersigned members of the National Health Sector Coordinating Committee, Central Joint Steering committee endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| H.E. Dr Tedros Adhanom G/Yesus Minister of Health | Ministry of Health |  |  |
| H.E. Ato Mekonen Manyazewal State Minister | Ministry of Finance and economic Development |  |  |
| H.E. Dr Kebede Worku. State Minister | Ministry of Health |  |  |
| H.E. Ambassador Raffaele de Lutio | Ambassador of Italy representing the EU. |  |  |
| Mrs. Marion Kelly. | Co chair HPN Donors Group |  |  |
| Mr Glenn E. Anders | Mission Director USAID |  |  |
| Mr Ishac Diwan | Resident Representative the World Bank |  |  |
| Ato Kebede Asrat | Executive Director, CRDA |  |  |
| Dr Olusegun Babaniyi | WHO Representative |  |  |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS)

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

Annually the Ministry of Health and partners develop Plan of Action for immunization Program which includes budget source both from government and partners and ISS fund is utilized based on the Plan of Action approved by the ICC

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The ICC is the decision making body in setting the criteria for ISS fund utilization. With regard to getting ISS fund from GAVI, no problem has been encountered so far. However, problem is encountered with the regional health bureaus on the timely utilization and liquidation of fund disbursed. With repeated reminders very few regions have managed to liquidate the funds on time.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006:  $4,607,677

Remaining funds (carry over) from 2005:  __0______________

Balance to be carried over to 2007: 0

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | NA |  |  |  |  |
| Injection supplies | NA |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation | 123,041 |  | 123,041 |  |  |
| Maintenance and overheads | 40,620 |  |  | 40,620 |  |
| Training | 577,962 |  | 577,962 |  |  |
| District micro plan | 318,034 |  | 318,034 |  |  |
| IEC / social mobilization | 0 |  |  |  |  |
| Outreach( per diem, fuel and Kerosene | 580,645 |  | 105,575 | 475,070 |  |
| Supervision | 188,884 |  | 156,095 | 32,789 |  |
| Monitoring and evaluation | 360,000 |  | 360,000 |  |  |
| Epidemiological surveillance | 0 |  | NA |  |  |
| Vehicles | 0 |  |  |  |  |
| Cold chain equipment | 2,360,327 | 2,360,327 |  |  |  |
| Other: (Coverage survey) | 148,164 | 0 | 109,051 | 39,113 (stationery.electric,telephone, etc) |  |
| Total: | 4,697,677 | 2,360,327 | 1,749,758 | 587,592 |  |
| Remaining funds for next year: |  |  |  |  |  |

NB: The figures under the column district indicates only for some regions that sent reports for few districts

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

Major activities conducted in 2006: - District level micro-planning was conducted in all regions - DQS training was conducted at national, regional, district and Health Facility level - New vaccine introduction training was conducted before the introduction of the pentavalent vaccine - Refresher training for instructors of health Service Extension Workers was conducted - MLM in service and pre-service training conducted - Supportive supervision to regions and districts done by the EPI field officers and EPI team at the central level - Annual national level EPI review meeting was conducted - RED approach implemented in all districts - Comprehensive Multi-year plan developed - National EPI coverage survey conducted - Cold chain users training was conducted in three regions Problems encountered: - Despite technical, material and financial support from federal government and partners the immunization coverage in Somali and Afar regions remains very low.

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for: Not yet scheduled for the next DQA________

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted? The 1st DQA which the country has passed was conducted in January 2003.

What were the major recommendations of the DQA ?

The major and immediate recommendations were: - Institute vaccine and injection supplies monitoring ( Balance sheets or ledgers) at every level - Ensure all Health Units (HU) use tally sheets and save them for at least 3 years as is MOH policy - Reintroduce routine supervision schedules for all levels and ensure that feed back is documented in visitor’s books, feed back format etc - 4Improve the supply of all reporting formats, particularly tallies at the HUs - Implement report receipt date policy at all levels

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

YES                              NO

X

## If yes, please report on the degree of its implementation and attach the plan.

During DQS training at all levels all the above recommendations were discussed with the concerned bodies and their implementation being checked during supervisory visits and review meetings.

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

National EPI Coverage Survey was conducted in 2006. DPT3 coverage at national level (card +history) was 66% and five of the 11 regions achieved DPT3 coverage of >80%

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

A total of 15 main ICC and ICC technical committee meetings were conducted in 2006. The main ICC meetings were chaired by the State Minister for Health and the ICC technical committee were chaired by the Family Health Department Head. There is one civil society member: CORE Group/CRDA(Christian Relief Development Association)

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| DPT-Hep B-Hib | Single dose | Single dose | 1st quarter of 2007 | December 19,2006 |

Please report on any problems encountered.

No problem is encountered so far

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Pre-introduction activities: - New vaccine introduction training at national and sub national levels - Revision of recording and reporting formats - Ensuring of availability and functioning of cold chain equipment - Storage capacity increased at all levels through procurement of cold rooms, refrigerators, cold boxes and vaccine carriers - Timely distribution of vaccines - Guideline developed and distributed to all levels how the new vaccines should be introduced including the phasing in and no catch up vaccination, change made from ice packing to chilled water packing, freeze sensitivity of vaccines etc Post introduction activities in first quarter of 2007 - Since the introduction of the new vaccine, continuous monitoring and supportive supervision are being made and 6 months after the introduction there is a plan to conduct evaluation of the new vaccine introduction

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received in: 2005

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Already reported in 2005 APR

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) were conducted in 2004 and 2002 respectively.

Please summarize the major recommendations from the EVSM/VMA

EVSM: - Improve storage capacity at the central store to accommodate the increasing traditional and new vaccines - Improve stock management to avoid over and under stock of vaccines - Improve vaccine distribution to the lower level to avoid vaccine stock out at the peripheral level VMA: - Improve wastage control at all levels - Improve distribution efficiency at all levels - Improve stock control at all levels - Improve cold chain reliability at all levels

Was an action plan prepared following the EVSM/VMA : Yes/No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

- Storage capacity at central, regional and health facility level increased - Computerized Stock management system (SMT) is installed and training on Stock management Tool and vaccine management was given at the regional level. Computers are provided for the regional cold stores. Cold chain users training was given to health workers

The next EVSM/VMA will be conducted in: 2007

## *All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind: Was received in kind from 2002  to 2004.

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| NA |  |  |

Please report on any problems encountered.

No sustainable finance for supply of injection materials (in 2005 and 2006 it was covered by Irish Aid and UNICEF and in 2007 by World Bank fund under protecting basic services.) No information from which source it is going to be covered in 2008.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

Since the discontinuation of injection safety support from GAVI, Development Cooperation of Ireland and UNICEF have been supplying the injection materials. For 2007, it will be procured by Protecting Basic Services (PBS) fund through the World Bank support.

#### Please report how sharps waste is being disposed of.

#### The following are the methods of disposal - Incinerators Incinerator is one of the commonest methods of waste disposal. As some of the dug pits are shallow and not well protected, it remains health hazard particularly for the community. To alleviate such problems training is often given on immunization safety. In the future, if there is a possibility of getting fund most health facilities without incinerators will have one in place. The other forms of injection waste disposal are: - Burning and burying - Open burning in a dug pit

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

The MOH has developed a plan for safe injection and sharps waste management and will be implemented in the near future.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

NA

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines | 2,812,723 | 46,729,884 | 40,839,631 | 42,855,151 | 45,408,660 |
| Injection supplies | 1,837,000 | 1,851,751 | 1,992,613 | 1,131,629 | 2,284,184 |
| Personnel | 479,017 | 6,674,605 | 8,381,860 | 9,055,678 | 9,724,893 |
| Other operational expenditures | 913,586 | 7,440,011 | 9,660,862 | 10,973,884 | 12,710,352 |
| Cold Chain equipment | 2,957,754 | 1,869,152 | 2,692,842 | 2,651,419 | 3,086,486 |
| Vehicles | 128,662 | 57,222 | 0 | 59,534 | 0 |
| Outreach(perdiem, fuel and kerosene) | 677,114 | 4,737,117 | 6,347,385 | 6,919,479 | 7,481,885 |
| District micro planning | 318,034 |  |  |  |  |
| Training | 627,962 | 1,560,600 | 1,591,812 | 1,082,432 | 1,104,081 |
| Supervision, monitoring and evaluation | 548,884 | 1,847,535 | 1,940,026 | 2,037,027 | 2,138,879 |
| Other | 518,608 | 72,828 | 63,672 | 54,122 | 55,204 |
| Total | 11,819,344 | 72,840,705 | 73,510,703 | 76,820,355 | 83,994,624 |
| Total Immunization Expenditures |  |  |  |  |  |
| Total Government Health Expenditures |  |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  |  |  |  |  |
| GAVI | 4,607,350 |  |  |  |  |
| UNICEF | 5,031,525 |  |  |  |  |
| WHO | 580,470 |  |  |  |  |
| World Bank (grant) |  |  |  |  |  |
| Other (Irish Aid) | 1,600,000 |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

| Table 3a: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
|  |  | NA |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3b: Country Vaccine Co-Financing in US $ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  | NA |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3c: Country Vaccine Co-Financing in US$ |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |  |  |  |  |  |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  | NA |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |  |  |  |
| --- | --- | --- | --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? For non GAVI vaccines |  |  |  |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF | Yes | All vaccines | UNICEF/World Bank and others |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |  |  |  |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
|  | NA |  |  |
| 1st Awarded Vaccine (specify) |  |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |  |  |  |
|  | Tick for Yes | List Relevant Vaccines |  |
| Budget line item for vaccine purchasing | NA |  |  |
| National health sector plan |  |  |  |
| National health budget |  |  |  |
| Medium-term expenditure framework |  |  |  |
| SWAp |  |  |  |
| cMYP Cost & Financing Analysis |  |  |  |
| Annual immunization plan |  |  |  |
| Other |  |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |  |  |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |
| 3. |  |  |
| 4. |  |  |
| 5. |  |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |  |  |
| 1. Limited resource capacity of the government |  |  |
| 2. Expensive cost of new vaccines |  |  |
| 3. |  |  |
| 4. |  |  |
| 5. |  |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

The report is the same as the 2006 JRF, however the number of children to be vaccinated is revised upward based on the CMYP 2006 to 2010. Total birth is used instead of surviving infants to estimate vaccine requirement.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 2,904,831 | 2,997,056 | 3,076,043 | 3,159,096 | 3,244,392 | 3,331,990 | 3,421,954 | 3,514,347 | 3,609,234 |
| Infants’ deaths | 285,149 | 294,042 | 236,855 | 243,250 | 249,818 | 256,563 | 263,490 | 270,605 | 277,911 |
| Surviving infants | 2,619,682 | 2,703,014 | 2,839,188 | 2,915,846 | 2,994,574 | 3,075,427 | 3,158,464 | 3,243,742 | 3,331,323 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 2,054,283 | 2,165,226 |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 1,811,430 | 1,938,894 |  |  |  |  |  |  |  |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* …......... (DPT1-He.B1-HiB1) |  |  | 2,676,157 | 2,843,187 | 2,984,840 | 3,165,391 | 3,250,856 | 3,338,629 | 3,428,772 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DPT3-He.B3-HiB3 |  |  | 2,399,314 | 2,558,868 | 2,725,289 | 2,898,832 | 3,079,759 | 3,233,199 | 3,428,772 |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) |  |  | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 1,297,666 | 1,564,101 | 1,999,428 | 2,211,367 | 2,433,294 | 2,665,592 | 2,840,222 | 2,987,195 | 3,248,311 |
| Infants vaccinated / to be vaccinated with BCG | 1,954,940 | 2,160,597 | 2,460,834 | 2,622,050 | 2,822,621 | 2,998,791 | 3,182,417 | 3,338,629 | 3,428,772 |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 1,556,834 | 1,691,533 | 1,999,428 | 2,211,367 | 2,433,294 | 2,665,592 | 2,908,661 | 3,162,912 | 3,248,311 |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The presentation of the vaccine is the same; however the number of children to be vaccinated with penta1 is changed based on the country CMYP 2006 to 2010.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of DPT-Hep.B-Hi.B vaccine.  (Please provide additional tables for additional vaccines and number them 6a, 6b, 6c etc)

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required | 7,801,689 | 9,513,799 | 10,113,164 |
| Doses to be funded by GAVI | 7,801,689 | 9,513,799 | 10,113,164 |
| Doses to be funded by country | 0 | 0 | 0 |
| Country co-pay in US$/dose* | 0 | 0 | 0 |
| Total co-pay | 0 | 0 | 0 |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

NB. Co-financing will be started in 2011

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

Not applicable

4. Health Systems Strengthening (HSS)

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : April 2007

Current Health Systems Support will end in : June 2010

# Funds received in 2007 : 	Yes/No

If yes, date received: 16/04/2007

If yes, total amount:   US$ 23, 733,388 Million

It is expected to have the 2nd instalment of funds for 2007; US$ 45,107,415 by August 2007.

Funds disbursed to date:  				US$ 3,500,880

Funds in the process of disbursement                       US$ 20,174,910

Balance of installment left: 				US$ 57,598

Requested amount to be disbursed for 2008 	US$ 3,826,566

(N.B. considering that the 2nd installment of 2007 would be in August- September 2007, the 2008 disbursement would be required in January/February 2008).

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget): Yes/No

If not, why not ? How will it be ensured that funds will be on-budget? Please provide details.

All donations, loans and internal sources of funding are included in the government budget. The Ministry of Finance and Economic Development (MOFED) communicates this to the regional Bureaus of Finance and Economic Development (BOFED) and these in turn to Woredas. In all cases funding specified to sectors and tied to projects are also indicated and included in the federal subsidy to regions and regional block grants to Woredas.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

The funds were received in Mid April, 2007 for implementation in only two and a half months. Some of the activities that require extended time for implementation were pushed to 2nd half of 2007 for implementation using the 2nd 2007 disbursements. On the other hand activities that had been in the pipeline and those for which prearranged condition existed were given more emphasis for implementation till end June 2007. Implementation of all the activities planned in the Health workforce mobilization, distribution and motivation component has started as planned. Funds allocated to conduct refresher training of Health Extension Workers and to support the apprenticeship program of HEW training as well as for the Integrated Refresher Training of Woreda and Health Centre Management Teams were distributed to regions to start the activities soon. The Family Health Department of MOH has made contractual agreement with the Paediatric Society of Ethiopia to conduct the 4th activity of this component, the IMNCI training, before end June 2007. Implementation of activities under the supply, maintenance and distribution of PHC drugs, equipment and infrastructure component has progressed well, and particularly the construction part had progressed much more than what was planned with the 1st instalment. Although it was planned to upgrade 35 HS to HC with the 1st instalment, the arrangements with the implementer; GTZ, has advanced well ahead and agreement is signed to implement 500. This is the target of upgrading HS to HC during the HSADP III in which the 212 to be funded by GAVI are included. Thus a total of 7,020,295 USD out of the total 19,500,000 USD for the same is in the process of getting transferred to GTZ. It is understood that constructions and procurements would be efficient if done early and all together than in fragmented manner. Thus this approach is proposed for the future as well. The other activity in this component; procurement of medical equipment of both HC and HP and for this UNICEF is requested to give cost estimates and the funds ready to be transferred to UNICEF. Funds allocated for construction of 50 HP in the emerging regions has been distributed to the four regions (Afar, Gambella, Somali, and Benishangul Gumuz). While two of the activities in the third objective; Organization and Management of Health Services at the district level and below have progressed well, it was found out that time left is too short to implement some of the activities included under the implementation of Health Commodities Supply System (HCSS) master plan. The budget allocated for annual review meetings of HEP is distributed to the regions. Specifications were prepared and bid process started to procure IT equipment for HMIS; and funds allocated for strengthening HMIS distributed to the regions to conduct training. Among the activities in this component, request was made to IAPSO to procure vehicles. Although it was planned to conduct many activities in the implementation of HCSS master plan, it was assessed that some arrangements were not yet finalized including organization of new PHARMID. Accordingly only 100,000 USD is going to be used for this component out the 3,870,295 USD allocated for the same. It is planned to conduct the rest of planned activities in the 2nd half of 2007 and early 2008.

Are any Civil Society Organizations involved in the implementation of the HSS proposal? If so, describe their participation?

The Paediatric Society of Ethiopia has been given the task of training health workers in IMNCI course. Agreement is made and the funds ready to be transferred to the same. It is hoped that the same approach continues for the next phases too.

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

It is found out that implementation of activities for which clear arrangements exist shall commence earlier and faster than the activities that need preparatory steps. Particularly procurements and construction works have already established system and can also be carried out efficiently if agreement is signed once than in fragmented manner. Also the transaction cost as well as price of single and early payments would be lower than the case with repeated bid process and repeated orders. Agreement is signed with GTZ to upgrade more HS to HC in short time than indicated in GAVI HSS proposal. Thus it is proposed to implement the activities under the Supply, Distribution and Maintenance Systems (i.e. upgrading HS to HS and equipment for HC) earlier than proposed before. On the other hand some preparatory steps needed for implementation of the HCSS master plan didn’t progress as expected. It is thus proposed to keep this activity which was planned under the management and organization component, towards the end of the project period. Accordingly rearrangement of fund flows in the two components is proposed while the plan in the health workforce component can be kept as it was.

| GAVI Health Services Support Budget in US$ Proposal Revised May 2007. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 2006/07 | 2007/08 | 2008/09 | 2009/10 | Total |
| Health workforce |  |  |  |  |  |  |
| Refresher course for 25,050 HEWs |  | 1,546,875 | 4,140,625 | 1,070,313 | 1,070,313 | 7,828,126 |
| Apprenticeship for 12600 HEWs students |  | 0 | 1,023,500 | 609,650 | 609,650 | 2,242,800 |
| Capacity strengthening for woreda |  | 659,835 | 659,835 | 659,835 | 659,835 |  |
| health management team |  |  |  |  |  | 2,639,340 |
| Training of Health workers for IMNCH |  | 360,000 | 360,000 | 360,000 | 360,000 | 1,440,000 |
|  |  | 2,566,710 | 6,183,960 | 2,699,798 | 2,699,798 | 14,150,266 |
| Supply, distribution and maintenance systems |  |  |  |  |  |  |
| Upgrading from HS to HC (212 units) |  | 3,250,000 | 16,250,000 | 0 | 0 | 19,500,000 |
| Equipment Health Centre A (30) |  | 362,000 | 724,000 | 0 | 0 | 1,086,000 |
| Equipment Health Centre B (270) |  | 970,315 | 4,830,092 |  |  | 5,800,407 |
| Construction of 100 Health Posts |  | 375,000 | 375,000 | 0 | 0 | 750,000 |
| Equipment for 5000 HP type B |  | 5,089,500 | 5,089,500 | 0 | 0 | 10,179,000 |
| Equipment for 2340 HP type A |  | 4,987,800 | 4,987,800 | 0 | 0 | 9,975,600 |
|  |  | 15,034,615 | 32,256,392 | 0 | 0 | 47,291,007 |
| Organization and management |  |  |  |  |  |  |
| 4x4 supervision vehicle for 109 WHOf |  | 835,000 | 1,670,000 | 0 | 0 | 2,505,000 |
| IT equipment for 109 WHOf |  | 300,000 | 0 | 0 | 0 | 300,000 |
| HEP annual regional review meetings |  | 86,750 | 115,000 | 116,750 | 125,017 | 443550 |
| Monitoring and Evaluation |  | 890,018 | 861,768 | 860,018 | 851,751 | 3,463,550 |
| Support for implementation of HCSS |  | 3,870,295 | 3,870,295 | 0 | 0 | 7,740,590 |
| Management of HSS |  | 150,000 | 150,000 | 150,000 | 150,000 | 600,000 |
|  |  | 6,132,063 | 6,667,063 | 1,126,768 | 1,269,768 | 15,052,690 |
| TOTAL |  | 23,733,388 | 45,107,415 | 3,826,566 | 3,826,566 | 76,493,933 |

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

# Attachments.

- Minutes of the meeting of the Central Joint Steering Committee,  May 08, 2007

- Evaluation of HSDP II, (Latest Health Sector Review Report)

- Consolidated report of the 1st year implementation of HSDP III. (Latest progress report of Health Sector Program)

- Report of the account HSS funds are transferred to. (Health MDG Designated Pooled Account, Bank Acc. No.  0160101352600, National Bank of Ethiopia)

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Area for support | 2006/07 (Expenditure) |  | 2007/07 (Balance) | Expected 2nd instalment of 2007/08 | 2008/09 (Request) |
|  | Transferred(Disbursed) | Disbursement in process |  |  |  |
| Activity costs |  |  |  |  |  |
| Objective1. Health Workforce Mobilization, Distribution and Motivation |  |  |  |  |  |
| Activity1.1.Integrated Refresher Training courses for HEWS: | 1,546,875 | 0 | 0 | 4,140,625 | 1,070,313 |
| Activity 1.2. Apprenticeship for 12600 HEWs students | 0 | 0 | 0 | 1,023,500 | 609,650 |
| Activity 1.3. Capacity strengthening for woreda health management team | 659,835 | 0 | 0 | 659,835 | 659,835 |
| Activity 1.4 Training of Health workers for IMNCH | 0 | 360,000 | 0 | 360,000 | 360,000 |
| Objective 2. Supply, Distribution and Maintenance Systems for PHC drugs Equipment and Infrastructure |  |  |  |  |  |
| Activity 2.1 Upgrading from HS to HC | 0 | 7,020,295 | - 3,770,295 | 16,250,000 | 0 |
| Activity 2.2 Equipment Health Centre A (30) | 0 | 362,000 | 0 | 724,000 | 0 |
| Activity 2.3 Equipment Health Centre B (270) | 0 | 970,315 | 0 | 4,830,092 | 0 |
| Activity 2.4 Construction of 100 Health Posts | 375,000 | 0 | 0 | 375,000 | 0 |
| Activity 2.5. Equipment for 5000 HP type B | 0 | 5,089,500 | 0 | 5,089,500 | 0 |
| Activity 2.6. Equipment for 2340 HP type A | 0 | 4,987,800 | 0 | 4,987,800 | 0 |
| Objective 3. Organization and management of Health Services at District level and below. |  |  |  |  |  |
| Activity 3.1. 4x4 supervision vehicle for 109 WHO | 0 | 835,000 | 0 | 1,670,000 | 0 |
| Activity 3.2. IT equipment for 109 WHO | 0 | 300,000 | 0 | 0 | 0 |
| Activity 3.3. HEP annual regional review meetings | 86,750 | 0 | 0 | 115,000 | 116,750 |
| Activity 3.4. Monitoring and Evaluation | 832,420 | 0 | 57,598 | 861,768 | 860,018 |
| Activity 3.5. Support for implementation of the HCSS | 0 | 100,000 | 3,770,295 | 3,870,295 | 0 |
| Support costs |  |  |  |  |  |
| Management costs | 0 | 150,000 |  | 150,000 | 150,000 |
| M&E support costs |  |  |  |  |  |
| Technical support |  |  |  |  |  |
| TOTAL COSTS | 3,500,880 | 20,174,910 | 57,598 | 45,107,415 | 3,826,566 |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |  |
| --- | --- |
| Major Activities | 2007 |
| Objective 1: | Health Workforce Mobilization, Distribution and Motivation |
| Activity 1.1: | The funds for Integrated Refresher Training Courses of 4,950 HEWS is distributed to regions and training activities is ongoing by RHB: |
| Activity 1.2: | Apprenticeship for HEWs students is not planned with the 1st instalment of 2007 funds. But preparatory work and information is shared with regions to conduct the same in the second half of 2007. |
| Activity 1.3: | The funds allocated for capacity strengthening for woreda health management teams is distributed and training of staff of Woreda and HC started with aim to train 1,860 staff. . |
| Activity 1.4: | The training of Health workers in IMNCI is planned to be conducted by the Pediatric Society of Ethiopia. Contractual agreements done and the Society will conduct the training of 1,350 health workers before end June 2007 and funds in the process of being transferred to the same. |
| Objective 2: | Supply, Distribution and Maintenance Systems for PHC drugs Equipment and Infrastructure |
| Activity 2.1: | Contract is signed between the MOH and GTZ to Upgrading 500 HS to HC. As part of this agreement 7,020,295 USD will be transferred to GTZ soon and the rest of the funds will be transferred form the next installments. |
| Activity 2.2: | UNICEF is requested to provide cost estimate and funds will be transferred soon to UNICEF to procure Equipment for Health Centre A. |
| Activity 2.3: | UNICEF is requested to provide cost estimate and funds will be transferred to UNICEF to procure Equipment for Health Centre B. |
| Activity 2.4: | Fund for the Construction of 50 Health Posts is distributed to four emerging regions and the regions have started tender process. |
| Activity 2.5. | UNICEF is requested to provide cost estimate and funds will be transferred to UNICEF to procure Equipment for HP type B. |
| Activity 2.6 | UNICEF is requested to provide cost estimate and funds will be transferred to UNICEF to procure Equipment for HP type A. |
| Objective 3: | Organization and management of Health Services at District level and below. |
| Activity 3.1: | Request was made to UNDP (IAPSO) to procure 36 four wheel drive vehicles for distribution to Woredas |
| Activity 3.2: | Specifications were prepared and bid process started by the relevant departments and units of the MOH to procure IT equipment for 109 Woredas. |
| Activity 3.3: | Funds for the HEP annual regional review meetings were allocated for regions and transferred. |
| Activity 3.4: | Funds were distributed to regions to conduct training g in HMIS. The left over money will be utilized at federal level. |
| Activity 3.5. | Selected activities of the implementation of HCSS master plan have started with 100,000 USD of the 1st installment. |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| % of woredas with timely funding for HEWs refresher course | Woreda finance report | 95% | Official reports | 2006/07 | 95% | 2010 |
| % of TVET schools with resources for apprenticeship | TVET report through REB | 100% | Official reports | 2006/7 | 100% | 2010 |
| Number of contracts signed for expansion HS to HC | MOH Records | 0 | MOH documents | May 2007 | 212 | 2010 |
| # of regions with AWP for logistics Master Plan | RHB reports | 0 |  |  | 9 | 2010 |
| # HEWS attending refresher courses per year | MOH records | 1,603 | HEP report | Jan. 2007 | 13,200 | 2008 |
| % of apprenticeships with 1/15 tutor/trainee | TVET records | No data, assumed to be none | TVET reports | 2006/07 | 90% | 2010 |
| % of HEWs trainees with EPI complete checklist | TVET records | Not data assumed to be none | TVET reports | 2006/07 | 90% | 2010 |
| # of upgraded Health Stations (cumulative) | Woreda Health Offices and RHB reports | 0 | Consolidated annual HSDP report | 2006 | 212 | 2010 |
| # of Health Posts equipped (equipment in place , cumulative) | * |  |  |  |  |  |
| # of Health Centres equipped (cumulative) | * |  |  |  |  |  |
| % of Health Posts in cluster system for cold chain efficiency | * |  |  |  |  |  |
| % of woredas with updated/accurate stock reports | * |  |  |  |  |  |
| % of Health Posts with 10day Kerosene stock | * |  |  |  |  |  |
| # of woredas equipped for support superv.(max 109) | * |  |  |  |  |  |
| % of HPs providing EPI , twice a month (at least) | * |  |  |  |  |  |
| % of HEW recording refrigerator temp. twice daily |  |  |  |  |  |  |
| % of women attending at least one ANC | Health Services statistics | 50.4% | Health and Health Related Indicators 1998 Eth.C. (2005/06) | June 2006 | 80% | 2010 |
| % of HPs providing TT during ANC | * |  |  |  |  |  |
| % of rural kebeles with access to full HEP package | * |  |  |  |  |  |
| % of HPs with no essential.drugs shortage last 3 months | * |  |  |  |  |  |
| % of pregnant women with access to BEOC | * |  |  |  |  |  |
| % of HP supervised once in past two months | * |  |  |  |  |  |
| % of HEP review recommendations included in .WorHO workplan | * |  |  |  |  |  |
| Number / % of districts achieving ≥80% DTP3 coverage | * |  |  |  | 90% | 2010 |
| Pentavalent (DPT3) coverage( from 69% baseline 2005) | Health Services records and reports | 75.6% | Health and Health Related Indicators 1998 Eth.C. (2005/06) | June 2006 | 85% | 2010 |
| Measles coverage (from 59% baseline 2005) | Health Services records and reports | 65.6% | Health and Health Related Indicators 1998 Eth.C. (2005/06) | June 2006 | 85% | 2010 |
| % of children 6-12months having rec. Vit.A last 6 months | * |  |  |  |  |  |
| % of children12-59 months rec. Albendazole last 6 months | * |  |  |  |  |  |
| % of children with Diarrhea receiving ORT/ORS at HP level | * |  |  |  |  |  |
| % of “clean deliveries” | Health services statistics | 15.1 | Health and Health Related Indicators 1998 Eth.C. (2005/06) | June 2006 | 32% | 2010 |
| % of children treated with the IMNCI protocol at HC level | * |  |  |  |  |  |
| Under Five Mortality rate | Surveys | 123/1000 | DHS 2005 | 2005 | 85/1000 | 2010 |

* Baseline will be established in collaboration with UNICEF for those indicators marked *.  It is planned to set baseline before end 2007.

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

The targets for ANC, DPT3 and Measles have been achieved as compared to the 2005 baseline. The Number of contract agreements for upgrading HS to HC has also been more than the plan target. The baseline for most of the indicators has not been set so far. It is hoped that this will be accomplished before end 2007.There is no plan to revise the monitoring and evaluation system. Some time will be taken to establish the baselines. The impact of the GAVI HSS can not be assessed as the funds were transferred very recently.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) |  |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on |  |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ |  |  |
| Injection Safety Reported on |  |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) |  |  |
| New Vaccine Request including co-financing completed and XL sheet attached |  |  |
| Revised request for injection safety completed (where applicable) |  |  |
| HSS reported on |  |  |
| ICC minutes attached to the report |  |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report |  |  |

6.  	Comments

ICC/HSCC comments:

~ End ~

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

Percentage of  clean deliveries includes deliveries by trained HEWs as well as  by skilled attendants