Global Alliance for Vaccines and Immunization (GAVI)

APPLICATION FORM FOR COUNTRY PROPOSALS

Guyana

For Support to:

Immunization Services

April 2007

## CONTENTS

| SECTION |  | SUPPORT | PAGE |
| --- | --- | --- | --- |
| 1. | Executive Summary | ALL | 2 |
| 2. | Signatures of the Government and National Coordinating Bodies |  |  |
|  | - Government and the Health Sector Strategy Committee | HSS |  |
|  | - Government and the Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 4 |
|  | - The Inter-Agency Coordinating Committee for Immunization (ICC) | ALL | 5 |
| 3. | Immunization Programme Data | ALL | 6 |
|  | - Immunization Fact Sheet |  | 6 |
|  | - Comprehensive Multi-Year Immunization Plan |  | 7 |
| 4. | Immunization Services Support (ISS) | ISS | 11 |
| 5. | Health Systems Strengthening Support (HSS) | HSS |  |
|  | - Proposed GAVI Health Systems Strengthening Support |  |  |
|  | - HSS Financial Analysis and Planning |  |  |
|  | - Management and Accountability of GAVI HSS Funds |  |  |
|  | - Involvement of Partners in GAVI HSS Implementation |  |  |
| 6. | Injection Safety Support (INS) | INS |  |
| 7. | Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC) | ALL | 14 |
| 8. | Documents required for each type of support | ALL | 15 |
| Annex 1 – Banking Form |  | ISS | 16 |

## Executive Summary

Brief Country Profile

Guyana covers an area of 83,000 square miles (215,000 square kilometres) and is located along the north-eastern coast of South America.  The country is divided into ten administrative regions that vary significantly in population density, geography, ethnicity, income level, health care access, and vaccination coverage.  The population, estimated at 751,223 in the 2002 Bureau of Statistics Census, is clustered primarily within the five smaller coastal regions.  By contrast, the four main hinterland (interior) regions are very sparsely populated, covering nearly three-quarters of Guyana’s land mass but containing only 10% of the population.  Twenty-eight percent of the population lives in urban areas, primarily in the capital city of Georgetown.  In 2002, over 35% of the population of Guyana was less than 15 years old, 11.8% was less than 5 years old, and 10.5% was over 60 years old.

Guyana is rich in natural resources with an economy based on agriculture, gold, bauxite, and timber.  Despite this natural wealth, Guyana remains one of the poorest countries in the western hemisphere.  According to the 1999 Living Conditions Survey conducted by the Government of Guyana, 36% percent of the country’s population lives in absolute poverty, with 19% living in conditions of extreme poverty.  In the rural interior, populated predominantly by Amerindians, 78% of the population lives in absolute poverty.  Although some progress has been made over the past few years, more recent indicators confirm that the Guyana’s economic and social development problems persist.  In 2004, the United Nations Development Program Human Development Index ranked Guyana 103rd out of 177 countries and, in 2005, the Guyana Bureau of Statistics estimated the country’s GNI per capita at U.S. $830.

Challenges for the Expanded Programme on Immunization

The objective of the Expanded Programme on Immunization is to reach and maintain overall immunization coverage of 95% or greater in every region, sub-region, district, and village of Guyana.  Unfortunately, this level of coverage has yet to be realized.  Despite the best efforts of a dedicated EPI staff, the national DPT3 coverage rate in 2006 was 93%, with significant disparities in coverage at the regional and sub-regional levels.  These areas of low coverage are mainly in the hinterland and “riverain” communities, where access and communication are difficult and maintaining the cold chain is a daily challenge.  Often, travel in these areas is only possible by boat or by air and can be prohibitively expensive.  The cost of fuel alone can limit the capacity of health care professionals to reach vaccination target populations.  Lack of reliable sources of electricity and high fuel costs can hinder the ability of providers to ensure the integrity of the cold chain.  These difficulties are further exacerbated by the underdeveloped communication infrastructure in these regions, with most health care facilities relying on radio transmission.

Despite these challenges, the Ministry of Health and its partner organizations recognize the importance of addressing regional and ethnic disparities in vaccination coverage and ensuring that all children have access to quality health care.  Since the last EPI evaluation in 2000, significant progress has been made in this regard.  The Ministry of Health and partners such as UNICEF, PAHO, the Inter-American Development Bank, the World Bank, the Global Fund to Fight AID, Tuberculosis and Malaria, and the GAVI Alliance have made substantial investments in the transportation, communication, and cold chain infrastructure in several of Guyana’s more remote regions.  The Ministry of Health alone has invested over U.S. $200,000 toward such improvements. These expenditures have resulted in increased EPI capacity and vaccination coverage in several hinterland regions.  For example, from 2003 to 2006, DPT3 coverage in Region 7 increased from 82% to 94%.  Similar results were achieved in Region 9.  However, the financial cost of such improvements in the interior regions is substantial and much more remains to be done.

Synopsis of proposal

Given the pressing need for support for activities in the hinterland regions and other low coverage areas, the Ministry of Health is submitting a request for funding to GAVI for Immunization Services Support.  The funding requested in this application will primarily be used to increase access to vaccination for the target population in Region 1, the hinterland Region with the lowest coverage levels (DTP3 coverage rate of 66% in 2006).

The total value of the support requested is estimated to be U.S. $8,300 spread nearly evenly over a three-year period beginning in September of 2007.  As outlined in Table 8 below, these projections presuppose a one-percent yearly increase over this three year period.  If achieved, this will raise the overall coverage rate in Guyana from 93% in 2007-2008 to 96% in 2009-2010.  To achieve this level of coverage, approximately 140 additional children will need to be vaccinated with DTP per year (given as pentavalent vaccine).  The Ministry of Health and its partners are aware that funding is available for the entire 5 year period ending in 2012.  However, after detailed discussion, it was concluded that further increases above this 96% coverage level are unlikely given the significant barriers faced by the Expanded Programme on Immunization in Guyana.

Ministry of Health Institutional Capacity

The Ministry of Health in Guyana has already proven its ability to successfully manage and implement activities related to GAVI Alliance funding.  Starting in 2001, Guyana received approximately one million U.S. dollars of support for the provision of biologics and logistics over a five-year period. The Expanded Programme on Immunization used these funds to successfully integrate the pentavalent vaccine (DPT/Hepatitis B/Hib) into the country’s routine vaccination services.  According to plan, the Government of Guyana assumed total responsibility for the cost of this vaccine at the end of 2005, becoming the only GAVI-funded country to assume independent financial management of a new vaccine in the schedule time-frame. We are pleased to report that, for the year 2006, coverage rates for pentavalent vaccine remained stable at 93% and there have been no interruptions of vaccine supply following the cessation of GAVI new vaccine support.

Stakeholders

The following proposal was prepared by the Ministry of Health with support from representatives of the Pan American Health Organization at the request of the Interagency Coordinating Committee on Immunization (ICC) in Guyana.  The ICC has reviewed and endorsed the contents of this application.

## Government and the Inter-Agency Coordinating Committee for Immunization

The Government of Guyana commits itself to developing national immunization services on a sustainable basis in accordance with the multi-year plan presented with this document.

Districts’ performance on immunization will be reviewed annually through a transparent monitoring system. The Government requests that the Alliance and its partners contribute financial and technical assistance to support immunization of children as outlined in this application.

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Signature: …………………………………… | Signature: …………………………………… |
| Title: …………………………………… | Title: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

National Coordinating Body: Inter-Agency Coordinating Committee for Immunization:

We, the members of the ICC met on the 20th of March, 2007 to review this proposal.  At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

  - The endorsed minutes of this meeting are attached as DOCUMENT NUMBER 5.

| Agency/Organisation | Name/Title |
| --- | --- |
| Ministry of Health, Guyana | Dr. Rudolph Cummings/Chief Medical Officer |
| Ministry of Health, Guyana | Dr. Janice Woolford/MCH/EPI Officer |
| Ministry of Health, Guyana | Ms. Clarice Watson/Surveillance Coordinator |
| Ministry of Health, Guyana | Mr. Noel Holder/Chief Medex |
| Ministry of Health, Guyana | Ms. Bibi Halfrose/DCNO |
| Ministry of Health, Guyana | Ms. Claudette Simon/MCH Admin Manager |
| PAHO | Dr. Peter Troell |
| UNICEF | Mr. Dennis Arends |
| Rotary International | Mr. Fritz Mclean |

In case the GAVI Secretariat has queries on this submission, please contact:

| Name: Dr. Rudolph Cummings | Title: CMO MOH, Chair of ICC |
| --- | --- |
| Tel No.: +592-226-1224 +592-227-3509 | Address: Ministry of Health Brickdam, Georgetown Guyana, South America |
| Fax No.: +592-2226-1224 |  |
| Email: rcummings@solutions2000.net |  |

The GAVI Secretariat is unable to return submitted documents and attachments to individual countries.  Unless otherwise specified, documents may be shared with the GAVI partners and collaborators.

## The Inter-Agency Coordinating Committee for Immunization

Agencies and partners (including development partners, NGOs and Research Institutions) that are supporting immunization services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC).  The ICC is responsible for coordinating and guiding the use of the GAVI ISS support.  Please provide information about the ICC in your country in the spaces below.

Profile of the ICC

| Name of the ICC: Inter-agency Coordination Committee on Immunization |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date of constitution of the current ICC: 1989 |  |  |  |  |
| Organisational structure (e.g., sub-committee, stand-alone): Stand alone |  |  |  |  |
| Frequency of meetings: Quarterly |  |  |  |  |
| Composition: |  |  |  |  |
|  | Function | Title / Organization | Name |  |
|  | Chair | Chief Medical Officer, Ministry of Health | Dr. Rudolph Cummings |  |
|  | Secretary | MCH/EPI Officer, Ministry of Health | Dr. Janice Woolford |  |
|  | Members (alphabetical) | - Chief Nursing Officer, MOH - European Union Delegation of the Commission - Ministry of Amerindian Affairs - DCNO (ag), MOH - Chief Medex, MOH - Program Officer, CIDA - PAHO/WHO Representative, Guyana - Rotary International - Budget Officer, Ministry of Finance - Ministry of Health (Planning Department) - MCH Advisor, PAHO/WHO - Surveillance Coordinator, MOH - UNICEF Representative, Guyana - MCH Admin Mgr, MOH, Guyana | - Ms. Grace Bond - Ms. P. Cummings - Ms. Ritva Sullman - Ms. M. Grant - Ms. Bibi Halfrose - Mr. Noel Holder - Ms Anna Illes - Dr. Kathleen Israel - Mr. Fritz Mc Lean - Mr. V.R. Persaud - Ms. S. Roberts-McKoy - Dr. Louis Seaone - Ms. Clarice Watson - Mr. Johannes Wedenig - Ms. Claudette Simon |  |

Major functions and responsibilities of the ICC:

Provide a forum to:

-  Discuss MOHL and donor needs with regard to the Expanded Programme on Immunization.

-  Collaborate on the development of EPI initiatives.

-  Improve the policy environment to ensure proper discussion of issues of mutual concern.

-  Coordinate allocation of critical resources to avoid duplication.

-  Evaluate progress and the need for additional assistance on implementation of plans of action.

Three major strategies to enhance the ICC’s role and functions in the next 12 months:

1.  Incorporate input from selected members of the ICC during EPI budget development.

2.  Include selected members of the ICC in the National EPI Review.

3.  Arrange visits to low coverage areas for select members of the ICC to meet with stakeholders to discuss challenges and solutions.

## Immunization Programme Data

## Immunization Fact Sheet

Table 1: Basic facts (most recent; specify dates of data provided)

| Population | 751,223 (2002, Guyana Bureau of Statistics)1 764,991 (2005 estimate, Guyana Bureau of Statistics) 2 769,095 (2006 estimate, U.S. Census Bureau)3 | GNI per capita | $1010 US (2005, World Bank)4 $830 US (2005, Bureau of Statistics)5 |
| --- | --- | --- | --- |
| Surviving Infants* | 16, 391 (2004, Guyana Registry Office)6 15,257 (2005, MOH)7 | Infant mortality rate | 54/1000 (2001, MICS)8 47/ 1000 (2005, UNICEF)9 20.8/1000 (2004, MOH)10 |
| Percentage of GDP allocated to Health | 5.54% (2006, MOH)11 | Percentage of Government expenditure on Health | 7.91% (2006, MOH)12 |

Surviving infants = Infants surviving the first 12 months of life

1  Guyana Bureau of Statistics.  Guyana Population and Housing Census Report, 2002.

2  Guyana Bureau of Statistics.  Population Projections Guyana 2005-2025.  2006.

3  U.S. Census Bureau.  Total Mid-Year Population, Guyana 2006.  International Database. (Available at www.census.gov)

4  World Bank. World Development Indicators database, April 2006

5  Guyana Bureau of Statistics. Statistical Bulletin.  Annex 5, selected socio-economic indicators.  2005.

6   Guyana Registry Office, 2004

7  MOH Guyana. Expanded Programme on Immunization Report. 2006

8  Guyana Bureau of Statistics with UNICEF.  Multiple Indicator Cluster Survey Guyana.  2001.

9  UNICEF. State of the World’s Children. 2007.

10  MOH Guyana Statistical Unit.  As reported in: Ministry of Health with PAHO/WHO. National Strategic Plan for the Reduction of Maternal and Neonatal Mortality in Guyana, 2006-2010.

11, 12  MOH Guyana. Planning Expenditure Report.  2006

Table 2: Trends of immunization coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunization coverage (in percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey (MICS) |  | Disease | Number of reported cases |  |
|  |  | 2005 | 2006 | 2001 | 200… |  | 2005 | 2006 |
| BCG |  | 96 | 94.7 | 97 |  | Tuberculosis* | NA | NA |
| DTP (Given as pentavalent) | DTP1 | 93 | 94.7 | 95 |  | Diphtheria | 0 | 0 |
|  | DTP3 | 93 | 93.0 | 86 |  | Pertussis | 0 | 0 |
| Polio 3 |  | 93 | 92.2 | 85 |  | Polio | 0 | 0 |
| MMR (first dose) |  | 92 | 90.0 | 452 |  | Measles | 0 | 0 |
| Td (Pregnant women) |  | 971 | 98.01 | 61 |  | NN Tetanus | 0 | 0 |
| Hib3 (given as pentavalent) |  | 93 | 93.0 | NA |  | Hib ** | 0 | 0 |
| Yellow Fever |  | 91 | 90.0 | NA |  | Yellow fever | 0 | 0 |
| HepB3 (given as pentavalent) |  | 93 | 93.0 | NA |  | HepB sero-prevalence* | NA | NA |
| Vit A supplement | Mothers (<6 weeks post-delivery) | NR | NR | NR |  |  |  |  |
|  | Infants (>6 months) | NR | NR | NR |  |  |  |  |

NA = Not Available; NR = Not Relevant

1 Estimated value for pubic sector only

2 Given between age 12-23 months in Guyana, the MICS value represents children given vaccine at or near 12 months only.

*If available      ** Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to:

Ministry of Health Guyana with UNICEF, Multiple Indicator Cluster Survey. (2001).

Data reported: Percentage of children aged 12-23 months who received immunization by 12        months of age; and percentage of women with a birth in the last 12 months who were protected against neonatal tetanus.

## Comprehensive Multi-Year Immunization Plan

  - A complete copy (with an executive summary) of the Comprehensive Multi-Year Plan for Immunization is attached, as DOCUMENT NUMBER 3.

The following tables record the relevant data contained in the cMYP, indicating the relevant pages.

Table 3: Current Vaccination Schedule: Traditional, New Vaccines and Vitamin A Supplement (cMYP page 5)

| Vaccine (do not use trade name) | Ages of administration (by routine immunization services) | Indicate by an “x” if given in: |  | Comments |
| --- | --- | --- | --- | --- |
|  |  | Entire country | Only part of the country |  |
| BCG | Birth | X |  |  |
| DPT/Hib/Hep B | 2, 4 and 6 months | X |  |  |
| DPT | Booster at 18 months and 3 years 9 months | X |  |  |
| OPV | 2, 4 and 6 months; boosters at 18 months and 3 years 9 months | X |  |  |
| IPV | 2, 4 and 6 months; boosters at 18 months and 3 years 9 months | X |  | If suspected or confirmed immunosuppression in infant/child or immediate household. |
| MMR | 12-23 months and 3 years 9 months | X |  |  |
| YF | 12-23 months | X |  | Booster at 10 year intervals |
| Td | Pregnant women, vulnerable and high risk populations | X |  | 1 or 2 doses in pregnancy if not fully vaccinated prior to pregnancy |
| Hep B | High risk populations (e.g. health care workers) | X |  | 3 shot series |
| Vitamin A | Not relevant |  |  |  |

Summary of major action points and timeframe for improving immunization coverage identified in the cMYP on page 9.

| Major Action Points | Timeframe |
| --- | --- |
| 1. Improve the competence of Community Health Workers in providing routine vaccination services in hinterland and remote areas. Training will need to be conducted annually due to high staff turnover. | 2nd quarter of every year from 2007-2012 |
| 2. Increase staff access to remote areas through improved: - inter-sectorial coordination - transportation system - communication capacity | - monthly meetings - 2007 and 2009 - 2007-2009 |
| 3. Increase cold chain capacity to improve availability of vaccines at local level. | 2007 and 2008 |
| 4. Improve monitoring and evaluation through quarterly meetings to allow for earlier identification of dropouts and follow up visits with home vaccinations as needed. | Quarterly meetings in 2007-2012 |
| 5. Strengthen human resource capacity by filling vacant posts. | 2007-2009 |
| 6. Identify dropouts earlier and aggressively pursue through home visits, other outreach activities and through social mobilization activities (such as Vaccination Week in the Americas activities). | 2007-2012 |

Table 4: Baseline and annual targets

| ###### Number |  | ###### Baseline and targets |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Base-year | Year of GAVI application | Year 1 of Program | Year 2 of Program | Year 3 of Program | Year 4 of Program | Year 5 of Program |
|  |  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Births |  | 14,660 e | 14,074 | 14,074 | 14,074 | 14,074 | 14,074 | 14,074 |
| Infants’ deaths |  | 246 e | 221 | 221 | 221 | 221 | 221 | 221 |
| Surviving infants |  | 14,414 e | 13,853 | 13,853 | 13,853 | 13,853 | 13,853 | 13,853 |
| Pregnant womena |  | 14,430 | 13,853 | 13,853 | 13,853 | 13,853 | 13,853 | 13,853 |
| Infants vaccinated with BCG |  | 13,877 | 13,370 | 13,511 | 13,652 | 13,792 | 13,792 | 13,792 |
| BCG coverage* |  | 95 | 95 | 96 | 97 | 98 | 98 | 98 |
| Infants vaccinated with OPV3 |  | 13,285 | 12,883 | 13,021 | 13,160 | 13,298 | 13,298 | 13,298 |
| OPV3 coverage** |  | 92 | 93 | 94 | 95 | 96 | 96 | 96 |
| Infants vaccinated with DTP3*** |  | 13,340 | 12,883 | 13,021 | 13,160 | 13,298 | 13,298 | 13,298 |
| DTP3 coverage** |  | 93 | 93 | 94 | 95 | 96 | 96 | 96 |
| Infants vaccinated with DTP1*** |  | 13,654 | 13,160 | 13,298 | 13,437 | 13,437 | 13,437 | 13,437 |
| Wastage rate in base-year and planned thereafter |  | 0 (single) | 0 | 0 | 0 | 0 | 0 | 0 |
| Infants vaccinated with MMRb (given at 12-23 months) |  | 13,691 | 12,973 | 12,745 | 12,883 | 13,021 | 13,160 | 13,299 |
| MMR coverage** |  | 90 | 90 | 92 | 93 | 94 | 95 | 96 |
| Pregnant women vaccinated with Td |  | 14,173 | 13,576 | 13,576 | 13,576 | 13,576 | 13,576 | 13,576 |
| Td coverage**** |  | 98 | 98 | 98 | 98 | 98 | 98 | 98 |
| Vit A supplement | Mothers (<6 weeks from delivery) | NR | NR | NR | NR | NR | NR | NR |
|  | Infants (>6 months) | NR | NR | NR | NR | NR | NR | NR |

e = Estimated value

a  Pregnant women from the public sector only

b  MMR given from 12-23 months of age

*  Number of infants vaccinated out  of live births

**  Number of infants vaccinated out of surviving infants (MMR/15257)

***  Indicate total number of children vaccinated with either DTP alone or combined

**** Number of pregnant women vaccinated with Td (prior to or during pregnancy) out of total pregnant women

Please indicate the method used for calculating TT and coverage:

A /B; where A = the number of women (if unvaccinated) receiving at least 2 doses of Td prior to delivery or 5 to 6 doses of tetanus containing vaccine prior to pregnancy and;

B = the number of pregnant women seeking care in the public sector

Table 5: Estimate of annual DTP drop out rates

| Number | Actual rates and targets |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Drop out rate [ ( DTP1 - DTP3 ) / DTP1 ] x 100 | 2.3 | 2.3 | 2.1 | 2.1 | 1.0 | 1.0 | 1.0 |

Table 6: Summary of current and future immunization programme budget

(cMYP Annex 1, pages 1 & 2)

|  | Estimated costs per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Vaccines & Injections (Biological/Logistics) | 526.02 | 469.63 | 495.93 | 523.70 | 553.03 | 584.00 |
| Personnel | 523.91 | 554.56 | 585.74 | 617.35 | 652.08 | 690.27 |
| Transportation & Maintenance | 160.28 | 171.33 | 180.40 | 189.95 | 199.93 | 210.39 |
| Training | 72.59 | 17.47 | 92.01 | 21.15 | 84.72 | 20.67 |
| Social Mobilization | 93.82 | 134.28 | 75.96 | 55.34 | 58.44 | 89.45 |
| Surveillance | 25.56 | 26.99 | 33.50 | 35.09 | 31.78 | 39.45 |
| Research | 9.34 | 36.69 | 7.07 | 7.46 | 7.88 | 8.32 |
| Monitoring and Evaluation | 53.33 | 56.31 | 60.47 | 62.80 | 66.31 | 70.03 |
| Supervision | 27.46 | 28.69 | 29.93 | 31.21 | 32.49 | 33.79 |
| Vehicles | 101.40 | 0.00 | 22.08 | 0.00 | 0.00 | 133.15 |
| Cold-Chain Equipment | 35.68 | 0.00 | 0.65 | 15.00 | 0.00 | 4.04 |
| Other Equipment (e.g. telecommunications) | 13.82 | 0.00 | 0.00 | 0.00 | 0.00 | 17.44 |
| GRAND TOTAL | 1643.20 | 1495.95 | 1583.73 | 1559.05 | 1686.65 | 1900.99 |

Table 7: Summary of current and future financing and sources of funds (cMYP Annex1, pages 1 & 2)

|  |  | Estimated financing per annum in US$ (,000) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Budget chapter | Funding source | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| Vaccines & Injections (Biological/Logistics) | Government | 526.02 | 469.63 | 495.93 | 523.70 | 553.03 | 584.00 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Other | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Personnel | Government | 523.91 | 554.56 | 585.74 | 617.35 | 652.08 | 690.27 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Other | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Transportation & Maintenance | Government | 160.28 | 171.33 | 180.40 | 189.95 | 199.93 | 210.39 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Other | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Training | Government | 59.56 | 5.91 | 71.42 | 6.59 | 74.06 | 9.98 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | PAHO | 3.03 | 1.56 | 10.59 | 4.56 | 0.66 | 0.69 |
|  | UNICEF | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 | 10.00 |
| Social Mobilization | Government | 28.20 | 29.77 | 43.22 | 33.20 | 35.06 | 50.89 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | PAHO | 65.63 | 104.50 | 20.96 | 22.13 | 23.37 | 24.68 |
|  | HSDU* | 0.00 | 0.00 | 11.78 | 0.00 | 0.00 | 13.87 |
| Surveillance | Government | 19.75 | 20.85 | 22.02 | 23.25 | 24.56 | 25.93 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | PAHO | 5.81 | 6.13 | 11.48 | 11.84 | 7.22 | 13.52 |
| Research | Government | 6.28 | 5.58 | 5.89 | 6.22 | 6.57 | 6.93 |
|  | GAVI (DQA) | TBD | TBD | TBD | TBD | TBD | TBD |
|  | PAHO | 1.06 | 31.12 | 1.18 | 1.24 | 1.31 | 1.39 |
|  | UNICEF | 2.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Monitoring and Evaluation | Government | 53.33 | 56.31 | 60.47 | 62.80 | 66.31 | 70.03 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Other | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Supervision | Government | 16.90 | 17.66 | 18.42 | 19.21 | 19.99 | 20.79 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | UNICEF | 10.56 | 11.04 | 11.51 | 12.00 | 12.50 | 13.00 |
| Vehicles | Government | 0.00 | 0.00 | 22.08 | 0.00 | 0.00 | 133.15 |
|  | GAVI | 101.40 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | Other | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Cold-Chain Equipment | Government | 17.50 | 0.00 | 0.65 | 15.00 | 0.00 | 0.76 |
|  | GAVI | 15.68 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | PAHO | 2.50 | 0.00 | 0.00 | 0.00 | 0.00 | 3.28 |
| Other Equipment | Government | 0.32 | 0.00 | 0.00 | 0.00 | 0.00 | 17.44 |
|  | GAVI | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
|  | HSDU* | 13.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| GRAND TOTAL |  | 1643.20 | 1495.95 | 1583.73 | 1559.05 | 1686.65 | 1900.99 |

## Health Sector Development Unit – funded jointly by Inter-American Development Bank, World Bank and Global Fund to Fight AIDS, Tuberculosis and Malaria.

## TBD – To be determined

## Immunization Services Support (ISS)

Please indicate below the total amount of funds you expect to receive through ISS:

Table 8: Estimate of funds expected from ISS for Guyana 2008-2010

|  | 2006 | 2007* | 2008** | 2009** | 2010** | 2011** | 2012** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP3 Coverage rate | 93% | 93% | 94% | 95% | 96% | 96% | 96% |
| Number of infants reported / planned to be vaccinated with DTP3 (as per table 4) | 13340 | 12883 | 13021 | 13160 | 13298 | 13298 | 13298 |
| Number of additional infants that annually are reported / planned to be vaccinated with DTP3 |  |  | 138 | 139 | 138 |  |  |
| Funds expected ($20 per additional infant) |  |  | 2760 | 2780 | 2760 |  |  |

*  Projected figures

**  As per duration of the cMYP

If you have received ISS support from GAVI in the past, please describe below any major lessons learned, and how these will affect the use of ISS funds in future.

Please state what the funds were used for, at what level, and if this was the best use of the flexible funds; mention the management and monitoring arrangements; who had responsibility for authorising payments and approving plans for expenditure; and if you will continue this in future.

| Major Lessons Learned from Phase 1 | Implications for Phase 2 |
| --- | --- |
| 1. Not Applicable |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |
| 6. |  |

If you have not received ISS support before, please indicate:

a) When you would like the support to begin?:

If possible, by September 1, 2007.

b) When you would like the first DQA to occur?

If possible, October 2007.

c) How you propose to channel the funds from GAVI into the country?

Once the funding has been released, it is channelled through the financial management unit of PAHO Headquarters to the country office.

Ms. Linda S. Kintzois

Treasurer

Pan American Health Organization

525 Twenty-Third Street, N.W.

Washington D.C. 20037

USA

Tel: 202 974 3550

d) How you propose to manage the funds in-country?

The funds will be managed through the PAHO Guyana office, according to an agreed work plan and in collaboration with counterpart staff of the Ministry of Health.

e) Who will be responsible for authorising and approving expenditures?

In accordance with administrative procedures established within the Ministry of Health, the MCH/EPI officer determines spending priorities for the EPI program, with approval from the Ministry of Health Planning Department and the Ministry of Finance.

As the agency selected to administer funds, PAHO will ultimately be responsible for authorizing the disbursements.

  - Please complete the banking form (annex 1) if required

This form has not been completed at this time.  It will be submitted as soon as possible.

7.  Additional comments and recommendations from the National Coordinating Body (Health Sector Strategic Committee / ICC)

## 8. DOCUMENTS REQUIRED FOR EACH TYPE OF SUPPORT

| Type of Support | Document | DOCUMENT NUMBER | Duration * |
| --- | --- | --- | --- |
| ALL | WHO / UNICEF Joint Reporting Form | 1 and 2 |  |
| ALL | Comprehensive Multi-Year Plan (cMYP) | 3 | 2007-2012 |
| ALL | Endorsed minutes of the National Coordinating Body meeting where the GAVI proposal was endorsed | 4 |  |
| If relevant | Endorsed minutes of the ICC meeting discussing the requested GAVI support | 5 |  |
| Addition | Signatures of ICC Members | 6 |  |
| HSS | National Health Sector Strategic Plan |  |  |
| HSS | Medium Term Expenditure Framework ** |  |  |
| HSS | Recent Health Sector Assessment documents |  |  |
| HSS | Outline of HSS Programme with budget and Justification for support or HSS Relevant parts of National Planning Document |  |  |
| HSS | Other Health Systems Strengthening Plans / estimates |  |  |
| Injection Safety | National Policy on Injection Safety including safe medical waste disposal (if separate from cMYP) |  |  |
| Injection Safety | Action plans for improving injection safety and safe management of sharps waste (if separate from cMYP) |  |  |
| Injection Safety | Evidence that alternative supplier complies with WHO requirements (if not procuring supplies from UNICEF) |  |  |

* Please indicate the duration of the plan / assessment / document where appropriate

** Where available

ANNEX 1 – The completed banking form and cover letter will be submitted as soon as possible

| GLOBAL ALLIANCE FOR VACCINES AND IMMUNIZATION |  |  |  |  |  | ##### Banking Form |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SECTION 1 (To be completed by payee) |  |  |  |  |  |  |  |  |  |  |
| In accordance with the decision on financial support made by the Global Alliance for Vaccines and Immunization dated . . . . . . . . . . . , the Government of . . . . . . . . . . . . . . . . . . . hereby requests that a payment be made, via electronic bank transfer, as detailed below: |  |  |  |  |  |  |  |  |  |  |
| #### Name of Institution: (Account Holder) |  |  |  |  |  |  |  |  |  |  |
| #### Address: |  |  |  |  |  |  |  |  |  |  |
| #### City – Country: |  |  |  |  |  |  |  |  |  |  |
| Telephone No.: |  |  |  | Fax No.: |  |  |  |  |  |  |
| #### Amount in USD: |  | (To be filled in by GAVI Secretariat) |  |  | Currency of the bank account: |  |  |  |  |  |
| For credit to: Bank account’s title |  |  |  |  |  |  |  |  |  |  |
| Bank account No.: |  |  |  |  |  |  |  |  |  |  |
| At: Bank’s name |  |  |  |  |  |  |  |  |  |  |
| #### Is the bank account exclusively to be used by this programme? |  |  |  |  |  |  | YES ( ) NO ( ) |  |  |  |
| #### By whom is the account audited? |  |  |  |  |  |  |  |  |  |  |
| # Signature of Government’s authorizing official: |  |  |  |  |  |  |  |  |  |  |
| #### Name: |  |  |  |  |  |  |  |  | Seal: |  |
| #### Title: |  |  |  |  |  |  |  |  |  |  |
| #### Signature: |  |  |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |  |  |

| SECTION 2 (To be completed by the Bank) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # FINANCIAL INSTITUTION |  |  |  | CORRESPONDENT BANK (In the United States) |  |
| Bank Name: |  |  |  |  |  |
| Branch Name: |  |  |  |  |  |
| Address: |  |  |  |  |  |
| City – Country: |  |  |  |  |  |
| Swift code: |  |  |  |  |  |
| Sort code: |  |  |  |  |  |
| ABA No.: |  |  |  |  |  |
| Telephone No.: |  |  |  |  |  |
| Fax No.: |  |  |  |  |  |
| I certify that the account No. . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . is held by (Institution name) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .at this banking institution. |  |  |  |  |  |
| The account is to be signed jointly by at least …… (number of signatories) of the following authorized signatories: |  |  | Name of bank’s authorizing official: |  |  |
| 1 Name: Title: |  |  | Signature: |  |  |
|  |  |  | Date: |  |  |
| 2 Name: Title: |  |  | Seal: |  |  |
| 3 Name: Title: |  |  |  |  |  |
| 4 Name: Title: |  |  |  |  |  |

COVERING LETTER

(To be completed by PAHO representative on letter-headed paper)

### TO:    GAVI – Secretariat

### Att. Dr Julian Lob-Levyt

### Executive Secretary

C/o UNICEF

Palais des Nations

CH 1211 Geneva 10

Switzerland

| On the ……………………………… I received the original of the BANKING DETAILS form, which is attached. I certify that the form does bear the signatures of the following officials: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Name |  |  | Title |
| Government’s authorizing official |  |  |  |  |  |
| Bank’s authorizing official |  |  |  |  |  |
| Signature of PAHO Representative: |  |  |  |  |  |
| Name |  |  |  |  |  |
| Signature |  |  |  |  |  |
| Date |  |  |  |  |  |

References

Government of Guyana, Poverty Reduction Strategy Paper (2006).

Guyana Bureau of Statistics, “Population Projections Guyana 2005-2025” (2006).

Guyana Bureau of Statistics, Statistical Bulletin, at Annex 5: Selected Socio-economic Indicators (2005).

Guyana Bureau of Statistics, Guyana Population and Housing Census Report (2002).

Guyana Bureau of Statistics and UNICEF, Multiple Indicator Cluster Survey Guyana (2001).

Ministry of Health Guyana, Expanded Programme on Immunization Report (2006).

Ministry of Health Guyana Statistical Unit, National Strategic Plan for the Reduction of Maternal and Neonatal Mortality in Guyana 2006-2010.

Ministry of Health Guyana, Planning Expenditure Report (2006).

Ministry of Health Guyana and PAHO, EPI Situational Analysis 2004 – Regions 1, 7, 8, and 9 (2005).

Ministry of Health and PAHO, Rapid Assessment of the System-wide Barriers and Good Practices in the Expanded Programme on Immunization. (2004)

Ministry of Health, National Health Plan 2003-2007. (2003)

Ministry of Health Guyana, PAHO, and UNICEF, National Immunization Program Financial Sustainability Plan (2003).

Ministry of Health Guyana, Five-Year Immunization Plan 2001-2005.  (2001)

Ministry of Health Guyana and PAHO, Evaluation of Guyana’s Expanded Programme on Immunization (2000).

United Nations Development Programme, Guyana in Human Development Report (2006).

UNICEF, “State of the World’s Children” (2007).

United States Census Bureau, “Total Mid-Year Population: Guyana 2006,” in International Database, available at http://www.census.gov.

World Bank, World Development Indicators Database (April 2006), available at http://devdata.worldbank.org/external. CCProfile.asp?PTYPE=CP&CCODE=GUY.

It is important to note that some inner city areas of the capital, Georgetown, also have low vaccination coverage. The Ministry of Health intends to utilize existing funds for initiatives to improve the identification of vaccination dropouts and increase the level of home visiting for vaccination in these urban areas.  This will include vaccination outreach campaigns during Vaccination Week in the Americas.

The formula to calculate a vaccine wastage rate (in percentage): [ ( A – B ) / A ] x 100.   Whereby: A = The number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B =  the number of  vaccinations with the same vaccine in the same period. For new vaccines check table   after Table 7.1.