May 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY:

Date of submission: 15 May 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  √ Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2006

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

The financial input of GAVI for immunization of the DPR Korea is managed through the bank account (082/250) in the Foreign Trade Bank, DPR Korea. ICC holds its meeting for assessment and evaluation so as to ensure the correct application of the fund assisted for the original purpose and both the GAVI program manager and the financial manager in line with the decision of the ICC meeting then pay the fund. There is no difficulty in fund usage.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 US$271,050_____________

Remaining funds (carry over) from 2004 None_________

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 0 |  |  |  |  |
| Injection supplies | 0 |  |  |  |  |
| Personnel | 0 |  |  |  |  |
| Transportation | 15,000 | 8,000 | 7,000 |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | 20,000 | 8,000 | 12,000 |  |  |
| IEC / social mobilization | 25,000 | 6,000 | 8,000 | 11,000 |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation | 123,000 | 53,000 | 70,000 |  |  |
| Epidemiological surveillance | 10,000 | 5,000 | 3,000 | 2,000 |  |
| Vehicles | 8,000 | 3,000 | 3,000 | 2,000 |  |
| Cold chain equipment | 5,000 | 1,000 | 2,000 | 2,000 |  |
| Other …………. (specify) | 65,050 | 15,000 | 20,000 | 30,050 |  |
| Total: | 271,050 | 99,000 | 125,000 | 47,050 |  |
| Remaining funds for next year: | None |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’. None

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Along with works to inspire people who are to be vaccinated to intentionally participate in this undertaking, IEC activities were conducted in various methods and ways. - In order to find the reason for low coverage of DPT, survey on adverse reaction was done, further measures taken and surveillance strengthened. - Delay in dispatch of vaccines and syringes were removed by organizing the transportation campaigns from the national level to provincial levels and from the provincial to county.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

YES                              NO

√

## If yes, please report on the degree of its implementation.

The main recommendations of DQA were training of staff, strengthening reporting, estimating denominators calculation of wastage rate and printing disseminating updated guideline. - Training of more than 5000 service providers planned for 2005-2006, first two batches conducted in 2005 - Issues of wastage rate, denominators and reporting were highly emphasized during training - Updated guideline printed and distributed to all level

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

Survey on the rate of inoculation in 2005

-The national EPI personnel surveyed DPT3 coverage on 24 Ris in 12 counties of 6 provinces from 17th October to 15th November 2005: the result was 76% ~ 80 % with the average of 78.9% by the average annual increment of 6.8%. - The provincial EPI personnel conducted the review of the immunization coverage for every target county once a quarter. - The county EPI personnel conducted the review of the immunization coverage for each antigen at Ri level once a month and made suggestions.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH…January ~December    YEAR 2005

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Total 1, 649,200 doses of HB vaccines received, all shipment were on time. There was no shortage of vaccines in 2005.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

- In view of the nationwide HB vaccination in 2004, the workshops for all organizers and vaccinators concerned were conducted in each leve and IEC activities intensified with the result of vaccination coverage of 91% up. - Prominent doctors who were good at service and efforts for improving the immunization coverage were acknowledged. - IEC works, survey on AEFI, surveillance, information and access to lower levels were intensified to increase the DPT3 coverage along with the counselling: as a result coverage of DPT3 was increased to 79%.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Proportion of utilization of funds: invested at the respective consumption rate of 30% for transportation of vaccines, 40% for workshops, 10% for IEC activities and 10% for evaluation and encouragement. Activities conducted: - Transportation was done according to the system of delivery from the national to the provincial, from the provincial to the county and from the county to Ri levels respectively with the rate of once a quarter from the national level, once a month from the provincial level and also once a month from the county level. - Workshops were done once at the national level, twice at the provincial level and 4 times at the county level. - IEC works were conducted through radios, TV and household education and household visits of the section doctors. - Directions for the lower levels were done once by the national level, twice by the provincial level and 12 times by the county levels respectively.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

- Total 1,362,100 pc of autodestruct syringes received from GAVI. - No difficulties or problem in supply chain encountered.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

- To ensure the injection safety, AD syringes supported by GAVI were used for vaccination and used syringes and needles put into safety boxes to be incinerated in the incinerators and buried 1-meter depth underground. - The incinerators were effectively used for safe disposal of injection supplies. - Constraints: Bringing back the sharps and waste from Ri to county is a problem and waste of resources. It would be nice to construct incinerators at Ri level. Additional funds for this purpose is needed.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Safe disposal of used syringes and wastes at all levels | Having one incinerators at each of the country and Ri level | 200 incinerators constructed on 2004 at county level | - Lack of availability of fund - Transportation of sharps and wastes from Ri to county | Construction of incinerators at Ri levels. |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

None

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial sustainability plan was developed and submitted in Sep. 2005 and reviewed in Nov. 2005.

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for HB.  (new vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Hep B (specify) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
|  | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| A: Proportion funded by GAVI/VF (%)*** | 25 | 100 | 100 | 100 | 100 | 75 |  |  |  |  |
| B: Proportion funded by the Government and other sources (%) | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| C: Total funding for …………. (new vaccine) | 135,450 | 581,800 | 581,800 | 581,800 | 581,800 | 436,350 |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Developing EPI multi year plan including details financial strategy | First draft is almost completed |  | commitment of fund from partners |  |  |  |
| 2. Reduce wastage rate | Staff trained | Data is being collected | N/A | 35% |  |  |
| 3. |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2007

Section 3 is related to the request for new and under used vaccines and injection safety for 2007.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 419,378 | 419,378 | 419,378 | 419,378 |  |  |  |  |  |
| Births | 420,000 | 420,000 | 420,000 | 420,000 |  |  |  |  |  |
| Infants’ deaths |  |  |  |  |  |  |  |  |  |
| Surviving infants | 419,378 | 419,378 | 419,378 | 419,378 |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* | 314,571 | 333,689 | 356,971 | 419,378 |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006and beyond with 3rd dose of DTP (DTP3)* | 301,652 | 316,488 | 335,502 | 348,084 |  |  |  |  |  |
| NEW VACCINES **HB ( Hep B) |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2006 and beyond with 1st dose of DTP (DTP1)* HB(new vaccine) | 417,840 | 377,126 | 419,378 | 419,378 |  |  |  |  |  |
| Infants vaccinated 2005(JRF) / to be vaccinated in 2006 and beyond with 3rd dose of HB ( new vaccine) | 417,147 | 367,787 | 419,378 | 419,378 |  |  |  |  |  |
| Wastage rate in 2005 and plan for 2006 beyond*** HB. ( new vaccine) | 1.33 | 1.25 | 1.25 | 1.25 |  |  |  |  |  |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005(JRF) / to be vaccinated in 2006 and beyond with TT2 | 405,000 | 395,987 | 420,000 | 420,000 |  |  |  |  |  |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2006 and beyond with BCG * | 399,479 | 377,126 | 419,378 | 419,400 |  |  |  |  |  |
| Infants vaccinated in 2005(JRF) / to be vaccinated in 2006 and beyond with Measles * | 381,997 | 384,599 | 415,000 | 415,000 |  |  |  |  |  |

* Indicate actual number of children vaccinated in 2004 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- There observed some discrepancy in the present numbers of pregnant women and the new borne other than the expected figures as reported last year. - The figures in above table are as UNICEF/WHO JRF - Starting from July 2006 shift to combined vaccine Hep B+DPT is approved, it may affect positively coverage of DPT - Target for 2008 onward will be in reflected in EPI multi year plan, which is going to be prepared by June.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Vaccines of HepB + DPT are expected to be introduced from July 2006.

Table 4: Estimated number of doses of Hep B+DPT vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of: 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

None

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| - Increased DPT3 coverage - Ensure injection safety - Strengthening management surveillance and supervision | - DPT3 coverage 80% by 2005 - 90% safe disposal of waste - 10% reduction in dropout rate - Regular monthly supply at Ri level - At least once per month supervision | - 197 units reached more than 80% DPT3 coverage - More than 90% safe disposal of waste at county level - National DPT3 coverage 78.7% - 100% regular supply - More than 90% monthly supervision | - Lack of fuels for transportation - Lack of availability of incinerator at Ri level | - To increase DPT3 coverage upto 82% in 2006 - Construction of Ri incinerators - Improvement of personnel and complete visits to omitted households |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 15 may 2006 |  |
| Reporting Period (consistent with previous calendar year) | Jan-Dec 2005 |  |
| Table 1 filled-in | Jan 2006 |  |
| DQA reported on | Dec 2004 |  |
| Reported on use of 100,000 US$ | May 2004 |  |
| Injection Safety Reported on | July 2004 |  |
| FSP Reported on (progress against country FSP indicators) | August 2004 |  |
| Table 2 filled-in |  |  |
| New Vaccine Request completed | November 2005 |  |
| Revised request for injection safety completed (where applicable) | N/A |  |
| ICC minutes attached to the report | Yes |  |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of the Democratic People’s Republic of Korea

Signature:	…Dr. Choe Chang Sik …………………………………………...……………...

Title: Vice-minister, Ministry of Public Health

Date:  May 10 , 2006

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements, as verbally confirmed by the Government.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Ministry of Public Health, DPRK | Prof. Dr. Choe Chang Sik, Vice minister |  | Academy of Medical Science, DPRK | Dr. Han Hyon Chol, Deputy Director |  |
| Ministry of Public Health, DPRK | Dr. Chor Ung Jun, Director, SHCDCB |  | Central Hygiene & Anti epidemic Institute | Dr. Han Kyong Ho, Director |  |
| Ministry of Public Health, DPRK | Dr. Pak Jong Min., Director, External Affairs Dept. |  | Ministry of Public Health, DPRK | Dr. Jong Bong Ju, Program manager for GAVI |  |
| State planning Commission, DPRK | Mr. Ri In Jun, Director, External Affairs Dept. |  | Ministry of Public Health, DPRK | Dr. Han Yong Sik, Senior Officer, SHCDCB |  |
| Ministry of Finance, DPRK | Mr. O Myong Il, Director, External Affairs Dept. |  | UNICEF, Pyongyang | Ms. Pierrette Vuthi, Representative |  |
| Ministry of Education, DPRK | Mr. Chae Ryang Il, Director, External Affairs Dept. |  | WHO, Pyongyang | Dr. Tejbir Walia, Representative |  |
| Korean Democratic Women’s Union | Ms Pak Song Ok, Director, External Affairs Dept. |  |  |  |  |

~ End ~