Annual Progress Report 2006

Submitted by

The Government of

The Republic of Moldova

to the

# Date of submission: 15.05.2007

Annual progress report (this report reports on activities in 2006 and specifies requests for 2008, Jan.-Dec.)

*Unless otherwise specified, documents may be shared with GAVI partners and collaborators as well as the general public.

Signatures Page for ISS, INS and NVS

For the Government of the Republic of Moldova

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: Deputy Minister GOLOVIN Boris | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The ICC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |
| GOLOVIN Boris, deputy minister | Ministry of Health |  |  |
| BAHNAREL Ion, General Director | National Scientific and Practical Center of Preventive Medicine |  |  |
| OSOIANU Iurie, deputy director | National Company for Health Insurants |  |  |
| PEREBICOVSCHI Liubovi, health sectors | Ministry of Financing |  |  |
| RAY VIRGILIO TORRES | UNICEF Moldova Representative |  |  |
| URSU Pavel | WHO Liaison Office in the Republic of Moldova |  |  |
| MELNIC Anatolie Head of General Epidemiology Department | National Scientific and Practical Center of Preventive Medicine |  |  |

Signatures Page for HSS  - NOT APPLICABLE

For the Government of ………………..…………………………………

| Ministry of Health: | Ministry of Finance: |
| --- | --- |
| Title: …………………………………… | Title: …………………………………… |
| Signature: …………………………………… | Signature: …………………………………… |
| Date: …………………………………… | Date: …………………………………… |

We, the undersigned members of the National Health Sector Coordinating Committee, ……………………………………… (insert name) endorse this report on the Health Systems Strengthening Programme. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI Alliance monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.

The HSCC Members confirm that the funds received from the GAVI Funding Entity have been audited and accounted for according to standard government or partner requirements.

| Name/Title | Agency/Organisation | Signature | Date |
| --- | --- | --- | --- |

# Progress Report Form:  Table of Contents

# Report on progress made during 2006

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

    - Immunization Data Quality Audit

    - ICC Meetings

  - GAVI Alliance New and Under-used Vaccines (NVS)

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI Alliance financial support (US$100,000) for introduction of the new vaccine

    - Evaluation of Vaccine Management System

1.3		Injection Safety (INS)

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI Alliance injection safety support (if received in the form of a cash contribution)

2.  Vaccine Co-financing, Immunization Financing and Financial Sustainability

3.  Request for new and under-used vaccine for 2008

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year 2008 and projections for 2009 and 2010

  - Confirmed/revised request for injection safety support for the year 2008 and 2009

- Health System Strengthening (HSS)

- Checklist

- Comments

Text boxes supplied in this report are meant only to be used as guides.  Please feel free to add text beyond the space provided.

# 1.  	Report on progress made during 2006

## Immunization Services Support (ISS) - NOT APPLICABLE

Are the funds received for ISS on-budget (reflected in Ministry of Health and Ministry of Finance budget): Yes/No

If yes, please explain in detail how it is reflected as MoH budget in the box below.

If not, explain why not and whether there is an intention to get them on-budget in the near future?

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

#### 1.1.2	Use of Immunization Services Support

In 2006, the following major areas of activities have been funded with the GAVI Alliance Immunization Services Support contribution.

Funds received during 2006 _______________

Remaining funds (carry over) from 2005 ________________

Balance to be carried over to 2007 __________________

Table 1: Use of funds during 2006*

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: |  |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation and utilization of funds were discussed.

Please report on major activities conducted to strengthen immunization, as well as problems encountered in relation to implementing your multi-year plan.

#### Immunization Data Quality Audit (DQA)

Next* DQA scheduled for _________

*If no DQA has been passed, when will the DQA be conducted?

*If the DQA has been passed, the next DQA will be in the 5th year after the passed DQA

*If no DQA has been conducted, when will the first DQA be conducted?

What were the major recommendations of the DQA ?

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

## YES                              NO

## If yes, please report on the degree of its implementation and attach the plan.

## Please highlight in which  ICC meeting  the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2006 (for example, coverage surveys).

1.1.4. ICC meetings

How many times did the ICC meet in 2006 ? Please attach all minutes.

Are any Civil Society Organizations members of the ICC and if yes, which ones ?

1.2. GAVI Alliance New & Under-used Vaccines Support (NVS)

#### Receipt of new and under-used vaccines during 2006

When was the new and under-used vaccine introduced? Please include change in doses per vial and change in presentation, (e.g. DTP + HepB mono to DTP-HepB) and dates shipment were received in 2006.

| Vaccine | Vials size | Doses | Date of Introduction | Date shipment received (2006) |
| --- | --- | --- | --- | --- |
| Hepatitis B | 2 dose vial |  | September 2002 |  |
| Hepatitis B | 2 dose vial | 147,000 |  | 30.03.2006 |
| AD Syringes |  | 155,500 |  | 11.03.2006 |
| Safety Boxes |  | 1,750 |  | 11.03.2006 |

Please report on any problems encountered.

NO PROBLEMS

#### Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Training: With the WHO Euro support a regional Effective Vaccine Store Management training course was conducted in Moldova involving national vaccine store mangers from 7 countries. Cold Chain: The cold chain inventory was updated covering all primary health care facilities throughout the country. Monitoring and Surveillance: Forms for monitoring vaccination coverage and vaccine stocks/wastage were duplicated and distributed for all health facilities. Vaccination coverage and vaccine stocks were monitored on monthly base at health facility/district/national levels. Case based surveillance was performed for acute Hepatitis B in children, which include laboratory investigation and notification of each case to the national level. A hepatitis B serum -prevalence population based study was initiated to assess the impact of the vaccination toward reducing the burden of disease.

#### Use of GAVI funding entity support (US$100,000) for the introduction of the new vaccine

These funds were received on : 27.06.2002_

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

The financial support (US$100,000) for the introduction of the new vaccine was received on 27 June 2002 at the Treasury account of the National Center of Preventive Medicine. The use of GAVI funds started in September 2003 and included the following activities approved by the MoH and ICC: Repairs at the national vaccine storage and installation of 2 backup autonomous power generators -$17,300, Procurement of computers for the national electronic surveillance system on vaccination coverage -$28,774 Refurbishment and equipment for the national Hib and measles laboratory - $14,165 TOTAL used in 2003 -$60,239 Finalization of the refurbishment at the national vaccine store -$ 2,966 Procurement of computers for the national electronic surveillance system on vaccination coverage -$19,385 Finalization of the refurbishment of the national Hib and measles laboratory. -$ 5,658 Printing of vaccination coverage monitoring reports -$ 863 TOTAL used in 2004 -$28,872 installation of autonomous power generators in 11 district level vaccine stores -$ 9,727 TOTAL used in 2005 -$ 9,727 Office equipment and stationary supplies -$ 1,162 TOTAL used in 2006 -$ 1,162 Balance of funds at the end 2006 -$ 0

    - Effective Vaccine Store Management/Vaccine Management Assessment

The last Effective Vaccine Store Management (EVSM)/Vaccine Management Assessment (VMA) was conducted in 2004

Please summarize the major recommendations from the EVSM/VMA

Pre-shipment and arrival procedures 1. VARs once initiated by the Assistant medical epidemiologist, should be submitted immediately to EPI supervisor for clearance. In principle, this should be completed within 3 days of the arrival. 2. VAR should be fully filled VAR report number may be taken as indicated in the general registry file for all supplies, or alternatively, a sequential new numbering system for VARs should be initiated. 4. In cases where paperwork is not complete (and especially lack of LRC), programme should be more firm with a defined deadline with the supplier to demand missing documents. Maintaining correct storage temperatures 1. It is strongly recommended that guidelines available for power cuts are transferred into a contingency plan and this plan be rehearsed at least once a year. 2. Programme manager is advised to initialize temperature charts and/or temperature monitoring summary sheets when they are reviewed. Buildings, equipment and transport 1. CFC units should be changed to CFC-free by the time of a big repair. 2. Although all intermediate stores are notified regarding pick up period, in order to have manageable volume of operations on a daily basis, it is recommended that intermediate stores are given fine days for pick up. Effective Maintenance 1. Keep preventive maintenance records. 2. Equipment replacement plan should be developed based on performance of units in the country. Effective Stock Management 1. Although diluent records can be found in monthly summary reports, it is strongly recommended that for each diluent a new batch card should be opened. 2. The assessment team also suggests introduction of an inventory control card to supplement current record system. Sample card is given in Annex 2. 3. Diluents should also be registered as a separate product either as a second line in stock registry or in a separate card. 4. The team strongly recommends that a computerized stock control system should be developed. This can be done by introducing new worksheet to the excel tool or alternatively a WHO-developed system could be introduced8. 5. Since there is a potential risk of programme interruption due to late payments, it is strongly recommended that primary series should be given higher priority by the finance department. Reliable delivery to intermediate stores 1. Although distributed quantities can be reviewed through batch records and monthly distribution/inventory forms; the assessment team recommends a copy of issue voucher to be kept at the primary store level. This can easily be done by using the 3rd copy of issue vouchers. Minimize damage during distribution 1. VVM status should be noted on the issue voucher. Standard operating procedures 1. In order to ensure correct practices and sustain quality it is highly recommended that routine procedures be translated into SOP format. 2. Technical content of the wall poster should be carefully reviewed before second printing. Especially sensitivity of vaccines and shake test should be updated according to latest WHO guidelines. Since FW is no longer used by the programme, this section should be removed and replaced with Freeze-tag® Financial and Human Resources 1. Purchase of primary series vaccines should be given highest priority to ensure necessary quantities at all times. 2. Donor assistance should be seeked especially in support of training purposes. 3. One additional technical staff is recommended to be recruited to support the storekeeper.

Was an action plan prepared following the EVSM/VMA : Yes/No

If so, please summarize main activities under the EVSM plan and the activities to address the recommendations.

| Actions | Status |
| --- | --- |
| Pre-shipment and arrival procedures |  |
| 1. VARs once initiated by the Assistant medical epidemiologist, should be submitted immediately to EPI supervisor for clearance. In principle, this should be completed within 3 days of the arrival. | Implemented |
| 2. VAR should be fully filled VAR report number may be taken as indicated in the general registry file for all supplies, or alternatively, a sequential new numbering system for VARs should be initiated. | Implemented |
| 4. In cases where paperwork is not complete (and especially lack of LRC), programme should be more firm with a defined deadline with the supplier to demand missing documents. | Implemented |
| Maintaining correct storage temperatures |  |
| 1. It is strongly recommended that guidelines available for power cuts are transferred into a contingency plan and this plan be rehearsed at least once a year. | Implemented |
| 2. Programme manager is advised to initialize temperature charts and/or temperature monitoring summary sheets when they are reviewed. | Implemented |
| Buildings, equipment and transport |  |
| 1. CFC units should be changed to CFC-free by the time of a big repair. | Under consideration |
| 2. Although all intermediate stores are notified regarding pick up period, in order to have manageable volume of operations on a daily basis, it is recommended that intermediate stores are given fine days for pick up. | Under consideration |
| Effective Maintenance |  |
| 1. Keep preventive maintenance records. | Not implemented. Missing appropriate personnell |
| 2. Equipment replacement plan should be developed based on performance of units in the country. | Plan developed but missing financing |
| Effective Stock Management |  |
| 1. Although diluent records can be found in monthly summary reports, it is strongly recommended that for each diluent a new batch card should be opened. | Implemented |
| 2. The assessment team also suggests introduction of an inventory control card to supplement current record system. Sample card is given in Annex 2. | Not applicable |
| 3. Diluents should also be registered as a separate product either as a second line in stock registry or in a separate card. | Implemented |
| 4. The team strongly recommends that a computerized stock control system should be developed. This can be done by introducing new worksheet to the excel tool or alternatively a WHO-developed system could be introduced8. | Under consideration |
| 5. Since there is a potential risk of programme interruption due to late payments, it is strongly recommended that primary series should be given higher priority by the finance department. | Implemented |
| Reliable delivery to intermediate stores |  |
| 1. Although distributed quantities can be reviewed through batch records and monthly distribution/inventory forms; the assessment team recommends a copy of issue voucher to be kept at the primary store level. This can easily be done by using the 3rd copy of issue vouchers. | Implemented |
| Minimize damage during distribution |  |
| 1. VVM status should be noted on the issue voucher. | Not applicable |
| Standard operating procedures |  |
| 1. In order to ensure correct practices and sustain quality it is highly recommended that routine procedures be translated into SOP format. | under development |
| 2. Technical content of the wall poster should be carefully reviewed before second printing. Especially sensitivity of vaccines and shake test should be updated according to latest WHO guidelines. Since FW is no longer used by the programme, this section should be removed and replaced with Freeze-tag® | Under consideration |
| Financial and Human Resources |  |
| 1. Purchase of primary series vaccines should be given highest priority to ensure necessary quantities at all times. | Implemented |
| 2. Donor assistance should be seeked especially in support of training purposes. | Under consideration |
| 3. One additional technical staff is recommended to be recruited to support the storekeeper. | Not acomplished |

The next EVSM/VMA* will be conducted in : 2009__

*All countries will need to conduct an EVSM/VMA in the second year of new vaccine support approved under GAVI Phase 2.

## 1.3 Injection Safety

#### Receipt of injection safety support

Received in cash/kind

Please report on receipt of injection safety support provided by the GAVI Alliance during 2006 (add rows as applicable).

| Injection Safety Material | Quantity | Date received |
| --- | --- | --- |
| Received in cash | $32,000 | 06 October 2005 |
| Received in cash | $29,000 | 30 December 2005 |

Please report on any problems encountered.

The most difficult step was to engage local production of safety boxes. This process took more than six months. The second issue was related to the length of the bidding process that takes more than 3 months. As a result the safety boxes have been provided only in autumn 2006.

#### Progress of transition plan for safe injections and safe management of sharps waste.

If support has ended, please report how injection safety supplies are funded.

The policy of the Ministry of Health of R. Moldova is that 100% of injections given in both the public and private health sectors for any purpose must be safe. It means that every injection must be given with a sterile single-use syringe and needle, which is then safely disposed of after use. All injectable antigens provided by the national immunization programme (both primary series and boosters) should be given through only auto-disable syringes (ADs). Only ADs should be used during supplemental immunization activities for both children and adults. The Government of Moldova provided $106,769 for procurement of AD syringes and reconstitution syringes in 2006, that covered 100% of all immunization needs. One hundred percent of immunizations in Moldova are conducted using AD syringes. During 2006 all syringes for routine immunizations were procured with funds provided by the Government while GAVI injection safety funds were used for the procurement of Safety boxes. A competition of local producers of safety boxes was accomplished, that allowed achieve a reasonable price per local produced safety box (0.7$/box). Alternative solutions, including recycling, melting etc. of used syringes, are also under consideration. In order to monitor the use of safety boxes at the health facility level an indicator is included in the monthly vaccination reports (no. of used safety boxes per 100 of used syringes). To compare, the value of the indicator was: in 2002 - 0.73, in 2003 - 0.86 in 2004 - 0.83 in 2005 - 0.87 in 2006 – 0.49 During 2003-2005 usage of safety boxes per 100 syringes was more than 0.83, that means almost all immunization syringes were collected properly into safety boxes. The value of the indicator (0.49) in 2006 reflects problems of supply of safety boxes due to delays registered with initiation of the local production of safety boxes. After the supply started, that does not represent more an issue.

#### Please report how sharps waste is being disposed of.

According to the national policy, used injection equipment should be addressed within the context of the National regulation on medical waste disposal. It means that syringes and needles be collected immediately after use, in single-use sharps puncture resistant containers, which are colour coded (yellow), labelled “Biological hazard” and are destructed together with their content. Up to date the achievements of Moldova regarding to the safe disposal of sharp waste produced by the immunization program are as follows: Disposable syringes and needles, including auto-disable and reconstitution syringes, are disposed of immediately following use in a designated safety box or sharps puncture-proof container. The needle is not recapped or removed from the syringe: the whole combination is inserted into the safety box directly after use. A system tracking stocks, the distribution and utilization of injection equipment and safety boxes is introduced countrywide and is integrated in monthly vaccination reports. Additional waste from injections (cap, syringe packaging) are disposed of as common waste. Full safety boxes are incinerated in small numbers by open burning in a pit, iron vessels. These methods of destruction are particularly practiced by small producers of sharp waste (village health centres and posts, small family doctors centres) Residue from incineration (oxidized needles, vials, etc.) are buried in a common waste pit. Possibilities for radical solution of medical waste destruction through building 1-3 plants are explored.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharps waste.

The main problem related to the transition for safe injections and sharps waste disposal is related to the destruction of sharp waste. The current practice of burning safety boxes is not considered environment friendly and is regarded as a temporary solution. Implementation of high temperature incineration is also questionable due to the need of huge investments, problems meeting environment regulations, ensuring sustainability of the process. The safe sharp waste disposal was subject of a number of meetings and workshops involving national and international organizations, NGOs. Possibilities for radical solution of medical waste destruction through building 1-3 plants are explored. That requires important investments and also raises issues related to sustainability of running those facilities. Other options include using autoclaves and shredders. Unfortunately, an agreement was not achieved yet regarding the most cost effective and sustainable solution. Taking into consideration immunization services are integrated in Moldova with primary health care, it is worth mentioning safe disposal of immunization sharp waste must be addressed in the context of disposal of all medical waste produced by health facilities, as it represent only a small fraction of that. Actually there is a need to solve the issue of disposal of all hazardous medical waste generated by health facilities.

#### Statement on use of GAVI Alliance injection safety support in 2006 (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI Alliance injection safety support in the past year:

In 2005 Republic of Moldova has received two instalments of funds (for 2005 and 2006) from the approved GAVI support for injection safety at the Treasury account of the National Center of Preventive Medicine: 1st instalment – 06 October 2005 ($32,000) 2nd instalment - 30 December 2005 ($29,000) Due to the late arrival of funds at the time required to proceed all formal procedures to allow use of funds, funds on injection safety started being used in 2006. The expenditures were as follows: - Initiation of the local production of safety boxes, procurement of safety boxes -$16,699 - Strengthening the information system to monitor stocks and usage/wastage of syringes and safety boxes -$5,541 - Strengthening the laboratory support for infectious diseases following unsafe injections and for those preventable by vaccinations -$6,044 TOTAL expenditures in 2006 – $28,284 Balance for 2007 - $32,716

# 2. 	Vaccine Co-financing, Immunization Financing and Financial Sustainability - NOT APPLICABLE

Important note: Under Phase 2 of the GAVI Alliance, all countries are expected to co-finance the introduction of new vaccines from the start of Phase 2 (except for the introduction of measles second dose into routine immunization). The Annual Progress Report has been modified to help monitor the experiences of countries with the new GAVI Alliance policies of vaccine co-financing. We are asking countries to complete three new tables of information and answer some questions about your experience.

The purpose of Table 2 is to understand trends in overall immunization expenditure and financing context. It provides key updated cMYP information on an annual basis.

Table 3 is designed to help the GAVI Alliance understand country level co-financing of GAVI awarded vaccines - both in terms of doses and in terms of monetary amounts. If your country has been awarded more than one new vaccine in Phase 2 through GAVI Alliance, please complete a separate table for each new vaccine being co-financed.

The purpose of Table 4 is to understand the country-level processes related to integration of co-financing requirements into national planning and budgeting.

Much of the information for all three tables can be extracted from the comprehensive multi-year plan, as well as the country proposal to GAVI, and the confirmation letter from the Alliance. For 2006, the figures recorded should be actual updated expenditures, not projections. Please report for the years till the end of your cMYP. Total co-financing can be calculated with the XL sheet provided for calculating the vaccine request.

| Table 2: Total Immunization Expenditures and Financing Trends in US $ |
| --- |
| Total Immunization Expenditures and Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Immunization Expenditures |  |  |  |  |  |
| Vaccines |  |  |  |  |  |
| Injection supplies |  |  |  |  |  |
| Personnel |  |  |  |  |  |
| Other operational expenditures |  |  |  |  |  |
| Cold Chain equipment |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total Immunization Expenditures |  |  |  |  |  |
| Total Government Health Expenditures |  |  |  |  |  |
| Immunization Financing |  |  |  |  |  |
| Government (incl. WB loans) |  |  |  |  |  |
| GAVI |  |  |  |  |  |
| UNICEF |  |  |  |  |  |
| WHO |  |  |  |  |  |
| World Bank (grant) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Financing |  |  |  |  |  |

| Table 3a: Country Vaccine Co-Financing in US $ |
| --- |
| For 1st GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3b: Country Vaccine Co-Financing in US $ |
| --- |
| For 2nd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 3c: Country Vaccine Co-Financing in US$ |
| --- |
| For 3rd GAVI awarded vaccine. Please specify which vaccine (ex: DTP-HepB) |
| Actual and Expected Country Co-Financing | 2006 | 2007 | 2008 | 2009 | 2010 |
| Total number of doses co-financed by country |  |  |  |  |  |
| Total co-financing by country |  |  |  |  |  |
| Of which by |  |  |  |  |  |
| Government |  |  |  |  |  |
| Basket/Pooled Funding |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Other (please specify) |  |  |  |  |  |
| Total Co-Financing |  |  |  |  |  |

| Table 4: Questions on Vaccine Co-Financing Implementation |
| --- |
| Q. 1: What mechanisms are currently used by the Ministry of Health in your country for procuring EPI vaccines? |
|  | Tick for Yes | List Relevant Vaccines | Sources of Funds |
| Government Procurement- International Competitive Bidding |  |  |  |
| Government Procurement- Other |  |  |  |
| UNICEF |  |  |  |
| PAHO Revolving Fund |  |  |  |
| Donations |  |  |  |
| Other (specify) |  |  |  |
| Q. 2: How have the proposed payment schedules and actual schedules differed in the reporting year? |
| Schedule of Co-Financing Payments | Proposed Payment Schedule | Date of Actual Payments Made in Reporting Year | Delay in Co-Financing Payments |
|  | (month/year) | (day/month) | (days) |
| 1st Awarded Vaccine (specify) |  |  |  |
| 2nd Awarded Vaccine (specify) |  |  |  |
| 3rd Awarded Vaccine (specify) |  |  |  |
| Q. 3: Have the co-financing requirements been incorporated into the following national planning and budgeting systems ? |
|  | Tick for Yes | List Relevant Vaccines |
| Budget line item for vaccine purchasing |  |  |
| National health sector plan |  |  |
| National health budget |  |  |
| Medium-term expenditure framework |  |  |
| SWAp |  |  |
| cMYP Cost & Financing Analysis |  |  |
| Annual immunization plan |  |  |
| Other |  |  |

| Q. 4: What factors have slowed and/or hindered mobilization of resources for vaccine co-financing ? |
| --- |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |
| Q. 5: Do you foresee future challenges with vaccine co-financing in the future? What are these ? |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |
| 5. |  |

3.  	Request for new and under-used vaccines for year 2008

Section 3 is related to the request for new and under-used vaccines and injection safety for 2008.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided. Targets for future years MUST be provided.

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

| Table 5 : Update of immunization achievements and annual targets. Provide figures as reported in the JRF in 2006 and projections from 2007 onwards. |
| --- |
| Number of | Achievements and targets |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 42,383 | 42,356 | 43,203 | 44,067 | 44,728 | 45,399 | 46,080 | 46,771 | 47,473 |
| Infants’ deaths | 522 | 510 | 475 | 485 | 492 | 499 | 507 | 514 | 522 |
| Surviving infants | 41,861 | 41,846 | 42,728 | 43,582 | 44,236 | 44,900 | 45,573 | 46,257 | 46,951 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of DTP (DTP1)* | 40,850^ | 40,320^ | 41,462 | 41,878 | 42,086 | 42,297 | 42,509 | 42,721 | 42,935 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of DTP (DTP3)* | 40,617^ | 39,534^ | 41,251 | 41,664 | 41,872 | 42,081 | 42,292 | 42,503 | 42,716 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 1st dose of Hepatitis B vaccine | 42,084 | 42,356 | 42,352 | 42,775 | 42,989 | 43,204 | 43,420 | 43,637 | 43,855 |
| Infants vaccinated till 2006 (JRF) / to be vaccinated in 2007 and beyond with 3rd dose of Hepatitis B vaccine | 41,171^ | 41,428^ | 41,885 | 42,305 | 42,516 | 42,729 | 42,943 | 43,157 | 43,373 |
| Wastage rate till 2006 and plan for 2007 beyond*** ………….. ( new vaccine) | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% |
| INJECTION SAFETY**** (NOT APPLICABLE) |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated / to be vaccinated with TT | 40264 | 40238 | 40641 |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with BCG | 41266 | 41473 | 42352 |  |  |  |  |  |  |
| Infants vaccinated / to be vaccinated with Measles (1st dose) | 41041 | 40212 | 41462 |  |  |  |  |  |  |

* Indicate actual number of children vaccinated in past years and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

^    These figures represent children vaccinated by the first birthday (by 15 months of age for measles containing vaccine). They do not match the figures reported in the Joint

Reporting Form as the figures from the Joint reporting form are produced based on the birth cohort 12-23 months of age.

  - Confirmed/Revised request for new vaccine (to be shared with UNICEF Supply Division)

for 2008

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

Targets for 2008 were adjusted (slightly lowered) according to the latest trends in the number of births Denominators are changed taking into consideration the latest figures and trends of the birth rate and IMR. During 2001 and 2002 birth rates continued to decrease following the trend of the last 10 years. In 2003 there was observed a small increase (0.6%) of the birth rate comparing to the previous year. In 2004 the number of births has increased significantly (+6.3%) comparing to 2003. In 2005 the birth rate has decreased by 1.7% comparing to 2004 and in 2006 it had the same value asin 2005. Denominator figures for 2007-2013 were updated in order to meet the latest demographical patterns and differ comparing to initial figures submitted in the application form and in previous annual reports. They include a projected annual increase of births by 1.0% for 2007-2009 and of 0.5% for 2010-2013. Vaccination coverage targets for 2007-2013 were updated in order to match projections of births.

#### Please provide the XL sheet for calculating vaccine request duly completed and summarize in table 6 below. For calculations, please use same targets as in table 5.

Table 6.  Estimated number of doses of Hepatitis B vaccine, monovalent, 2 dose vial.

Due to Moldova was not approved yet for GAVI 2nd stage new vaccine support the table below was completed following the previous report model.

Moldova will receive in 2008 the final part of the 150% additional support for 2007 and 2008 provided by GAVI to countries that introduced HepB mono vaccine.

In 2007 the country has received 90%  of the required number of doses.

For 2008 it is expected to receive the 60% balance of the granted support.

The table IS NOT APPLICABLE for Moldova as it was not approved yet for GAVI 2nd stage new vaccine support

| Vaccine : | 2008 | 2009 | 2010 |
| --- | --- | --- | --- |
| Total doses required |  |  |  |
| Doses to be funded by GAVI |  |  |  |
| Doses to be funded by country |  |  |  |
| Country co-pay in US$/dose* |  |  |  |
| Total co-pay |  |  |  |

*As per GAVI co-financing policy, country grouping and order of vaccine introduction

Table 7: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3   Confirmed/revised request for injection safety support for the year 2008 - NOT APPLICABLE

Table 8: Estimated supplies for safety of vaccination for the next two years with …… (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 8a, 8b, 8c, etc. Please use same targets as in Table 5)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. Health Systems Strengthening (HSS) - NOT APPLICABLE

This section only needs to be completed by those countries that have received approval for their HSS proposal. This will serve as an inception report in order to enable release of funds for 2008. Countries are therefore asked to report on any activity in 2007.

# Health Systems Support started in : _________________

Current Health Systems Support will end in : _____________

# Funds received in 2007 : 	Yes/No

If yes, date received : (dd/mm/yyyy)

If Yes, total amount : 	US$ ___________

Funds disbursed to date :  				US$ ___________

Balance of installment left: 				US$ ___________

Requested amount to be disbursed for 2008 	US$ ___________

Are funds on-budget (reflected in the Ministry of Health and Ministry of Finance budget) : Yes/No

If not, why not ? How will it be ensured that funds will be on-budget ? Please provide details.

Please provide a brief narrative on the HSS program that covers the main activities performed, whether funds were disbursed according to the  implementation plan, major accomplishments (especially impacts on health service programs, notably the immunization program), problems encountered and solutions found or proposed, and any other salient information that the country would like GAVI to know about. More detailed information on activities such as whether activities were implemented according to the implementation plan can be provided in Table 10.

Are any Civil Society Organizations involved in the implementation of the HSS proposal ? If so, describe their participation?

In case any change in the implementation plan and disbursement schedule as per the proposal is requested, please explain in the section below and justify the change in disbursement request. More detailed breakdown of expenditure can be provided in Table 9.

Please attach minutes of the Health Sector Coordinating Committee meeting(s) in which fund disbursement and request for next tranche were discussed. Kindly attach the latest Health Sector Review Report and audit report of the account HSS funds are being transferred to. This is a requirement for release of funds for 2008.

| Table 9. HSS Expenditure in 2007 (Please fill in expenditure on HSS activities and request for 2008. In case there is a change in the 2008 request, please justify in the narrative above) |
| --- |
| Area for support | 2007 (Expenditure) | 2007 (Balance) | 2008 (Request) |
| Activity costs |  |  |  |
| Objective 1 |  |  |  |
| Activity 1.1 |  |  |  |
| Activity 1.2 |  |  |  |
| Activity 1.3 |  |  |  |
| Activity 1.4 |  |  |  |
| Objective 2 |  |  |  |
| Activity 2.1 |  |  |  |
| Activity 2.2 |  |  |  |
| Activity 2.3 |  |  |  |
| Activity 2.4 |  |  |  |
| Objective 3 |  |  |  |
| Activity 3.1 |  |  |  |
| Activity 3.2 |  |  |  |
| Activity 3.3 |  |  |  |
| Activity 3.4 |  |  |  |
| Support costs |  |  |  |
| Management costs |  |  |  |
| M&E support costs |  |  |  |
| Technical support |  |  |  |
| TOTAL COSTS |  |  |  |

| Table 10. HSS Activities in 2007 (Please report on activities conducted in 2007) |
| --- |
| Major Activities | 2007 |
| Objective 1: |  |
| Activity 1.1: |  |
| Activity 1.2: |  |
| Activity 1.3: |  |
| Activity 1.4: |  |
| Objective 2: |  |
| Activity 2.1: |  |
| Activity 2.2: |  |
| Activity 2.3: |  |
| Activity 2.4: |  |
| Objective 3: |  |
| Activity 3.1: |  |
| Activity 3.2: |  |
| Activity 3.3: |  |
| Activity 3.4: |  |

| Table 11. Please update baseline indicators. Add other indicators according to the HSS proposal. |
| --- |
| Indicator | Data Source | Baseline Value | Source | Date of Baseline | Target | Date for Target |
| 1. National DTP3 coverage (%) |  |  |  |  |  |  |
| 2. Number / % of districts achieving ≥80% DTP3 coverage |  |  |  |  |  |  |
| 3. Under five mortality rate (per 1000) |  |  |  |  |  |  |
| 4. |  |  |  |  |  |  |
| 5. |  |  |  |  |  |  |
| 6. |  |  |  |  |  |  |

Please describe whether targets have been met, what kind of problems have occurred in measuring the indicators, how the monitoring process has been strengthened and whether any changes are proposed.

# 5.	Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission |  |  |
| Reporting Period (consistent with previous calendar year) | Yes |  |
| Government signatures |  |  |
| ICC endorsed |  |  |
| ISS reported on | Not Applicable |  |
| DQA reported on | Not Applicable |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| Immunisation Financing & Sustainability Reported on (progress against country IF&S indicators) | Not Applicable |  |
| New Vaccine Request including co-financing completed and XL sheet attached | Yes (No co-financing) |  |
| Revised request for injection safety completed (where applicable) | Not Applicable |  |
| HSS reported on | Not Applicable |  |
| ICC minutes attached to the report | Not Applicable |  |
| HSCC minutes, audit report of account for HSS funds and annual health sector evaluation report attached to report | Not Applicable |  |

6.  	Comments

ICC/HSCC comments:

No comments

~ End ~

# Footnotes

If baseline data is not available indicate whether baseline data collection is planned and when

Important for easy accessing and cross referencing

# Text boxes

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided

- Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in a 2-dose vial, 5% for any vaccine in 1 dose vial liquid.

- Buffer stock: The buffer stock is recalculated every year as 25% the current  vaccine requirement

- Anticipated vaccines in stock at start of year 2008: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock.  Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines.

- AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines.

- Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines.

- Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes