12 May, 2006

Progress Report

Partnering with The Vaccine Fund

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: Mongolia Date of submission: 12 May, 2006 Reporting period: 2005 ( Information provided in this report MUST refer to 2005 activities ) ( Tick only one ) : Inception report  First annual progress report  Second annual progress report  Third annual progress report  Fourth annual progress report  Fifth annual progress report  Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

According to the Health Minister’s order no. 213 from September 2004, from 2006 the new vaccine will be started to cover Umnugovi, Bulgan, Dornod, Sukhbaatar, Govi-Altai, Tuv, Orkhon and Uvs aimag, from 2007 to 2008 all the rest aimags. In 2008 the pentavalent vaccine will be introduced all over the country. In the frame of preparational work following activities have been done: - Conducted a training of pentavalent vaccine among 490 health workers and nurses in the above mentioned 8 aimags. - “About Pentavalent vaccine” guidelines for parents was developed and distributed. - ”Immunization guidebook ” have been renewed and distributed to new parents of 8 aimags. - Renewed immunization card, immunization coverage forms were introduced and distributed to provinces and Ulaanbaatar. - 44400 dose of Pentavalent vaccine, 436500 AD syringes were distributed. - Out of 15359 children 15308 were administered 1 doses. (Immunization coverage 99.7% - Out of 12615 children 12526 were administered 3 doses of Pentavalent vaccine (Immunization coverage 99.3%) for the last 2005 year. - No AEFI were registered after Pentavalent vaccine introduction in the last year. - 78.7% of parents were obtained appropriate information on Pentavalent vaccine - Improved feedback of family doctors and AEFI, to fill in surveillance forms - Recommendation on Pentavalent vaccine, immunization guidebooks have been distributed to every new child - Developed ”Multi year plan 2006-2010” by the National Immunization Program of the National Center for Communicable Disease supported by MoH, WHO and UNICEF and international partners, JICA and GAVI. Main goal of this plan is to ensure high quality and maintain high coverage of immunization, in order to reduce child mortality and improve child health by controlling or eliminating all vaccine preventable diseases targeted by the National Immunization Program of National Center for Communicable Diseases, Ministry of Health of Mongolia. During the period of preparation the Inter Agency Coordinating Committee ( ICC ) meeting were held third times. ( Minutes taken from these meetings are attached). Main topics discussed during the first meeting are: - Progress report of Pentavalent vaccine introduction into routine immunization in the selected areas - Presentation on “Improvement of vaccination coverage againts Hep B by administering birth dose within 24 hours” Main agenda of the second meeting is: - Project activities of Safe immunization and injection practices in Mongolia. - Introduction of Multi year plan 2006-2010. Main agenda of the third meeting is: - Data Quality Self-assessment, findings and recommendations - National immunization Days, Preliminary plan Some main comments, given by ICC members are: - According to the National Immunization schedule Hepatitis B vaccine birth dose was given within 24-48 hours in 1991. The MOH new requirement for birth dose hepatitis B vaccine administration within 24 hours has been implemented from September, 2004 and national coverage for birth dose has reached 83% by national reporting form. The form (from sum to aimag, from aimag to National center for communicable diseases, from district to NCCD through Ulaanbaatar EPI manager) has changed with accurate time within 24 hours. However registration forms of birth dose at delivery house or routine vaccine form was not reflect only 24 hours. There is difficult to monitor data of reporting system and registration form. Therefore UNICEF, EAPRO approved short term project to strengthening hepatitis B immunization program with insuring the quality of vaccine for immunization, cold chain system and birth dose administration witin 24 hours. - Increasing the Government commitment gradually through annual increases in the Immunization Fund. - Increasing commitments from local authorities for capital maintenance. - Identifiying an alternative multi lateral or bi lateral donor. Following comments have been done: - Any changes of the introduction plan should be discussed by ICC - To reflect the financial sustainability plan of supply of pentavalent vaccine and AD syringes after GAVI - Expanded administration of birth dose of vaccines within 24-48 hours ( according to National Schedule ) into within 24 hours In 2005, the immunization activities funded by the National Immunization Fund there were 318,000 doses of BCG on 64,376,470 tugrugs, 244,000 doses of polio vaccine on 68,747,000 tugrugs, 447,280 syringes on 26,465,460 tugrugs have been purchased (27 % of all budget for EPI antigens), respectivily. Encountered problem: - Financing of pentavalent vaccine after 2010. It is recommended that the Government of Mongolia develop a co finincing of pentavalent vaccine from 2011. - Financing gaps of cold chain equipment and maintenance costs.

#### 1.1.2	Use of Immunization Services Support

In 2005, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005 _ 390,912  US $_______

Remaining funds (carry over) from 2004 ___No__

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PUBLIC SECTOR |  |  | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 361,440 | 201,600 | 159,840 |  |  |
| Injection supplies | 9,472 | 6,676 | 2,796 |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training | 12,000 |  | 12,000 |  |  |
| IEC / social mobilization | 6,000 |  | 6,000 |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation | 2,000 |  | 2,000 |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other ( equipment for training) |  |  |  |  |  |
| Total: | 390,912 | 208,276 | 182,636 |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

- Major activities, conducted to strengthen immunization: - Identification of barriers in immunization - Organization of the National Workshop on “Reach every soum, bag and district” - Completion of the training for hospital staff and voluntary activists on EPI in Convergent Basic Social Services targeted soum / districts where UNICEF provides technical and financial support - Development a special training programme on maintenance and use of cold chain equipment - Create a special programme of immunization data software - Improvement of hospital wastage management - Conducted to repair of cold chain broken equipment and procurement needed equipment - Fitted up of immunization room, waiting-room, consultation room, vaccination room, WC, allowed the creation of favourable environment for children and parents in selected areas - Conducted to administrate hepatitis B vaccine within 24 hours after birth 2. Research - Conducting of Administrate hepatitis B vaccine within 24 hours after birth in Orkhon, Darkhan, Selenge aimags. - Conducting of cold chain equipment temperature 3. Problems - Weak of registration procedure of primary in the soum and bag levels - Lack of health workers’s knowledge on administration hepatitis B vaccine within 24 hours after birth - Lack of knowledge on using vaccine transportation and cold chain monitoring - Lack of immunization waste management and safety immunization at aimag and soum level

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

.√

YES                              NO

## If yes, please report on the degree of its implementation.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

During Jan-Mar of 2005 in Ulaanbaatar, Govi-sumber and Dornogovi aimags have been using random survey methods, survey was conducted among 176 children under one years of age. According to this survey, the coverage of pent vaccine was 96,0%.

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH       Jan       YEAR   2006

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

| Tritanrix (HB ) GlaxoSmithKline Biologicals s.a. Rixensart-Belgium - 52600 human doses Combained vaccineDTPw-HB ( 2 x 0.5 ml Dose/Dosis ) Hiberix SmithKline Beecham GlaxoSmithKline Biologicals s.a. Rixensart-Belgium-52600 human doses Haemophilus influenzae type b (Hib) vaccine ( 2 x 0.5 ml Dose/Dosis ) There were not any problems during the receiving these vaccines. |  |
| --- | --- |

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

| 1. Preparation of introduction of pentavalent vaccine - Pentavalent vaccine introduction order has been released by the director of Health departments of Umnugovi, Bulgan, Dornod, Sukhbaatar, Govi-Altai, Tuv, Orkhon and Uvs aimags. 2. Preparation of introduction of pentavalent vaccine 2.1 Safe injection - Procurement of safe immunization equipments Umnugovi, Bulgan, Dornod, Sukhbaatar, Govi-Altai, Tuv, Orkhon and Uvs aimags. - Introduction of AD syringes into EPI program at nationwide. - Developed the guidelines on safe injection technique and using of AD syringes and distributed. - The Health Unit of Bayanzurkh and Songinokhairkhan districts, as well as the National Center for Communicable Disease by order number 120 of 2005 of the Health Minister an immunization room was fitted by providing these rooms with canon, TV, DVD, projector, digital photo camera, table and chair set, computer set, display, 29 inch TV etc. for training purposes. - In order to improve of hospital wastage were carried out an experiment that allowed to create newly in Mongolia a voque ECOMO-05 incinerator. The incinerator receipt commission appointed by order number 121 of 2005 of the Health Minister had accepted the ECOMO-05 and to be received to the 2 Health centre of UB city. - The training program on Technical data, exploitation safety, operational rule, principle and instruction was prepared by professional engineers and technicians. According to present program, a training was successfully organized on June 16, 2005 among 35 immunization medical assistants of 21 aimags and 9 districts of capital. - Fitted up of immunization room, waiting-room, consultation room, vaccination room, WC, allowed the creation of favorable environment for children and parents. 2.2 Procurement of pentavalent vaccine, needed for 2006 and it’s distribution to the second phase sites. The instruction of pentavalent vaccine has been translated into Mongolian and distributed to all immunization units. In the second phase Umnugovi, Bulgan, Dornod, Sukhbaatar, Govi- Altai, Tuv, Orkhon and Uvs aimags were procured by pentavalent vaccine. Distribution of vaccines has quarterly based to the provinces. 2.3 Cold chain - The cold chain capacity in second phase introduction area has been evaluated the readiness for receiving vaccines has been provided. - Prepared a special training program on maintenance and use of cold chain equipment and a day training for 35 medical assistants was organized. - Repaired 15 of cold chain broken equipment and refrigerators in Darkhan, Orkhon, Selenge aimags. - Conducted of study on cold chain temperature and monitoring by the tiny talk 2.4 Report forms: - Immunization cards and coverage data reporting forms have been updated to reflect the addition of pentavalent vaccine - Other related reporting forms are revised - In order to complete a general database of children attended immunization in whole Mongolia, to amalgamate and work up reports connected with immunizations was issued a directive for processing of immunization data software. - The program was invented which was installed in computers of 21 aimags and 6 districts and a work was organized to connect immunization computers to the internet. 2.5Training and advocacy: - Conducted workshop on ”Introduction of pentavalent vaccine into the National EPI “ in 8 aimags among the health managers and workers ( 320 ). - Training of vaccinators ( 170 people ) - 165 health workers trained on Safe Immunization practices /use of AD syringes and safety box/. - “Voluntary activists training” was organized among 450 voluntary activists in 8 aimags. - Some necessary equipment for the training have been purchased - Developed, printed and distributed the guideline “Pentavalent vaccine” for medical workers ( 3000 copies) - Printed and distributed the leaflet for parents about pentavalent vaccine ( 32000 copies ) - Broadcasting of announcements by radio ( 90 times ) and TV ( 48 times ) - For purpose of improving knowledge and skills of doctors majoring in immunization, increase the availability of training appliances, were printed 1000 pieces of guide-books and 2000 pieces of Income and expenses daily accounting of immunization for nurses by distributing them to immunization teams and doctors of all aimags and capital. As a result of training were increased the knowledge of medical workers by 28%. | . |
| --- | --- |

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

Training – 12,000 US $ IEC/Socail mobilization-6,000 US $ Monitoring and evaluation- 2,000 US $

## Injection Safety

#### 1.2.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

In 2005, the following procurement of safety equipment has done in accordance with implementation of immunization programm AD syringes for BCG -61,300 pcs AD syringes for penta and other vaccines- 528,900 pcs Reconstitution syringes for BCG – 6,300 pcs Reconstitution syringes for pentavaccine – 29,900 pcs reconstitution syringes for measles- 9,700 pcs Safety boxes – 7,100 pcs

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

#### AD syringes are used for all immunization vaccines starting from January, 1, 2005. Now days we have distributed 436500 ps of AD syringes. Used AD syringes are wasted into the safety boxes and destroying open burning with making of protocols. In the frame of the safe immunization project, there is project of installation of incinerators has been implementing and its installation in. The training on safe immunization technique have been conducted among 490 medical workers .

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage of DTP-3 vaccine Proportion of immunization units with adequate supply of injection safety equipment Vaccine wastage rate DTP | 95% 100% 1,6 | 99% 100% 1,7 |  |  |

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/ The Vaccine Fund injection safety support in the past year:

For the Training as total there was the amount of 12,000 US $ been spent Outputs of the training: - Adopted the knowledge about the immunization activity and particularly pentavalent vaccine among the decision makers - Upgrading the knowledge in safety injection and injection technique in accordance with introduction of pentavalent vaccine. - Improvement of the activity of health volunteers Communication advocacy and Manual and guidelines 6000 US $ 1,500 copies of brochures with laws, programs, orders and instructions on Immunization have been printed and distributed to Health workers during the training, 3,000 copies of guidelines on “ The pentavalent vaccine” developed and printed, 32,000 copies of the manual for parents have been printed, a leaflet “ The pentavalent vaccine for your child” have been printed as well. 20,000 “ Immunization certificate on full immunization has been printed and distributed to parents / when their’ child received first dose of vaccine at the Health Center.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan . Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Financial sustainability plan of immunization activity included as part of Mongolia EPI programme Multy Year Plan for 2006-2010. These recommendations were developed following planning and costing for the national immunization program in September 2005. Recommendations for implementation cover 5 areas. - Linking the MYP to the Master Health Plan Budgeting and Planning Systems - Developing planning Structure and Function at Central Program Level - Monitoring of Planning Outcomes - Mobilizing resources for planning implementation - Increasing program efficiency

Subsequent Progress Reports:	According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources. Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for ………….  (new vaccine)) for each new vaccine.

| Proportion of vaccines supported by * | Annual proportion of vaccines |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 |
| A: Proportion funded by GAVI/VF (%)*** | 25 | 50 | 75 | 100 | 100 | 100 | 50 | - | - | - |
| B: Proportion funded by the Government and other sources (%) | - | - | - | - | - | - | 50 | 100 | 100 | 100 |
| C: Total funding for DTP+HepB+ Hib (new vaccine) | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Number of | Achievements and targets |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS | 43445 | 45815 | 46824 | 47854 | 48907 | 49983 | 51082 | 52206 | 53355 |
| Births | 44461 | 46917 | 47950 | 49005 | 50083 | 51185 | 52311 | 53462 | 54638 |
| Infants’ deaths | 1016 | 1102 | 1126 | 1151 | 1176 | 1202 | 1229 | 1256 | 1283 |
| Surviving infants | 43445 | 45815 | 46824 | 47854 | 48907 | 49983 | 51082 | 52206 | 53355 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 42691 | 27981 | 18878 | 9174 | - | - | - | - | - |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 43043 | 31644 | 18454 | 8969 | - | - | - | - | - |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* DTP+HepB+ Hib (new vaccine) | - | 15308 | 26610 | 37130 | 47152 | 48691 | 49763 | 50857 | 51976 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP+HepB+ Hib ( new vaccine) | - | 12526 | 26497 | 36971 | 46950 | 48483 | 49550 | 50640 | 51754 |
| Wastage rate in 2005 and plan for 2005 beyond*** DTP+HepB+ Hib . ( new vaccine) | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 | 1.11 |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with TT2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 43406 | 44613 | 46032 | 47045 | 48080 | 49649 | 50742 | 51858 | 52999 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 44064 | 42258 | 44951 | 45940 | 46950 | 47983 | 49039 | 50118 | 51220 |

* Indicate actual number of children vaccinated in 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

- Under we have mentioned some changes in baseline targets and wastage rates. - The birth in 2005 was less than estimated. - The vaccine wastage factor was 1.7 in 2005. The reason is: 93% were wasted according to open vial policy. In order to reduce the vaccine wastage rate, on January 1, 2005 has been approved the Health Minister’s order no. 242 with the some changes in open vial policy, e.g. open vaccines might be used for up to a week, exept reconstituted vaccines.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2006

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

No

Table 4: Estimated number of doses of DTP+HepB+ Hib vaccine (specify for one presentation only): Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

Remarks

- Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided - Wastage of vaccines: Countries are expected to plan for a maximum of 50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. - Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement - Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. - AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. - Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. - Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes

#### 3.3	Confirmed/revised request for injection safety support for the years 2007-2008

3.4 Table 6: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

3.5. Table 7: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

  - Table 8: Estimated supplies for safety of vaccination for the next two years with measles (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.6. Table 9: Estimated supplies for safety of vaccination for the next two years with  HepB -birth dose/(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.7. Table 10: Estimated supplies for safety of vaccination for the next two years with  HepB –doses 2-3(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

3.7. Table 11: Estimated supplies for safety of vaccination for the next two years with  DT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

If quantity of current request from the GAVI letter of approval, please present the justification for that difference.

No

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage pentavalent vaccine Vaccine wastage | 95,0% 1.11 | 99,3% 1,11 |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | 12. May.2006 |  |
| Reporting Period (consistent with previous calendar year) | 2005 |  |
| Table 1 filled-in | √ |  |
| DQA reported on |  |  |
| Reported on use of 100,000 US$ | √ |  |
| Injection Safety Reported on | √ |  |
| FSP Reported on (progress against country FSP indicators) |  |  |
| Table 2 filled-in | √ |  |
| New Vaccine Request completed | √ |  |
| Revised request for injection safety completed (where applicable) |  |  |
| ICC minutes attached to the report | √ |  |
| Government signatures | √ |  |
| ICC endorsed | 12.May. 2006 |  |

6.  	Comments

ICC/RWG comments:

Main topics discussed during the first meeting are: - Progress report of Pentavalent vaccine introduction into routine immunization in the selected areas - Presentation on “Improvement of vaccination coverage againts Hep B by administering birth dose within 24 hours” Main agenda of the second meeting is: - Project activities of Safe immunization and injection practices in Mongolia. - Introduction of Multi year plan 2006-2010. Main agenda of the third meeting is: - Data Quality Self-assessment, findings and recommendations - National immunization Days, Preliminary plan Some main comments, given by ICC members are: - According to the National Immunization schedule Hepatitis B vaccine birth dose was given within 24-48 hours in 1991. The MOH new requirement for birth dose hepatitis B vaccine administration within 24 hours has been implemented from September, 2004 and national coverage for birth dose has reached 83% by national reporting form. The form (from sum to aimag, from aimag to National center for communicable diseases, from district to NCCD through Ulaanbaatar EPI manager) has changed with accurate time within 24 hours. However registration forms of birth dose at delivery house or routine vaccine form was not reflect only 24 hours. There is difficult to monitor data of reporting system and registration form. Therefore UNICEF, EAPRO approved short term project to strengthening hepatitis B immunization program with insuring the quality of vaccine for immunization, cold chain system and birth dose administration witin 24 hours. - Increasing the Government commitment gradually through annual increases in the Immunization Fund. - Increasing commitments from local authorities for capital maintenance. - Identifiying an alternative multi lateral or bi lateral donor. Following comments have been done: - Any changes of the introduction plan should be discussed by ICC - To reflect the financial sustainability plan of supply of pentavalent vaccine and AD syringes after GAVI - Expanded administration of birth dose of vaccines within 24-48 hours ( according to National Schedule ) into within 24 hours