2005

Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

COUNTRY: DEMOCRATIC SOCIALIST REPUBLIC OF SRI LANKA

Date of submission: May 2006 Reporting period: 2005 ( Tick only one ) : Inception report ( First annual progress report ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report ( Text boxes supplied in this report are meant only to be used as guides. Please feel free to add text beyond the space provided. *Unless otherwise specified, documents may be shared with GAVI partners and collaborators

# Progress Report Form:  Table of Contents

# Report on progress made during 2005

  - Immunization Services Support (ISS)

1.1.1	Management of ISS Funds

  - Use of Immunization Services Support

1.1.3	Immunization Data Quality Audit

  - GAVI/Vaccine Fund New and Under-used Vaccines

1.2.1	Receipt of new and under-used vaccines

1.2.2	Major activities

    - Use if GAVI/The Vaccine Fund financial support (US$100,000) for introduction of the new vaccine

1.3	Injection Safety

    - Receipt of injection safety support

    - Progress of transition plan for safe injections and safe management of sharps waste

    - Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

2.  Financial Sustainability

3.  Request for new and under-used vaccine for 2007

  - Up-dated immunization targets

  - Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for year…

  - Confirmed/revised request for injection safety support for the year…

- Please report on progress since submission of the last Progress Report based on the indicators

selected by your country in the proposal for GAVI/VF support

5.  Checklist

6.  Comments

7.  Signatures

# 1.  	Report on progress made during 2005

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

## Immunization Services Support (ISS)

#### 1.1.1	Management of ISS Funds

Please describe the mechanism for management of ISS funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

Please report on any problems that have been encountered involving the use of those funds, such as delay in availability for programme use.

Not Necessary to fill, as advised by the GAVI Review Report July 2004.

#### 1.1.2	Use of Immunization Services Support

In 2004, the following major areas of activities have been funded with the GAVI/Vaccine Fund Immunization Services Support contribution.

Funds received during 2005

Remaining funds (carry over) from 2004

Table 1: Use of funds during 2005

| Area of Immunization Services Support | Total amount in US $ | AMOUNT OF FUNDS |
| --- | --- | --- |
|  |  | PUBLIC SECTOR | PRIVATE SECTOR & Other |
|  |  | Central | Region/State/Province | District |  |
| Vaccines | 568,000 |  |  |  |  |
| Injection supplies | 211,500 |  |  |  |  |
| Personnel |  |  |  |  |  |
| Transportation |  |  |  |  |  |
| Maintenance and overheads |  |  |  |  |  |
| Training |  |  |  |  |  |
| IEC / social mobilization |  |  |  |  |  |
| Outreach |  |  |  |  |  |
| Supervision |  |  |  |  |  |
| Monitoring and evaluation |  |  |  |  |  |
| Epidemiological surveillance |  |  |  |  |  |
| Vehicles |  |  |  |  |  |
| Cold chain equipment |  |  |  |  |  |
| Other …………. (specify) |  |  |  |  |  |
| Total: | 779,500 |  |  |  |  |
| Remaining funds for next year: |  |  |  |  |  |

*If no information is available because of block grants, please indicate under ‘other’.

Please attach the minutes of the ICC meeting(s) when the allocation of funds was discussed.

Please report on major activities conducted to strengthen immunization, as well as, problems encountered in relation to your multi-year plan.

Strengthening Vaccine storage /Transport facility (a) Central Level Ministry of Health has taken steps to build a central cold room complex and construction work has just been completed in December 2005. There was substantial delay in construction due to many unavoidable logistic issues. Once the contractor has handed over the building to the Department of Health, cold rooms will be installed with the support of UNICEF. It is expected that this will be functioned by mid 2006 and will save money by avoiding vaccine storage in private cold stores. Steps have been taken to strengthen the central level vaccine delivery activities. Two new vaccine transport vehicles with more delivery capacity will be added to the transport fleet. One vehicle will be donated by the World Bank and the other will be purchased under the GAVI 100,000 US$ for which the tenders are been processed. (b) District Level With the support of UNICEF cold rooms were planned to be installed in fourteen (14) Regional Medical Supply Divisions (including 8 Tsunami affected districts) to strengthen the cold store facility and nine (09) generators will be provided. Vaccine transport vehicles were provided to six RMSDs to ensure the vaccine delivery from district (RMSD) to divisions (MOH). ( c) Divisional Level Tsunami affected health care facilities were provided with necessary logistic facilities by the Government, local NGO and International agencies (including WHO, UNICEF and World Bank) to ensure delivery of immunization service without any interruption. Strengthening Injection Safety Practices The Government of Sri Lanka has taken a policy decision to replace AD syringes for all immunizations in the country. In 2005 only AD syringes were used in the immunization practice. In addition to the GAVI supply of injection safety items, the Government of Sri Lanka has procured the balance requirement for the country. Improving the quality of immunization Services It has been proposed to improve the quality of immunization services in the country, in 2005-2009 with the support of World Bank funded Health Sector Development Project with 1.3 million US$. Major component of this project is to improve the infrastructure and other logistic facilities to provide the immunization service, setting model immunization and child & mother well being clinics in all 271 health divisions and to the training of staff in EPI services. Planning activities have already been completed and training has been started at the last quarter of 2005. National cold chain assessment was done by an international team with the support of local experts. This was funded by the UNICEF. ( Annexure I ) With the support of UNICEF, regional workshops on maintenance of cold chain and enhancing AEFI surveillance were conducted in 06 districts including north-east province. This will be continued in 2006. The total funds allocated for this is around 7000 US$. Disease surveillance reviews had been conducted in all tsunami affected districts, covering the EPI services. WHO has provided the funds for these reviews.

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

Has a plan of action to improve the reporting system based on the recommendations from the DQA been prepared?

If yes, please attach the plan.

## YES                              NO

## If yes, please report on the degree of its implementation.

It was plan to carry out immunization data quality assessment in 2005 with the support of WHO and WB funds. However, this was postponed due to the increased workload of central and district level EPI managers due to the post tsunami activities.

## Please attach the minutes of the ICC meeting where the plan of action for the DQA was discussed and endorsed by the ICC.

Please report on studies conducted regarding EPI issues during 2005 (for example, coverage surveys).

## GAVI/Vaccine Fund New & Under-used Vaccines Support

#### 1.2.1	Receipt of new and under-used vaccines during 2005

Start of vaccinations with the new and under-used vaccine:           MONTH - January           YEAR - 2003

Please report on receipt of vaccines provided by GAVI/VF, including problems encountered.

Phase I of the GAVI funded Hepatitis B immunization programme was started in January 2003 covering 3 provinces of the country and Phase II was started in January 2004 covering another 3 provinces. In 2005 entire country was covered. Sri Lanka received 1,509,100 doses (1, 131, 800 doses in 10 doses vials and 377,300 doses in 2 doses vials) as requested for 2005. All vaccines arrived without any delay and were in good condition. UNICEF is coordinating this activity between GAVI and Ministry of Health, Sri Lanka. These vaccines were distributed to the regional and divisional centres in time without any significant disturbance.

#### 1.2.2	Major activities

Please outline major activities that have been or will be undertaken, in relation to, introduction, phasing-in, service strengthening, etc. and report on problems encountered.

Vaccine distribution to the DDHS/MOH/Health Unit/Hospital Regional Medical Supply Division (RMSD) storekeepers distribute vaccines to all DDHS/MOOH and hospitals under cold chain conditions. RE/MO (MCH) have given the estimated amount of vaccine (maximum 2 months supply) to be distributed to the MOOH offices. RE and MO (MCH) supervise these activities. After evaluation of the vaccine stock returns received from the MOOH/DDHS, RMSD, the storekeeper will supply the new stocks to the MOOH/DDHS in consultation with RE/MO (MCH) in the division. Monitoring of cold chain and inventory control will be done in all stages according to the guidelines given by the Central Epidemiology Unit. All Officers in-charge / Store keepers at all RMSD were given training on cold chain management including storage and documentation in order to enhance the service delivery. This was funded by UNICEF. Monitoring and Evaluation Close monitoring, supervision and evaluation of the EPI is important for the sustenance of the programme. Presently used EPI indicators i.e. vaccine coverage, vaccine wastage and rate of AEFI is used for this purpose. Monitoring of hepatitis B immunization coverage, vaccine wastage and adverse events reported following hepatitis B immunization is done at DDHS/MOH level and at district level. Epidemiological Unit is responsible for monitoring at national level as for other EPI antigens. EPI reviews were conducted in 18 districts during in 2005.

#### 1.2.3	Use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

Please report on the proportion of 100,000 US$ used, activities undertaken, and problems encountered such as delay in availability of funds for programme use.

ICC has closely monitored the progress of utilization of 100,000 US$ and reviewed it at each ICC meetings held in the year. ( Annexure II: Expenditures of GAVI 100,000 US$) Strengthening Vaccine delivery At present the EPI programme spends around 1.5% of its total cost for vaccine transport. The cost for the above activities at central level could be reduced by reorganizing the present vaccine transport / distribution from the central to the districts. Therefore it was identified to purchase a new vaccine delivery vehicle with more vaccine delivery capacity. As identified unspent money of 100,000 US$ was available, ICC has granted approval to utilize this money for purchasing a vaccine delivery vehicle. At present, it is following the government tender procedure, and handled by the transport division, MoH. The purchasing process was expected to be completed in 2005, but has been delayed due to the lengthy government procedure. It is expected that this could be finalised in 2006.

## Injection Safety

#### 1.3.1	Receipt of injection safety support

Please report on receipt of injection safety support provided by GAVI/VF, including problems encountered

Sri Lanka has received injection safety supplies as requested for 2005. ( 0.5ml AD syringes 3,867,100, BCG AD syringes 427,200, Reconstitution syringes 5ml 65,100, 2ml 40,700 and 48, 875 safety boxes) All injection safety supplies have been arriving without any delay, according to the shipment schedule. UNICEF is coordinating this activity between GAVI and the Ministry of Health, Sri Lanka. These supplies have been distributed to the regional and divisional centres in time. There was a consignment of 0.5ml AD syringes ( DESTRO JET) of 249,100 (GAVI (PO 50020962, B/L CPHZ0/3175), which was bulk packed ( 100 AD syringes in one pack). This type of AD syringes may be good for mass immunization programmes, but the Epidemiology Unit of Sri Lanka does NOT recommended these bulk packed AD syringes for routine EPI programme in the country. Sri Lanka has informed GAVI and UNICEF, that bulk packed AD syringes will NOT be used in the country as Sri Lanka is not satisfied with the bulk packing and made a request, that only single blister or paper packed AD syringes be provided in future. ( Annexure III) MoH has purchased AD syringes for all immunizations, which are not covered by the GAVI funding. Hence, at present Sri Lanka is exclusively using AD syringes in its EPI programme. Used AD syringes after collection into the safety boxes are burned or buried at a suitable place. Even though it was earlier planned to construct incinerators in all districts to burn used AD syringes, this has not materialised due to unforeseen reasons.

#### Progress of transition plan for safe injections and safe management of sharps waste.

#### Please report problems encountered during the implementation of the transitional plan for safe injection and sharp waste

Disposal of the used injection items still remains an unsolved problem in the country. There were many discussions, and proposals to provide incinerators in districts. (Under the World Bank project, it was proposed to construct incinerators in all district hospitals for waste disposal.) However, the new development shows that the WB is not supporting the provision of incinerators as a policy. At present the country is practising the burning and burial of the used injections at identified sites. However, Sri Lanka plans to carry out a pilot project on recycling of used injection materials (syringes) and looking for donor (GAVI?) support for the planned project.

Please report on the progress based on the indicators chosen by your country in the proposal for GAVI/VF support.

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Coverage Hep B Wastage Hep B AEFI | >90% 15% Zero Injection related adverse events following Immunizations | Phase I Areas - 2005 Hep B I > 95% Hep B III > 95% Phase II Areas - 2005 Hep B I > 95% Hep B III >95% Phase III areas - 2005 Hep B I > 90% Hep B III > 65% Sri Lanka - 2005 Hep B I - 93.5% Hep B III – 86.7% 10% In Sri Lanka, there is a surveillance system for AEFI. It has shown, that the areas where AD syringes have been introduced, the Injection related adverse events following Immunizations have significantly dropped. A survey done in one district is supporting the AEFI surveillance findings. | Our programme started in 2003 and was phased for 3 years. In phase III areas, the cohort to receive Hep B III is possible only from May 2005. (I st dose in Jan at the age of 2 months, II nd dose in March at the age of 4 months and III rd dose in May at the age of 6 months). It is necessary to follow an entire birth cohort with all 3 doses for one whole year to assess the coverage for Hep B III. This is the reason for the low coverage for Hep B III in PHASE III areas and in the country. Sri Lanka is using two presentations of Hep B vaccine: 2 & 10 doses vials. Available information suggested that the wastage for 2 doses vials is less than 10% and for 10 doses vials it is between 10% - 15%. Country vaccine returns does not give the usage by vials, and it is only by total number of doses issued and used. Therefore it is difficult to estimates the wastage by vials and over all wastage is considered as 10%. |  |

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

Sri Lanka did not receive GAVI/The Vaccine Fund injection safety support in the form of a cash contribution.

# 2.  	Financial sustainability

Inception Report:	Outline timetable and process for the development of a financial sustainability plan. Describe assistance that may be needed for developing a financial sustainability plan.

First Annual Progress Report: 	Submit completed financial sustainability plan by given deadline. Describe major strategies for improving financial sustainability.

Country FSP is submitted to the GAVI in August 2005. Sri Lanka has received the comments from the GAVI review board and reported back the certain clarification on comments given by GAVI. (Annexure IV )

Subsequent Progress Reports:

According to current GAVI rules, support for new and under-used vaccines is covering the total quantity required to meet country targets (assumed to be

equal to DTP3 targets) over a five year period (100% x 5 years = 500%).  If the requested amount of new vaccines does not target the full country in a given

year (for example, a phasing in of 25%), the country is allowed to request the remaining (in that same example: 75%) in a later year.  In an attempt to help

countries find sources of funding in order to attain financial sustainability by slowly phasing out GAVI/VF support, they are encouraged to begin

contributing a portion of the vaccine quantity required.  Therefore, GAVI/VF support can be spread out over a maximum of ten years after the initial

approval, but will not exceed the 500% limit (see figure 4 in the GAVI Handbook for further clarification).  In table 2.1, specify the annual proportion of five

year GAVI/VF support for new vaccines that is planned to be spread-out over a maximum of ten years and co-funded with other sources.

Please add the three rows (Proportion funded by GAVI/VF (%), Proportion funded by the Government and other sources (%), Total funding for

Hep B ( New vaccine)) for each new vaccine.

| Table 2.1: Sources (planned) of financing of new vaccine Hepatitis B |
| --- |
| Proportion of vaccines supported by * | Annual proportion of vaccines |
|  | 2003** | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| A: Proportion funded by GAVI/VF (%)*** | 100% (48%)¶ | 100% (77%)¶ | 100% | 100% | 100% | 75%** | - | - | - | - |
| B: Proportion funded by the Government and other sources (%) |  |  | - | - | - | 25% | 100% | 100% | 100% | 100% |
| C: Total funding for Hep B (new vaccine) |  | 471 , 500 US$ | 568,000 US$ |  |  |  |  |  |  |  |

* Percentage of DTP3 coverage (or measles coverage in case of Yellow Fever) that is target for vaccination with a new and under-used vaccine.

** The first year should be the year of GAVI/VF new vaccine introduction

*** Row A should total 500% at the end of GAVI/VF support (¶ Note: Sri Lanka has  implemented a phase basis introduction of new vaccine. Therefore100% for year 2003-4, does not reflect the entire  population of the country, but given areas only, i.e.GAVI funded proportion for given years wae and 77%.)

In table 2.2 below, describe progress made against major financial sustainability strategies and corresponding indicators.

Table 2.2:	Progress against major financial sustainability strategies and corresponding indicators

| Financial Sustainability Strategy | Specific Actions Taken Towards Achieving Strategy | Progress Achieved | Problems Encountered | Baseline Value of Progress Indicator | Current Value of Progress Indicator | Proposed Changes To Financial Sustainability Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Introduce a separate Budget line For Immunization programme to ensure Improve national government funding flows | The proposal for special budget line for EPI has been reviewed by the Finance division of MoH. This proposal is planned to be submitted to the Finance Ministry by mid 2006 | Finance Division, MoH agreed as a policy. | - | No Separate budget line for immunization services, within the MoH. The Epidemiology Unit (EPI Unit) will have a separate account as the first step and subsequently get the separate budget line for immunization service. | Epidemiology Unit ( EPI Unit) has a separate account from 2005, and it is expected that from 2007, there will be a separate budget line in the MoH | - |
| 2. Resource mobilization / Donor support for introducing new vaccine (Hib) in 2007 or 2008 | - Carried out a burden study on Hib - Make meningitis as a notifiable disease to improve surveillance through the empowered legislations. | Hib Study completed in 2005 - Meningitis has been gazetted as a notifiable disease in the country. | - | No BoD / enough data on Hib in Sri Lanka | Hib Study findings are disseminated with the medical professionals / associations. Notification based estimation of disease incidence is continuing |  |
| 3. Resource mobilization / Donor support for improving the quality of immunization service and surveillance - World Bank Grant | - Settings model clinics in each division (n=270) in the country in order to improve the quality of EPI services | WB has approved the PoA and released funds ( First instalment i.e 50% for 2005) to both Central MoH and all Provincial MoH | Slow implementati-on of the activities | % of WB funds Utilized by the Ministry of Health and Provincial Ministries of Health and number of model clinics established (in 2005, this is zero %) | Training of district staff on establishing model clinics is continuing |  |
| 4. Resource mobilization / Increased reputation among donors | - Conducting international training programme (eg GTN Training on AEFI & Vaccine Procurement) - Carry out a safety and immunogenicity study of single dose of live attenuated JE vaccine at 12 months - Applied for carrying out a vaccine trial for vaccine efficacy and safety of Pneummococcal conjugate vaccine with the collaboration of GAVI /ADIP ( 2005) - Carrying out surveillance on streptococcus pneumonia and sero typing with the collaboration of SAPNA & GAVI PneumoADIP ( started Jan 2005) - Carrying out surveillance of Rota virus infections and sero typing with the collaboration of IVI/ South Korea & GAVI Rota ADIP ( started March 2005) Carrying out Rota virus study and transmission of bacterial respiratory pathogens studies in Tsunami affected areas with collaboration of Nagasaki University, Japan A study on utilization of private sector in immunization service in Colombo Municipality Area was carried out. | Third GTN international training programme on AEFI was held in July 2005 in Sri Lanka Planning is completed and study will be done in 2006 Sri Lanka has been selected as a one of the Asian sites. This study will be conducted in 2006-2007 Started surveillance in Jan 2005 as in the schedule and study is continuing. Started in April 2005 and study is continuing. Study was started in 2005 and study is continuing Study was completed in 2005 |  | Number of international training programmes conducted each year ( minimum one programme/year) Number of researches started and completed each year ( minimum one research to be started / year) At present limited information is available on private sector utilization in immunization services | Conducted two GTN training programmes in 2004 The private sector is contributing around 20% of total immunizations in the Colombo Municipality area |  |
| Improve Programme Efficiency Introducing open vial policy Rescheduling of clinic sessions Use of Multi form of vaccine vials ( 5 and 10 ml for measles) | The open vial policy was introduced in Jan 2005 to minimized the vaccine wastage MoH will develop guidelines for rescheduling clinic sessions MoH uses multi formed vaccine vials for measles from 2005 | A circular was issued by the Director General of Health Services to implement open vial policy in national EPI programme MoH is reviewing the guidelines for rescheduling clinic sessions MoH has included specifications for 5 and 10 ml measles vials into the procurement documents since 2005 | There was no supplier for 5 doses vials for year 2006 | At present the average wastage for all liquid vaccines is around 25-40% and it is expected to reduce the vaccine wastage to less than 10% | Open vial policy is introduced in 2005. Vaccine wastage for measles has reduced from 30% to below 20% |  |
| 6. Improve vaccine procurement / Introduction of bulk vaccine procurement | Bulk procurement of vaccines for Sri Lanka and Maldives from 2007 | Discussions started for signing a MOU between Sri Lanka and Maldives on bulk procurement of vaccines | Slow progress due to lengthy procedures to be followed, due to international trade practices |  |  |  |

# 3.  	Request for new and under-used vaccines for year 2006

Section 3 is related to the request for new and under used vaccines and injection safety for 2006.

- Up-dated immunization targets

Confirm/update basic data approved with country application: figures are expected to be consistent with those reported in the WHO/UNICEF Joint

Reporting Forms.  Any changes and/or discrepancies MUST be justified in the space provided (page 12). Targets for future years MUST be provided.

| Table 3 : Update of immunization achievements and annual targets |
| --- |
| Number of | Achievements and targets |
|  | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 |
| DENOMINATORS |  |  |  |  |  |  |  |  |  |
| Births | 362,000¶ | 361,453¶¶ | 370,000 | 375,000 | 380,000 | 385,000 | 390,000 | 395,000 | 400,000 |
| Infants’ deaths ( In 2005, estimated IMR 11.2 for 1000) | 4054 | 3,845 | 4392 | 4200 | 4256 | 4,312 | 4,368 | 4,424 | 4,480 |
| Surviving infants | 357,946 | 357,043 | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose of DTP (DTP1)* | 347,213* | 348,781* | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of DTP (DTP3)* | 340,418* | 342,410* | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| NEW VACCINES ** |  |  |  |  |  |  |  |  |  |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 1st dose Hep B. (new vaccine) | 258,540 | 337,866 | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| Infants vaccinated 2005 (JRF) / to be vaccinated in 2005 and beyond with 3rd dose of Hep B ( new vaccine) | 227,140 | 310,030 | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| Wastage rate in 2005 and plan for 2005 beyond*** Hep B ( new vaccine) | 15% | 12% | 10% | 10% | 7.5% | 7.5% | 7.5% | 5% | 5% |
| INJECTION SAFETY**** |  |  |  |  |  |  |  |  |  |
| Pregnant women vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with TT2 | 327,712 | 331,705 | 370,000 | 375,000 | 380,000 | 385,000 | 390,000 | 395,000 | 400,000 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with BCG * | 343,589 | 344,292 | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |
| Infants vaccinated in 2005 (JRF) / to be vaccinated in 2005 and beyond with Measles * | 349,281 | 353,281 | 365,608 | 370,800 | 375,744 | 380,688 | 385,632 | 390,576 | 395,520 |

¶ Reported births at the Registrar General Office, Sri Lanka, for year 2004    ¶¶ Estimated births by the Population Division, MoH

* Indicate actual number of children vaccinated in 2004  and 2005 and updated targets (with either DTP alone or combined)

** Use 3 rows (as indicated under the heading NEW VACCINES) for every new vaccine introduced

*** Indicate actual wastage rate obtained in past years

**** Insert any row as necessary

Please provide justification on changes to baseline, targets, wastage rate, vaccine presentation, etc. from the previously approved plan, and on reported figures which differ from those reported in the WHO/UNICEF Joint Reporting Form in the space provided below.

There is a possibility of over or under estimation of population (births), due to many reasons, particularly due to the reporting issues. As mentioned in previous APRs, there is a fluctuation of births. As our crude birth rate is also provisional and slightly fluctuating, Sri Lanka has made a simple assumption of 5000 additional births for each year. However, Sri Lanka will adjust its estimates of births with all available information in future. This is the reason that APR estimates slightly differ every year. For the calculation of estimated live births for 2005, projected estimated population for 2005 and provisional birth rates for 2004 was used. ( Please refer country’s Annual Progress Report 2004, where our estimate of birth for 2005 was 370,000 ) But the Registrar General reported 362,000 live births in 2004. IMR has taken as 11.2/1,000 live births, as given by the Population and Statistic Division, Ministry of Health, Sri Lanka, Report 2005. Private sector immunization data is still not integrated into the National EPI information system. Gradual expansion of private sector with maternal and child welfare services is taking place in private medical institutions. Particularly BCG for infants and Tetanus Toxoid immunization for pregnant mothers performed in private medical institutions are not reflected in the National EPI data. Our estimated wastage rate for new vaccine (Hep B) for year 2005 was15%. But due to good practices, it was reduced to well below 15% ( 12% ?) in 2005.

3.2	Availability of revised request for new vaccine (to be shared with UNICEF Supply Division) for 2007

In case you are changing the presentation of the vaccine, or increasing your request; please indicate below if UNICEF Supply Division has assured the availability of the new quantity/presentation of supply.

The Presentation of the vaccine (Hep B) will not be changed for 2007. The estimates of vaccines & injection safety requirement are changed. ( Please refer APR 2004) Sri Lanka will continue Monovalent Hep B vaccine. 25% required Hep B vaccine will be received in 2 doses vials and 75% in 10 doses vials. Our overall wastage is 10%. However it is difficult to get wastage for 2 & 10 doses vials separately in our reporting setting. Therefore our estimates for 2007 are based on the estimated wastage factors of 10% for 2 doses and 15% for 10 doses vials separately.

Table 4: Estimated number of doses of Hep B  vaccine (10 DOSES): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

* Table 4a: Estimated number of doses of Hep B  vaccine (2 DOSES): Please repeat this table for any other vaccine presentation requested from GAVI/The Vaccine Fund

At this point it is unable to calculate the anticipated vaccines in stock at start of year 2006 onwards, particularly with incomplete coverage (due to phase effects) and wastage of the vaccine. The stock balance could be made only once the phasing is over in year 2005.

** 2007 Hep B Requirement = 2 doses 335,864   and 10 doses 1,030,593 = Total 1,366,457

*Please report the same figure as in table 3.

Table 5: Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support for the years 2006 -2007

Table 6: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 7: Estimated supplies for safety of vaccination for the next two years with  DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 8 Estimated supplies for safety of vaccination for the next two years with Measles (One table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

Table 9: Estimated supplies for safety of vaccination for the next two years with TT (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4 to 8)

#### If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference.

# 4. 	Please report on progress since submission of the last Progress Report based on the indicators selected 	by your country in the proposal for GAVI/VF support

| Indicators | Targets | Achievements | Constraints | Updated targets |
| --- | --- | --- | --- | --- |
| Please see 1.3.2 |  |  |  |  |

# Checklist

Checklist of completed form:

| Form Requirement: | Completed | Comments |
| --- | --- | --- |
| Date of submission | Yes | Electronic version sent on 15 May 2005. Printed copy will be sent in due course. |
| Reporting Period (consistent with previous calendar year) | Yes | 2005. |
| Table 1 filled-in | Yes |  |
| DQA reported on | NA |  |
| Reported on use of 100,000 US$ | Yes |  |
| Injection Safety Reported on | Yes |  |
| FSP Reported on (progress against country FSP indicators) | Yes | FSP report submitted to GAVI in September 2005. |
| Table 2 filled-in | Yes | Sri Lanka has already received the request for year 2005, as it was approved by the GAVI. This report revised request for year 2006 onwards only. |
| New Vaccine Request completed | Yes |  |
| Revised request for injection safety completed (where applicable) | Yes | Sri Lanka Injection safety is for 3 years and support will be ended in year 2006 |
| ICC minutes attached to the report | Yes | Year 2005 minutes are attached. (Annexure V) |
| Government signatures | Yes |  |
| ICC endorsed | Yes |  |

6.  	Comments

ICC/RWG comments:

7.	Signatures

For the Government of Democratic Socialist Republic of Sri Lanka

Signature:	……………………………………………...……………...

Title: Secretary,

Ministry of Health Care and Nutrition, Sri Lanka								Date:           May 2006

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| Department of Health Services Ministry of Health | Dr. HAP Kahandaliyanage, Director General of Health Services |  | WHO | Dr Agostino Borra WHO Representative |  |
| Department of Health Services Ministry of Health | Dr. M. Fernando Deputy Director General of Health Services (Public Health) |  | UNICEF | Dr Aberra Bekele Head, Early Childhood Programme |  |
| Epidemiology Unit, Ministry of Health | Dr MRN Abeysinghe Epidemiologist |  | World Bank | Dr Daya Samarasinghe Health Specialist |  |
| Family Health Bureau Ministry of Health | Dr V Karunaratne Director Maternal & Child Health |  | JICA |  |  |
| Sarvodaya | Dr V. Ariyaratne Executive Director | . | Rotary International |  |  |

# Text boxes

Partnering with The Vaccine Fund

√

Remarks

Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: Countries are expected to plan for a maximum of:50% wastage rate for a lyophilized vaccine in 10 or 20-dose vial; 25% for a liquid vaccine in a10 or 20-dose vial; 10% for any vaccine (either liquid or lyophilized) in 1 or 2-dose vial. Buffer stock: The buffer stock is recalculated every year as 25% the current vaccine requirement Anticipated vaccines in stock at start of year 2006: It is calculated by counting the current balance of vaccines in stock, including the balance of buffer stock. Write zero if all vaccines supplied for the current year (including the buffer stock) are expected to be consumed before the start of next year. Countries with very low or no vaccines in stock must provide an explanation of the use of the vaccines. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes