## 0. Introduction
Tool-package for country-led deployment of cold chain equipment
This tool-package is intended for countries aiming to undertake the deployment of cold chain equipment (CCE) under Gavi 6.0 cash grant under the country-led deployment modality. It provides countries with a set of key tools that are mandatory and critical for an efficient and successful deployment of CCE under this modality.
The submission of the first three tabs (R&R, Risk-Matrix, Gantt Chart) form part of the legal grant agreement and also form part of the consolidated cash grant application and need to be submitted together with the cash grant application to Gavi for IRC review. Subject to Gavi clearance, funds will be transferred to the respective UNICEF CO to manage the budget under the HACT modality as per country-led deployment modality and approved budget.
The Monitoring template is required for monthly/quarterly submission on deployment progress and Installation Checklist for ILR/SDD is to confirm adequate installation and needs to be completed by the technician for each installation and signed off by a Government official.
Content:
I. Roles & Responsibilities
Accountablity framework to outline the key responsibilities by each critical parameter and stakeholder to facilitate the management of the project including the respective accountabilities.
II. Risk-Matrix
To prevent and manage risks prior and during project implementation. This should facilitate a smooth deployment and minimize delays and costs in implementation.
III. Deployment Gantt Chart
For adequate planning from receipt of goods and customs clearance to distribution, installation and training, the Gantt Chart template reflects key activity areas to be considered and represents the baseline for progress monitoring.
IV. Monitoring Implementation
A monitoring template is included to facilitate regular monitoring of the implementation status based on the approved deployment plan. It is to be submitted on monthly basis for first batch (that is subjected to a Post-Installation Ispection) and quarterly basis for remaining batches.
V. Monitoring Financial Utilization
A monitoring template is included to facilitate regular ongoing monitoring of the financial utilization of the grant against the respective budget item lines of the country-led deployment. The budget and financial utilization is based on the approved deployment plan and activities. It is to be submitted on six-monthly basis and does not replace the Final Certified Statement from DFAM.
VI. Installation Checklist for ILRs
As part of the commissioning of the CCE, a checklist is provided to ascertain adequate and quality installation of the equipment including whether end-user training has been conducted. The form has to be signed off by a Government official and is to be returned back to the respective Government department. It should be used for updating the progress reporting as well as for updating the country inventory for cold chain equipment.
VII. Installation Checklist for SDDs
As part of the commissioning of the CCE, a checklist is provided to ascertain adequate and quality installation of the equipment including whether end-user training has been conducted. The form has to be signed off by a Government official and is to be returned back to the respective Government department. It should be used for updating the progress reporting as well as for updating the country inventory for cold chain equipment.
*****

## 1. Roles & Responsibilities
NOTE: The matrix has prepopulated activities, which are based on the standard country-led deployment activities and apply accross all countries. Please complete all cells highlighted in yellow for your country as per the project activities. Further, for any comments, please include these in row 9 "Additional Comments" under the respective activities.
Step/Responsible party | Project Management | Procurement & Shipment | Customs cleareance | Transport In-Country | WH/Storage | ToT Technicians | Installation & Training | Post Installation Inspection | Monitoring & Reporting | Insurance
UNICEF GPD | Role & responsibility: Coordination with UNICEF CO (and SD) on any issues arising resulting in delay in project implementation, quality issues of installation and issues related to HACT and financial management. Further, supporting and strengthening the capacity across the different project activities with in-country key stakeholders. | NA | NA | NA | NA | Role & responsibility: Provide required support and guidance for the ToT for technician together with SD. | NA | Role & responsibility: Provide guidance and support to country together with SD for the Post Installation inspection in a country-led deployment context. | NA | NA
Unicef SD | Role & responsibility: Coordination with UNICEF CO and PD on any significant observations from the PII report requiring adjustments in the project implementation. Further, supporting and strengthening the capacity across the different project activities with in-country key stakeholders. | Role & responsibility: As per MOU, this includes Procurement of WHO Pre-qualified equipment and timely deliveries, including standard shipping documents. 1) Manage the procurement and shipment of the CCE supplies in consultation with the supplier and Gavi. 2) Provide required updates to country on the procurement and shipment of CCE supplies. | NA | NA | NA | Role & responsibility: Provide required support and guidance for the ToT for technician together with GPD. | NA | Role: Overseeing the PII process and coordinating with CO for a country-led PII. Responsibility: Selection of sample size accommodating for local conditions. Working with CO to identify suitable solution for an objective assessment (e.g. external to UNICEF/Govn. Health). Data analysis and ensuring PII report is issued. Highlight any significant findings to be addressed. | NA | Role & Responsibility: Ensures appropriate insurance of the CCE supplies during off shore shipment into the country
Unicef CO | As the project lead agency, cooperate with the Government for the project management of CCE country-led deployment. Role & responsibility: (1) Provide overall technical and management assistance to the Government/MoH (2) Coordinate with UNICEF GPD & SD, Gavi, MoH, suppliers on preparation, procurement, shipments, clearance, in-country installation and post installation monitoring, including addressing any delays and/or quality issues related to project implementation together with the Govn/PMT/NLWG. (3) Manage the funds for the activities outlined in this matrix to facilitate the in-country deployment and installation of country-led service bundled equipment, following the HACT modality and in line with UNICEFs Financial Rules & Regulations. (4) Submit project progress report and completion report. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Role & responsibility: (1) Coordinate with UNICEF SD in procurement of CCE. (2) Coordinate shipment planning (3) Coordinate with MoH on the goods receipt. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Role: INSERT HERE, WHETHER UNICEF UNDERTAKES THE CUSTOMS CLEARANCE OR SUPPORTS ON BEHALF OF THE GOVERNMENT OR OTHER Responsibility: (1) COORDINATION ROLE, IF APPLICABLE (2) SUPPORTING CUSTOMS PROCESSES / TIMELY RELEASE, IF APPLICABLE (3) All costs for customs clearance of equipment will be charged to the approved country-led deployment budget (excluding demurrage charges). | Role: INSERT HERE, WHETHER UNICEF SUPPORTS THE DISTRIBUTION VIA CO LTA's OR GOVERNMENT MANAGES THE DISTRIBUTION, OR IT IS A MIX. Responsibility: (1) (2) (3) .... INSERT HERE THE SPECIFIC ACTIVITIES, DEPENDING ON THE DISTRIBUTION MODALITY AGREED WITH GOVERNMENT. | Role: INSERT HERE, WHETHER UNICEF SUPPORTS THE DISTRIBUTION VIA CO LTA's OR GOVERNMENT MANAGES THE DISTRIBUTION, OR OTHER. Responsibility: (1) (2) (3) .... INSERT HERE THE SPECIFIC ACTIVITES, DEPENDING ON THE STORAGE MODALITY AGREED WITH GOVERNMENT. | Role: Support with coordination between MOH, supplier and UNICEF GPD & SD. Support review of training curriculum. Responsibity: Plan for the training and facilitate administrative arrangements for training. Responsible for the financial management under HACT to facilitate the training arrangement. Provide support for review of training curriculum and input of country specific to UNICEF GPD/SD. Further, procure SDDs units and techniciaan tools for practical demonstration. Facilitate the participation of the technicians at the training | Role: Provide technical support and coordination for installation and end-user training Responsibility: (1) UNICEF CO will be undertaking monthly monitoring in collaboration with the PMTs on the progress of the deployment (including installation/end-user training). Any quality issue in installation and/or end-user training should be reported to the PMT/NLWG for resolution. (2) UNICEF CO will be submitting quarterly monitoring progress report to UNICEF GPD on the progress of the deployment (including installation/and end user traning) and clarifying any challenges/delays faced. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Role: Coordinate with UNICEF GPD & SD for implementation of country-led PII. Responsibility: In coordination with the Government identifying suitable independent third party monitoring (TPM) company as feasible, or alternative solution. (1) Submit clearance of identified TPM to UNICEF GPD & SD. (2) Engage the TPM for the PII. (3) Provide required resources for the PII. (4) Support development of country-specific tools for PII based on global checklist and provide same to the TPM for the PII. (5) Coordinate with TPM and UNICEF GPD & SD on training for PII. (6) Address findings of PII report. | Role: UNICEF CO will as the lead agency support the country with monitoring, data collection, and reporting activities on the project implementation. Responsibility: Support monitoring (including supportive supervision) of each stage of the project including procurement and shipment, customs clearance, in-country distribution, installation and end-user training. a) In-country Distribution UNICEF will engage with PMT for regular monitoring and updates on distribution status and any challenges/changes. Further, ensure regular monitoring reports are issued. b) Installation & Training UNICEF consultants and, the cold chain team will regularly perform quality checks on installation & end-user training. Any quality issue in the installation should be reported to the PMT/NLWG for resolution. c) Progress Reporting UNICEF CO will ensure that reports related to the progress of project implementation are prepared through the PMTs/NLWGs and are submitted on time as per the agreed-upon reporting format and frequency with UNICEF GPD. Further, for the PMT/NLWG to ensure there is no deviation from the final deployment plan for the cold chain equipment or these are mitigated. This includes timely submission of PMT/NLWG-endorsed progress report each quarter and financial utilization report every six months. d) General Project Implementation (1) Plan and conduct field monitoring visits before, during, and after installation. 2) Conduct regular PMT/NLWG and high-level meetings to monitor the implementation process and endorse different plans and deviation plans (3) Involve UNICEF field offices with the local PMTs/NLWGs and SLWG/State EPI team to ensure adequate monitoring and documentation (4) Regularly review planned activities against implementation and take corrective measures, when needed. (5) Monitor fund flow to ensure timely release and appropriate utilization as per UNICEF regulations and rules / grant agreement provisions (6) Keep regular update and engagement with GPD to monitor the progress with specific focus on security compromised areas and financial fiduciary oversight for F&C states. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Roles & Responsibility: (1) INSERT HERE CONFIRMATION ON INSURANCE FOR AREAS WHERE UNICEF WOULD BE RESPONSIBILE (E.G. TRANSPORTATION, WH ETC.) (2) Provide technical support to the Government/PMT in case of any insurance claims to be submitted to UNICEF related to the off-shore delivery of the equipment.
Supplier | NA | Role & responsibility: Ensure timely availability of the goods as per issued and confirmed PO. Provision of all standard shipping document. A two year replacement warranty applies in the event of any component failure arising from defective design, materials or workmanship. The warranty period comes into effect upon dispatch of goods from supplier. | NA | Coordinate timely in-country distribution as per the operational deployment plan and manage (including) any deviations) through the PMT. | Coordinate warehouse arrangement for CCEOP equipments on behalf of the Government. | Role: Provide training to the MOH technicians as per agreed training curriculum and ensure adequate training outcome. Responsibility: Ensure that training is sufficient for MOH technicians to install and manage preventive maintenance and repair of the equipment. | NA | NA | NA | NA
Government | Role: The Government retains the overall responsibility for the CCE country-led deployment project implementation. INSERT HERE, WHETHER GOVERNMENT HAS OUTSOURCED SOME OF THE PROJECT COMPONENTS TO UNICEF. Responsibility: Overall coordination of the work of the national and sub-national LWG/ PMT committees. (1) Develop and review the logistics plans (2) Ensure regular meeting of PMT/NLWG at all levels (3) Manage the technicians’ teams at different states (4) Facilitate the payment for the technicians who will undertake the CCE installation. (5) Ensuring final ODP reflecting any deviations, is submitted to GPD. NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Role & responsibility: Coordinate shipment planning with NLWG/PMT committees and UNICEF CO. | Role: INSERT HERE, WHETHER GOVERNMENT UNDERTAKES THE CUSTOMS CLEARANCE OR UNICEF SUPPORTS ON BEHALF OF THE GOVERNMENT OR OTHER Responsibility: (1) Government to ensure in a timely manner availability of all necessary documentation needed for customs clearance process (including pre-clearance process) (2) Any demurrage charges resulting from a delayed customs clearance process, are the sole responsibility for the Government to settle and cannot be charged against this project. (3) .... (4) .... **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, IF REQUIRED. | Role: Responsible for developing logistics plan and coordinate with different states/districts to facilitate the equipment arrival to the final destinations. THE ABOVE TEXT IS MANDATORY - INSERT HERE, WHETHER GOVERNMENT MANAGES DISTRIBUTION FULLY OR PARTIALLY AND WHETHER UNICEF SUPPORTS VIA CO LTA's OR GOVERNMENT Responsibility: (1) .... (2) .... (3).... INSERT HERE THE SPECIFIC ACTIVITES, DEPENDING ON THE AGREED DISTRIBUTION MODALITY. | Role: INSERT HERE, WHETHER UNICEF SUPPORTS THE DISTRIBUTION VIA CO LTA's OR GOVERNMENT MANAGES THE DISTRIBUTION, OR OTHER. Responsibility: (1) Register all the received equipment (Govn. WH & UNICEF WH) in National property database before further distribution. (2) .... (3) .... (4) .... INSERT HERE THE SPECIFIC ACTIVITES, DEPENDING ON THE AGREED STORAGE MODALITY. | Role: Nominate Government technicians Responsibility: Ensure CV'S of the nominated technicans are submitted to UNICEF prior to training and that the technicians are available to undergo the training. | Role: Coordinating/monitoring installation plan with certified MoH technicians and ensure timely and quality installation of CCE including end-user training. Responsibility: Certified MOH technicians, that have completed the CCE technician training, to install equipment and conduct end-user training. Return to UNICEF the Installation Check-List form certifying that the installation & end-user training took place and report any issues to PMT/NLWG. This includes. (1) Nominate and construct installation teams from the trained MoH CCE technicians (2) Prepare list of end-users that should be trained (3) Ensure revalidation of site readiness completed and timely site readiness of HFs for CCE installation. (4) Ensure installation is according to the recommended technical requirement and performed by certified technicians. (5) Any quality issue on installation and/or end-user training should be reported to the PMT/NLWG and addressed accordingly. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, AS REQUIRED. | Role & Responsibility: (1) Support the use of a locally sourced TPM company for an independent PII. (2) Provide required support to facilitate the access of the TPM team to the field (3) Provide enabling environment for the conduct of PII across the country. | Role: PMT/NLWG supervises the overall distribution and installation to ensure timely and quality delivery to the health facilities. It addresses any issues arising during the deployment to risk mitigate delays in project implementation. Responsibility: (1) PMT/NLWG identifies any issues/bottlenecks and takes corrective measures accordingly to avoid delay in the distribution. (2) PMT/NLWG and cold chain team will do regular supervision of installations, end-user training and perform quality checks, including reporting back on CCE product failures. (3) PMT/NLWG ensures that all project sites have been inspected and post inspection report is shared with UNICEF CO. (4) PMT/NLWG prepares quarterly implementation report cleared by PMT/NLWG for submission to UNICEF GPD. **** NB! THE ABOVE TEXT IS MANDATORY - THE COUNTRY CAN ADD ADDITIONAL COUNTRY SPECIFIC ACTIVITIES, AS REQUIRED. | Responsibility: INSERT HERE CONFIRMATION ON GOVERNMENT PROVIDED INSURANCE FOR ALL AREAS WHERE GOVERNMENT IS RESPONSIBLE RELATED TO CCE (E.G. TRANSPORTATION, WH ETC.)
ADDITIONAL COMMENTS

## 2. Risk-Matrix
RISK ASSESSMENT & MITIGATION PLAN MATRIX
Risk areas | RISK | Risk likely-hood | Risk impact | Risk level | Result of Risk Occurrence | Mitigation measures to control risk | Timeline | Action Points | Responsible FP
Process Related
Customs Clearance |  | Medium | High | High
Warehousing/ Storage |  | Low
Distribution to Sub-National or Service Point levels
Fund Management
Installation and end-user training
Emergency situation
Access issues due to: Flooding, Landslide, Security etc.
NOTE:
Please complete the Risk-Matrix for all columns C to K for all Risk Areas.
The 'Risk Level' will be the sum of 'Risk Likelihood' and 'Risk Impact' identified for each risk area.
It is important that risks are identified based on past experience as well.
Please add separate additional rows under the different "Risk Areas" for including all different risks identified that require different risk mitigation measures to be taken. (For example "Distribution" could have different type of risks and likelihood to occur and should then be listed in separate rows.

## 3. Deployment Gantt Chart
DEPLOYMENT PLAN - GANTT CHART
Country:
| # | Key Activities | Timeline for CCE implementation | [26 empty] | Responsible FP | Status/Comments
|  |  | Weeks | [11 empty] | Months
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| 1 | Bi-weekly meeting with PMT/NLWG | bar: Weeks 1; Weeks 3; Weeks 5; Weeks 7; Weeks 9; Weeks 11
Training | 2 | Training of cold chain technicians in installation of CCE | bar: Weeks 2 to Weeks 3
| 2a | * Webinar/Zoom/On-line training | bar: Weeks 2
| 2b | * Hands-on training | bar: Weeks 3
Shipping & Clearance (Lot 1) | 3 | Goods readiness and shipping from suppliers to port of entry | bar: Weeks 1
| 4 | Receipt of complete set of shipping documents | bar: Weeks 2
| 5 | Equipment pre-arrival clearance process | bar: Weeks 3 to Weeks 4
| 6 | Arrival of lot 1 of CCE at port of entry XX | bar: Weeks 5
| 7 | Customs clearance | bar: Weeks 6
Distribution & Installation (Lot 1) | 8 | WH storage | bar: Weeks 6
| 9 | In-country distribution lot 1 subject to Interim-PII (CCE type & Q = xxx) | bar: Weeks 7 to Weeks 9
| 10 | Installation & End-user training I (Q = xxx) | bar: Weeks 8 to Weeks 10
| 11 | Interim-PII | bar: Weeks 11 to Months 4
Shipping & Clearance (Lot 2) | 12 | Goods readiness and shipping from suppliers to port of entry | bar: Months 4
| 13 | Receipt of complete set of shipping documents | bar: Months 5
| 14 | Equipment pre-arrival clearance process | bar: Months 6 to Months 7
| 15 | Arrival of lot X of CCE at port of entry XX | bar: Months 8
| 16 | Customs clearance | bar: Months 9
Distribution & Installation (Lot 2) | 17 | WH storage | bar: Months 9
| 18 | In-country distribution lot 2 (CCE type & Q = xxx) | bar: Months 10 to Months 12
| 19 | Installation & End-user training (Q = xxx) | bar: Months 11 to Months 13
Shipping & Clearance (Lot 3) | 20 | Goods readiness and shipping from suppliers to port of entry | bar: Months 12
| 21 | Receipt of complete set of shipping documents | bar: Months 13
| 22 | Equipment pre-arrival clearance process | bar: Months 14 to Months 15
| 23 | Arrival of lot X of CCE at port of entry XX | bar: Months 16
| 24 | Customs clearance | bar: Months 16
Distribution & Installation (Lot 3) | 25 | WH storage | bar: Months 16
| 26 | In-country distribution lot 3 (CCE type & Q = xxx) | bar: Months 17
| 27 | Installation & End-user training (Q = xxx) | bar: Months 18
| 28 | Monitoring & Progress Reporting
| 29 | Submission of final ODP after implementation to UNICEF | bar: Months 18
NOTE:
The current Gantt Chart is only a sample with regards to the timelines.
Please complete the deployment Gantt Chart. This will form the baseline for progress monitoring.
Important to note for Y1 deployment
a) reflecting first test batch (est. 150-200 units)
b) Interim PII to be conducted, prior to subsequent batch installations.
Point a) and b) also apply for Y2 onwards countries, if a new type of equipment is being installated (e.g. ILR vs. SDD)
Off-Shore Shipments
If multiple off-shore shipments are required due to warehousing storage constraints, security reasons, deployment and installation capacity, project plans or other reasons, please insert additional rows for delivery and customs clearance.
Please note the template only shows timelines as example. To be reflected as per country context.
_______________________________________________________________________________________________________
Deployment timeline benchmarks:
Countries should consider timeline benchmarks below for deployments.
I. Pre-project Preparations: Upon Gavi approval of the cash grant application (e.g. issuance of Gavi Decision Letter), a number of key activities should be initiated to reduce the overall timeline for the project implementation. These key activities should be completed prior to the procurement of equipment and relate to:
  a) Preparations and planning for Government technicians training
  b) Arranging mechanisms for pre-customs clearance (as feasible)
  c) Identification of locally sourced independent 3PLs for the post installation inspection (only applicable for new countries to this modality under the cash grant)
  d) Assessing the warehouse and storage capacity for incoming equipment prior to distribution and depending on country arrangements, ensuring adequate plans are made (Govn. WH or UNICEF WH contracts)
  e) Assessing the readiness of the in-country distribution arrangements – depending on country arrangements, ensure adequate transportation is in place (Govn. transporters or UNICEF LTA holders)
  f) If RTMDs/EMS level 3 is selected for the CCE, reconfirm the feasibility for operating the data as per applicable Government legislation.
II. Preparations: Key activities should be completed between 1 to 2 months upon arrival of equipment. Preparation stage includes:
  a) Completing the customs clearance process
  b) Conducting the technicians training
  c) Revalidation of the ODP and formal clearance through NLWG/PMT
  d) Confirming warehouse and transportation arrangements are in place
  e) Confirming independent 3PL has been identified for future engagement for PII (post phase-1 deployment)
III. Deployments: Key activities including distribution, installation and end-user training. Timelines may vary due to security issues, number of units, seasonal challenges (e.g. monsoons, rainy season), logistical challenges (e.g. islands, mountainous areas, air transportation requirements) and country typology (e.g. fragile & conflict)
NOTE --> Please use the "Deployment Calculator" in tab 4 of this tool kit to calculate the overall estimated timeline for the activities related to in-country distribution and installation of the cold chain equipment. Please ensure these timelines (in column J12) are not exceeded in the Gantt Chart.
IV. Pre-Post Installation Inspections (PII) where required: Activities (contracting, training, implementation, data analysis and report issuance) should be completed within 3 to 6 months prior to the commencement of subsequent deployments for new countries adopting the approach. This introduces phased deployments for new countries to ensure quality installations and that issues identified during the PII are addressed before the further roll-out.
*******

## 4. Deployment Calculator (EN)
Calculator for deployment timelines (Distribution & Installation)
LIST - Dropdown | # | Core scale inputs | List | Input Cells | 1) | Core Capacity (HR) | 0
text | 1 | Total units (N) |  |  |  | Complexity Adjustment | 0
| 2 | Number of facilities (F) |  |  |  | Geography Adjustment | 0
|  | Installation capacity inputs |  |  | 2) | Final adjusted installation capacity (units/day): | 0
| 3 | Installation teams (T)
| 4 | Installations per team per day [use drop-down list] |  | 2
Geography inputs
| 5 | Geography type [use drop-down list] |  | 2
[5 empty] | 5) | Installation time | #DIV/0!
ILR |  |  |  |  | 6) | Base Distribution Rate | #DIV/0!
SDD |  |  |  |  | 7) | Geography + Season Adjustment | #DIV/0!
[5 empty] | 8) | Installation time logic | #DIV/0!
|  | Logistics system |  |  | 9) | Buffer/Country Typology | #DIV/0!
|  | Logistics system |  |  | 3) | Total estimated months* | #DIV/0!
| 6 | Hubs
| 7 | Truck cycle rate (trips/month per hub)
Urban | 8 | Seasonal disruption (0–0.5) |  |  |  | * this includes adjustments on geographical type, seasons, logistics capacities.
Mixed | 9 | Working days |  | 5
Rural |  | Buffer/Country typology
Fragile | 9 | Country Typology [use drop-down list] |  | 2
AT
F&C
NOTE:
Please note these timelines only apply for the activities related to distribution and installation. these timelines are only meant as a benchmark to ensure that the timelines in the Deployment Gantt Chart, do not exceed these, but the timelines can be shorter with regards to distribution/installation.
Please complete the yellow cells by country context, deployment targets, technicians available and transport capacity data. Countries should aim to deploy equipment within reasonable timelines to quickly close capacity gaps.
Clarifying notes:
* #1 "Total units (N)"= total units planned for procurement and distribution/installation.
* #2 "Number of facilities (F)"= total number of facilities that will receive the CCE. This number can be less than total CCE, if a facility receives more than one CCE unit.
* #3 "Installation teams (T)" = total number of technicians available for this project for the CCE installation.
* #4 "Installations per team per day"= please select the type of CCE from the drop down list (e.g. SDD or ILR (this label includes Freezers)) as it takes longer time to install SDDs compared to mains (ILR/Freezers)
* #5 "Geography type"= please select from the drop down list the adequate location for the installation (e.g. urban, mixed, rural, fragile context). This is important for the timeline calculation, as context of location also defines the complexity for distribution of the CCE and thus time required. If multiple locations apply, please select based on majority of the CCE or prepare two calculations, if it is almost split by 50% and 50%.
* #6 "Hubs"= refers to number of distribution points, from which the CCE will be distributed to districts and health facilities (e.g. only central or central + 2 x regional hubs)
* #7 "Truck cycle rate (trips/month per hub)" = refers to number of trips each truck available for CCE distribution will complete per month per distribution hub.
* #8 "Seasonal disruption" = refers to impact of weather and environmental hazards (e.g. monsoon rains, snow etc.) that impacts the routes severely for distribution. Select between 0, 0.1, 0.2, 0.3, 0.4, 0.5, while the scale 0 = no impact and 0.5 = high impact.
* #9 "Country Typology" = please select from the drop down list either AT = Accelerated Transitioning country or F&C = Fragile & Conflict country. These refer to Gavi country typologies approved for this country-led deployment modality.
*******

## 5. Monitoring Implementation
REPORTING ON IMPLEMENTATION SCHEDULE
DATE: ______________________ |  |  |  | COUNTRY: ______________________________
Sub-National | District | Health Facility | Product Model | Total Quantity Delivered to District or Health Facilities | Total Quantity Installed at District or Health Facilities | Planned Installation End Date | Actual Installation End Date | Number of Deviations | Comments
NOTE:
This reporting template is to be submitted:
a) on monthly basis for the first test batch
(unit Interim-PII has been concluded)
b) on quarterly basis for subsequent batches.

## 6.Monitoring FinanceUtilization
MONITORING REPORT ON FINANCIAL UTILIZATION*
REPORTING PERIOD: ______________________ |  |  |  |  | COUNTRY: ______________________________ |  |  | DATE: ______________________
Cost Categories | Quantities | Approved Unit Costs (USD) | Approved Amount (USD) | Committed Amount (USD) | Expended Amount (USD) | Total Utilized Amount (USD) | Total Balance Amount (USD) | Comments
Note: * The financial utilization report is linked to the implementation progress as an operational tool and does not constitute a financially certified utilization report.
NOTE:
This reporting template is to be submitted
every six months.

## 7. Installation checklist ILR
Annex E – Installation checklist On-grid refrigerator / freezer (Mains)
Note: The installation technician must fill in this checklist for each completed installation.
Mains powered refrigerator installation checklist |  |  |  | Date:
Country: |  |  | Region: | District: | Facility name:
Installation technician:
Installation company:
Address:
Tel:
Email:
Note: All checks must be satisfactory before Annex E can be signed / the installation is deemed completed.
CHECK 1 – System description
1.1 |  | Qualified supplier:
1.2 |  | Refrigerator/freezer Model:
Serial number: _____________________________
Model reference: _____________________________
Product number: _____________________________
CHECK 2 – Shipment details
2.1 |  | Was the shipment damaged? |  |  | ☐ Yes ☐ No
2.2 |  | Were any components missing or under-supplied? |  |  | ☐ Yes ☐ No
2.3 |  | Have damaged/missing/under-supplied parts been replaced? |  |  | ☐ Yes ☐ No ☐ Not applicable
Comments:
CHECK 3 – Functionality test
3.1 |  | Functionality test has been carried out in accordance with the qualified supplier’s instructions. |  |  | ☐ Yes ☐ No
3.2 |  | A detailed functionality test report been completed and signed by the technician; a copy of the report is attached. |  |  | ☐ Yes ☐ No
3.3 |  | 30-day temperature logger has been installed and is functional. |  |  | ☐ Yes ☐ No ☐ RMTD
3.4 |  | There is sufficient GSM coverage at the health facility. |  |  | ☐ Yes ☐ No ☐ Not relevant
Installation Technician confirmation on functionality
Installation Technician Signature: _____________________________________
CHECK 4 – Cabling and installation
4.1 |  | The voltage regulator has been installed and cabled correctly. |  |  | ☐ Yes ☐ No
4.2 |  | All electrical connections and cables are concealed and properly protected. |  |  | ☐ Yes ☐ No
Comments:
CHECK 5 – Training
5.1 |  | Number of health facility staff trained in usage of refrigerator
5.2 |  | Number of staff trained in preventive maintenance of refrigerator
5.3 |  | Number of staff trained in usage of 30 DTR / recording of temperature
5.4 |  | Warranty / claims procedure has been explained, including whom to contact in |  |  |  | ☐ Yes ☐ No
case of under-performance or downtime of equipment.
5.5 |  | Warranty / claims procedure and relevant contacts are attached to the fridge. |  |  |  | ☐ Yes ☐ No
CHECK 6 – Documentation
6.1 | Check if the following documentation has been supplied |  |  |  |  | Language:
| - User manual for all system components |  |  |  |  | ☐ Yes ☐ No
| - Technician’s manual |  |  |  |  | ☐ Yes ☐ No
| - Installation manual |  |  |  |  | ☐ Yes ☐ No
Comments:
CHECK 7 – Overall conclusions and recommendations
7.1 | Recommendation: |  |  |  |  | ☐ Pass ☐ Fail
If FAIL, list outstanding work still required:
If PASS, the installation can be handed over to the user.
Installation technician signature: _____________________________________
Health center responsible signature: ___________________________________
Name and designation: ______________________________________________
Rubber Seal
Of the Health facility/
District Health officer
Date: ______________________
Warranty/claims procedure
NOTE:
It is mandatory to use the Annex E template for completion of ILR/Freezer installation.
The form should be completed and signed off by the Government responsible.
Further to be noted, this form should be used for updating CCE inventories.

## 8. Check-list SDD instllation
Annex E – Installation checklist Solar Direct Drive refrigerator (SDD)
Note: The installation technician must fill in this checklist for each completed installation.
Solar refrigerator installation checklist |  |  |  | Date:
Country: |  |  | Region: | District: | Facility name:
Installation technician:
Installation company:
Address:
Tel:
Email:
Note: All checks must be satisfactory before Annex E can be signed / the installation is deemed completed.
CHECK 1 – System description
1.1 |  | Qualified supplier:
1.2 |  | Refrigerator /freezer Model:
Serial number: _____________________________
Model reference: _____________________________
Product number: _____________________________
1.3 |  | Solar panels:
Model Ref: __________________ Quantity of panels: ___________
Serial numbers ____________________________ ____________________________
Serial numbers ____________________________ ____________________________
Serial numbers ____________________________ ____________________________
Serial numbers ____________________________ ____________________________
CHECK 2 – Shipment details
2.1 |  | Was the shipment damaged? |  |  | ☐ Yes ☐ No
2.2 |  | Were any components missing or under-supplied? |  |  | ☐ Yes ☐ No
2.3 |  | Have damaged/missing/under-supplied parts been replaced? |  |  | ☐ Yes ☐ No ☐ Not applicable
Comments:
CHECK 3 – Solar panel installation
3.1 |  | Panel Orientation
|  | Has the panel been installed at the correct angle towards the equator? |  |  | ☐ Yes ☐ No
|  | Do shadows fall on the panel between 9:00am and 3:00pm? |  |  | ☐ Yes ☐ No
If YES, the system FAILS - if possible remove the shade or the panel must be moved.
3.2 |  | Panel support structure
|  | Are roof fixings in place and are they adequate? |  |  | ☐ Yes ☐ No
|  | Have theft-deterrent fasteners been used? |  |  | ☐ Yes ☐ No
3.3 |  | Lightning protection:
|  | Has the lightning protection circuit been correctly fitted? |  |  | ☐ Yes ☐ No
|  | Has the earth electrode been correctly fitted? |  |  | ☐ Yes ☐ No
|  | Has lightning protection system been tested for electrical continuity? |  |  | ☐ Yes ☐ No
Comments:
CHECK 4 – Array cabling and installation
4.1 |  | Only the solar array cable provided by supplier was used for installation? |  |  | ☐ Yes ☐ No
4.2 |  | Are all electrical connections and array cables concealed and properly protected? |  |  | ☐ Yes ☐ No
Comments:
CHECK 5 – Functionality test
5.1 |  | Functionality test has been carried out in accordance with the qualified supplier’s instructions. |  |  | ☐ Yes ☐ No
5.2 |  | A detailed functionality test report been completed and signed by the technician; a copy of the report is attached. |  |  | ☐ Yes ☐ No
5.3 |  | 30-day temperature logger has been installed and is functional. |  |  | ☐ Yes ☐ No ☐ RMTD
5.4 |  | There is sufficient GSM coverage at the health facility. |  |  | ☐ Yes ☐ No ☐ Not relevant
Installation Technician confirmation on functionality
Installation Technician Signature: _____________________________________
CHECK 6 – Training
6.1 |  | Number of health facility staff trained in usage of refrigerator
6.2 |  | Number of staff trained in preventive maintenance of refrigerator
6.3 |  | Number of staff trained in usage of 30 DTR / recording of temperature
6.4 |  | Warranty / claims procedure has been explained, including whom to contact in case of under-performance or downtime of equipment. |  |  | ☐ Yes ☐ No
6.5 |  | Warranty / claims procedure and relevant contacts are attached to the fridge. |  |  | ☐ Yes ☐ No
CHECK 7 – Documentation
7.1 | Check if the following documentations are supplied |  |  |  | Language:
| - User manual for all system components |  |  |  | ☐ Yes ☐ No
| - Technician’s manual |  |  |  | ☐ Yes ☐ No
| - Installation manual |  |  |  | ☐ Yes ☐ No
Comments:
CHECK 8 – Overall conclusions and recommendations
8.1 | Recommendation: |  |  |  | ☐ Pass ☐ Fail
If FAIL, list outstanding work still required:
If PASS, the installation can be handed over to the user.
Installation technician signature: _____________________________________
Health center responsible signature: ___________________________________
Name and designation: ______________________________________________
Rubber Seal
Of the Health facility/
District Health officer
Date: ______________________
Warranty/claims procedure
NOTE:
It is mandatory to use the Annex E template for completion of SDD installation.
The form should be completed and signed off by the Government responsible.
Further to be noted, this form should be used for updating CCE inventories.